## Sheet1
No. | Result | Activity | Milestone | Responsibility | Timeframe | [11 empty] | Remarks | Allocations
[5 empty] | J | F | M | A | M | J | J | A | S | O | N | D
Development Goal | To reduce the risk of Desert Locust plagues emanating from the Central Region of the DL distribution area in order to mitigate food security, economic and environmental concerns in the Central Region and beyond
Programme Goal | To strengthen the capacities and capabilities of the national, regional, and international components of Desert Locust management systems to implement effective and efficient preventive control strategies based on early warning and timely and environmentally sound early control interventions.
Indicator: Up to 8 of the Locust control Units in the Central Region practice at least X essential components of preventive control techniques / methods as part of their Desert Locust management strategy in a sustainable way (by end of the programme).
Programme Purpose, Phase II | Components of preventive Desert Locust management developed and adopted | Indicator: At least 1 component with regard to early detection, 1 component with regard to environmentally sound and economic control developed and adopted in at least 3 member countries, by CRC and DLCO-EA by 2003 |  | FAO EMPRES, MoAs of the member countries, LCUs | Timeframe J: Jan. 2001 - Dec. 2003
R-1 | Operational mandates of different regional organizations in DL management harmonized | I.R-1.1: At least 1 EMPRES country joins CRC as new member by 2002 | [14 empty] | Assumption: Regional organizations are willing to cooperate
I.R-1.2: A draft Memorandum of Understanding between CRC/DLCO (supported by EMPRES) on implementation of sustainable DL management concepts in the Central Region formulated by 2003
1.1 |  | Coordinate EMPRES/CR activities with various partners |  | FAO EMPRES staff
1.1.1 |  | Organize regional and inter-regional coordination meetings |  | AGPP, FAO EMPRES staff
1.1.1.1 |  | Organize 4th Consultative Committee Meeting | 01/02 (Cairo) | AGPP, FAO EMPRES staff | [13 empty] | USD 10,000
1.1.1.2 |  | Conduct EMPRES Staff Meeting | 01/02 (Cairo) | FAO EMPRES staff | [13 empty] | USD 3,000
1.1.1.3 |  | Organize CRC Meetings | 03/02 (Damascus) | AGPP, CRC | [13 empty] | USD 25,000 (USD 3,000 Coord. travel)
1.1.1.4 |  | Organize FAO / CRC / EMPRES / DLCO Meetings | 11/02 (Cairo) | CRC, DLCO, FAO EMPRES staff | [13 empty] | USD 3,000
1.1.1.5 |  | Organize EMPRES/CR - WR Meeting | 06/02 (Tunis, Cairo) | FAO EMPRES staff | [13 empty] | USD 3,000
1.1.1.6 |  | Organize 10th ELO Meeting | 10/02 (Jeddah) | ELO S.A., FAO EMPRES staff | [13 empty] | USD 20,000
1.1.2 |  | Undertake coordinating travel | up to 4 visits | FAO EMPRES staff
1.1.2.1 |  | Visit Eritrea | 04/02 (Asmara) | FAO EMPRES staff, CRC | [12 empty] | Consolidation of Country Focus Programme; Promotion of Eritrea to join the CRC | USD 3,000
1.1.2.2 |  | Visit Yemen, Saudi Arabia and Oman | 04-05/02 (Sana'a, Jeddah, Muscat) | FAO EMPRES staff, CRC | [12 empty] | Country Focus Programmes, ca. 4 weeks travel | USD 7,000
1.1.2.3 |  | Visit Jordan, Sudan, Saudi Arabia, U.A.E | Mai - June 2002 | AGPP, CRC | [12 empty] | Introduction of CRC Secretary to CRC member countries | USD 7,000
1.1.3 |  | Arrange for technical information visits | Up to 10 visits for national experts by 12/03 | CRC | [12 empty] | Residue Lab Egypt, LOCUSTOX Senegal, Locust Centre Mauritania, ICIPE station Sudan | USD 10,000 (2002)
1.2 |  | Develop mechanisms towards sustainability of improved DL management |  | FAO EMPRES staff | [12 empty] | Harmonization of technical mandates of CRC and DLCO-EA, Country Focus Programmes
1.2.1 |  | Support a working group consisting of staff from CRC, DLCO-EA | At least 1 Joint Technical Forum conducted between CRC, DLCO, EMPRES/CR (11/02 Cairo) | FAO, CRC, DLCO-EA | [12 empty] | Main agenda items: Harmonization of information systems at regional level, strategy questions and control operations. | ref. 1.1.1.4
1.2.1.1 |  | Conduct joint activities of shared responsibility | At least 3 tri-lateral activities are initiated in important areas of equal concern and documented in joined work plans | CRC, DLCO, FAO EMPRES staff | [12 empty] | 3.3 Harmonized DL reporting; 1.2.1.3 Improved DL management strategies; 4.4 Survey capacity Somalia; 4.3 Joint surveys; 5.1 Training standards; 6.1.4 Rapid deployment plans for aerial intervention; 7.1.4 Introduction of DGPS; 7.2 Assessment of environmental impact; 7.4 Introduction of bio-pesticides; 7.4.5 Guidelines for good spraying practices | ref. activity no.
1.2.1.2 |  | Harmonize DL reporting and information management systems between CRC, DLCO and DLIS | Draft concept submitted to AGPP for approval and comments by 08/02 | CRC, DLCO, DLIS, FAO EMPRES staff
1.2.1.3 |  | Develop common understanding between CRC and DLCO on improved preventive control management strategies | Draft concept ready for adoption and approval by AGPP by 11/02 | FAO, CRC, DLCO-EA | [12 empty] | Consultancy on concept drafting
1.2.2 |  | Organize (bi-lateral) Country Focus Programmes | At least 4 Country Focus Programmes are conducted by 12/03 | FAO EMPRES staff, ELOs
1.2.2.1 |  | Support CFP in Sudan | Recommendations for improved survey and information management systems operational by 10/02 | PPD Sudan, FAO EMPRES staff, CRC | [12 empty] | Improved Survey and reporting system, Data management , Contingency planning, Recourse management, Staff development mechanisms | USD 10,000
1.2.2.2 |  | Review CFP in Eritrea | Reviewed document ready by 05/02 and submitted for approval to AGPP and the MoA-ERI | PPQU Eritrea, FAO EMPRES staff | [13 empty] | USD 10,000
1.2.2.3 |  | Implement CFP in Yemen | First concrete activities are documented by 06/02 and results presented in the 10th ELOM | GDPP Yemen, FAO EMPRES staff | [13 empty] | USD 10,000
1.2.2.4 |  | Implement CFP in Ethiopia | First concrete activities are documented by 06/02 and results presented in the 10th ELOM | CPPTRD, FAO EMPRES staff | [13 empty] | USD 10,000
1.2.2.5 |  | Conduct CFP planning workshop in Saudi Arabia | Programme document ready and submitted for approval to AGPP and the Saudi MoA by 08/02 | GDPP, FAO EMPRES staff, CRC | [13 empty] | USD 2,000
1.2.2.6 |  | Conduct CFP planning workshop in Oman | Programme document ready and submitted for approval to AGPP and the Omani MoA by 08/02 | DGAAA, FAO EMPRES staff, CRC | [13 empty] | USD 2,000
1.2.2.7 |  | Support locust survey capacities in Somalia | DLIS received at least 4 quality reports by 12/02 | DLCO, FAO EMPRES staff | [12 empty] | DLCO-EA provides regular technical backstopping to the MoA and supervises the DLCO caretaker in Hargeisa | USD 20,000
1.2.2.8 |  | Develop and implement standard progress reporting format for EMPRES member countries | Reporting format distributed to member countries by 03/02 | FAO EMPRES staff, ELOs | [12 empty] | See activity 8.1.1
1.3 |  | Strengthen collaboration between EMPRES/CR and -WR | Areas of collaboration identified and at least 2 joint activities initiated and implemented by 12/02 | FAO EMPRES | [12 empty] | Potential areas: Survey and information systems, training approach, pesticides application technology, introduction of DGPS, field trials on bio-pesticides
1.4 |  | Promote CRC membership of non-member countries of the Central Region | At least one additional non-CRC member country has documented interest to join the CRC by 12/02 | CRC, FAO EMPRES staff
1.4.1 |  | Invite non-CRC EMPRES countries to CRC meetings | High level delegates from ERI and ETH attend CRC meeting by 03/02 | CRC | [13 empty] | USD 4,000
1.4.2 |  | Organize visits to non-CRC EMPRES member countries | At least 1 visit (Eritrea) conducted by 12/02 | AGPP, CRC | [13 empty] | ref. 1.1.2.1
R-2 | National & regional communication network enhanced | I.R-2.1: Timeliness in sending DL reports to DLIS improved 20% by 2001, 50% by 2002, 80% by 2003 | [14 empty] | Assumption: none
I.R-2.2: Fixed radio schedules defined and made standard communication procedures at 5 DL Units by 2003
2.1 |  | Stimulate pro-active attitude in information exchange among stakeholders (national and international) |  | ELOs, FAO EMPRES-staff | [12 empty] | ELOs will establish a communication system among member countries and DLIS.
2.1.1 |  | Introduce regular radio schedules for DL information | Documentation on the national radio networks made available to CRC and EMPRES by 05/02 | ELOs
2.1.2 |  | Provide LCUs with guidelines for regular radio communication | Guidelines developed and circulated by 07/02 | FAO EMPRES staff
2.1.3 |  | Make regular use of email system to inform DLIS, CRC, EMPRES and neigbouring countries of locust and climatic events | At least 1 email contact per month with each of the LCUs registered | ELOs
2.2 |  | Maintain and update communication and radio equipment |  | ELOs, FAO EMPRES-staff | [12 empty] | Unified radio model for further eLocust compatibility
2.2.1 |  | Assist in the establishment of national radio DL information networks | up to 5 additional radio stations installed in DJI and ERI by 11/02 | ELOs, FAO EMPRES staff | [13 empty] | USD 15,000
R-3 | DL early warning and information systems improved | I.R-3.1: RAMSES system installed and being used in at least 5 countries by 2003 | [14 empty] | Assumption: none
I.R-3.2: Remote sensing images incorporated into surveying decisions in at least 2 countries by 2003
3.1 |  | Build up national and regional DL information systems |  | ELOs, FAO EMPRES-staff | [12 empty] | Determination of types and sources of information to assess locust population. Determination of priorities for improved information systems.
3.1.1 |  | Define national information systems, requirements and needs | Saudi Arabia, Eritrea, Ethiopia, Oman, Egypt and Djibouti provided detailed summary to EMPRES and the CRC by 03/02 latest | ELOs
3.1.2 |  | Develop recommendations for improved information systems | Recommendations for improved information systems submitted for approval to the ELOs by 06/02 | FAO EMPRES-staff, DLIS
3.1.3 |  | Implement recommendations | Recommendations implemented at all LCUs by 12/02 | ELOs | [12 empty] | Follow up, NPO-S, DLIS
3.2 |  | National locust information routinely dispatched to DLIS | At least 1 "high quality" report per month and from each country arrived at DLIS ( < 25th of every month) within 5 days after completion of surveys | ELOs | [12 empty] | Reports should be passed to DLIS even if NO surveys been conducted!
3.3 |  | Harmonize DL information systems between CRC, DLCO-EA and DLIS | Regional Organizations alert the countries on special locust events | FAO EMPRES staff, DLIS, DLCO-EA | [12 empty] | In connection with 1.2.1.2 and 3.1
3.3.1 |  | Determine modalities of information management among the stakeholders |  | CRC, DLIS, DLCO-EA, EMPRES | [12 empty] | Topic of the CRC / EMPRES / DLCO-EA joint forum; Refer also to 1.2.1.1
3.4 |  | Incorporate DL data management systems at the LCUs | At least 2 additional LCUs started to make regular use of GIS by 12/03 (Sudan, Saudi Arabia, Oman) | ELOs, FAO EMPRES-staff | [12 empty] | Recording, analyzing survey results. NRI provides assistance in establishing RAMSES (GIS software, training, follow-up).
3.4.1 |  | Provide facilities for data management systems (RAMSES) | To up to 3 countries (Sudan, Saudi Arabia, Oman) by 12/02 | FAO EMPRES staff, CRC, LCUs | [12 empty] | Computer equipment, GIS software. Hard- and software already in place in Sudan | USD 28,000
3.4.2 |  | Train Information Officers on RAMSES | At least 2 national Information Officer trained on RAMSES by 02/02 | NRI | [12 empty] | Regional Information Officer and EMPRES staff should be qualified to assist in follow-up of the use of RAMSES as well as trouble shooting | USD 5,000 NRI training, USD 10,000 for consultancy
3.4.3 |  | Make regular use of RAMSES | Monthly DL reports produced on the basis of RAMSES outputs to the Heads of Department | ELOs | [12 empty] | At present LCUs ERI, ETH and YEM. Information Officers to collaborate with national Meteo Agencies
3.4.4 |  | Support development of case studies on the basis of RAMSES data sets | Case studies available from up to 2 countries ready by 12/02 (Ethiopia, Yemen) | GTZ, DLIS | [13 empty] | USD 10,000
3.5 |  | Introduce new technology including remote-sensing into early warning information system | Up to 3 countries receive SPOT satellite images by 12/03 | DLIS | [12 empty] | AGPP recruits remote sensing experts
3.5.1 |  | Provide extra training and software for use of satellite imageries | All LCUs are provided with according software by 09/02 | DLIS | [12 empty] | AGPP recruits remote sensing experts
3.5.2 |  | Improve collection and transmission of field data | eLocust installed and tested in up to 3 countries by 09/02 | GTZ, DLIS, FAO EMPRES staff | [12 empty] | Sudan, Yemen, Egypt, Eritrea | USD 20,000
3.5.3 |  | Assist countries in the use of modern data transmission technology | Up to 3 countries received backstopping by 12/02 | GTZ, DLIS, EMPRES staff | [12 empty] | Consultant | USD 10,000
3.6 |  | Carry out ground truthing operations | At least 1 ground truthing operations conducted by 09/02 | ELOs, FAO EMPRES-staff, DLIS | [12 empty] | Remote sensing specialist appointed at AGPP; Country to be identified | USD 8,000
R-4 | DL survey procedures of member countries improved | I.R-4.1: Survey plans developed and made integral procedure of the PPD in at least 4 member countries by 2003 | [14 empty] | Assumption: Security and accessibility of breeding areas in the Central Region assured
I.R-4.2: Key breeding areas of at least 2 member countries identified and described by 2003
I.R-4.3: Up to 2 joint border surveys conducted on 2 borders in the Central Region by 2003
4.1 |  | Develop sustainable and targeted survey procedures | At least 4 countries established and make use of survey plans by 12/03 | FAO EMPRES-staff, ELOs | [12 empty] | Records of distribution and densities of locust populations (in collaboration with WU).
4.1.1 |  | Develop reference survey plan for member countries | Final reference survey plan distributed to all member countries by 02/02 | FAO EMPRES staff
4.1.2 |  | Develop and make use of national survey plans | National survey plans developed and implemented in at least 3 additional countries (Yemen, Saudi Arabia, Egypt) by 06/01 | ELOs, FAO EMPRES staff | [12 empty] | EMPRES to assist member countries in the process
4.1.3 |  | Follow up use and handling of national survey plans | Up to 3 assessment visits by 11/02 | FAO EMPRES staff | [12 empty] | Eritrea, Egypt, Saudi Arabia
4.1.4 |  | Conduct workshop on improved survey procedures | 1 regional workshop conducted in Port Sudan by 11/02 | FAO EMPRES staff, WU | [12 empty] | In collaboration with WU | USD 20,000
4.2 |  | Define and describe potential breeding areas in the Central Region | At least 3 high frequency breeding areas are described and outputs incorporated into RAMSES and SWARMS GIS by 12/02 | FAO EMPRES-staff | [12 empty] | Records of delimitation and ecology of important breeding areas, historical records and meteorological / remote sensing data - should enter also into national the survey plans.
4.2.1 |  | Take inventory of DL high frequency and distribution habitats | Inventory compiled from at least 3 countries by 12/02 (report) | FAO EMPRES-staff | [12 empty] | Sudan, Yemen, Eritrea | USD 10,000
4.3 |  | Carry out joint surveys | 2 joint surveys conducted by 2003 | ELOs, FAO EMPRES-staff, CRC, DLCO-EA | [12 empty] | Other than Egyptian - Sudanese border
4.3.1 |  | Conduct joint border surveys | Up to 2 surveys conducted between Saudi Arabia - Yemen, Djibouti - Somalia by 09/02 | CRC, EMPRES staff, ELOs S.A., YEM, DJI, SOM | [12 empty] | up to 3 participants also from non-EMPRES CR countries participate in 2002 and 2003 | USD 15,000 (2002)
4.3.2 |  | Conduct joint in-country surveys | 1 In-country survey in Eritrea between Eritrean and Sudanese participants by 12/02 | ELOs Sudan, Eritrea | [12 empty] | For Sudanese and Eritrean participants only | USD 10,000
4.4 |  | Strengthen self-reliant survey capacity in Somalia | MoA and NGO staff are competent to conduct surveys and report on DL events in Somalia by 12/03 | FAO EMPRES-staff, DLCO-EA | [12 empty] | DLCO staff is capable to provide technical backstopping
4.4.1 |  | Develop survey plan for Somalia | Survey plan developed and submitted to DLCO for implementation by 06/01 | FAO EMPRES staff, DLIS
4.4.2 |  | Organize and carry out regular surveys | At least 6 surveys carried out per year in northern Somalia | DLCO-EA | [12 empty] | EMPRES provides operational support | USD 15,000
4.4.3 |  | Supervise and backstop survey and reporting operations | High quality reports regularly sent to DLIS and EMPRES | DLCO-EA | [13 empty] | USD 5,000
4.5 |  | Support national survey teams | Vehicles, computer equipment, field material, camping equipment provided to selected CRC countries by 2003 | CRC, GTZ | [12 empty] | Vehicles: Sudan, Jordan, Syria (2002), Egypt, Lebanon (2003); Field equipment: Iraq, Jordan, Kuwait, Lebanon, Bahrain, Qatar, Syria, U.A.E (2002); Camping equipment: Jordan, Lebanon, Sudan, Syria, Yemen (2003), Computer equipment: Yemen (2002) | USD 90,000 (2002); USD 55,000 (2003)
R-5 | DL technicians and officers qualified | I.R-5.1: At least 50 % of DL technicians trained in each CR country by 2003 | [14 empty] | Assumption: Political conditions and / or infrastructure permits equally conducted programme activities
I.R-5.2: At least 2 trainers trained according to agreed standards for each country by 2002
5.1 |  | Define training standards | Training standards defined and implemented in at least 3 countries by 04/02 | FAO EMPRES staff, CRC, DLCO-EA | [12 empty] | Standard level (criteria) of knowledge and technical skills trainees should know after the training.
5.2 |  | Define training needs on technical DL subjects at different levels | Training need in at least 5 countries (Sudan, Eritrea, Ethiopia, Yemen, Egypt) is known to CRC and EMPRES by 12/02 | ELOs, FAO EMPRES staff | [12 empty] | Subjects: survey and control operation, forecasting and information management. Including: staff situation, positions, plant protection technicians etc.
5.3 |  | Develop training curricula / manuals for ToT-courses | In English and Arabic, ready and introduced as training aids by 12/03 | FAO EMPRES staff | [12 empty] | In collaboration with NRI
5.3.1 |  | Prepare draft training manual | Draft ready by 08/02 and submitted to AGPP for approval | NRI | [12 empty] | Consultant | USD 20,000
5.4 |  | Assist universities in DL curricular development | At least 6 students enrolled at Univ. Khartoum per year | Uni Khartoum, DLCC, CRC | [13 empty] | roughly USD 20,000 per non-national student
5.4.1 |  | Support DL Diploma course at the University of Khartoum | At least 6 additional students are enrolled by 08/02 | Uni Khartoum, CRC, FAO EMPRES staff | [12 empty] | Scholarships provided by DLCC and CRC. Students should be involved in different field studies and other relevant investigations (Subjects: population biology, -dynamics etc.). | USD 120,000
5.4.2 |  | Support MSc fellowships | At least 1 MSc student supported by 10/02 | DLCC, CRC
5.5 |  | Organize various training courses at different levels | 1 international ToT seminar (2002), 1 regional S&C course (2003) | CRC , FAO EMPRES-staff | [12 empty] | Regional S&C training course conducted with selected Mastertrainers from the member countries
5.5.1 |  | Conduct international ToT training course | 1 ToT course in Oman by 05/02 | AGPP, NRI | [12 empty] | Course supported by CRC and EMPRES/CR | USD 30,000
5.5.2 |  | Conduct national S&C training courses | In up to 6 CRC / EMPRES/CR member countries | ELOs | [12 empty] | LCUs incorporate specialized locust training courses in their own national training programmes and will be able to maintain such system by 2003. Assistance to conduct the training courses will be provided from CRC / EMPRES upon request from the LCUs only. | USD 30,000
5.5.3 |  | Conduct local S&C training courses | In at least 3 member countries are organized for farmers, scouts and nomads by 12/02 | ELOs | [12 empty] | Organized by the LCUs for assistant staff, scouts, nomads. FAO-EMPRES staff may assist upon request.
5.5.4 |  | Provide on-the job-training for information and forecasting officers | Up to 3 Information Officers trained by 12/02 | DLIS | [12 empty] | During visits of DLIS Forecasting Officer | Travel costs DLIS: USD 4,000
5.5.5 |  | Organize campaign management and evaluation seminar | 1 regional seminar conducted by 12/02 | FAO EMPRES staff, CRC | [12 empty] | Consultant | USD 15,000 Consultant; USD 10,000 Course Cost
5.6 |  | Develop and introduce regular training impact mechanisms | Impact evaluation carried out by 2003 | LCUs, FAO EMPRES-staff | [12 empty] | Monitoring against agreed standards (see 5.1). ELOs should provide reports on training impact during the annual ELOMs.
5.6.1 |  | Develop standard training impact assessment guidelines | Guidelines developed and circulated by 08/02 | FAO EMPRES-staff, ELOs | [12 empty] | Consultant | USD 5,000
R-6 | Contingency plans available and implemented | I.R-6.1: National contingency plans for recession monitoring and control for outbreak, upsurges and plagues adopted in up to 6 countries by 2002 | [14 empty] | Assumption: none
6.1 |  | Introduce national contingency and rapid deployment plans into the locust management system |  | LCUs, FAO EMPRES staff | [12 empty] | CPs cover scenarios from recession to plague situation incl. needs for manpower, equipment, supplies and operational funds, and monitoring. Modeling tool reviewed and introduced by WU.
6.1.1 |  | Conduct regional Contingency Planning seminar | 1 CP seminar conducted by 03/02 | AGPP, FAO EMPRES staff, CRC | [12 empty] | Consultant | Consultant USD 10,000; Course Cost USD 20,000
6.1.2 |  | Review Contingency Planning Guidelines | Reviewed guideline ready by 12/02 and circulated | FAO EMPRES staff | [12 empty] | Consultant | USD 5,000
6.1.3 |  | Develop rapid deployment plan for aerial interventions in the CR | Aerial deployment plan ready and circulated by 12/02 | DLCO-EA | [12 empty] | Plan to be submitted to AGPP, EMPRES and CRC
6.1.4 |  | Adopt and implement contingency planning and rapid deployment approaches at national level | At least 3 national contingency plans adopted and implemented at national level by 10/02 | ELOs, FAO EMPRES staff | [12 empty] | Other member countries than SDN should undertake efforts to draft national contingency plans
6.1.5 |  | Re-activate national steering committees | Up to 3 of the member countries created national CP steering committees by 10/02. FAO to be informed of the constitution and mandate. | MoAs, ELOs | [12 empty] | Composition: LCU, PPD, MoA, local governments, MoF, Meteo Agency. Assess the locust situation. Review the likely origin of resources needed to implement CPs to assure that supplies can be made available at short notice in case of emergencies. State preparedness and prepositioning of resources. | (1) Recession: National responsibility. (2) Upsurge - Outbreak: National and EMPRES responsibility. (3) Plague: National and international community
6.2 |  | Allocate funds for emergency pesticide stock | Funds allocated by 09/02 | CRC | [13 empty] | USD 100,000
R-7 | Efficient and environmentally safer control methods introduced | I.R-7.1: At least 1 new additional control technology introduced in at least 3 countries by 2003 | [14 empty] | Assumption: Locust infestation permits field trial
7.1 |  | Facilitate development of and testing of new technologies taking into account human health and the environment | Recommendations on environmentally safer campaign operations formulated by 2003 | MoAs, FAO EMPRES staff, CRC | [12 empty] | Subjects: Mycopesticides, PAN, barrier treatment, IGRs; Registration process to be fostered; Assessment of environmental impact.
7.1.1 |  | Conduct various field trials on selected technologies | At least 1 technology tested at least semi-natural conditions by 10/02 | FAO EMPRES staff, GTZ, ELOs | [12 empty] | In collaboration with potential national and international institutions and EMPRES/WR | USD 50,000 (ICIPE re. PAN); USD 50,000 other trials
7.1.2 |  | Organize field workshops on new control methods and products | Up to 2 demonstrations conducted by 12/02 | GTZ, ELOs | [12 empty] | In collaboration with ICIPE and LUBILOSA staff and EMPRES/WR | USD 20,000
7.1.3 |  | Test new spray equipment and suggest improvements | 1 workshop conducted in Cairo by 07/02 | AGPP, FAO EMPRES staff, CRC, NRI, Companies | [12 empty] | Consultant; Panel from CR: Oman, Sudan, Yemen, Saudi Arabia | USD 20,000
7.1.4 |  | Introduce DGPS technology for aerial pesticide application | Up to 2 DGPS sets installed and demonstrated (1 Saudi aircraft and 1 DLCO-EA aircraft equipped) by 12/03 | FAO EMPRES staff, CRC, DLCO-EA, LCU Saudi Arabia | [12 empty] | Participation form CRC countries in the demonstration | USD 40,000
7.2 |  | Assess environmental impact of locust control operations | Ecological sensitive areas in at least 1 member country identified by 2003. The hazardous effect of pesticides on locust operators reduced by X % by 2003. | FAO EMPRES staff, DLCO-EA
7.2.1 |  | Carry out blood testing programme | Blood testing survey conducted in at least 2 countries (Eritrea and Sudan) conducted by 09/02 | FAO EMPRES staff, DLCO-EA, ELOs | [13 empty] | USD 5,000
7.2.2 |  | Identify and describe ecological sensitive areas | At least 2 sensitive areas are described by 12/02 | FAO EMPRES staff | [13 empty] | USD 10,000
7.3 |  | Support operational research projects | Up to 6 additional projects initiated and implemented by 12/02 | FAO EMPRES staff, CRC | [12 empty] | Cost-shared between EMPRES and CRC, limit USD 15,000. | USD 90,000
7.4 |  | Promote the use of proven technologies | Import permissions for metarhizium anisopliae from up to 3 member countries obtained by 2003 | MoAs, FAO EMPRES staff, CRC, DLCO-EA
7.4.1 |  | Follow up registration process of metarhizium products in Sudan | Significant progress made towards registration of metarhizium in Sudan by 12/02 | ELO Sudan
7.4.2 |  | Promote registration process in Eritrea | Significant progress made towards registration of metarhizium in Eritrea by 12/02 | ELO Eritrea
7.4.3 |  | Analyze the genetic make-up of Eritrean metarhizium isolate (ER-1) | Genetic correspondence known by 12/02 | ELO Eritrea, FAO EMPRES staff | [12 empty] | LCU Eritrea makes sample of ER-1 available for testing | USD 5,000
7.4.4 |  | Develop guidelines for barrier treatment | First draft ready by 12/02 | AGPP, GTZ, EMPRES staff | [12 empty] | Consider biotic and abiotic factors | USD 3,000
7.4.5 |  | Promote phasing out of ENS | Remaining countries submitted inventories of ENS and vehicle mounted ULV sprayers in CRC and EMPRES by 06/02 | ELOs | [12 empty] | Egypt, Ethiopia, DLCO-EA
7.4.6 |  | Prepare guidelines for good spraying practices | Guidelines prepared and circulated by 10/02 | FAO EMPRES staff, CRC, DLCO-EA
7.4.7 |  | Incorporate spray monitoring form in eLocust programme | eLocust programme modified by 12/02 | DLIS | [13 empty] | USD 3,000
7.5 |  | Support national control teams | Up to 2 vehicle mounted ULV sprayers and up to 5 hand-held ULV sprayers each provided to selected countries by 12/02 | CRC, GTZ | [12 empty] | Vehicle mounted sprayers: Egypt, Djibouti, Sudan. Hand-held sprayers to all CRC countries | USD 55,000
7.6 |  | Provide LCUs with DL references | Various DL reference distributed to the LCU in the CR by 12/03 | CRC, AGPP, GTZ, EMPRES staff | [12 empty] | Literature CD ROM, Video tape, Reference books, FAO Guideline in Arabic language | USD 17,000
R-8 | Systematic method of campaign evaluation developed | I.R-8.1: Two economic case studies conducted by 2002 | [14 empty] | Assumption: none
I.R-8.2: Models to identify efficient control strategies via scenarios completed by 2003
8.1 |  | Develop suitable campaign evaluation mechanisms |  | FAO EMPRES-staff, WU | [12 empty] | More quantitative data on DL key parameters required (See also Result 3 and 4), e.g. DL population estimates, extent of breeding, spatial distribution, relation to vegetation, control efficiency and impact etc.
8.1.1 |  | Develop and circulate reporting format for use by ELOs | New reporting format on EMPRES progress at national level finalized and in use by ELOs by 06/02 | FAO EMPRES staff
8.1.2 |  | Review baseline document on current campaign organization and practice in the CR | Review completed by 06/02 | FAO EMPRES staff | [12 empty] | Consultant | USD 5,000
8.1.3 |  | Review discussion paper on improved preventive control strategies | Review completed by 12/02 | FAO EMPRES staff | [12 empty] | Consultant | USD 5,000
8.1.4 |  | Apply new version of spray monitoring form | Spray monitoring form used by all LCUs on routine basis during DL campaigns by 10/02 | ELOs
8.2 |  | Analyze socio-economic impact of campaigns | (1) At least 2 case studies conducted by 2002 (2) ELS Model up-dated by 2002 | FAO EMPRES staff (Uni Hanover / Uni Gothenburg) | [12 empty] | Farmers reaction on DL infestation, possible impact of DL damage.
8.2.1 |  | Conduct socio-economic case studies | 1 case study on farmers' reaction on locust plagues conducted in Egypt by 12/02 | FAO EMPRES-staff | [12 empty] | Consultant | USD 15,000
8.2.2 |  | Up date economic impact assessment computer model | ELS model up-dated by 12/02 | FAO EMPRES-staff | [12 empty] | Consultant
8.2.3 |  | Liaise with bilateral institutions carrying out socio-economic studies |  | FAO EMPRES staff | [12 empty] | Bilateral institutions keep EMPRES informed of the results
8.3 |  | Investigate scenarios on survey and control operations to improve strategies | Computer base model reviewed and introduced by 2002 | FAO EMPRES staff, WU | [12 empty] | (See also Result 6) Events of DL development, extent and impact of control operations, environmental effects etc. Aim: formulation of improved preventive control strategies.
8.3.1 |  | Review and up-date campaign simulation model for control studies | Ready on CD ROM for campaign and contingency planning by the LCUs by 12/02 | WU | [13 empty] | USD 5,000
Acronyms and Legends:
| CRC: | FAO Commission for Controlling the Desert Locust in the Central Region
| DLCO-EA: | Desert Locust Control Organization for Eastern Africa
| DLIS: | Desert Locust Information Service of FAO (AGPP)
| ELO: | EMPRES Liaison Officer
| GTZ: | Deutsche Gesellschaft fur Technische Zusammenarbeit
| LCU: | Locust Control Unit
| NRI: | Natural Resources Institute
| MoA: | Ministry of Agriculture
| WU: | Wageningen University
Continuous long-term activity beyond 2002 Work Plan:
Short-term "routine" activity restricted to 2002 Workplan:
Short-term "key" activity restricted to 2002 Workplan:
Milestone: