WFP/EB.1/2008/7-B Summary of Summary Evaluation Report Columbia PRRO

For consideration

Draft Decision

The Board takes note of “Summary Evaluation Report Colombia PRRO 10366.0” (WFP/EB.1/2008/7-B) and encourages further action on the recommendations, taking into account considerations raised by the Board during its discussion.

Background

The goal of the PRRO was to protect and stabilize the livelihoods of IDPs and enhance their resilience to shocks, through two complementary strategies. The relief component, at 38 percent of the budget, provided assistance through general food distributions to newly displaced IDPs, longer-term IDPs identified as food-insecure, confined and blockaded communities, and non-registered IDPs, who were not reached by other major donors. The recovery component, at 62 percent of the budget, assisted: primary schoolchildren and pre-school children aged 3 to 6 through school and pre-school feeding; pregnant and lactating women, their children under 2 years and children at nutritional risk, through targeted supplementary feeding as take-home rations; and other vulnerable communities in need of rebuilding their livelihoods, through food for work (FFW) and food for training (FFT). (Par.3)

This mid-term evaluation was carried out in February and March 2007. During a three-week mission, 6 departments and 53 projects were visited, 10 meetings were held with implementing partners and WFP staff, and more than 25 key informants were interviewed in Bogotá. The evaluation team was composed of four external consultants and supported by a WFP evaluation officer. (par. 4)

Relevance

Overall, the protracted relief and recovery operation (PRRO) was highly relevant to the needs of Colombia’s IDPs. The relief component offered immediate assistance in the aftermath of IDP displacement and the recovery component offered a flexible response to evolving IDP needs in the months following displacement. (par. 5)

Each programme component was found appropriate in varying degrees and for different reasons (par. 7):

-Relief was highly relevant in proposing appropriate programme modalities to address the needs of IDPs when they were at their most vulnerable. Given WFP’s corporate mandate, the evaluators regarded the fulfilment of relief as a priority.

-School feeding was appropriate in helping IDP children to reintegrate into society. It constituted a suitable follow-on activity for the relief-to-recovery continuum.

-Pre-school feeding was appropriate in providing support as IDP children moved beyond immediate post-displacement. This component may have been handicapped by a lack of clarity as to whether its objectives were educational, nutritional or both.

-The vulnerable group feeding components — assisting pregnant and lactating women, their children under 2 and children at risk of malnutrition — was relevant to the particular needs of these target groups.

-FFW and FFT provided an appropriate response to evolving IDP needs in a wide variety of livelihood recovery activities.

Performance of the PRRO

The Strategic Objective formulation of the PRRO was directed exclusively to livelihoods. This was not fully appropriate in current Colombian conditions, in which nutrition and education goals could also have been included. Shortcomings in the design of the logical framework limited its usefulness in helping the country office recognize which programme components to prioritize and which to scale down or focus differently. (par. 8-9)

The current PRRO made important operational improvements on the previous one. The entire logistics operation seemed to be running efficiently: food losses were nearly eliminated, in spite of the real danger of delivering food in many areas; and local food purchases were an important programme innovation. However, a significant pipeline break in late 2006, caused by a funding default, resulted in major disruption to beneficiaries, implementing partners and sub-office operations. (par. 15)

Regarding partnerships, the PRRO demonstrated joint ownership between WFP and government agencies. The introduction of a mechanism to provide recommendations on project proposals, based on a tripartite regional committee, was a good innovation. Implementing and community-based partners appeared to work well with WFP, but had uneven capacities for quality performance. Although the benefits of local interaction between WFP and its implementing partners were recognized, there was concern regarding the high number of partners. This stretched the country office’s supervision capacity, thus increasing the risk of political influence affecting some projects. (par. 17)

Connectedness

WFP’s strong links with government counterparts fostered the latter’s assumption of larger roles in responding to the IDP crisis. However, even assuming that the Government could take full financial and implementation responsibility for a US$50 million IDP programme, political realities implied that there were large segments of the IDP population that would not be reached. One of the objectives of the next operations might be to create a management model for a PRRO that could be run by the Government and executed by implementing partners within a set time. Developing a time-bound and specific exit strategy was not necessarily relevant in Colombia, where the IDP situation was likely to deteriorate in the foreseeable future. (par. 21)

Results

The effectiveness of component activities varied, but overall they exceeded target numbers. Relief beneficiaries were 122 percent of the 18-month target; school feeding reached 100 percent of the two-year target; pre-school feeding reached 113 percent of the target; pregnant and lactating women, 135 percent; FFW, 155 percent; and FFT, 156 percent. Only children at risk reached less than target, at 94 percent. Substantial over-accomplishment in all but one component and 129 percent accomplishment of the overall PRRO goal, compared with only 68 percent of budgeted food resources, suggested that the ration was being “economized” by distributing fewer months of food to reach more beneficiaries than called for in the programme design.(par. 22)

Other important effects were observed. Several communities in the most dangerous areas spoke of WFP’s presence enhancing their sense of physical protection; this was especially the case for communities at risk. PRRO -supported community-based activities had probably created and enhanced social cohesion − a particularly noteworthy result following the psycho-social disintegration caused by displacement. There were reports of unanticipated psychological benefits accruing to programme beneficiaries because of implementing partners’ integrated, holistic programming. There was widespread recognition that WFP efforts had contributed to raising awareness about IDP issues at the national level. At the local level, key informants noted that the PRRO indirectly contributed to “creating a humanitarian space ceded by the armed groups”, which did not exist prior to WFP’s arrival in the zone. (par. 28)

Future Considerations

The current PRRO was fully appropriate to the humanitarian situation in Colombia, and according to most interviewees the IDP focus would likely remain valid for the foreseeable future of five to ten years. Regarding whether WFP should engage in higher-profile advocacy, real trade-offs must be carefully weighed. A more politicized discourse at the national level could compromise the collaborative relationships seen in the field and the current recognition of WFP as a neutral party. This could have a negative impact on WFP’s secure access to needy populations. In addition, it seemed likely that the prospects for lasting peace were not good in the medium term, so only a limited number of additional activities could be taken on without over-burdening the programme. (par. 29)

The evaluation touched on the following policy questions: (i) Regarding the role of WFP in supporting the Government of Colombia’s efforts to improve IDP lives, how much of the programme should be assumed by the Government? (ii) Regarding a rapid, timely response to IDPs, and in view of the actions taken so far, to what extent could the Government be expected to improve its efficiency? and (iii) What is the value added by food aid compared with other possible modalities of support for non-relief interventions? Answers to these questions will involve complex policy discussions between WFP and the Government of Colombia while the next PRRO is prepared. (par. 30)

Recommendations

The Recommendation Matrix and Management Response are annexed in the original document.