WFP/EB.2/2009/6-G SUMMARY EVALUATION REPORT REPUBLIC OF THE CONGO PRRO 103121

Description of the Operation

The PRRO lasted for 24 months at a total cost to WFP of US$10.4 million. The goal was improved food security and socio-economic recovery of affected people. [par.4]

Planned recovery components: FFE, HIV, FFW and capacity development. [par.7]

PERFORMANCE HIGHLIGHTS

Operation design: Relevance and Appropriateness

- Using FFW to rehabilitate damaged infrastructure for food-insecure segments of the population was appropriate.

- FFE was an appropriate response to attempt to reverse this downward school enrolment trend.

- HIV/AIDS components was appropriate [par.11]

Country office could not met planned distribution due to pipeline breaks and transport difficulties for the first have of 2008. WFP delivered 7% of planned tonnage in 2007 and 13% for 2008. FFW activities were directly linked to the capacity of NGOs which has been weak. [par.16-18]

Results

It was difficult to assess results of the FFW component given the weak reporting. FFW operations were too dispersed geographically and through multiple partners, and seem to have been driven by a demand-side approach rather than a coherent prioritized vision of what WFP’s country office should be doing. [par.27]

Regarding the HIV/AIDS component, no study has been conducted to establish the comparative advantages for people assisted by WFP in relation to unassisted people. [par.28]

The main objective of the FFE component was to increase attendance particularly of girls in WFP-assisted schools. No study had been conducted to establish the comparative advantage of WFP-assisted schools against non-assisted schools. Data generally indicated that in most schools where FFE was implemented there had been a general increase in school enrolment. It is, however, difficult to attribute this improvement to FFE alone because it is in line with the general trend throughout the country. [par.29-30]

Cross-Cutting Issues

The evaluation team discovered that components distributing household rations – FFW and PLHIV – did not have reliable gender-disaggregated data on beneficiaries. [par.32-33]

CONCLUSIONS AND RECOMMENDATIONS

Overall Assessment

- There were major constraints to implementing the FFW component at the level envisaged in the PRRO design, not least of which was the lack of a robust food pipeline.

- WFP’s activities when implemented were well received.

- More constant monitoring could have helped isolated areas

- The HIV/AIDS component also suffered from irregular food distributions.

- The Government of the Republic of the Congo’s commitment to school feeding is high.

- Strong partnerships must be established to ensure that interventions create a sustainable hand-over. [par.34-39]

Issues for the Future

- Moving to higher-level results analysis should be the goal.

- It will be necessary for the Government to systematize nutrition education in health centres and to organize nutritional assistance for PLHIV in each hospital as an integral part of ART support.

- WFP must take all necessary measures to ensure that the logistics obstacles faced in the Republic of the Congo are analysed and addressed. [par.40-42]

Recommendations

- Consolidate the types of activities supported by FFW

- FFW activities should complement the other activities being supported

- It is essential that coordination and cooperation mechanisms are in place and truly functional

- It is essential to overcome the logistics obstacles [par. 43-46]