# Appendix 8

Minutes of the debriefing meeting of the Mid-term evaluation mission for the  Integrated Horticulture & Nutrition Development Project (BGD/97/041), Department of Agriculture Extension, Ministry of Agriculture

Draft

The meeting was held on 18th May 2003 at 2:30 PM under the Chairmanship of Joint Secretary, Ministry of Agriculture (MOA). The list of participants of the meeting is enclosed (Annexure-I).

The Chairman welcomed the participants and requested to introduce themselves. After the introduction he requested the team leader to proceed with his presentation.

Team leader of the mid-term evaluation mission Dr. Eduardo Quiroga presented draft mission report. He reported that, the evaluation was to assess systematically and objectively the relevance, performance and success of the project interventions, within the result oriented framework. The mission commenced on 28th April 2003 and conducted field activities from 1 to 9 May, 2003. The mission was composed of 6(six) member of which 4(four) from GOB, one from FAO and the team leader from UNDP. The mission reviewed all relevant documents and interacted with the beneficiaries in 14 HDTC’s.

Dr. Quiroga informed that the project meets the needs of the direct beneficiaries and addresses the learning requirement of landless and deprived women of rural households. Nearly 16,000 women from landless households have been successfully organized in groups. They have also accumulated savings. There are 987 farmer groups that have opened bank accounts with savings reaching Tk. 1,880,100. Farmers have manifested satisfaction with their voluntary associations. Besides nutrition education, they are learning new production and post-harvest technologies with potential for better income. Women’s social mobility and participation in household and community activities has increased. This has actively empowered women and has boosted their self-esteem.

A critical mass of manpower in the field of horticulture is being developed and upto December 2002, 1420 field level officials were trained in 11 different courses. 15350 farmers were also trained in 16 different subjects.

Nutritional awareness raising campaigns and 48 food preparation demonstrations were conducted.

Besides, 1375 vegetable nutrition garden, 7 high density banana, 31 high density litchi, 36-high density mango, 48 mushroom, 6 post-harvest and 45-household level processing and fruit village demonstrations were established/conducted.

A good number of Mother tree orchards, clonal hedges were established in all 15 HDTC, 80,000 elite planting materials of fruits & quality planting materials.

The mission made the following recommendations.

Recommendations:

- The current number of existing groups should be strengthened rather than expanded. Technical training to beneficiaries in horticultural production systems and home-based food processing should consolidate acquired knowledge and become market oriented and marketing driven. Within the participatory framework, each HDTC should consider drafting its own business plan for the remainder of the Project considering farmers’ needs, physical production potential, actual production capability, credit requirements. Taking into account of all these factors, the type and length of technical assistance will be determined & also the HDTC objectives & targets for the remained of the project can be drafted.

- Consider training in literacy and numeration for all members not yet functionally literate.

- For the remainder of the project, the technical assistance must be field oriented and conduct its work with the participation of the direct beneficiaries & extension staff.

- The training manuals must be suited to convey the message to the functionally literate farmer & be laminated.

- Where opportunities arise, institutional collaboration should be organized with civil society, especially in the areas of crop production & marketing, credit & sustainability issues.

- A result-oriented monitoring procedure, to measure the Projects management operations & activity execution of the 15 HDTC’s business plans, must be in place as soon as possible. A logical framework analysis should be conducted for each of the HDTC & the Project as a whole & it should be updated.

- Organise farmers club after the IPM clubs in order to embedding the knowledge within the rural communities and Identify natural leaders in the rural community in order to achieve dynamic sustainability. DAE can organise farmers day twice a year in maintaining sustainability efforts of IPM & future horticulture clubs.

- The GOB should consider furnishing the Rangamati HDTC and filling several other personnel requirements and equipment for other HDTCs.

- For the remainder of the Project, it will be vital to ensure the continuity of the national personnel in order to ensure successful results.

- When the forthcoming UNDP guidelines for national execution (NEX) are issued consider preparing a new workable management framework encompassing the management of the 15 HDTCs.

- After the formulation of the 15 work plans for the HDTCs, as the number of activities may increase as compared to the present context, consider reviewing the budget to ensure successful results.

- The UNIA management of technical assistance component should ensure greater results in monitoring and in coordination with key stakeholders. Consultants reports, including backstopping visits, should circulate rapidly among end-users, no more than 10 working days after consultants’ departures.

- The project should concentrate on capacity development through situational analysis of the constraints to building this capacity within the context of each HDTC. Requests for technical assistance should emerge from end users. The UNIA must deploy hands-on efforts to ensure that technical assistance is participatory and field oriented. All consultants’ recommendations have to be validate by consultants with end users before their departure.

- Provided allocated funds permit, the term of senior Horticulture program Development Expert should be extended to cover the project time horizon. If there a felt need for further work of Nutrition Education specialist an extension of his/her duties can be considered. The project will benefit if separate consultants on Food processing, Post harvest technologist, plant Propagation & Tissue culture specialist could be fielded. Provision for unspecified consultant can be fixed for 6 m/m instead of 2 m/m.

After the long presentation was over the chairman requested opinions from the participants.

Mr. Anwor Iqbal representing BARC wanted to know about the method of institutionalising the present effort, knowledge and activity at the end of the project when there will be no consultants & fund. He proposed to establish linkage with other similar projects like NNP, Government bodies & NGOs.

In his reply Mr. Quiroga stated that the proposed strategy of sustainability is to organise Horticulture club in the from of IPM club. He further stated that at present linkage with NGO is there but it must be strengthened in a way Milk vita is linked up with milk producers group.

Deputy secretary (Extension) MOA questioned about the need of training on literacy and source of resource for such training since it not included in the TAPP.

Mr. Quroga replied that for successful marketing and income generation farmers must know to read and count properly. BRAC has developed an innovative method of adult education which is acclaimed by many people around the world. The project may adopt such method.

Director, BAN-HRDB, Mirza Altaf Hossain asked the mission whether they have observed any positive indication of increased consumption of horticultural crops and nutritional status of the mother & children due to project intervention. He also proposed for undertakeing collaborating program with Health ministry.

Mission leader replied that at present there is no indication that project farmers are producing enough surplus vegetables & spices but their skill & knowledge have certainly developed. However consumption will not be a difficult issue to address, if adequate production is there, but marketing will be a big problem if proper planning is not done.

FAO representative in her remark pointed out that business plan for horticultural centres may not be a realistic idea and will be difficult to implement. The project has got two component one is horticulture & the other is nutrition. Therefore proper attention on the nutrition component should be given. She also mentioned that the project has initiated various technical program like planting material production, MTO, mushroom & post harvest handling but should we need to change our focus from technology transfer to run HDTC on semi  commercial basis. She pointed out that the business action plan may be prepared for the beneficiaries, considering the women farmer. They will basically consume nutritious  vegetables & food produced by themselves & the surplus will be sold to the market for supplementary income generation.

Mr Quroga replied that awareness raising on nutrition is required & the project has trained more one thousand person. But the biggest challenge what the project may face in future, if only production is considered, considerable loss of produces will take place due to the nature of their high perishability if business plan is not made. The proposed business plans will be for the farmers not for the HDTCs. This is in line with the UNDP’s goal of poverty reduction. Therefore we recommended for the business plan.

The representative of National Nutrition Project stated that in the report the magnitude of achievement was not mentioned against the target as a result the success of the project could not measured in terms of data & figures. However the nutritional assessment of such a project at this stage is premature.

Deputy Resident Representative of UNDP agreed with the comments of some of the participants on making the report complete by providing required figures with empirical findings and quantifiable out come, against the success criteria and indicators. He also pointed out that use of resources, efficiency of project should also be adequately high lighted in the final report. In general, he agreed with the recommendation of the evaluation report, its proposal on business plan & to follow result oriented monitoring approach.

Program officer, UNDP, in her comment stated that in principle the comments and recommendations are agreeable. But the evaluation should have focused on such issues like efficiency of project management and project delivery. In the mean time  40% of time has elasped but 23% of fund has been spent but what is the real outcome, where we stand & where we go should go were not indicted in the report. Outputs should be measured against indicators.

FAO’R taking floor stated that, the project is a technology transfer project targeting different type of beneficiaries. Technical approach of the project & other related issue should be considered in future action plan and any business plan if required to be prepared should focus on beneficiaries.

Chairman of the session, in his concluding remarks told that, the discussion was in depth and fruitful. He thanked the mission leader for the mission report and participant for their valuable suggest on the report.