ANNEX 1

Terms of Reference

Mid-Term Evaluation

BGD/97/041: Integrated Horticulture and Nutrition Development Project

# Introduction

With a population of around 140 millions Bangladesh is the 8th most populous nations in the world. Nearly 84 percent of the total population live in rural areas and are directly or indirectly engaged in a wide range of agricultural activities.

The share of agriculture in the country’s GDP declined from about a 50% during the 1970s to 30% in the late 1990s. Within this, crops contribute 71% of the agriculture sector, (livestock 9%, fisheries 10%, and forests 10%) Agriculture sector generates employment for about 63 percent of the labour force. In 2001-2002 agricultural exports of primary products constituted 9.4 % of total exports of the country.

Lack of required capital, inadequacy of appropriate technology, post harvest loses, uncertainty of fair price for agricultural commodities, and limited knowledge of the population about nutrition  (including fruits and vegetables) are considered as major constraints for food security sector. On top of this, the availability of cultivable land is decreasing. Only 2.5 % of the land is under permanent crop and other mainly occupied by rice and wheat crop. Horticulture (including vegetables) represents only 5% of the total area. In fact, horticultural sector has been relatively neglected and relegated to play a minor role in food production, as the priority is being given to cereal and staple substitute production in the attempt to achieve self-sufficiency.

## Background

Most of the problems in the horticultural sector are closely linked to the agricultural production systems prevailing in the country. Farmers, traditionally engaged in rice based farming systems, are reluctant to take risks by changing the system. In addition, priority is given to the staple crops. The constraints facing the horticultural production sub-sector are numerous: seasonal fluctuations in fruits and vegetable production with low productivity, limited availability of improved varieties of fruits, vegetables and spices, lack of access to quality planting material, lack of knowledge among the farmers in the use of improved production techniques and crop practices, plant protection systems, insufficient technologies, research outputs and post harvest and marketing related problems.

Malnutrition remains a serious health concern in Bangladesh. The direct victims are the children and women. Despite number of programmes undertaken to improve the situation, a 56% of prevalence of child malnutrition, and a 96‰ under-five mortality rate, reflect the food and nutrition insecurity in Bangladesh. This is considered as a direct consequence of limited access and availability to nutritious foods, due to poverty. Moreover, there is a lack of nutrition education, which also leads to an alarming lowering of nutritional standards among a major section of the population.

In this context, in its fifth Five-year Plan (1997-2002) and three years rolling plan (2002-2004) the GOB pledged to increase both production and productivity of horticultural crops. It was envisaged to facilitate the production of profitable high value cash crops together with major fruits and vegetables on a year round basis. While commercialising these products through application of appropriate technology, priority was to be given to quality and quantitative improvement of these commodities. Improvement in nutrition should go along with the efforts to enhance production.

## IHND project

UNDP funds the BGD/97/041-integrated horticulture and nutrition development project with the objective of improving the food and nutrition security situation by increasing the availability of food on continuous basis to supplement the national effort towards self-sufficiency and arrest the endemic malnutrition situation through the horticultural crop production. The project is meant to enhance the level of food-security and nutrition by improving the efficiency of the horticultural production system and associated support services such as marketing, processing, post harvest lost preventions etc. through the application of modern technology transfer programmes, and diversified cropping patterns, that will promote the production and the productivity and higher incomes to the small and marginal farming communities in a sustainable manner. The project is also designed to improve the nutritional status of the targeted beneficiaries through creating an environment in which households have increased the nutritional awareness and get sufficient access to fruits and vegetables at affordable prices throughout the year.

### The immediate objectives

The immediate objectives of the project are:

- To develop sustainable capability among low income communities, specifically poor women farmers, in increasing productivity and year round production of horticultural crops (fruits, vegetables and spices) through the introduction of superior quality planting materials and seeds promotion of production skills

- To minimise post-harvest losses, improve post-harvest handling and maximise primary producers profits and income through the promotion of on-farm and community-based produce handling methods as well as to enhance marketing support services

- To promote income generating activities, including agro-processing, to enable the optimum utilisation of horticultural produce to supplement family incomes, with additional support from micro-credit and food assistance programmes especially for poor and disadvantaged women

- To increase the nutritional awareness among the beneficiaries and to develop a comprehensive food-based nutrition programme to reduce malnutrition in the target groups comprising of mainly women and children

### Project strategy and Key stakeholders,

The project is designed to concentrate on 15 Horticulture Development Training Centres (HDTC). The initial selection of site is facilitated through the use of secondary data and discussions with local people/leaders, government officials. Verification and validation will be done through the conduct of PRAs and community needs assessment exercise s with participation of the villages.

The HDTCs will be equipped with basic tissue culture facilities that will be operated on a semi-commercial scale to produce disease-free planning material, a mushroom production facility and a fruit-vegetable processing facility. In terms of manpower capability of the DAE, a training programme will take care of the orientation and short term training of the all relevant employees (SMOs, Block supervisors) within the country, selected study tours to neighbouring countries in the region, in service training of on technology transfer activities.

The target beneficiaries of the project are the small, marginal and landless farmers, particularly women within the areas of the Horticulture Centres. During the time frame of the project, it has been envisaged to target approximately 31400 farmer beneficiaries out of whom 23,900 would be women farmers. In is also expected to target 1,370 technical personnel in both public and private sectors. Thus the project is to train nurserymen/women who having received elite material for propagation will be raising quality planting materials with the assistance of the DAE staff. The project will also provide traders with skills in handling; grading and packaging produce and even assist those who will develop export links. Finally the project will provide nutrition awareness and education programmes through supply of highly nutritious fruits and vegetables.

Among the stakeholders, Department of Agricultural Extensions (DAE) under the Ministry of Agriculture executes the project. In view of its technical expertise and experience in the development and application of technologies in agriculture, Food and Agriculture Organisation of the United Nations holds the responsibilities of the UN implementing agency. At the national level, the project is coordinated by a National Steering Committee, chaired by the Secretary, Minister of Agriculture with the National Project Director (DG, DAE) as member secretary in order to provide policy advice and guidance.

### Current Status

The integrated Horticulture and Nutrition Development Project was signed in June 2000. The project is designed to achieve the project objectives within five years of its implementation. The project activities were started in October 2000. The year 2001 reported limited achievements due to the delay in initials start-up: fielding missions and other recruitment of man power, setting up and orientation of field officers at the field level, procurement etc. After completion of this initial start-up, the year 2002 demonstrated rather full-length achievements of the expected results. In fact the recruitment of national consultants were mainly done in two phases and therefore the project activities were geared up at the beginning of 2002 and in real sense got its momentum in the last quarter of 2002.Due to the delays in implementing the project activities, it was agreed during the first TPR held in July 2002, that the mid-term, evaluation will take place during the first quarter of the year 2003.

# OBJECTIVES OF THE EVALUATION

In accordance with the policies and procedures established by UNDPand FAO a mid-term evaluation of the project by a joint evaluation-team was foreseen in the project document. The United Nations Development Programme (UNDP), FAO and GOB wish to assess the progress of implementation with regard to activities (outputs), level of achievement of results (outputs and outcomes) and objectives within given time frame and to ascertain its effectiveness .and impacts of the project in order to make decisions on any necessary changes in the overall design and orientation of the project, prepare detailed work-plans for the remainder of the project and make decisions about the desirability and modalities for expansion of project coverage. To this end the evaluation will make recommendations for the future of the project, including any adjustments or re-orientations of the project, if required. Detailed proposals will be made for the future plan of work and the need and potential for expanding IHND activities and a set of criteria for selecting the areas for future expansion. The mission will draw attention to any lessons of general interest.

# SCOPE OF THE EVALUATION

The evaluation must be results-oriented and include systematically and objective assessments of the relevance,  effectiveness, efficiency, and sustainability of the project interventions. The main objective of the evaluation is to assess the progress of the IHND project to date, and the validity of its overall approach.

- Make an in-depth review of the project, design, the execution/implementation modality and the efficiency, the institutional arrangements and their adequacies.

- Assess outputs in relation to inputs and objectives, outcomes if any and impact achieved so far and their sustainability and operational constraints to efficient implementation, operational and financial management of the project.

- Indications of progress or lack thereof in the achievement of the project objectives should be identified.

The evaluators should record successes and failures, best and worst practices, and future challenges and constraints: any significant lessons that can be drawn from the implementation of the project to guide future development interventions. Focus should be on relevance, performance, and success of the project while recording measures or implementation strategies that are “good lessons, or “bad lessons” so that they should be avoided in future. In the later case, the evaluators should also provide remedial actionable measures/ recommendations for specific issues. They should also provide a broader basis of generic lessons if any.

The joint evaluation mission members will thus evaluate (and report on):

- Relevance of the project to development priorities and needs, in particular the people’s priority as identified in Project Document and the Common Country Assessment (CCA) of Bangladesh.

- Clarity, and realism of the project's development and immediate objectives, including specification of targets and identification of beneficiaries and prospects for sustainability.

- Quality, clarity and adequacy of project design including:

- clarity and logical consistency between, inputs, activities, outputs and progress towards achievement of objectives and outcomes (quality, quantity and time-frame);

- realism and clarity in the specification of prior obligations and prerequisites (assumptions and risks);

- realism and clarity of external institutional relationships, and in the managerial and institutional framework for implementation and the work plan;

- likely cost-effectiveness of the project design.

- Efficiency and adequacy of project implementation including:

- management arrangements and modalities of the executing and implementing agencies;

- availability of funds as compared with budget for both the donor and national component, proper fund allocation/usage and the over-budgeting issue;

- the quality and timeliness of input delivery by UNDP,  FAO and the Government;

- work efficiency and implementation difficulties;

- adequacy of monitoring and reporting;

- the extent of national support and commitment;

- and the quality and quantity of administrative and technical support by FAO.

- Project results, including a full and systematic assessment of outputs produced to date 	(quantity and quality as compared with workplan and progress towards achieving the 	immediate objectives). The mission will especially review, the:

- technical reports, training manuals, studies, surveys and publications will be reviewed in terms of quality, validity or acceptability, quantity and coverage (geographical / population);

- extent to which the processes and methods pursued by the project were designed and implemented to facilitate sustainable impact on livelihoods of poor households, in particular the nutrition status of women and children ;

- targeting and selection and follow up of beneficiaries;

- whether adequate mechanisms are in place in the project for consulting with and obtaining feedback from the stakeholders.

- The prospects for sustaining the project's results by the beneficiaries and the host institutions after the termination of the project. The mission should examine in particular:

- the sustainable impacts on the livelihoods of the poorest households and the women and children within those households, especially nutrition impacts;

- the extent to which the project could establish itself as strategically important project for the Ministry of Agriculture, Government of Bangladesh based on its specificity and scope of activities and impact achieved so far.

- The cost-effectiveness of the project.

- In view of the results of the project the feasibility and desirability of expanding its work into other areas.

# PRODUCTS EXPECTED FROM THE EVALUATION

The main output of the evaluation will be an independent and comprehensive report for which the mission under the guidance of the Team Leader  is fully responsible for and which may not necessarily reflect the views of the Government, FAO or UNDP. The report will be of sufficient detail and quality, with annexes and working papers as required, covering a detailed review of the entire project in line with usually accepted standards and requirements of UNDP and FAO. The report will be prepared in approximate conformity to the following headings:

- Executive Summary

- Introduction

- Project and its development Context

- Findings and conclusions

  - Project Objectives and their Relevance

  - Project Concept and Design

  - Project Management and Implementation (efficiency, effectiveness, implementation and management arrangements, Areas of corrective actions Areas of potential success)

  - Progress towards Achievement of Project Objectives and Sustainability

  - Cost effectiveness of the project

- Project Results (activities, outputs outcome and impact)

- Recommendations

- Lessons Learned

- Annexes (TOR, Itinerary, list of persons interviewed, summary of field visits, list of documents reviewed, questionnaires used and summary of results and any other relevant material)

Recommendations will clearly be based on findings and stated in operational terms. They will address all issues identified by the evaluation mission including changes in modalities, processes and ways of working and,  in particular the purposes or the evaluation, i.e.:

- the future plan of work;

- the need and potential for expanding IHND activities and a set of criteria for selecting the areas for future expansion.

The evaluation team will compile a Project Evaluation Information Sheet (PEIS) for UNDP incorporating a) definition and purpose, b) Policy and c) Procedures and will submit 5 copies. The mission will also compete the FAO project evaluation summary sheet.

# METHODOLOGY / EVALUATION APPROACH

- The evaluation mission will work independently and will keep UNDP, FAO and the Government of Bangladesh informed about the progress in the evaluation. Weekly review meetings will be held.

- The evaluation team will prepare a work plan in consultation with the Government of Bangladesh, FAO, UNDP and the project team.

- The mission will review all relevant Project/FAO/UNDP documents and relevant secondary materials such as: Project Document (Prodoc), TAPP, Audit Reports, PIP, Quarterly Progress Report, relevant files, correspondences, documents connected with the project.

- The mission will consult with Government especially those departments related to the project and those government agencies involved in horticulture activities.

- The mission will consult with representatives from all 15 Horticulture development centres and will visit sample centres to be decided by the team.

- The evaluation mission will get in touch with major donors and CSOs/NGOs (if found relevant) and national institutions involved in horticulture activities. Finally the mission will maintain close liaison with the UNDP.

- The evaluators should obtain the views of the target groups, direct beneficiaries and other stakeholders on how the project is affecting them and their recommendations for addressing relevant issues.

- Checklist of queries to be asked in the field as defined in Annex A (UNDP guidelines for the evaluation report) may be used to capture the whole range of information needed.

- A wrap-up meeting will be convened for all concerned during which the evaluators will present the Independent Evaluation Report to the Executing Agency (the draft report will be circulated to all concerned at least 48 hours in advance). Comments from all stakeholders will be noted for incorporation into the final report.  The Team Leader will be responsible for finalisation of the report and submission to UNDP.

- UNDP will ensure circulation of the report to all concerned.

# Evaluation Team

The evaluation will be conducted jointly by a 6-member team. The members of the team should not be directly involved with the management of the project in order to ensure the independence/impartiality of the evaluation. Thus the team should include

- 4 national members representing the Ministry of Agriculture, IMED, ERD and the Planning Commission

- A representative from FAO (International Expert)

- A representative from UNDP (Team Leader-International Consultant)

### Qualifications

### The Team Leader-International Expert

The candidate should have higher degree in economics/Agricultural economics or related fields. The incumbent should be sufficiently competent as an evaluator with at least 10 years prior experience in evaluating agriculture and food security related projects. Preferably (s)he has experience in assessing the ratings for overall project outputs, outcomes and development impacts. Experience in economic analysis of the various project components and of the project as a whole is essential. Experience in the South Asian context and familiarity with UNDP programmes would be an added advantage. Excellent proficiency in English is a must.

### International Expert

Higher degree (preferably PhD) in the field of Horticulture and nutrition or related fields. Minimum fifteen years working experience in the field of horticultural production, technology development and technology transfer to the communities. He/she should have proven ability to assess technical aspects and components of the project as inputs to evaluation team. Experience in the South Asian context and familiarity with UNDP programmes would be an added advantage. Excellent proficiency in English is a must.

# Implementation Arrangements

## Timeframe

The duration of the evaluation in the field will be 3  weeks.

- The evaluators will study the Terms of Reference and submit a work plan (within 2 days).

- The evaluators will review the materials and consult with all stakeholders to seek feedback (12 days, including field visits).

- The evaluators will prepare a midway issues report (1 days)

- Well in advance of the end of the evaluation they will prepare the draft Independent Evaluation Report (5 days)

- The evaluators will organise a wrap-up meeting (1 day) (the draft report will be circulated to all concerned at least 48 hours in advance).

- At the end of the wrap up meeting the evaluation team will collect the views and comments from all concerned and the team leader will finalise and submit the report to UNDP (1 week).

## Consultations in the field

The mission will consult with representatives from all 15 Horticulture development centres and will visit sample centres to be decided by the team. Evaluation Mission will get in touch with major donors (if found relevant) and national institutions involved in horticulture activities. Moreover, the mission will also consult with Government especially those departments related to the project and those government agencies involved in horticulture activities. Finally the mission will maintain close liaison with the UNDP.

The expenses for conducting the evaluation will be borne by the project (BGD97041 project budget lines BL: 16.02 and 16.03) and the remuneration of the hired consultants will be according to standard UN rates. Evaluation mission members nominated by the GOB will be entitled to DSA while away from their duty station. The budget line for the mission costs is managed by both FAO and UNDP. Payment of fees to the Consultants of the team will not be concluded until the final report has been accepted.

## Background documents

The following background documents will be made available the mission on arrival.

- CCF 1996-2000; CCF 2001-2005

- CCA, 2000

- Project Document: BGD/97/041, IHND

- TAPPs

- Audit Reports

- Annual Progress Reports

- Quarterly Progress Reports

- Workplans

- Reports of the Annual Tripartite Review Meetings

- Results Oriented Monitoring Indicators (ROMIs)

- Latest Approved Budgets and Letters of Agreement

- CO SRFs/ROAR

- UNDP Format for Evaluation Reports (including PEIS)

In addition to the above, the Evaluation Mission will have access to project files and other pertinent miscellaneous documents, correspondence and reports.

Rangamathi, Kishoreganj, Mymensingh, Jamalpur, Rangpur, Nawabganj, Natore, Pabna, Meherpur, Rajbari, Khulna, Barisal, Feni Khagrachari, and Bandarban