ANNEX 4

METHODOLOGY, TIMING AND ORGANIZATION

Purpose Of The Mid-Term Assessment

Within UNDP’s policy framework of monitoring, reporting and evaluation procedures, the mid-term evaluation provides project management and stakeholders at large the opportunity to identify appropriate actions to:

- Address particular issues in design, implementation and management, and

- Reinforce initiatives that demonstrate the potential for success.

In conformity with aforementioned policies, this exercise must be results-oriented and must include assessments of relevance, performance and success of development interventions. In consequence, the present evaluation must consider UNDP’s shift to Results Based Management paradigm. As is known, to a large degree, this is a response to the demand for enhanced development effectiveness.  Among other things, it has become evident that well managed projects with efficient outputs did not have discernable effects on development. The attention has therefore centered on outcomes: realistic and positive changes in specific development conditions. Indeed, by focusing on outcomes, UNDP aims for results where they are most needed— in people’s lives.

The RBM approach, through the M&E systems, aims to assess performance at all levels of programming with respect to:

- progress towards outcomes

- contribution of UNDP to the outcomes through outputs,  and

- partnership strategies

Essentially, the method and field procedures proposed to undertake the present  evaluation is:

- to move the process away from assessing outputs against project objectives

- to assess instead how outputs contribute together  with the assistance of partners to a  change of development outcomes.

In reality,  the actual approach to conduct the present evaluation has to be necessarily synchronic and flexible to ensure fairness and transparency. The activity process is analyzed through a  synchronic treatment by globally reconstituting and taking into account the project framework at a given time frame, avoiding  spurious comparisons or inferences from events unrelated in time.

In sum, two issues have overriding consideration in the formulation of the methodology.

- First, the cornerstone of the Project under review is capacity development. It aims to develop the abilities of individuals and institutions, individually and collectively, to enhance the level of food security and nutrition through improvements in the efficiency of horticultural production systems and associated support services. Ultimately the target population, composed of small and marginal farming communities encompassing women from landless households, is expected to improve its productivity and incomes levels together with nutritional status. Accordingly, in terms of capacity development, it will be necessary to assess the interrelated dimensions of the process of technology transfer to improve productivity and the institutional adjustment needed to take full economic advantage of the new technology encompassing enhancing nutritional status.

- . Second, there has  been a shift in the assessment of development interventions. Previously the focus was on outputs. Now the focus is on outcomes. This shift in focus has reinforced the results-oriented approach in evaluation.

Methodology, Implementation And Timeframe

Methodology

From the above considerations, it became evident that the participatory approach was in step with the above issues. The participatory approach is a collaborative evaluation process. It builds on strengths and it values the contribution of everyone involved. Every stakeholder has an opportunity to present its case.

These attributes make this approach compatible with the shift from outputs to outcomes within the results-oriented framework.  Because it allows greater stakeholders’ participation in the evaluation process. Specifically, project management participates in selecting the outcomes produced for assessment, encompassing outcomes in process and those unexpected.

A framework  of the participatory approach supported by the results chain concept in the context of the results oriented evaluation should provide the guidelines to conduct the present evaluation. The fundamentals of the participatory approach can be summarized in a few principles.

The Participatory Approach

- Principle 1. Participatory evaluation focuses on achievements and learning.

Focus on Achievement

- To assess achievements,  the participatory approach applies the “results chain” and the “substantive focus” of evaluations within the framework of results oriented evaluation.

The results chain identifies three levels of results. They are of composite nature, that is, the set of actions of each level must be achieved satisfactorily so that the next level can begin. If you undertake the right set of activities or actions, you should achieve the first level of results or changes you want – outputs, as illustrated below. The three levels of results are:

    - Short-term results = outputs

    - Medium results = outcomes (immediate development objectives)

    - Long-term results = impacts (development objectives).

Activity

Completed

Activity

Output

Outputs are tangible products (including services) of a project that are necessary to achieve the objectives of a project.  Outputs represent the completion of activities and are the type of products over which managers have vital influence.

Outcome is an actual or intended change in development conditions that UNDP interventions are seeking to support. It describes a change in development conditions  between the completion of outputs and the achievement of impact. The Prodoc’s immediate development objectives are outcomes.

Impact is the overall long term effect or the ultimate effect attributable to a development intervention. The Prodoc’s development objectives are the expected impacts.

Through the evaluation’s substantive focus,  the interrelated dimensions of relevance, performance and success must be assessed. These three dimensions are the core of an evaluation exercise as opposed to an audit. The following criteria is used to assess each dimension.

- Relevance - the degree to which the objectives of a Project remain valid and pertinent as originally planned or as subsequently modified owing to changing circumstances within the immediate context and external environment of that Project.

- Performance - the extent to which a Project is implemented in an effective, efficient and timely manner.

  - Effectiveness - the extent to which a Project achieves its immediate objectives or produces its desired outcomes.

  - Efficiency - the optimal transformation of inputs into outputs.

  - Timeliness of inputs and results.

- Success. The following criteria constitute success.

- Sustainability - durability of positive Project results after the termination of the technical cooperation channeled through that Project; static sustainability - the continuous flow of the same benefits, set in motion by the completed Project to the same targets; dynamic sustainability - the use or adaptation of Project results to a different context or changing environment by the original targets and/or other targets.

- Capacity Development – to what extent individuals, organizations (governmental and non governmental) develop their abilities individually and collectively to perform functions, solve problems and achieve the immediate development objectives associated with the Project.

- Impact - results of a Project that are assessed with reference to the development objectives or long-term goals of that Project; changes in a situation, whether planned or unplanned, positive or negative, that a Project helps to bring about.

Focus on Learning

The systematic assessment of the relevance, performance and sustainability leads to the notion of capacity development. This is the process by which individuals, groups, organizations and sectors enhance and organize their systems, resources and knowledge. These are reflected in their abilities (individually and collectively) to perform functions, solve problems and set and achieve objectives.

Learning can be used to move towards action. Hence, the participatory evaluation is action oriented because it must be useful to both people and organizations. This provides the substratum from which to draw lessons from the evaluation.

- Principle 2. Participatory evaluation allows for an appreciation of shared activities, coordinated efforts and linkages among those who are involved in conducting a Project. In turn, this makes it possible to assess potential or actual synergies in operation.

Synergy is referred to as the “2+2=5 effect” because the parts of a system may produce more working together than they can apart. The Chinese saying, “If three persons join together the soil may be turned into gold” provides an example. A participatory evaluation is compatible with the search of processes leading to synergy.

- Principle 3. In a participatory evaluation evaluators and stakeholders must jointly assume the analysis of substantive focus.

Within the participatory framework, the joint analysis of substantive focus can be conducted through the application of the following Five Key Evaluation Questions. In brief, the three principles of participatory evaluation advance the understanding of the evaluation issues, the Five Key Evaluation Questions make its implementation operational.

Implementation

- First Question:  Did we do what we said we would do?

This question is concerned with assessing the progress achieved within the framework of the Project.

- Second Question: What did we learn about what worked and what did not work?

This question deals with the reasons for success. Finding out what worked well and what did not is central in this process. As an evaluation’s fundamental focus is on learning.

Such knowledge will emerge as part of the evaluation encounter within the participatory approach. Another set of issues of considerable importance have to do with synergy within Project activities.

The remaining questions (from 3 to 5) are, to a large extent, dependent on the kind of data collected and analyzed in the first two questions. Nonetheless, the leading issues in each of the questions can be identified.

- Third Question: What difference did it make that we participated in this Project?

The answer to this question comes from the analysis of the Project’s relative success (or lack of success) as measured by the criteria described above. The following issues are fundamental. Are the technologies implemented sustainable? If so, is the sustainability of a static or a dynamic nature?

- Fourth Question: What could we do differently?

This question deals with the recommendations. Proposals aim at enhancing the effectiveness, quality or efficiency of the Project. They will be stated within a timeframe (short, medium and long term) and identify the organizations responsible for the follow-up action. All recommendations should be linked to conclusions.

- Fifth Question: How we do we plan to use the evaluation findings for continuous learning?

Evaluation exercises provide information and facts that, when accepted and internalized, become knowledge that promotes learning. In turn, it enhances performance and success.   Lessons learned are generalizations based on evaluation experiences with Projects that abstract from the specific circumstances to broader situations. Frequently, lessons highlight strengths or weaknesses in design, and implementation that affect performance, outcome and impact.

Timeframe Proposed

The Collection and Analysis of the Evidence

The field visits will take place from the 1 to 9 May, 2003. See attached schedule of visits prepared with the participation of all stakeholders.

Within the framework of outputs and outcomes achieved, perceptions on these results will be gathered from open-ended interviews, group interviews, direct observations, documentation and other field techniques suitable to the issue at hand.

Perceptions will be elicited from farmers (male and female members of households) and extension agents from sites corresponding to the 15 Project Locations. In order to visit all locations the Mission was divided in two sub-teams.

Given the time and resources available to the Mission, a purposive sample of farmers  appears sufficiently representative to examine the effect of Project actions on the target population. Purposive or quota sampling is commonly used in market research or public-opinion polls. It leaves considerable freedom of choice to the interviewer in the selection of respondents. Although the technique varies from one researcher to another, there are restrictions related to specific characteristics, such as (age, socio economic status, etc.) or the respondents must be representative of a certain area (upazila, districts) or a specific group being interviewed, such as women of rural households in a given upazila.

Farmers (male and female members of households) interviewed can only be selected on their of their availability.  Particular effort will be placed to interact with farmers without land or share croppers as well as women members of rural households. It is understood that women will be represented within the context of cultural norms pervasive in rural Bangladesh.

To detect income changes induced by productivity gains, crop budgets will be collected for analysis .The current conditions and potential for horticultural production and nutrition status will be reviewed with particular emphasis.

To ascertain the quality of training provided, exclusive focus on the farmers (male and female members of households) was placed on the assumption that if  extension agents received quality training,  this  in turn  would be reflected on the training provided to farmers.

UNDP Evaluation Office. Results-oriented monitoring and evaluation. New York, 1999, p. 107

UNDP Evaluation Office. Handbook on monitoring and evaluating for results. New York, April 2002.

Michel Godet. Manuel de prospective stratégique. Vol.2, Paris: Dunod. p.101

See:.UNDP. Who are the question makers? A participatory evaluation handbook. New York, 1997, pp 9-15. Also Health Canada. Guide to project evaluation: a participatory approach. Ottawa, 1998, pp 7-13.

See: UNDP/EO (2001) Managing for results. Monitoring and Evaluation in UNDP. New York, Draft#3, p.3.

It is vital to consider that  Activities are Not Results. Activities are ACTIONS … Results are CHANGES

See: UNDP. Results oriented monitoring and evaluation. New York, 1997, pp 25-28

This sections was retained from the Evaluation Plan for recording purposes.

See: W.J.Goode and P.K. Hatt. Methods in social research. McGraw Hill Book Company. 1952, p. 230.