ANNEX 7

PROJECT MANAGEMENT ISSUES

This Annex intends to review issues on project management from the TOR (section 3). As introduction, UNDP’s shift to Results Based Management (RBM) as an institutional culture is discussed. Since the present Project was programmed before this paradigm shift, there are manifold implications reviewed, both, in terms of project management and evaluation issues. Subsequently, issues enumerated in TOR are tackled one by one.

7.1 The RBM Approach: Management Issues and Programming Procedures.

Although managing for results is not new to UNDP, what makes the current approach different is the determination to make RBM the driving force within the organization’s institutional culture and practice. Introducing the RBM approach aims to improve program management, effectiveness, and accountability by defining realistic expected results, monitoring progress toward the achievement of expected results, integrating lessons learned into management decision, and reporting on performance.

This paradigm shift in management has been, to a large degree, a response to the demand for enhanced development effectiveness.  Among other things, it has become evident that well managed projects with efficient outputs did not have discernable effects on development. The attention has therefore centered on outcomes: realistic and positive changes in specific development conditions. The shift in focus is illustrated in Fig. 1. Indeed, by focusing on outcomes, UNDP aims for results where they are most needed— in people’s lives.

The RBM approach, through the M&E systems, aims to assess performance at all levels of programming with respect to:

- Progress towards outcomes

- Contribution of UNDP to the outcomes through outputs, and

- Partnership strategies

INPUTS

experts, funds, equipment

OUTPUTS

people trained,

studies completed

OUTCOMES

jobs created,

incomes increased

IMPACT

Conditions improved:

health/

longevity

Figure 1. What are results: Outputs and Outcomes

(Adapted from UNDP 2000, Fig 1

The challenge to, both program management and the evaluation process, emerges with projects that were programmed before UNDP shifted its focus from outputs to outcomes. This is also the case with the present Project that was designed in the 1990s under the framework of an output-oriented project.  Henceforth, the Project will be referred to as input supply Project.

The cornerstone of the Project under review is capacity development. It aims to develop the abilities of individuals and institutions, independently and collectively, to enhance the level of food security and nutrition through improvements in the efficiency of horticultural production systems and associated support services. Ultimately, the target population, composed of small and marginal farming communities encompassing women from landless households, is expected to improve its productivity and income levels. Nutritional status is also expected to ameliorate.  Accordingly, in terms of capacity development outcomes, it will be necessary to assess the interrelated dimensions of the process of technology transfer to improve productivity and the institutional adjustment needed to take full economic advantage of the new technology encompassing enhancing nutritional status.

For the reasons evoked above, it should not be surprising if the expected outcomes in the quest to achieve development conditions have not been designed in the Prodoc.  A mid term evaluation is the best opportunity to review issues requiring decisions and actions, as indicated in the TOR. Specifically, a mid-term evaluation provides project management and stakeholders at large the opportunity to identify appropriate actions to:

- Address particular issues in design, implementation and management

- Reinforce initiatives that demonstrate the potential for success.

7.2  Management Issues Raised in TOR (section 3)

- Relevance of the project to development priorities and needs, in particular the people’s priority as identified in Project Document and the Common Country Assessment (CCA) of Bangladesh.

Considering the characteristics of the agricultural sector, the nutrition factor in sustainable human development, poverty alleviation and gender considerations, the Project objectives  propose a broad strategy to build the capacity of individuals and organizations. In addition, it aims to enhance the level of food security and nutrition by boosting the efficiency of horticultural production systems and associated income generation activities encompassing homemade food processing.

- The Project is relevant to the needs of the GOB and conforms to its priorities and current policies. Indeed, the GOB is committed to halve its malnourished population by the year 2015.

- The Project has the potential of successfully testing a capacity building strategy that ultimately leads to reduce poverty through an environmentally friendly, and knowledge-based technology, within the reach of the landless and without assets, in particular deprived women of rural households.  Thus, the Project has the potential to contribute to upstream policy making in poverty reduction in the country and elsewhere in the sub region with similar ecological and socioeconomic conditions. In terms of the CCA framework, the Project is relevant to three clusters of rights:

- Food and Nutrition (Right to Survival)

- Employment/Income (Right to Livelihood)

- Empowerment/Association (Right to Participation)

- These elements are in conformity with UN Common Country Assessment and the Administrator’s Long Term Operation Plan.

- The Project meets the needs of the direct beneficiaries. It addresses the learning requirements of landless and deprived women of rural households. It directs resources towards the interrelated dimensions of individual learning in the context of organizations. It intends to create an enabling environment for the target population, composed of landless and marginal farming communities, and strives to improve the productivity and incomes levels together with nutritional status.

- Clarity, and realism of the project's development and immediate objectives, including specification of targets and identification of beneficiaries and prospects for sustainability.

a) Project’s Immediate Objectives (Prodoc,  pp 37-44)

The Project’s immediate objectives are:

- To develop sustainable capability among low income communities, specifically poor women farmers, in increasing productivity and year round production of horticultural crops (fruits, vegetables and spices).  This will be achieved through the introduction of superior quality planting materials and seeds promotion of production skills.

- To minimise post-harvest losses, improve post-harvest handling and maximise primary producers’ profits and income through the promotion of on-farm and community-based produce handling methods.  Marketing support services will also be enhanced.

- To promote income-generating activities, including agro-processing, in order to enable the optimum utilisation of horticultural produce to supplement family incomes, with additional support from micro-credit and food assistance programmes especially for poor and disadvantaged women.

- To increase the nutritional awareness among the beneficiaries and to develop a comprehensive food-based nutrition programme to reduce malnutrition in the target groups comprised, mainly of women and children.

As indicated previously, the Project design reflects an input supply approach that prevailed in the programming framework before the RBM approach. This approach is reflected in the immediate and the development objectives. Thus:

The immediate objectives do not sequence the institutional adjustments needed to ensure beneficiaries’ income improvement derived from the technological innovations introduced to increase physical productivity. Experience shows that there are many projects in the developing world that have increased physical productivity through technological changes but incomes have stagnated, and sometimes decreased, due to lack of institutional framework.

Similarly the nutrition factor is not sequenced within the institutional framework needed to take advantage of the technological innovations introduced. Nutrition awareness through availability of vegetable crops is only part of the solution. Nutrition awareness is necessary, but not sufficient in itself, to enhance the nutrition status of a certain segment of society in a given context. Malnutrition is a complex problem with multiple factors, as discussed in Annex 6.

b) Project’s Development Objectives  (Prodoc, p37)

The Project’s development objectives are:

- To enhance the level of food security and nutrition by improving the efficiency of the horticultural production system and associated support services through the application of modern technologies and diversified cropping patterns that will bring about greater productivity and higher incomes to the small farmer communities in a sustainable manner.

- To improve the nutritional status of the population through creating an environment in which households have sufficient access to fruits and vegetables at affordable prices and the necessary knowledge and skills to prepare and consume these foods to complement their diet.,  This initiative would be targeted specifically at the poor women farmers of Bangladesh.

As suggested, it is not surprising that the development objectives reflect the immediate objectives’ problem.  There is no sequencing of institutional adjustment to take economic advantage of the technological innovations including the nutrition factor as in the case of the immediate objectives. The conceptual framework of this dichotomy between institutions and technology is outlined in Annex 5.

In all fairness, this project was programmed under the input supply approach. At that time, the approach assumed that the on-site availability of technological inputs, and/or extension resources, was sufficient for technological change to take place and that socioeconomic development will necessarily ensue. Many researchers and development practitioners in the 70s, and 80s criticized this approach as the “invisible hand” that would create rural institutions to ensure sustainable growth. In reality, this method proved costly in terms of human resources and rarely built effective rural institutions to support sustainable farming systems.

As there is no “invisible hand”, the current challenge of how to create viable rural institutions for sustainable farming systems is more compelling.  As technological constraints on growth of agricultural productivity have become less binding, there is an acute need for institutional adjustments (innovations) that will result in a more effective realisation of the new technical potential within the human development framework.

Finally, targeting in the selection of beneficiaries was adequate. According to the Progress Report, up to December 2002, there has been 21 060 beneficiaries incorporated to the Project, representing 67% of total group.   76% of the beneficiaries are women representing the expected proportion by the end of the Project. So far 50% of beneficiaries come from landless households, 34% from marginal landholdings and only 16% from small landholdings. The representation of women is substantial. This is as it should be since these women represent the poor and assetless, a vulnerable segment of the rural world.

3. Quality, clarity and adequacy of project design including:

- Clarity and logical consistency between, inputs, activities, outputs and progress towards achievement of objectives and outcomes (quality, quantity and time-frame);

Within the input supply project framework, the linkages among objectives, inputs, activities, outputs and expected outputs are logical with respect to the transfer of the technology component of the Project. Experience and evidence show that when outcomes are produced within the input supply framework, these are tenuous and seldom sustainable because they are dependent on external supply of inputs.  Very little or no effort is directed in institutionalizing the outcome.

The institutional transformations required to successfully exploit the technology introduced were implicit in the Prodoc and in particular in the strategy proposed.  As in discussed in Annex 5, an institutional framework is vital for effective Project operation and to ensure sustainability. Institutional framework considerations encompass focusing on market development and the marketing procedures of the crops introduced by the Project. There is considerable evidence showing that since technological change is a powerful source of demand for institutional change, it is in the market structure where this demand is felt almost immediately. When production increases due to technological change, traditional market structures are unable to respond adequately to a volume several times larger than before. As result, either prices will plummet or benefits will be leaked to those equipped to take advantage of this situation.  This can be a serious constraint in the process of increasing income for targeted beneficiaries.

Beneficiaries must command a total understanding of the factors governing the economic exploitation of horticultural crops. If the benefits of horticultural crops do not accrue on targeted beneficiaries, the process of the technological transformation, and thus, poverty reduction can be compromised.

In terms of the nutrition objectives, it is not clear if awareness alone will have significant effects on the malnutrition situation in the Project area. Given the complexity of the causes of child malnutrition, illustrated in Fig 1 of Annex 6, efforts to identify the determinants of diets in a vulnerable segment of the targeted population should be considered. In this manner, it should be possible to uncover promising relationships between variables to draw lessons for future intervention.

- realism and clarity in the specification of prior obligations and prerequisites (assumptions and risks);

The Prior Obligations and Pre-Requisites (section G) are all clear and realistic. The issues related with role and functions of National Project Coordinator and other staff will be clarified when the latest National Execution procedures are issued by UNDP. In terms of administration of resources, the specifications reflect the fact that the ultimate responsibility of managing financial resources rests with UNDP. UNDP is administering these funds put in trust by taxpayers from contributing member countries. The reality is that taxpayers are concerned and want to know how their resources are being put to use.  They also desire knowledge of the difference these resources are making in the lives of people in the recipient countries.

The section (F) analyses risk from the assumption that once technological inputs reach the Project area, horticultural production will inevitably take off. This assumption is devoid of development experience and has been examined earlier. Although it does identify problems of transportation (inordinate delays from ferry transportation), it dismisses it as being beyond the scope of the Project. It is an unrealistic analysis of risk, if one accepts the need of an institutional framework as prerequisite to ensure the generation of income from exploiting the technology introduced.

Section F’s analysis of the lack of continuity of government personnel is a real risk that is common among many projects. The solution is not realistic. Firm commitment from DAE is vague. Perhaps contract documents among interested parties could have been considered.

- realism and clarity of external institutional relationships, and in the managerial and institutional framework for implementation and the work plan;

The Prodoc is a technical and legal document, therefore, synonyms are to be avoided or used guardedly.  Unfortunately the terminology in this particular point is imprecise. Be as it may, the term external institutional relationships appear to refer to Annex 7 of Prodoc. This is a contractual agreement between the Executing Agency and UNIA (FAO). Since this is a legal document within the domain of international law, it is ordinarily outside the scope of an evaluation mission, unless a specific matter is brought to the attention of the mission.

Again the term managerial and institutional framework for implementation and the work plan within the framework of Prodoc is imprecise. If it refers to Annex 9 (Organizational Structure of the DAE) without a precise issue, it is not useful for anyone to make gratuitous remarks, especially since DAE has conducted many projects applying extension methods.

However, there are substantive issues with regards to the Work Plan (Annex 5 of Prodoc)

Admittedly, many of the forthcoming comments reflect again the flaws of input supply programming.

- The Provisional Plan 2000-2002 lists 92 activities (Annex 5 of Prodoc). There is neither output nor outcome planning.

- The Inception Report submits a Work Plan from January to June 2001 listing 92 activities without output nor outcome planning.

- In the the Tripartite Meeting of July 2002, Project Management submits a budget for the pilot phase that ends in December 2002. Although the budget no longer lists the 92 activities, it appears clustered in categories like HRD, farmers training, demonstrations, seminar and workshops, field days, exhibition, multiplication of planting materials, establishment of laboratory at the HDTC, collaboration with WFP, PRA and baseline survey, promotional activities and manual and impact monitoring. Although clustering similar activities may facilitate output production, the planning of outcome production is still missing.

- The Work Plan 2003 has a somewhat similar cluster of activities: farmers training; in-service training; foreign training and study tour; demonstrations; seminar workshops, field days, exhibitions; fruits and nursery; laboratory facility; farmers groups activities; awareness, advocacy and promotion; monitoring and impact assessment; mission meetings and project reviews. For the first time, activities in each cluster are targeted in number. The planning of outcome production is still missing.

By contrast, the current UNDP Programming Manual (February 2003) contains two instruments:

- The work plan (Annex 5C) where simultaneously Objectives/Outputs/Responsibilities are identified, and

- The Project Results and Resources Framework (Annex 5D) is an instrument which specifies activities, outcomes, outcome indicators, and outcomes that certain outputs planned to achieve.

Project management should consider using these instruments henceforth.

- Likely cost-effectiveness of the project design

There appears to be a logical incongruence in this point because cost-effectiveness is a tool applied during project appraisal. This will become clear when this point is reviewed below.

4. Efficiency and adequacy of project implementation including:

- management arrangements and modalities of the executing and implementing agencies;

All available definitions (OECD 2002; UNDP 1997, 2002) converge on the definition of efficiency as a measure of how economically resource/inputs (funds, expertise, time, etc.) are converted to results.

With respect to modalities of execution and implementation, UNDP has global procedures for these purposes referred to as national execution (NEX). The latest version is about to be issued. So far, good working arrangements appear to have taken place within the framework of national execution.

One clear perception has emerged, however, during the mission execution. Both partners, the GoB as executing agency, and FAO, as  UNIA, appear unaware of the fact that UNDP is operating under a new management paradigm: the RBM. It is no longer input supply that UNDP searches but tangible outcomes in development effectiveness. Although the GoB retains overall responsibility for the implementation of the UNDP assistance, both GoB and UNIA should adhere to the principles of RBM as  development partners. Otherwise, development results on the ground are compromised because RBM is a radical departure from input supply, as discussed earlier.

More in the domain of the administration of financial resources, the perception has emerged that UNDP development partners do not appear knowledgeable that the ultimate responsibility of managing financial resources rests with UNDP. As indicated above, this is because UNDP is administering funds that are put in trust by taxpayers from contributing member countries.

- Availability of funds as compared with budget for both the donor and national component, proper fund allocation/usage and the over-budgeting issue;

The evaluation process examines budgets and associated arrangements in terms of resources and how they are likely to effect projects results or sustainability. This is because the main purpose of an evaluation is to draw lessons on the relevance, performance, and success/failure of projects.

The answer to this point appears to require an audit approach because audit exercises are concerned with financial allocations and compliance with existing rules and regulations in the context of use of funds. In fact, the Audit Reports for 2001 and 2002 raise disturbing concerns. Both reports converge on the need of enhanced internal control systems to improve Project performance. They also converge on the need to improve the maintenance of accounts, record keeping system, monitoring and evaluation.

- the quality and timeliness of input delivery by UNDP,  FAO and the Government;

The Mission’s perception is that UNDP has delivered inputs in a timely fashion considering its limitations to perform activities such as procurement. UNDP is in a difficult position to meet client satisfaction because local prices for most items for procurement are practically identical to world prices. UNDP often will prefer world-known brands because of warranty whereas national organizations are happy to put up with a clone, for example.

Likewise, the GoB has delivered, on the whole, inputs in timely fashion. There have been exceptions where certain HDTCs are not yet fully equipped and personnel have not been assigned. National authorities interviewed have indicated their intention for speedy action to close the gap.

Although FAO has delivered, on the whole, high quality inputs, the timeliness has suffered from time to time. This is mainly due to a lack of closer field monitoring in technical assistance. For example, the Mission did not find a summary record of consultants’ recommendations with follow up actions. In reality, it appeared that FAO was involved only in the necessary arrangements for the consultants’ arrival and departure. It is a reasonable expectation that the UNIA should  attempt to adhere to the management principles of the RBM approach.

- work efficiency and implementation difficulties;

From the visit to the 14 HDTCs with their technical staff and the interaction with direct beneficiaries (see Annex 3 for a list of beneficiaries met), it appears that work efficiency was adequate. From time to time, work to be done in experimental plots needed improving in aspects such as like cleaning weeds, and the like.

In terms of implementation, as stated previously, the Project management was implementing a pilot phase of Project. In this context, implementation appeared smooth in the sense of executing activities—with little or planning toward the achievement of outputs and ultimately outcomes.  In an earlier section,  UNDP’s shift of management and programming rationale with  its implications to implementation has been discussed.

- adequacy of monitoring and reporting;

The Prodoc and the Inception Report stressed the need to collect base line data in order to establish a M&E system to facilitate effective monitoring of Project’s management operations and activity execution. The quality of a baseline study is commonly determined by its usefulness in helping to assess social/economic or technological/institutional changes that take place in the Project area as consequence of its interventions. During the present evaluation work, the Baseline Survey (submitted on February 2003) has been useful to understand the Project area. It is possible, however, that there was insufficient  information on agricultural economics issues, such as  crop budgets, farm budgets, etc.

There is a M&E Unit distributing monthly and quarterly reports. While these actions move adequately, the conceptual content reflects the supply-oriented project. The reasons for this state of affairs have already been evoked.

Therefore, there will be need to revamp the M&E unit towards the results-oriented approach. This is absolutely vital due to the complex nature of the Project. The efficiency and effectiveness of the Project staff is significantly influenced by the quality of management. The results of three systems need to be monitored simultaneously

- Activity execution in production-marketing of crops introduced

- Activity execution in nutrition awareness-malnutrition issues

- Management operations in 15 HDTC

Immediate revamping of the M&E system into a results oriented framework will help in the development of management skills to ensure the effective use of personnel and financial  resources as well as timely execution of Project activities into outputs and outcomes.

To summarize, the revamping of the M&E unit into a results-oriented approach in order to monitor simultaneously the Project’s 3 sub systems that need to be addressed with urgency.

- The extent of national support and commitment;

From meetings with representatives of DAE centered on performance issues of Project, it became evident that there is substantive national support and commitment to conduct the Project successfully.

- The quality and quantity of administrative and technical support by FAO.

As indicated earlier FAO has fielded high quality technical support. But on the whole, the technical and administrative support requires a proactive approach for the remaining of the Project horizon. A project, like the present, totally concerned with technological transformations on farm and linking with nutrition and malnutrition issues, has been the core of FAO actions and programs for decades. It is natural, therefore, to expect a proactive leadership geared to obtain tangible results on the ground. The success of the Project will be decided by tangible results on farmers’ plot, landless households’ vegetable gardens and the like.  This is where FAO is expected to display its know-how, experience and leadership capabilities.

Specifically, there have been moderate difficulties with the timely arrival of consultants. The evidence available indicates that consultants’ reports reached the end user with considerable delay. In the case of the backstopping reports, they have not reached the end users yet. In most instances, recommendations have not been validated with the end user and monitoring of recommendations appears largely ignored..

- Project results, including a full and systematic assessment of outputs produced to date (quantity and quality as compared with work plan and progress towards achieving the immediate objectives).

The evidence available (Inception Report and Project Progress Report 2001-2201) show activity execution. Because of the input supply approach, there is no quantified indicators of success. The formulation of indicators of success (referred  to as “success criteria” in the Prodoc) has methodological snags. Indicators are “signs that show changes in certain conditions or results from specific interventions. They provide evidence of progress of project activities in the attainment of development results” (UNDP, 1997, p 41). The Prodoc offers, as success criteria, often activities to be conducted, and a few times, actual tangible changes,  but without measurement.

From the methodology standpoint, it is not possible, therefore, to assess to what degree outputs have been achieved. Neither is it possible to understand how outputs will lead to outcomes. Outputs and outcomes lack quantified indicators of success in the Inception Report and posterior budgeting exercises (see section of budgets above).

In fact,  as mentioned above, the work plans (both in the Inception Report and 2002) simply listed the 92 activities without targeting physical execution and associated disbursement.  The 2003   work plan has targeted a number of activities to execute during the year without estimated disbursement. In sum, it is intricate to establish a quantified rate of achievement. Although there has been observable progress towards achieving immediate results.  These findings are congruent with Audit Report of  2002. “The rate of project delivery could not be ascertained as the annual work plan and physical and financial progress report was not produced.”

One structural reason for these shortcoming lies in the Prodoc’s input supply oriented framework combined with lack of RBM knowledge.  As explained within the framework of the “results chain” (see Annex 4),  activities are not results. Activities are actions … results are changes, as illustrated in Figure 2 below.

Activity

Completed

Activity

Output

Fig. 2 Output Planning Process

This deficit can be improved easily as UNDP has excellent manuals available for this purpose, i.e UNDP (1997;2002) and many others from other donors.

As realistic as they are these unwitting design shortcomings bringing about complications in measuring activity execution within the framework of RBM, the field visits conducted in 14 HDTCs testify that the Project has successfully implemented key results that should be considered as outputs.

- Nearly 16, 000 women from landless households have been successfully organized in groups. This is approximately half of the targeted population.

- From discussions conducted with women’s groups, their organizational commitment enabled them to become organized. Through this organization they could share common views that led to greater self-confidence. This process signifies empowerment.

- The type of training imparted to women’s groups (primarily nutrition, and horticultural production including home-made food processing) meets their current needs. They often requested more training in horticultural and associated activities.

- There are early signs of successful income generation initiatives primarily based on homemade food processing techniques acquired through the Project.

- Crop budgets collected from selected vegetables by the Mission show encouraging financial net returns to farmer-operators ranging from 8500 Tk/ ha for Indian spinach to 77 000 Tk/ha for green chilli. Okra and tomato command 27 400 Tk/ha and 36 500 Tk/ha, respectively. These net returns have taken into account inputs, interest on inputs (20%), land lease, labor, and management cost (50% of labor).

The cardinal challenge ahead is how to translate these early results of empowerment, awareness-raising of better nutrition, potential productivity from proposed horticultural innovations, into better incomes sustainable across all direct beneficiaries. This has been the paramount concern of the Mission.

The Project is indeed at a turning point. It requires a forward looking strategy within the framework of RBM and an institutional framework.   As in discussed in Annex 5, an institutional framework is vital for effective Project operation and to ensure sustainability. Institutional framework considerations encompass focusing on market development and the marketing procedures of the crops introduced by the Project. There is considerable evidence showing that since technological change is a powerful source of demand for institutional change, it is in the market structure where this demand is felt almost immediately. When production increases due to technological change, traditional market structures are unable to respond adequately to a volume several times larger than before. As result, either prices will plummet or benefits will be leaked to those equipped to take advantage of this situation.  This can be a serious constraint in the process of increasing income for targeted beneficiaries.

- The mission will review technical reports, training manuals, studies, surveys and publications will be reviewed in terms of quality, validity or acceptability, quantity and coverage (geographical / population);

The Appendix attached contains the training documents produced. The two most important deal with plant propagation/nursery management and fruit production and handling techniques. They are directed to extension officers. Although successful experiences from adaptation efforts in Bangladesh are presented, some of the data is generic but useful for teaching purposes.  There are a dozen publications concerning diffusion (advocacy) of fruit production techniques and nursery management; mushroom and banana production; cabbage/cauliflower production; post harvest and marketing issues; nutrition posters.

As mentioned previously, the Project has been according to Management in a pilot phase, thus the training materials were targeted to trainers.

Indeed the PPR 2001-2002 (table 2, 3) show that in Training of Trainers (ToT) and in-service training, there were 550 participants in 2001 and 870 in 2002. Most of  the training sessions lasted 5 days and approximately 80% dealt with the production and harvesting of fruits and vegetables.  The remainder sessions were concerned with nutrition issues. In 2002,  30 participants were trained for two days on project management and accounts. There are no expected outputs identified from these clusters of activities.

Table 6 of PPR 2001-2002 shows study tours. Within the framework of a poverty alleviation project oriented to build capacity among the poor, assetless people and women from landless households, the Mission finds it difficult to understand the specific purpose of a tour to Thailand by six managers of DAE, MOA, Planning Commission and ERD. Managers do not normally get involved in operations in the field and have the means to find out information on fruits and vegetables through libraries, internet and other research materials.

Although women farmers can always find educational information by visiting their counterparts in Nepal, the ecological and socioeconomic conditions are so different that it would be far too complicated to transfer any particular technique or method.

A more effective method to learn at the farm level is to organize visits to technically successful farmers from not so successful farmers. Experience shows that the context for learning is more amenable and transfer of know-how and techniques often possible, provided the lessons to be learned by farmers are clearly outlined and means provided for knowledge transfer.

It is also reported that there has been three different workshop and eleven seminars on horticulture, project implementation and monitoring, extension methodology and impact assessment, field implementation strategy. The question of what is the follow up keeps arising. Development experience shows that the dissemination of information without structuring outputs, insufficient targeting of audience with almost no  follow up actions, has been costly. It has rarely built capacity.

In sum, though activities are being executed and outputs associated with mobilization of the target population, awareness raising  empowerment of farmer’s womens groups are being achieved, it is difficult to imagine how the remainder outputs are going to be accomplished due to the lack of structuring. If this approach continues, one can wonder if planned outcomes will occur on the ground. Ultimately, the technical assistance must be field oriented (i.e. catering for the needs of 15 HDTCs) and conduct its work with the participation of the direct beneficiaries and extension staff. The training manuals must be suited to convey the message to the functionally literate farmers. The pages must be laminated for lasting effect.

- The mission will review the extent to which the processes and methods pursued by the project were designed and implemented to facilitate sustainable impact on livelihoods of poor households, in particular the nutrition status of women and children ;

From visiting 14 HDTCs, the following processing methods appeared useful to enhance the nutrition status of the family unit but were targeted to women:  home-based food processing techniques, and recipes effective  to cook the newly introduced vegetables, seed selection and preservation. However, these methods require improvement. The food processing techniques introduced have very limited shelf life. Above all, there are no estimates of the quantity of women that have taken up these methods and to what extent malnutrition has improved..

- The mission will review the targeting and selection and follow up of beneficiaries;

As already indicated above, targeting in the selection of beneficiaries was adequate. As of December 2002, there has been a substantial participation of women from landless households. By all accounts, this is one vulnerable segment in the rural world. As mentioned, for lack of monitoring within the RBM framework, at this point in time, it is not possible to ascertain what percentage of the beneficiaries have adopted the innovations proposed in terms of horticultural production systems and nutrition awareness.

Some HDTCs staff suggest that approximately 10% of the number of farmers that have received training in the centres adopt the proposed technologies. It is argued that this figure is based on previous experiences nationally. The percentage appears reasonably. The point here is that the Project has a M&E unit and that UNDP advocates result oriented analysis in project management, therefore, it should be possible to confirm whether 10% of farmers are taking up the technology proposed.

- The mission will review whether adequate mechanisms are in place in the project for consulting with and obtaining feedback from the stakeholders.

From the visit of 14 HDTCs, and especially from the interaction with technical staff and direct beneficiaries, it appears that a direct rapport has been established with precise beneficiaries. This is further supported by the participation of block supervisors in the process. Governmental authorities at the central and regional level appear accessible to interact with the Project as well. There was no difficulty with interacting with donors.

- The prospects for sustaining the project's results by the beneficiaries and the host institutions after the termination of the project. The mission should examine in particular:

- the sustainable impacts on the livelihoods of the poorest households and the women and children within those households, especially nutrition impacts;

Perhaps it is far too early to even expect indications of impact since the Project Management considers it is conducting only the pilot stage. However, the potential for impact is sizeable. In the nutrition aspects, given the complexity of the causes of child malnutrition, as already illustrated in Fig 1 of Annex 6, Project management should consider conducting efforts to identify the determinants of diets of children under age 5 and pregnant and lactating women. This is the most vulnerable segment in rural society. To make some promising points of future intervention evident, the relationships between variables should be examined. This effort should lead to upstream lessons for policy making. In all likelihood, this effort can be conducted under the leadership of the nutrition consultant and the participation of local officers of the health organizations and the M&E unit.

- the extent to which the project could establish itself as strategically important project for the Ministry of Agriculture, Government of Bangladesh based on its specificity and scope of activities and impact achieved so far.

The Project has the potential to successfully test a capacity building strategy that ultimately leads to reduce poverty through an environmentally friendly, and knowledge-based technology.  This technology  would be within the reach of the landless, assetless and poor population, especially  deprived women of rural households.   Thus, the Project has the potential to contribute to upstream policy making in poverty reduction in the country and elsewhere in the sub region with similar ecological and socioeconomic conditions. Up to now, because of the conceptual framework in which it was designed, outputs and outcomes are not identified and it is not possible to ascertain what has been achieved in terms of the immediate results.

- The cost-effectiveness of the project.

In order of importance, as measured by the number of times mentioned in TOR, cost effectiveness has to be the most transcendental concept.

Project appraisal concepts are not always easy to measure. The most recent UNDP evaluation manual (2002, p 99) defines cost-effectiveness as “the relation  between the costs (inputs) and results produced by a project. A project is more cost-effective when it achieves its results at the lowest possible cost compared with alternative projects with the same intended results.” To apply this definition we need a nearly complete set of information. It is established that agricultural technology is location-specific and often bound by institutional structures.

Gittinger (1982) within the framework of evaluating agricultural projects states that cost effectiveness is a technique in which benefits cannot be reasonably measured in money terms. The framework may be used within a project to choose among alternative technologies considered to produce intermediate project outputs. It is most often done in the form of the “least-cost-analysis.” The preferred alternative is the one that has the lowest present worth, and the preferences may change when different interest rates are used to determine the present worth.

Cost is reasonably easy to identify and quantify. It is the benefit streams that are complex to identify and quantify, particularly in nutrition and social projects. The Project’s Prodoc, and for that matter other Prodocs within the framework of programs and projects financed by UNDP, do not identify the expected streams of benefits either for society or individual farms. Perhaps, the first lesson learned is that to examine cost effectiveness in a reasonably objective manner, the project preparation process should identify the streams of potential benefits to the different beneficiaries.

Since costs are identifiable and quantifiable, then it would be possible to apply measures of project worth, such as, benefit-cost ratios, net benefit-investment ratios, internal rate of return, and others. These measures would go a long way in obtaining reasonably objective measurements of cost effectiveness.

In this current exercise, an estimate based on experience on the costs of inputs and results produced will be used as proxy to cost-effectiveness. In any event, the absence of projects similar to the present makes it difficult to draw comparative estimates of cost-effectiveness.  Moreover, though at present it is possible to identify the cost of inputs, the ongoing results produced (women empowerment, mobilization of  farmers’ groups, awareness raising in nutrition, etc.) are difficult to quantify.

Nonetheless, from the standpoint of resource use, it is possible to state that there has been value for the resources spent.

- In view of the results of the project the feasibility and desirability of expanding its work into other areas.

It is essential to consolidate what has been achieved so far.. Once the nutrition and the farming systems proposed are internalized by the target population, it may possible to assess the feasibility of expanding the project concept elsewhere.  As stated earlier, the project concept has ample potential for policy making in poverty reduction strategies.

#### Appendix 1

TRAINING DOCUMENTS PRODUCED BY IHND PROJECT

1.	Plant Propagation and Nursery Management – Training Manual.

Compiled and Edited by: Dr. S. P. Ghosh, Sr. Horticulture Programme Development Expert and Dr. A. B. Siddiqui, National Project Coordinator.

I. H. N. D. P. (Bangladesh/97/041), DAE , Khamarbari, Farmgate, Dhaka,

July, 2002. Illustrated.

2.	Fruit Production and Handling- Training Manual. Compiled and Edited

by: Dr. S. P. Ghosh, Sr. Horticulture Programme Development Expert and

DR. M. M. Rahman Khan, Fruit Production Specialist. I. H. N. D. P. (Bangladesh/97/041), DAE , Khamarbari, Farmgate, Dhaka,

July, 2002. Illustrated.

3.      Mushroom Production- Compiled by IHNDP. 15 pages, Illustrated, July, 2002.

Mushroom Production in Bengali. Compiled by IHNDP. 15 pages, Illustrated, July 2002.

4.	An Over-View,  Horticulture in Bangladesh. English Version Compiled by        IHNDP, No author.

The list of training manual and advocacy material is given below:

1.   Training Manual (Fruit Production)

2.   Training Manual (Plant Procpagation and Nursery management)

3.   Mushroom Production (training manual)

4.   Poster on Mushroom

5.   Poster on Banana

6.   Booklet on Mushroom

7.   Booklet on Banana

8.   Brochure on Nutrition

9.   Booklets on Nutri8tion Extension on Complementary foods.

10. Folder on Fashal sangrahatter Projukti (Post harvest)

11. Folder on Aye Bridhe Biponan Kaushal.(Marketing)

12. Folder on Fruit and vegetables Processing.

13. Booklets on osamaya Fullcopy Badhacopy. (Cabbage & cauliflower production)

14. Poster on take seasonal fruits for better nutrition.

15. Booklet on Appropriate use for vegetables.

UNDP. UNDP Results framework. Technical Note. Draft/Revision 5. New York,  December 2000, New York

Annex 4 contains the method and field procedures proposed to undertake the present evaluation.  In principle, the process moves away from assessing outputs against project objectives towards and assessment how outputs contribute together with the assistance of partners to a  change of development outcomes.

UNDP Evaluation Office. Results-oriented monitoring and evaluation. New York, 1999, p. 107

UN. Bangladesh: Common Country Assessment Overview. Dhaka, 2000, p. 15

Ruttan, V. Induced innovation and agricultural development. Food Policy. Vol 2, No. 3 Aug 1977, p 216

See for example: WB. The design of organizations for rural development project. Washington, 1980

UNDP. Development effectiveness. Review of evaluative evidence. New York, September 2000.

See: Audit Report 2001 (section vii); Audit Report 2002,pp 13-14

It is perhaps not surprising that the 2001 Audit Report found that “financial management structure is not appropriate…monitoring , evaluation and reporting systems are absent… internal control system is not satisfactory” (section vii). The 2002 Audit Report reiterated that “monitoring and evaluation were not done by the project authority…internal control systems should be enhanced for better performance of the project.” (p 7, 14)

See: Audit Report of  2002. p 13

See: Hayami, Y.& V. Ruttan. Agricultural development: an international perspective. Baltimore: The John Hopkins Press, 1971, pp 215-230