GOVERNMENT OF THE PEOPLE’S REPUBLIC OF  BANGLADESH

UNITED NATIONS DEVELOPMENT PROGRAMME

FOOD AND AGRICULTURE ORGANIZATION OF THE UNITED NATIONS

GOB/UNDP/FAO JOINT MID TERM EVALUATION MISSION

INTEGRATED HORTICULTURE AND NUTRITION DEVELOPMENT PROJECT

(BGD/97/041)

MISSION REPORT

Mission Members

Ms. Saleha Khatun,  Director, IMED, GOB

Ms. Zinaida Irfat, Deputy Chief, Planning Commission, GOB

Ms. Rebeca Sultana, Deputy Chief, Ministry of Agriculture, GOB

Mr. Murshid Ahmed, Assistant Chief, ERD, GOB

Mr. Samenugus Hilemariam, FAO Consultant

Mr. Eduardo Quiroga, Team Leader

June 2003

# TABLE OF CONTENTS

List of Abbreviations

Acknowledgements

EXECUTIVE SUMMARY

1.	INTRODUCTION

2.	THE PROJECT AND ITS DEVELOPMENT CONTEXT

3.	FINDINGS AND CONCLUSIONS

  - Project Concept and Design

  - Project Implementation

3.3	Efficiency

3.4  	Effectiveness

  - Project Management Arrangements

  - Areas for Consolidating Action

  - Areas of Potential Success

  - Project Results

4. 	RECOMMENDATIONS

- LESSONS LEARNED

ANNEXES

- Terms of Reference

- Mission Itinerary

- List of Persons Interviewed

- Methodology and Mission Implementation

- Issues on Sustainable Farming Systems

- The Nutrition Component in the Context of National Malnutrition Issues

- Project Management Issues

- Minutes of the Debriefing Session with Stakeholders

List of Abbreviations

| ADAB | Association for the Development Agencies in Bangladesh |
| --- | --- |
| ADB | Asian Development Bank |
| BARC | Bangladesh Agricultural Research Council |
| BBS | Bangladesh Bureau of Statistics |
| BIDS | Bangladesh Institute of Development Studies |
| BRDB | Bangladesh Rural Development |
| BS | Baseline Survey |
| CEP | Community Empowerment Project |
| DAM | Department of Agriculture Marketing |
| DANIDA | Danish International Development Agency |
| DLS | Department of Livestock Services |
| DOF | Department of Fisheries |
| EEC | European Economic Community |
| ERD | Economic Relations Division |
| FAO | Food and Agriculture Organization of the United Nations |
| FD | Forest Department |
| FSR | Farming Systems Research |
| GDP | Gross Domestic Product |
| GO | Government Organizations |
| GOB | Government of Bangladesh |
| HDTC | Horticulture Demonstration & Training Centre |
| HYV | High Yielding Variety |
| IFAD | International Fund for Agriculture Development |
| IMED | Implementation Monitoring & Evaluation Division |
| LDC | Least Developed Country |
| MOA | Ministry of Agriculture |
| MOP | Ministry of Planning |
| MV | Modern Variety |
| NAEP | National Agricultural Extension Policy |
| NPAN | National Plan of Action for Nutrition |
| NPC | National Project Co-ordinator |
| NPD | National Project Director |
| NARS | National Plan of Action for Nutrition |
| NGOs | Non-Governmental Organizations |
| NILG | National Institute of Local Government |
| ODA | Overseas Development Administration |
| PEM | Protein Energy Malnutrition |
| PKSF | Palli Karma Sahayak Foundation |
| PRA | Participatory Rural Appraisal |
| SHD | Sustainable Human Development |
| SMS | Subject Matter Specialist |
| TAECC | Thana Agricultural Extension Co-ordination Committee |
| TAO | Thana Agricultural Officer |
| TDCC | Thana Development Co-ordination committee |
| UNDP | United Nations Development Programme |
| UNICEF | United Nations International Children Emergency fund |
| USAID | United States Agency for International Development |
| VBOs | Village Based Organizations |
| WFP | World Food Programme |
| WFS | World Food Summit |

# Acknowledgements

The Mission wishes to express its deep gratitude to the Government of the People’s Republic of Bangladesh for the courtesies extended while executing its mandate. A particular thanks is due to Mr. Md. Nurul Amir, Joint Secretary (Extension); Mr. E. H. Khandker, Director General, Department of Agricultural Extension, Ministry of Agriculture, who have graciously met with the Mission to discuss development issues.

Mr. Jorgen Lissner, UNDP Resident Representative/UN Coordinator; Mr.Larry Maramis, Deputy Resident Representative; Ms. Shireen Kamal Sayeed, Assistant Resident Representative, Ms. Ayashanie Medagangoda Labe, Programme Officer; and other representatives of donor agencies, shared their perceptions on the Project’s potential and constraints with the Mission.

The Mission recognizes and appreciates the effective support provided by the FAO Representative in Bangladesh, Ms. Bui Thi Lan and her staff. Mr. A.K.M. Sayedur Rahman, Programme Officer, provided assistance in organizing the Mission’s appointments.

Appreciation is extended to the Project’s management: Mr. A.K. Rashid Udin Ahmed, National Project Director; Mr. A.B. Siddiqui, National Project Coordinator, and each of the Horticultural Demonstration and Technical Centers (HDTC) who generously spent considerable time with the Mission to provide the information requested. In particular, the Mission has been moved by the openness with which beneficiaries, notably women’s groups, have shared their enthusiasm for the expected outcomes. Their names are listed in Annex 3.

EXECUTIVE SUMMARY

Purpose

In accordance with policies and procedures established by UNDP and FAO, a Mid Term Evaluation was jointly mandated by the GOB, UNDP and FAO. Within the results-oriented framework, the Evaluation was to assess systematically and objectively the relevance, performance, and success of the Project interventions.

The objectives of the Project’s evaluation are:

- To assess progress to date and validate the overall approach.

- To review the design, the execution/implementation modality, the efficiency, and the institutional arrangements.

- To assess outputs in relation to inputs and objectives, impact achieved so far and their sustainability and operational constraints to efficient implementation.

- To recommend adjustment or re-orientation of the Project, if any.

The review of Project management issues and those related to the technical design encompassing the horticultural and nutrition components requiring decisions and actions have been predominant. These are dealt with in Annexes 5,6 and 7; only the essential features are expounded in this Main Report. Indeed, the recommendations focus on outlining a strategy to gear the Project towards a framework to generate outcomes. Above all, an actionable guideline is proposed to launch now an institutional framework needed to reinforce early indications of potential success in the generation of benefit streams to marginal farmers and assetless folk who are predominantly women from landless households.

The Mission commenced on 28 April 2003 and there were briefing sessions with the UN implementing agency, UNDP management and program officers, Project management and GOB representatives held in Dhaka. The Mission conducted field activities from 1 to 9 May, 2003.

The Mission was composed of GOB representatives: Ms. Saleha Khatun, Director,

IMED; Ms. Zinaida Irfat, Deputy Chief, Planning Commission; Ms. Rebeca Sultana,

Deputy Chief, Ministry of Agriculture; Mr. Murshid Ahmed, Assistant Chief, ERD., Mr.

Samenugus Hilemariam, FAO Consultant. The team leader was Mr. Eduardo Quiroga,

Evaluation Specialist.

###### Method and Procedures

It became evident that the participatory approach was in step with the TOR requirements. The participatory approach is a collaborative evaluation process. It builds on strengths and it values the contribution of everyone involved. Every stakeholder has an opportunity to present its case.

The Mission consulted with the technical staff of all of the 15 Horticultural Demonstration and Technical Centers (HDTC) and  interacted with the direct beneficiaries, notably women of landless households as they represent approximately 75% of targeted beneficiaries. Their perceptions were elicited within the framework of outputs and outcomes achieved. he names of all persons interviewed are in Annex 3.

Detailed technical discussions were also conducted on design, implementation, management, and monitoring issues. The complete list of field visits and working sessions with stakeholders is in Annex 2.

Although there was data available, analytical information to conduct a results-oriented evaluation was unavailable. This was because the Prodoc was designed outside of the RBM paradigm. In consequence, the M& E procedure currently focuses on input supply distribution. However, within the limited time available and through the use of techniques, such as Focus Group Discussion, the Mission could validate the current status of the Project’s progress through field visits conducted in beneficiaries’ plots.

Overall, the Mission’s approach has been forward-looking. Despite the limited time available, given the Project’s complex technical scope and the ramifications of UNDP’s shift in paradigm management, it is the Mission’s considered opinion that it has been able to understand the Project’s pervasive issues;  and the concept together with expected results in order to submit to the consideration of all stakeholders, its findings, recommendations and lessons learned on the Project’s development results.

Findings

Project Concept and Design

### The Project is designed to concentrate on 15 Horticulture Technical Demonstration Centers (HDTC). The selection of sites has been facilitated through the use of secondary data and discussions with local people/leaders and government officials. The HDTCs are equipped with basic tissue culture facilities, operated on a semi-commercial scale to produce disease-free planning material, a mushroom production facility and a fruit-vegetable processing facility. In terms of DAE’s manpower capability, a training program has been enhancing the skills of all relevant officers (SMOs, Block supervisors) through selected study tours to neighboring countries in the region and in service training about technology transfer activities.

The development of technical capability of beneficiaries will be the core element of the Project. In training an estimated 31,400 men and women through the 15 HDTC’s, the Project hopes to achieve its targets of capacity building and human resource development. These will include farmwomen, homestead owners, marginal farmers, landless farmers, primary school teachers, school children, unemployed rural youth and NGO’s. Training activities will vary in duration and content depending on the needs of the situation. Nurserymen/women and traders will also be beneficiaries of this training.

The Project’s target beneficiaries are the small, marginal and landless farmers, particularly women within the areas of the HDTCs. During the Project’s time frame, it has been envisaged to target approximately 31, 400 farmer beneficiaries out of whom 23,900 would be women farmers. It is also expected to target 1,370 technical personnel in both public and private sectors. Thus, the Project is to train nurserymen/women who having received elite material for propagation and will be raising quality planting materials with the assistance of the DAE staff. The Project will also provide traders with skills in handling, grading and packaging produce and even assist those who will develop export links. Finally, the Project will provide nutrition awareness and education programmes through supply of highly nutritious fruits and vegetables.

Overall the Project design reflects an output oriented approach that prevailed in the programming framework before the institutionalization of the RBM paradigm within UNDP. The immediate objectives fail to sequence the institutional adjustments needed to ensure beneficiaries’ income improvement derived from the technological innovations introduced to increase physical productivity. This is a  key expected outcome.  Similarly, the nutrition factor is not sequenced within the institutional framework needed to take advantage of the technological innovations introduced. Nutrition awareness through availability of vegetable crops is only part of the solution. Nutrition awareness is necessary, but not sufficient in itself, to enhance the nutrition status of a certain segment of society in a given context.

In terms of development objectives, one assumption of the output  oriented approach was that the on-site availability of technological inputs, and/or extension resources, was sufficient for technological change to take place and that socioeconomic development will necessarily ensue. As this assumption was devoid of development experience, the current challenge of how to create viable rural institutions for sustainable farming systems is more compelling.

Relevance

Considering the characteristics of the agricultural sector, the nutrition factor in sustainable human development, poverty alleviation and gender considerations, the Project objectives propose a broad strategy to build the capacity of individuals and organizations. In addition, it aims to enhance the level of food security and nutrition by boosting the efficiency of horticultural production systems and associated income generation activities encompassing homemade food processing.

- The Project is relevant to the needs of the GOB and conforms to its priorities and current policies. Indeed, the GOB is committed to halve its malnourished population by the year 2015.

- The Project has the potential of successfully testing a capacity building strategy that ultimately leads to reduce poverty through an environmentally friendly, and knowledge-based technology, within the reach of the landless and without assets, in particular deprived women of rural households.  Thus, the Project has the potential to contribute to upstream policy making in poverty reduction in the country and elsewhere in the sub region with similar ecological and socioeconomic conditions. In terms of the CCA framework, the Project is relevant to three clusters of rights:

- Food and Nutrition (Right to Survival)

- Employment/Income (Right to Livelihood)

- Empowerment/Association (Right to Participation)

- These elements are in conformity with UN Common Country Assessment and the Administrator’s Long Term Operation Plan.

- The Project meets the needs of the direct beneficiaries. It addresses the learning requirements of landless and deprived women of rural households. It directs resources towards the interrelated dimensions of individual learning in the context of organizations. It intends to create an enabling environment for the target population, composed of landless and marginal farming communities, and strives to improve the productivity and incomes levels together with nutritional status.

Project Implementation

The Project has completed the start up phase. The response has been encouraging. The process of social mobilization has been successful. 60% of the total targeted population has been mobilized. Women participation among direct beneficiaries is within the target (75%).  It has imparted several types of training to raise awareness on nutrition issues, among other skills, to targeted beneficiaries.  The Project has spent 23% of total resources allocated within 40% of the execution period.

The crux of the problem is that from the methodology standpoint, it is unfeasible to establish a quantified rate of achievement.

There is one structural reason for these design shortcomings. It is the output oriented framework combined with lack of RBM knowledge.  Perhaps, it is not surprising that the M&E system is short in RBM oriented records. This unit needs to shift to the RBM framework with the utmost urgency.

There has been observable progress towards achieving immediate results. New relationships, attitudes and values that govern interaction among folks in the Project area that contribute to economic and social development have emerged. This is also known as social capital and is a critical ingredient for development effectiveness.

Direct observations and the field data collected by the Mission suggest that there are outputs produced on in process, not amenable to quantification.  They have the potential to contribute towards the achievement of immediate objectives.

- The Project has successfully organized beneficiaries in all the 15 HDTCs in farmer groups. More than half of the expected number is already participating in Project activities of which 75% are women of landless households. Interaction with direct beneficiaries, notably women, shows commitment and active participation. It has been reported that some groups provide crisis loans to its members with a 10% interest rate as opposed to the usury rates between 120 to 240%.

- In fact, there is evidence indicating that the Project’s farmers, especially women, are motivated to change and are market oriented.

- There are 987 farmer groups that have opened bank accounts with savings reaching Tk. 1,880,100. Each group member saves a fixed rate of Tk 5-10 per week. This testifies to the desire for increased material welfare. Group discussions held by the Mission with farmers groups in the HDTCs confirmed the desire for increased wealth and expectations that change (the innovations introduced by the Project) will in fact increase wealth.

- These attitudes are essential requisites for motivation to change. They point to the vital need of producing and demonstrating successful innovations. And they all constitute indispensable social capital that is vital for social and economic development.

- Group discussions suggest that Project outputs in process are already useful to the targeted beneficiaries, especially women from landless households. From visiting 14 HDTCs, the following techniques were being diffused:   home-based food processing, , recipes to cook the newly introduced vegetables, seed selection and preservation. Women manifested their appreciation to intermediary outputs imparted by the Project. This is most likely because, a certain amount of vegetables and home-based foods processed, are consumed by the family unit with possible improvement in dietary conditions among targeted beneficiaries. However,  there are no estimates of the quantity of women that have taken up these techniques and to what extent malnutrition has improved.

- Although only 15% of targeted beneficiaries are male, there is an overall acceptance of these outputs delivered as corroborated by direct interaction with beneficiaries.

- Crop budgets collected by the Mission were analyzed from  a sample of summer vegetables (Indian spinach, okra, green chili) and winter vegetables (tomato). Unitary prices per ha for all inputs, interest on inputs (20%), land lease, labor, and management costs (50% of labor) were taken into account. It is noteworthy that since these are labor-intensive crops labor expenses represent typically between 41 and 48% of total cost. Net revenue per ha was computed by subtracting from gross revenue all costs.  The net financial results are encouraging for small shareholding  farmers. The range is as follows:

Green chili =  77 674 Tk/ha

Tomato  =  36 492 Tk/ha

Okra  =  27 408 Tk/ha

Indian spinach  =  8493 Tk/ha

The Baseline Survey has no information on the above crops for comparative purposes.

It is possible to state, therefore,  that there has been value for the resources spent as will be expounded below.

Project Results

As realistic as they are the unwitting design shortcomings bringing about snags in measuring activity execution within the framework of RBM, the field visits conducted in 14 HDTCs testify that the Project has implemented a sizeable number of activities. Therefore, the following pivotal outputs have been accomplished or are in process.

Social Mobilization of Targeted Beneficiaries

- Nearly 16, 000 women from landless households have been successfully organized in groups. This is approximately half of the targeted population. Several elements of empowerment emerged from discussions conducted with women’s groups.

- First, their organizational commitment enabled them to become organized. Local organization is a key element for development effectiveness because through this capability is often possible to manage resources for the benefit of the many rather than just the few.

- Second, through this organization they could share common views that led to greater self-confidence. Also, information as resource becomes possible since they now constitute an assembly with a common purpose.

- Third, the element of inclusion became evident, as poor women of landless families were traditionally excluded groups for priority setting and decision-making. This builds commitment to change.

- Finally, it can be expected from this process of empowerment, that accountability mechanism may emerge and are already emerging.

- The type of training imparted to women’s groups (primarily nutrition, and horticultural production including home-made food processing) meets their current needs. They often requested more training in horticultural and associated activities.

- There are early signs of successful income generation initiatives primarily based on homemade food-processing techniques acquired through the Project. In addition, crop budgets collected from selected vegetables show encouraging net returns to small shareholding farmers.

- The Project has successfully raised awareness about the importance of providing nutrition awareness in all of the HDTCs. A wide variety of vegetables is now being consumed as soups and pickles.

Training Imparted

A critical mass of manpower in the field of horticulture is being developed with capabilities to train trainers from the farming communities.  Up to December 2002, 1420 field level officials were trained in 11 different courses and 15,350 farmers were trained in 16 different subjects.

Many trained men and women farmers have already started growing mushrooms for home consumption as processed and fresh food.

The following demonstrations have been established: 1375 nutrition gardens, 7 high density banana plots, 31 high density litchi and 36 high density mango sites.

Nutrition Education/Awareness Raising

Awareness raising campaigns have been conducted on: hygienic preparation and handling of vegetables and fruits at the household level to reduce nutrient losses during cooking; and complementary low cost food associated with consumption of vegetables as soups, has been directed to housewives.

Horticultural Production Systems

As part of fruit village demonstrations, 6,030 homesteads were planted with 30,150 fruit-trees of litchi, mango, sapota, guava and lime.

A good number of Mother Tree Orchards, clonal hedges, have been established in all 15 HDTCs with recent fruit varieties.

More than 80,000 elite planting materials of fruits and quality planting materials of turmeric, ginger and vegetable seeds and mushroom spawns were produced and distributed to the farmers.

On mushroom demonstration, there were 48 on production, 48 on food preparation, 6 on post-harvest demonstrations and 45 on processing at household level.

RECOMMENDATIONS

For the Attention of Project Management

Consider the following actionable guideline to enable beneficiaries to continue enhancing their know-how in horticultural production systems and home-based food processing supported by (1) decentralized services and (2) motivated by a business approach to improve beneficiaries’ incomes. As subsidiary effect, there would be greater availability of nutritious vegetables and fruits to enhance diets in the Project area.

The Way Forward:  Business Plan for each HDTC and Decentralized Support Services

The fundamental principles are:

- The current number of existing groups should be strengthened rather than expanded.

- Technical training to beneficiaries in horticultural production systems and home-based food processing should consolidate acquired knowledge and become market oriented and marketing driven.

Business Plan for each HDTC

Within the participatory framework, each HDTC should draft a business plan centered on the needs and potential of direct beneficiaries. The plan should be managed by the farmers’ groups.

- Farmers’ needs must be assessed in detail or validated.

- Physical production potential must be determined in terms of ecological and climatic factors.

- Actual production capability, in terms of crops or produce processed, must be geared to the market and marketing arrangements should be organized in consequence.

- Based on the above, the credit requirements should be determined taking into account farmers’ groups savings.

- Taking into account the above factors, the type and length of technical assistance will be determined.

Decentralized Support Services

- For the remainder of the Project, the technical assistance must be field oriented. It should cater for the needs of 15 HDTCs and conduct its work with the participation of the direct beneficiaries and extension staff. The training manuals must be suited to convey the message to the functionally literate farmers. The pages must be laminated for lasting effect.

- Where opportunities arise, institutional collaboration should be organized with civil society, especially in the areas of crop production and marketing, credit, sustainability issues (BRAC, Milk Vita, Helen Keller, and others). Possible collaborative arrangements can defer immediate necessary expenses and consequently produce benefits at an earlier date or even provide inputs that otherwise would be unavailable such as credit funds for crop production.

- Certain HDTCs could contain horticultural farm models supported by crop budgets and marketing strategies. If the market potential of certain HDTCs is limited, income-generating activities should therefore take greater predominance.

- Consider training in literacy and numbers  for all members, not yet functionally literate, to improve their capacity in the production and marketing of produce.

- A results-oriented M&E system must be in place urgently.  The results of three systems need to be monitored simultaneously

  - Activity execution in production-marketing of crops introduced

  - Activity execution in nutrition awareness-malnutrition issues

  - Management operations in 15 HDTC

  - A logical framework analysis should be conducted for each of the HDTC and the Project as a whole; and it should be updated until the end of the Project. Insufficient monitoring jeopardizes the performance of the Project and puts at risk the heavy investment by poor landless women.

The Nutrition Component

As subsidiary effect, there should be greater availability of nutritious vegetables and fruits to enhance diets in the Project area.  However, given the complexity of the causes of child malnutrition, in order to draw policy lessons, consider conducting efforts to identify the determinants of diets of children under age 5 and pregnant and lactating women. The idea is to make evident some promising points of future intervention.  To simplify the complexity of the nutrition system, it could be divided in three sub systems: crop production, processing and distribution to the consumer.

  - From standpoint of crop production, price relationships of all crops produced should be reviewed, the nutrition implications of current agricultural policies as reflected within the Project area, the workings of the agricultural credit in terms of how they affect food security and nutrition, and to what extent infrastructure considerations (physical and institutional) affect crop decisions, and other context specific issues.

  - From a processing and distribution point of view, the current mechanisms, procedures to distribute food within the Project area should reviewed, including the marketing margins and profits at each stage of the marketing chain; the nature and coverage of processed foods, if any; the cost of transportation of certain foods; and others.

  - The consumer habit subsystem should look at the food expenditure pattern within the Project area, food taboos, food consumption pattern within the family according to sex and age, and others. Seasonal variations should be detected from the sample studied.

  - Interwoven in all of the analysis should be the role of the public sector. Amounts, availability, acceptability, and effectiveness of different services related to nutrition provided by the public sector and budget analysis of different and existing programs need to be addressed such as, health and nutrition education, child feeding programs, etc.

The ultimate aim of this exercise is to develop a nutrition framework that would establish the relationship of diet to family income, to religion, to morbidity and income, to mortality and income, to educational level of parents, to use of health services, to presence of non nuclear family members, to occupation, to size of family and per capita food expenditure, to maternal employment (outside household), to safety of water supply (and other environmental hygiene factors), to awareness of nutrition, to practice of family

For the Attention of Project Management and Ministry of Agriculture

A Framework for Project Sustainability

Finally, based on the Mission’s consultations with key stakeholders, a long-term framework for sustainability purposes has been retained.

- The knowledge of enhanced horticultural production systems and home-based food processing must be embedded within the rural communities of the targeted beneficiaries. It should be patterned after the IPM clubs.

- Identify natural leaders in the rural communities of targeted beneficiaries.  These natural leaders with the support of the Project should ultimately provide an enabling environment in their communities, such that the Project results can achieve dynamic sustainability.

- The GOB through the DEA must play a catalytic role in maintaining the sustainability efforts of IPM and future Horticulture clubs. This initiative can be achieved through the organization of farmers’ days twice a year.   This platform would provide opportunities for farmers to interact amongst themselves and where new technical information could be released.

- Finally, in terms of an exit strategy, the GOB should take over full responsibility to continue the Project activities after project completion and provide necessary financial support from the national budget.

Possible Need of Additional Resources in several HDTC

The GOB should consider furnishing the Rangamati HDTC and filling several other personnel requirements and equipment for other HDTCs. For the remainder of the Project, it will be vital to ensure the continuity of the national personnel in order to ensure successful results.

For the Attention of GOB, UNDP, FAO

A Framework for Project Management

When the forthcoming UNDP guidelines for national execution (NEX) are issued and with the presence of the Horticulture Program Development Specialist and other relevant stakeholders, consider preparing a new workable management framework encompassing the management of the 15 HDTCs.

After the formulation of the 15 Business Plans for the HDTCs, as the number of activities may increase as compared to the present context, consider reviewing the budget to ensure successful results.

- Each HDTC objectives and targets for the remainder of the Project should be established. Taking into account the specific agroecologic setting, it must be oriented to increase the incomes of beneficiaries in a sustainable manner based on the technology transfer.

- An overall work plan covering the full Project horizon will be needed in terms of physical activity execution and associated cash flow. This must be supported by annual detailed work plan. A logical framework is essential supported by a results-oriented monitoring of outputs and outcomes.

- This plan should also consider overall manpower requirements and equipment until the end of the Project.

- The Project’s work plan should integrate all of the HDTCs work plans encompassing the logical framework supported by a results-oriented monitoring of outputs and outcomes.

For the Attention of UNIA

For the remainder of the Project, theUNIA management of technical assistance component should ensure greater results in monitoring consultants activities and in coordination with key stakeholders. It is vital that consultants’ reports, including backstopping visits, should circulate rapidly among end-users, no more than 10 working days after consultants’ departures.

The technical assistance for the remainder of the Project should concentrate on capacity development through situational analysis of the constraints to building this capacity within the context of each HDTC. Requests for technical assistance should emerge from end users. Therefore, the UNIA must deploy hands-on efforts to ensure that technical assistance is participatory and field oriented. All consultants’ recommendations have to be validated by consultants with end users before their departure.

The following consultants must be fielded.

Long Term:

- Senior Horticulture Program Development Expert: The project duration is 60 months but provision for a long-term international consultant is 45 months. Provided allocated funds permit, the consultant’s term should be extended to cover the Project time horizon.

Short-term

- International Consultants: The Nutrition Education Specialist has completed his/her duties. If, during the elaboration of the HDTCs Business Plans there is felt a need for further work from this consultant, an extension of his/her duties can be considered.

- Food Processing/Post Harvest Technologist, Plant Propagation & Tissue culture Specialist.  The Project will benefit, if separate consultants on each discipline could be fielded.

- Unspecified Consultants: Provision for unspecified consultants can be fixed for 6 m/m instead of 2 m/m because evidence shows that a 2m/m duty is ineffective.

Finally, with the active participation of Project management consider conducting a continuous quality control of the technology proposed to beneficiaries.

- At the project level, with the active participation of management organize a committee (composed by certain members of the team of consultants, advanced farmers from Project area and  other relevant areas and other sources of experienced individuals or organizations ) to validate the recommendations proposed by consultants. And in the future, all recommendations should be validated by the same committee and others as management sees fit, before consultant’s  departure.

- FAO backstopping mission could conduct continuous evaluation exercises about the technology being introduced and the training conducted in terms of its curricula and execution. The overall purpose would be to ensure results on the ground. The Regional FAO office is in an enviable position to conduct this work because of its programmed  visits,  access to technological information and experienced personnel.

LESSON LEARNED

In the search of ensuring food and nutrition security within the framework of right to survival, embedding high productivity know-how within the social structure of rural communities looms as a promising strategy. For example, IPM clubs and village nurseries appear to adapt themselves in farmers’ communities with a moderate degree of dynamic sustainability. Governmental efforts are required to continually rekindle the motivation of farmers through farmers’ days at least twice a year.  This platform would provide opportunities for farmers to interact amongst themselves and will be a venue where new technical information could be released.

- INTRODUCTION

Scope

In accordance with policies and procedures established by UNDP and FAO, a Mid Term Evaluation was jointly mandated by the GOB, UNDP and FAO. Within the results-oriented framework, the Evaluation was to assess systematically and objectively the relevance, performance and success of the Project interventions.

The objectives of the Project’s evaluation are:

- To assess progress to date and validate the overall approach.

- To review the design, the execution/implementation modality, the efficiency and the institutional arrangements.

- To asses outputs in relation to inputs and objectives, impact achieved so far and their sustainability and operational constraints to efficient implementation,

- To recommend adjustment or re-orientation of the Project, if any.

Although managing for results is not new to UNDP, what makes the current approach different is the determination to make Results Based Management (RBM) the driving force within the organization’s institutional culture and practice.  This paradigm shift in management has been, to a large degree, a response to the demand for enhanced development effectiveness.  Among other things, it has become evident that well managed projects with efficient outputs did not have discernable effects on development. The attention has therefore centered on outcomes: realistic and positive changes in specific development conditions. Indeed, by focusing on outcomes, UNDP aims for results where they are most needed— in people’s lives.

The challenge to, both program management and the evaluation process, emerges with projects that were programmed before UNDP shifted its focus from outputs to outcomes. This is the case with the present Project. It  was designed in the 1990s under the framework of an output-oriented project.  Henceforth, the Project interchangeably will be referred to as input supply project.

Consequently, the review of Project management issues and those related to the technical design encompassing the horticultural and nutrition components requiring decisions and actions have been predominant. These are dealt with in Annexes 5,6 and 7; only the essential features are expounded in this Main Report. Indeed, the recommendations focus on outlining a strategy to gear the Project towards a framework to generate outcomes. Above all, an actionable guideline is proposed to launch now an institutional framework needed to reinforce early indications of potential success in the generation of benefit streams to marginal farmers and assetless folk who are predominantly women from landless households.

The Mission was composed of GOB representatives: Ms. Saleha Khatun,  Director,

IMED; Ms. Zinaida Irfat, Deputy Chief, Planning Commission; Ms. Rebeca Sultana,

Deputy Chief, Ministry of Agriculture; Mr. Murshid Ahmed, Assistant Chief, ERD., Mr.

Samenugus Hilemariam, FAO Consultant. The team leader was Mr. Eduardo Quiroga,

Evaluation Specialist.

###### Methodology

The Mission reviewed all the Project documents, i.e. the Prodoc, Inception Report, FAO monitoring mission reports, technical reports produced, relevant files, correspondence and other documents connected with the Project.

It became evident that the participatory approach was in step with the TOR requirements. The participatory approach is a collaborative evaluation process. It builds on strengths and it values the contribution of everyone involved. Every stakeholder has an opportunity to present its case.

Because the participatory approach allows greater stakeholders’ participation in the evaluation process, this approach is compatible with the shift from outputs to outcomes within the results-oriented framework. Project management participates in selecting the outcomes produced for assessment, encompassing outcomes in process and those unexpected.

A framework of the participatory approach supported by the results chain concept in the context of the results oriented evaluation provided the directive to conduct the present evaluation. This is  part of the work plan prepared to conduct fieldwork encompassing consultations with beneficiaries in the Project area in coordination with the Project management in conformity with TOR (Annex 1). The overall methodology, timing, and organization is in  Annex 4.

Mission Implementation and Time Frame

The Mission commenced on 28 April 2003 and there were briefing sessions with the UN implementing agency, UNDP management and program officers, Project management and GOB representatives held in Dhaka. The Mission conducted field activities from 1 to 9 May, 2003.

The Mission consulted with the technical staff of all of the 15 Horticultural Demonstration and Technical Centers (HDTC). Divided in two sub-teams, the Mission visited 14 HDTCs.  Detailed technical discussions were conducted on design, implementation, management, and monitoring issues. The complete list of field visits and working sessions with stakeholders is in Annex 2.

The Mission interacted with the direct beneficiaries in 14 HDTCs, notably women of landless households as they represent approximately 75% of targeted beneficiaries. Their perceptions were elicited within the framework of outputs and outcomes achieved.  These perceptions were gathered through open-ended interviews, group interviews, direct observations, documentation and other field techniques suitable to the issue at hand.

It was instructive for the Mission to hold focused interviews with women’s groups who were actually launching income generation initiatives. The names of all persons interviewed are in Annex 3.

Although there was data available, analytical information to conduct a results-oriented evaluation was unavailable. This was because the Prodoc was designed outside of the RBM paradigm. In consequence, the M& E procedure currently focuses on input supply distribution. This unit needs to shift to the RBM framework with urgency. However, within the limited time available and through the use of techniques, such as Focus Group Discussion, the Mission could validate the current status of the Project’s progress through field visits conducted in beneficiaries’ plots. In this context, Annex 7 reviews project management as mandated by the TOR (Annex 1) and issues are tackled one by one. This is done against the backdrop of UNDP’s shift to RBM  as an institutional culture.  Since the present Project was programmed before this paradigm shift, the manifold implications, both, in terms of project management and evaluation issues are examined.

Improving the income of small, marginal farmers and women from landless households is a central expected outcome. To obtain a glimpse of potential income changes that could be induced by productivity gains from the technology proposed by the Project, crop budgets were collected by the Mission during the HDTCs visits. (See: Appendix 1 of Annex 5).  An overview of the role of technological innovations in the context of sustainable farming systems and the institutional prerequisites needed for sustainable income generation in the Project area is examined in Annex 5.

To ascertain the quality of training provided, exclusive focus on farmers interviewed (female members of landless households) was placed on the assumption that if extension agents received quality training, this in turn would be reflected on the training provided to farmers. Annex 7 (section 3) reviews training issues within the current programming framework and highlights the need to frame the technological changes introduced by the Project within an institutional framework to make the proposed farming system sustainable, especially in terms of income generation. Appendix 1 of  Annex 7 contains the documents produced.

Annex 6 sketches a framework to identify the determinants of diet among vulnerable segments in the Project area. This exercise can provide lessons for future interventions and policy development.

A debriefing session to share the Mission’s preliminary findings and recommendations with GOB authorities, executing agency, and stakeholders was held on 18 May. Annex 8 contains the minutes of the debriefing session.

###### Structure of the Report

The structure of the present report consists of an introduction, the Project’s development context, the findings and conclusions, followed by lessons learned. Specifically, the findings are examined with special reference to Project design, relevance, implementation issues related to efficiency, effectiveness and management arrangements.  The Project outputs/outcomes are delineated. Recommendations focus on reinforcing initiatives that demonstrate the potential for success and ascertaining consolidating action.

Overall, the Mission’s approach has been forward-looking. Despite the limited time available, given the Project’s complex technical scope and the ramifications of UNDP’s shift in paradigm management, it is the Mission’s considered opinion that it has been able to understand the Project’s pervasive issues;  and the concept together with expected results in order to submit to the consideration of all stakeholders, its findings, recommendations and lessons learned on the Project’s development results.

2.	THE PROJECT AND ITS DEVELOPMENT CONTEXT

The Integrated Horticulture and Nutrition Development Project (the Project) was signed in June 2000. It was designed to achieve its objectives within an implementation period of five years. Activities were launched in October 2000. The year 2001 reported limited achievements due to start-up delays, notably manpower recruitment and procurement. When start-up activities were completed in 2002, expected results were achieved. During the first TPR (July 2002), it was agreed that the mid-term evaluation would take place during the first quarter of 2003.

Problems that the Project Seeks to Address

The Project seeks to address pervasive problems in horticultural production systems and associated nutrition issues. Farmers are traditionally engaged in rice based farming systems. As the risks associated with changing production systems are substantial, priority is given to the staple crops. These risks are compounded by limited availability of improved varieties of fruits, vegetables, and spices; lack of access to quality planting material and plant protection systems. It is not surprising therefore, that farmers lack training in the use of improved production techniques, post harvest and marketing technologies; thus low productivity is typical. This is aggravated by seasonal fluctuations in fruits and vegetable production throughout the agricultural year.

Development experience around the world suggests that horticultural production (vegetable, fruits, spices) has the economic potential to enhance income of small landholders  because it is labor intensive and carries high prices in the market. Market and marketing arrangements are critical because horticultural crops are perishable and seasonal. Even with home processing, horticultural crops cannot be totally consumed by the family unity. There remains a surplus for the market. But they should reach the consumer in good appearance and acceptable quality often within a narrow margin of a few days, if not hours. Otherwise, losses due to spoilage are imminent.

Malnutrition is a serious health concern in the country. The direct victims are children and women. Despite the number of programmes undertaken to improve these conditions, the prevailing child malnutrition rate is 56% and the under-five mortality rate is 96%. These rates reflect moderate food and nutrition insecurity. This is considered as a direct consequence of limited access and availability to nutritious foods. The root cause of this situation is poverty and the situation is exacerbated by a lack of nutrition education.

The GOB, in line with its fifth Five-year Plan (1997-2002) and three years rolling plan, (2002-2004) has pledged to increase both production and productivity of horticultural crops. It is envisaged to facilitate the production of profitable high value cash crops together with major fruits and vegetables on a year round basis. While these crops will be commercialised through the application of appropriate technology, priority would be given to qualitative and quantitative improvement of these commodities. It is anticipated that improvements in nutrition should go hand in hand with the efforts to enhance production.

Project’s Immediate Objectives

The Project’s immediate objectives are:

- To develop sustainable capability among low income communities, specifically poor women farmers, in increasing productivity and year round production of horticultural crops (fruits, vegetables and spices) through the introduction of superior quality planting materials and seeds promotion of production skills.

- To minimise post-harvest losses, improve post-harvest handling and maximise primary producers profits and income through the promotion of on-farm and community-based produce handling methods as well as to enhance marketing support services.

- To promote income-generating activities, including agro-processing, to enable the optimum utilisation of horticultural produce to supplement family incomes, with additional support from micro-credit and food assistance programmes especially for poor and disadvantaged women.

- To increase the nutritional awareness among the beneficiaries and to develop a comprehensive food-based nutrition programme to reduce malnutrition in the target groups comprised mainly of women and children.

Project’s Development Objectives

The Project’s development objectives are:

- To enhance the level of food security and nutrition by improving the efficiency of the horticultural production system and associated support services through the application of modern technologies and diversified cropping patterns that will bring about greater productivity and higher incomes to the small farmer communities in a sustainable manner.

- To improve the nutritional status of the population through creating an environment in which households have sufficient access to fruits and vegetables at affordable prices and the necessary knowledge and skills to prepare and consume these foods to complement their diet, specifically targeting the poor women farmers of Bangladesh.

Overall the Project design reflects an output oriented approach that prevailed in the programming framework before the institutionalization of the RBM paradigm within UNDP. The immediate objectives fail to sequence the institutional adjustments needed to ensure beneficiaries’ income improvement derived from the technological innovations introduced to increase physical productivity. This is a  key expected outcome.  Similarly, the nutrition factor is not sequenced within the institutional framework needed to take advantage of the technological innovations introduced. Nutrition awareness through availability of vegetable crops is only part of the solution. Nutrition awareness is necessary, but not sufficient in itself, to enhance the nutrition status of a certain segment of society in a given context. Malnutrition is a complex problem with multiple factors, as discussed in Annex 6.

In terms of development objectives, one assumption of the output  oriented approach was that the on-site availability of technological inputs, and/or extension resources, was sufficient for technological change to take place and that socioeconomic development will necessarily ensue. As this assumption was devoid of development experience, the current challenge of how to create viable rural institutions for sustainable farming systems is more compelling.  As technological constraints on growth of agricultural productivity have become less binding, there is an acute need for institutional adjustments (innovations) that will result in a more effective realization of the new technical potential within the human development framework.

Implementing Agencies

The Project’s main stakeholders are: the Department of Agricultural Extensions (DAE) under the Ministry of Agriculture executes the Project. Because of its technical expertise in the development and application of technologies in agriculture, the Food and Agriculture Organisation of the United Nations (FAO) is the UN implementing agency (UNIA). The Project is coordinated by a National Steering Committee, chaired by the Secretary, Minister of Agriculture with the National Project Director (DG, DAE) as member secretary in order to provide policy advice and guidance.

Results Expected at the End of the Project

The diversification of the production base and intensification of agriculture is practically the only option open to the country. In this context, the following results are expected by the end of the Project:

- Improved food production, productivity and economic status of beneficiaries.

- Enhanced infrastructure facilities and technology transfer program for improving human resource capacity.

- Improved input supply of services.

- An organized produce disposal supply system (marketing)

- Increased availability of processed horticultural products.

- Improved nutrition through increased consumption and nutrition awareness.

- Sustainability and Project impact.

3.	FINDINGS AND CONCLUSIONS

  - Project Concept and Design

With only 0.09 ha of land per capita, Bangladesh has one of the lowest land per capita in the world. About 50 % of the rural homes own less than 0.2 ha/family with approximately 50 % of the total population living below the poverty line.

Historically, the horticultural sector has been relatively neglected and relegated to play a minor role in food production, as the government gave high priority to cereal and staple substitute production in an attempt to achieve self-sufficiency. Perhaps the country’s most important horticultural production unit is the homestead, of which there are 19.4 million with 15.9 million in the rural areas. In total area, these homesteads total  0.45 million hectares.

Homesteads are multi-purpose entities with dwellings, vegetables, spices, fruits and forest trees. For some families, these production units are the only source of existence that provides shelter, fuel wood and food. In better-endowed areas, homesteaders produce horticultural crops in adjacent fields, notably in the winter season when cereal crops are harvested.

Another significant feature in homestead farming is the role of women. Almost without exception, women play a major role in managing the homestead unit, apart from food preparation and other domestic activities for the family. Especially single and abandoned women, left destitute, play a major role as heads of households.  Since women have limited scope of off-farm employment, most are confined to homestead activities. It has been reported that about 80 % of the rural households have vegetables, fruits, and spices in their allotments. In consequence, across the country gender involvement in horticultural activities is comparatively substantial.

The intensity of cropping and the level of management varies from region to region, often dictated by soil and climatic limitations, choice of crops and their ability to adapt to a mixed cropping pattern. In hilly areas, where cereal production is somewhat limited, horticultural crops are grown throughout the year, especially at Modhupur in Mymensingh, Bhawal Garh in Dhaka, Lalmai area in Comilla, the Barind tract in Rajshahi, the Chittagong Hill Tracts and other hilly areas bordering the north-west boundary with India.

### The Project is designed to concentrate on 15 Horticulture Technical Demonstration Centers (HDTC). The selection of sites has been facilitated through the use of secondary data and discussions with local people/leaders and government officials. The HDTCs are equipped with basic tissue culture facilities, operated on a semi-commercial scale to produce disease-free planning material, a mushroom production facility and a fruit-vegetable processing facility. In terms of DAE’s manpower capability, a training program has been enhancing the skills of all relevant officers (SMOs, Block supervisors) through selected study tours to neighbouring countries in the region.  In-service training about technology transfer activities has also benefited officers’ abilities.

The development of technical capability of beneficiaries will be the core element of the Project. In training an estimated 31,400 men and women through the 15 HDTC’s, the Project hopes to achieve its targets of capacity building and human resource development. These will include farm women, homestead owners, marginal farmers, landless farmers, primary school teachers, school children, unemployed rural youth and NGO’s. Training activities will vary in duration and content depending on the needs of the situation. Nurserymen/women and traders will also be beneficiaries of this training.

The Project’s target beneficiaries are the small, marginal and landless farmers, particularly women, within the areas of the HDTCs. During the Project’s time frame, it has been envisaged to target approximately 31, 400 farmer beneficiaries out of whom 23,900 would be women farmers. It is also expected to target 1,370 technical personnel in both public and private sectors. Thus, the Project is to train nurserymen/women who having received elite material for propagation and will be raising quality planting materials with the assistance of the DAE staff. The Project will also provide traders with skills in handling, grading, and packaging produce and will even assist those who will develop export links. Finally, the Project will provide nutrition awareness and education programmes through supply of highly nutritious fruits and vegetables.

The main features of the Project’s strategy, besides the equipment required to run the HDTC’s, encompass:

- The development of skills and capabilities of the DAE and direct beneficiaries to cater to Project activity needs.

- Social mobilization and motivating the rural communities.

- Strengthening rural institutions and support services.

- Promoting income-generating activities.

- Establishing linkages with NGOs, GOs and other rural organizations.

- Capacity building and empowerment of women.

- Gender/WID focus.

From the design standpoint, the linkages among objectives, inputs, activities, outputs and expected outcomes are logical with respect to the transfer of technology component within the framework of an output oriented Project. Experience and evidence show that when outcomes are produced within this  framework, these are tenuous and seldom sustainable because they are dependent on external supply of inputs.  Very little or no effort is directed in institutionalizing the outcome.

The institutional transformations required to successfully exploit the technology introduced were implicit in the Prodoc, especially in the strategy proposed, but they were not fully articulated.  As in discussed in Annex 5, an institutional framework is vital for effective Project operation and to ensure sustainability. Institutional framework considerations encompass focusing on market development and the marketing procedures of the crops introduced by the Project. There is considerable evidence showing that since technological change is a powerful source of demand for institutional change, it is in the market structure where this demand is felt almost immediately. When production increases due to technological change, traditional market structures are unable to respond adequately to a volume several times larger than before. As result, either prices will plummet or benefits will be leaked to those equipped to take advantage of this situation.  This can be a serious constraint in the process of increasing income for targeted beneficiaries.

Therefore, beneficiaries must command a total understanding of the factors governing the economic exploitation of horticultural crops. If the benefits of horticultural crops do not accrue on targeted beneficiaries, the process of the technological transformation, and thus, poverty reduction can be compromised.

In terms of the nutrition objectives, it is not clear if awareness alone will have significant effects on the malnutrition situation in the Project area. Given the complexity of the causes of child malnutrition, illustrated in Fig 1 of Annex 6, efforts to identify the determinants of diets in a vulnerable segment of the targeted population should be considered. In this manner, it should be possible to uncover promising relationships between variables to draw lessons for future intervention.

Relevance

Considering the characteristics of the agricultural sector, the nutrition factor in sustainable human development, poverty alleviation and gender considerations, the Project objectives propose a broad strategy to build the capacity of individuals and organizations. In addition, it aims to enhance the level of food security and nutrition by boosting the efficiency of horticultural production systems and associated income generation activities encompassing homemade food processing.

- The Project is relevant to the needs of the GOB and conforms to its priorities and current policies. Indeed, the GOB is committed to halve its malnourished population by the year 2015.

- The Project has the potential of successfully testing a capacity building strategy that ultimately leads to reduce poverty through an environmentally friendly, and knowledge-based technology, within the reach of the landless and without assets, in particular deprived women of rural households.  Thus, the Project has the potential to contribute to upstream policy making in poverty reduction in the country and elsewhere in the sub region with similar ecological and socioeconomic conditions. In terms of the CCA framework, the Project is relevant to three clusters of rights:

- Food and Nutrition (Right to Survival)

- Employment/Income (Right to Livelihood)

- Empowerment/Association (Right to Participation)

- These elements are in conformity with UN Common Country Assessment and the Administrator’s Long Term Operation Plan.

- The Project meets the needs of the direct beneficiaries. It addresses the learning requirements of landless and deprived women of rural households. It directs resources towards the interrelated dimensions of individual learning in the context of organizations. It intends to create an enabling environment for the target population, composed of landless and marginal farming communities, and strives to improve the productivity and incomes levels together with nutritional status.

  - Project Implementation

3.3	Efficiency

The Project has completed the start up phase. The response has been encouraging. The process of social mobilization has been successful. 60% of the total targeted population has been mobilized. Women participation among direct beneficiaries is within the target (75%).  It has imparted several types of training to raise awareness on nutrition issues, among other skills, to targeted beneficiaries.  The Project has spent 23% of total resources allocated within 40% of the execution period.

The crux of the problem is that from the methodology standpoint, it is intricate to assess quantitatively  to what degree outputs have been achieved. Neither is it possible to understand how outputs will lead to outcomes. Outputs and outcomes lack quantified indicators of success in the Inception Report and subsequent budgeting exercises (see Annex 7). In fact, the Prodoc offers, as success criteria, often activities to be conducted, and a few times, actual tangible changes, but without measurement.

The work plans (both in the Inception Report and 2002) simply listed the 92 activities without targeting physical execution and associated disbursement.  The 2003   work plan has targeted a number of activities to execute during the year without estimated disbursement. There were no quantifiable indicators in any of the work plans.

Another way to obtain a glimpse of efficiency would be to estimate a proxy to cost-effectiveness. This is based on experience on the costs of inputs and results produced in similar projects. The absence of projects similar to the present makes it problematical to draw comparative estimates of cost-effectiveness.  Moreover, though at present it is possible to identify the cost of inputs, the ongoing results produced (women empowerment, mobilization of farmers’ groups, awareness raising in nutrition, etc.) are difficult to quantify.

In sum, it is unfeasible to establish a quantified rate of achievement. There has been observable progress towards achieving immediate results. New relationships, attitudes and values that govern interaction among folks in the Project area that contribute to economic and social development have emerged. This is also known as social capital and is a critical ingredient for development effectiveness.  It is possible to state, therefore,  that there has been value for the resources spent as will be expounded below.

- The use of female expertise to date has been extremely limited. This shortcoming will have to be addressed soon so that women can participate in a rate that commensurates with their availability.  The bulk of the expertise currently used in the Project execution is male.

3.4	Effectiveness

There is one structural reason for these design shortcomings. It is the output oriented framework combined with lack of RBM knowledge.  As discussed within the framework of the “results chain” (see Annex 4), activities are not results. Activities are actions. And results are tangible changes in the development context. Indicators are signs that show changes in certain conditions resulting from specific interventions.

Perhaps, it is not surprising that the M&E system is short in RBM oriented records. This deficit can be improved easily as UNDP has excellent manuals available for this purpose, i.e UNDP (1997; 2002) and many others from other donors. This unit needs to shift to the RBM framework with the utmost urgency.

Direct observations and the field data collected by the Mission suggest that there are outputs produced on in process, not amenable to quantification.  They have the potential to contribute towards the achievement of immediate objectives.

- The Project has successfully organized beneficiaries in all the 15 HDTCs in farmer groups. More than half of the expected number is already participating in Project activities of which 75% are women of landless households. Interaction with direct beneficiaries, notably women, shows commitment and active participation. It has been reported that some groups provide crisis loans to its members with a 10% interest rate as opposed to the usury rates between 120 to 240%.

- In fact, there is evidence indicating that the Project’s farmers, especially women, are motivated to change and are market oriented.

- As indicated above, there are 987 farmer groups that have opened bank accounts with savings reaching Tk. 1,880,100. Each group member saves a fixed rate of Tk 5-10 per week. This testifies to the desire for increased material welfare. Group discussions held by the Mission with farmers groups in the HDTCs confirmed the desire for increased wealth and expectations that change (the innovations introduced by the Project) will in fact increase wealth.

- These attitudes are essential requisites for motivation to change. They point to the vital need of producing and demonstrating successful innovations. And they all constitute indispensable social capital that is vital for social and economic development.

- Group discussions suggest that Project outputs in process are already useful to the targeted beneficiaries, especially women from landless households. From visiting 14 HDTCs, the following techniques were being diffused:   home-based food processing, , recipes to cook the newly introduced vegetables, seed selection and preservation. Women manifested their appreciation to intermediary outputs imparted by the Project. This is most likely because, a certain amount of vegetables and home-based foods processed, are consumed by the family unit with possible improvement in dietary conditions among targeted beneficiaries. However,  there are no estimates of the quantity of women that have taken up these techniques and to what extent malnutrition has improved.

- Although only 15% of targeted beneficiaries are male, there is an overall acceptance of these outputs delivered as corroborated by direct interaction with beneficiaries.

- Crop budgets collected by the Mission were analyzed from  a sample of summer vegetables (Indian spinach, okra, green chili) and winter vegetables (tomato). Unitary prices per ha for all inputs, interest on inputs (20%), land lease, labor, and management costs (50% of labor) were taken into account. It is noteworthy that since these are labor-intensive crops labor expenses represent typically between 41 and 48% of total cost. Net revenue per ha was computed by subtracting from gross revenue all costs.  The net financial results are encouraging for small shareholding  farmers. The range is as follows:

Green chili =  77 674 Tk/ha

Tomato  =  36 492 Tk/ha

Okra  =  27 408 Tk/ha

Indian spinach  =  8493 Tk/ha

The BS has no information on the above crops for comparative purposes.

- The successes of project interventions need to be exposed through farmers’ exchange visits from one HDTC to another. This will create awareness, build confidence, and increase motivation.

3.5 	Project Management Arrangements

The Prodoc and the Inception Report stressed the need to collect base line data in order to establish a M&E system to facilitate effective monitoring of Project’s management operations and activity execution. The quality of a baseline study is commonly determined by its usefulness in helping to assess social, economic or technological and  institutional changes that take place in the Project area as consequence of its interventions. During the present evaluation work, the Baseline Survey (BS), submitted on February 2003,  has been useful to understand the Project area. It is possible, however, that there was insufficient information on agricultural economics issues, such as  crop budgets, farm budgets, etc.

As mentioned, there will be need to revamp the M&E unit towards the results-oriented approach. This is absolutely vital due to the complex nature of the Project. The efficiency and effectiveness of the Project staff is significantly influenced by the quality of management. The results of three systems need to be monitored simultaneously

- Activity execution in production-marketing of crops introduced

- Activity execution in nutrition awareness-malnutrition issues

- Management operations in 15 HDTC

Immediate revamping of the M&E system into a results oriented framework will help in the development of management skills to ensure the effective use of personnel and financial resources as well as a timely execution of Project activities into outputs and outcomes.  This is crucial with a Project whose beneficiaries, on the whole, are becoming involved in horticultural production without previous experience or exposure to markets and marketing.

Otherwise, the staff and management of the Project, encompassing the 15 HDTCs, show commitment and ownership of the Project. This commitment should be translated into a bottom up management framework corresponding to the technical and organizational requirements of a complex Project. In reality, there are 15 sub Projects with their own agro-ecological characteristics, potentials and constraints. Each HDTC has been evolving according to its own characteristics and constraints.

From meetings with representatives of DAE centered on performance issues of Project, it was confirmed that there is substantive national support and commitment to conduct the Project successfully. In addition,  the GoB, on the whole, has delivered inputs in timely fashion. There have been exceptions where certain HDTCs are not yet fully equipped and personnel have not been assigned. National authorities interviewed have indicated their intention for speedy action to close the gap.

The technical inputs delivered by the UNIA have been of high quality technical. But on the whole, the technical and administrative support requires a proactive approach for the remaining of the Project horizon. A project, like the present, totally concerned with technological transformations on farm and linking with nutrition and malnutrition issues, has been the core of the UNIA actions and programs for decades. It is natural, therefore, to expect a proactive leadership geared to obtain tangible results on the ground. The success of the Project will be decided by tangible results on farmers’ plot, landless households’ vegetable gardens and the like.  This is where UNIA is expected to display its know-how, experience and leadership capabilities.

Specifically, there have been moderate difficulties with the timely arrival of consultants. The evidence available indicates that consultants’ reports reached the end user with considerable delay. In the case of the backstopping reports, they have not reached the end users yet. In most instances, recommendations have not been validated with the end user and monitoring of recommendations appears largely ignored.

The above appears due to a lack of closer field monitoring in technical assistance. For example, the Mission did not find a summary record of consultants’ recommendations with follow up actions. In reality, it appeared that UNIA was involved only in the necessary arrangements for the consultants’ arrival and departure. It is a reasonable expectation that the UNIA should attempt to adhere to the management principles of the RBM approach.

The Mission’s perception is that UNDP has delivered inputs in a timely fashion considering its limitations to perform activities such as procurement. UNDP is in a difficult position to meet client satisfaction because local prices for most items for procurement are practically identical to world prices. UNDP often will prefer world-known brands because of warranty whereas national organizations are happy to put up with a clone, for example.

The actual UNDP guidelines for national execution (NEX) will be issued imminently. Similarly, the Horticulture Program Development Specialist (International Senior Consultant) will join the Project as soon as contracting procedures are concluded. Based on the UNDP NEX guidelines and the participation of the International Senior Consultant, a new workable management framework should be hammered out among relevant stakeholders encompassing the management of the 15 HDTCs.

More within the framework of partnership, one perception has emerged. Both partners, the GoB, as executing agency, and FAO, as UNIA, appear insufficiently proactive with respect to UNDP new management paradigm: the RBM. It is no longer input supply that UNDP searches, but tangible outcomes in development effectiveness. Although the GoB retains overall responsibility for the implementation of the UNDP assistance, both GoB and UNIA should consider adhering to the principles of RBM as development partners. Otherwise, development results on the ground are compromised because RBM is a radical departure from input supply.

More in the domain of the administration of financial resources, the perception has also emerged that UNDP development partners do not appear knowledgeable that the ultimate responsibility of managing financial resources rests with UNDP. This is because UNDP is administering funds that are put in trust by taxpayers from contributing member countries.

3.6	Areas for Consolidating Action

Overall Issues

The Project is at a turning point. It needs to gear towards a framework to generate outcomes that will facilitate  the process of converting enhanced yields into higher incomes for the targeted population.

- To this end,  it is vital to consolidate the process of enhancing the capacity of low income women of landless households through horticultural production systems and the promotion of income generation activities.

- The process of technology transfer to increase yields through superior quality planting materials and better seeds have begun through demonstrations.  In fact, the target beneficiaries have manifested to the Mission, through group interviews in nearly all of the HDTCs, their appreciation and enthusiasm to continue in the learning curve.

- In essence, beneficiaries’ rising expectations have probably reached the point of no return. This stems from the production oriented training imparted by the Project.  Now is the opportune time to configure an institutional framework capable of converting enhanced yields to improved incomes. Otherwise socioeconomic development can be compromised.

- In the context of the Project Area, the institutional framework requires economic incentives to production. It will play a determining role in the adoption and sustainability of Project’s technological proposals. Among others, organizational adjustments are vital in the analysis of markets and organization of marketing arrangements; opportunities to obtain credit for production purposes; sustainable input supply and continuous extension support and technological information so that targeted beneficiaries can take full economic advantage of the technology proposed. These are the most evident elements identified by the Mission with its limited exposure to the Project area. Others may emerge from greater analytical effort and detailed knowledge of the Project area.

- Ultimately, it is the organizational arrangements implemented that will govern technology and the patterns of income distribution derived from the technology.

The following configuration is cardinal to enable beneficiaries to continue enhancing their know-how in horticultural production systems and home-based food processing supported by (1) decentralized services and (2) motivated by a business approach to improve beneficiaries’ incomes. As subsidiary effect, there would be greater availability of nutritious vegetables and fruits to enhance diets in the Project area.

The Way Forward:  Business Plan for each HDTC and Decentralized Support Servicess

A. The Business Plan

Each HDTC should draft a business plan centered on the needs and potential of direct beneficiaries within the participatory framework. The plan should be managed by the farmers’ groups.

- This bottom-up approach has to be based on a detailed assessment of farmers’ needs; centered on production potential within the context of agroecology, market opportunities, credit requirements, necessary marketing arrangements and cultural acceptability of specific crops; all supported by decentralized technical assistance services oriented to increase the incomes of beneficiaries in a sustainable manner. The business plan has to be market oriented and marketing driven.

B. Decentralized Support Services

Technical Assistance: Field Oriented and Participatory

For the remainder of the Project, the technical assistance needs to concentrate on capacity development through situational analysis of the constraints to building this capacity within the context of specific HDTCs. Therefore, technical assistance has to be field oriented (i.e. catering to the needs of 15 HDTCs). The work plan should reflect the needs and potential of beneficiaries. Raising land productivity through the design and promotion of low-input technologies that reduce production costs is paramount.

The work needs to be conducted with the participation of the direct beneficiaries and extension staff to ensure relevant and sustainable results. In consequence, the training manuals must be suited to convey the message to the functionally literate farmers. The pages must be laminated for lasting use with ample use of pictorial material.

As examined in Annex 5, in terms of the technology proposed in the Project, there has been little or no queries, for several reasons.

- It takes several agricultural campaigns to determine patterns or outcomes in technology adaptation.

- It appears that the source of nearly all proposed technologies come from the region and several consultants have submitted reports with recommendations. That is, it has been transferred from conditions somewhat similar to Bangladesh, with few possible exceptions.

- The process of technology adoption is dynamic, as such, periodic reviews are essential.  More importantly, as is concluded in the 2001-2002 PPR (p 40) , the single most important problem is how to make the technologies proposed a sustainable source of income generation. And this is where the Mission focused its attention.

However, there are actions that Project management should consider:

- To organize a committee (composed by certain members of the team of consultants, advanced farmers from Project area and  other relevant areas and other sources of experienced individuals or organizations ) to validate the recommendations proposed by consultants. And in the future, all recommendations should be validated by the same committee and others as management sees fit, before consultant’s  departure.

- FAO backstopping mission could conduct continuous evaluation exercises about the technology being introduced and the training conducted in terms of its curricula and execution. The overall purpose would be to ensure results on the ground. The FAO is in an enviable position to conduct this work because of its programmed  visits,  access to technological information and experienced personnel.

Market Oriented and Marketing Driven HDTCs

The BS (p xxix) indicates that farmers are acutely aware of current difficulties in the marketing system due to losses incurred for lack of transportation, storage/processing facilities and limited access to credit to finance marketing operations.

As better incomes come necessarily from the sale of produce, greater interaction with the market will be a predominant factor for the remainder of the Project. The Project should facilitate the beneficiaries’ successful interaction with the markets and capacity building in marketing procedures. Marketing should be tailored to the needs of each HDTC. It is especially vital to impart the skills for market development marketing support.  In the end, beneficiaries’ produce must be sold at the right time and place. And the prices must be remunerative to the beneficiaries and accessible to the consumer.

However, the Project should avoid becoming directly involved in market development and marketing as this would not be sustainable. The Project can facilitate logistic support to farmer groups for production, post-harvest handling, processing and marketing purposes (i.e. variety seeds, inputs, establishing market corners, transport and price information, etc).

The target population interacts with the market only as a marginal consumer of household goods. A successful interaction with the markets target beneficiaries requires a minimum of literacy and numerical training. This should not pose any difficulty as national NGOs methods and procedures have achieved worldwide status in this effort.

Overall, a tight-knit communication network should be developed between the farmer groups, field level extension personnel, and the Project technical team in order to cater to the needs and aspirations of the beneficiaries.

The BS (p xxi) brings out an important sociological finding. Men predominate in the decision-making and actual operations of marketing. This probably reflects observance of ‘Pardah,’ as warranted by the religion, is a sacred responsibility of the rural women.  Data outside the Project area, indicate that farmers claim not have time to market their increased production despite the fact that they could be incurring in losses. When probed whether women could get more involved in the process of marketing, such as retailing the produce in local markets, this was frowned upon as incompatible with prevailing cultural norms in rural areas. It will probably be important to probe further these sociological facts.

Certain HDTCs could contain horticultural farm models supported by crop budgets and marketing strategies. If the market potential of certain HDTCs is limited, income-generating activities should therefore take greater predominance. The HDTC in Rangamati may be in this kind of predicament.

Institutional Collaboration: Production and Marketing Linkages

According to BS (p xxviii) there are 29 NGOs within the Project area involved in horticultural development. Of which, 20 NGOs are involved in commercial horticultural farming. Project management needs to create synergic relationships with civil society.

Where opportunities arise, institutional collaboration with civil society, especially in the areas of crop production and marketing, credit, sustainability issues (BRAC, Milk Vita, Helen Keller, and others) are pivotal. In some HDTCs, the Project is training members of various NGOs. Collaborative arrangements in the areas noted can defer immediate necessary expenses and consequently produce benefits at an earlier date or make resources available that otherwise would not be.

Results-Oriented M&E

It is difficult to overemphasize that the above strategy needs a RBM oriented M&E system in place. Monitoring procedures to measure the Project’s management operations in the 15 HDTCs coordinated with activity execution are essential.  This can ensure that the beneficiaries can continue to be rewarded with higher incomes as well as the sustainability of capital and associated resources. Insufficient results oriented monitoring jeopardizes the performance of the Project and puts the heavy investment by poor landless women at risk.

- A logical framework analysis should be conducted for each of the HDTC and the Project as a whole; and it should be updated until the end of the Project.

- This is critical because the Project design contains innovative elements of horticultural production and many beneficiaries are becoming involved in market-oriented horticultural production without previous experience or exposure.

3.7	Areas of Potential Success

Early indications of potential success emerged in two areas.

1. Potential Profitable Returns From Crops Introduced by Project

Although the BS lacks the information for comparative purposes, the Mission has been able to obtain a glimpse of the profitability of the technological innovations proposed by the Project through crop budgets collected during the field visits to the HDTCs. Crop budgets were analyzed from a sample of summer vegetables (Indian spinach, okra, green chili) and winter vegetables (tomato). Unitary prices per ha for all inputs, interest on inputs (20%), land lease, labor, and management costs (50% of labor) were taken into account. It is noteworthy that since these are labor-intensive crops labor expenses represent typically between 41 and 48% of total cost.  . Net revenue per ha was computed by subtracting from gross revenue all costs. .

The net financial results are encouraging for small shareholding farmers. The range is as follows:

Green chili =  77 674 Tk/ha

Tomato  =  36 492 Tk/ha

Okra  =  27 408 Tk/ha

Indian spinach  =  8493 Tk/ha

Income Generating Operations Among Women Groups

The Mission had the opportunity to witness the inauguration of two retail stores in Ringamati. Four women saved up Tk 8000 to start up this business. The store carry approximately 30 items for sale of first necessity: soaps, matches, cigarettes, shampoo, biscuits, soft drinks, etc. With the techniques learned from the Project, mango, tamarind and green chili were processed for sale. As the operation just began, it was not possible to estimate profitability.

3.8	Project Results

As realistic as they are the unwitting design shortcomings bringing about snags in measuring activity execution within the framework of RBM, the field visits conducted in 14 HDTCs testify that the Project has implemented a sizeable number of activities. Therefore, the following pivotal outputs have been accomplished or are in process.

Social Mobilization of Targeted Beneficiaries

- Nearly 16, 000 women from landless households have been successfully organized in groups. This is approximately half of the targeted population. Several elements of empowerment emerged from discussions conducted with women’s groups.

- First, their organizational commitment enabled them to become organized. Local organization is a key element for development effectiveness because through this capability is often possible to manage resources for the benefit of the many rather than just the few.

- Second, through this organization they could share common views that led to greater self-confidence. Also, information as resource becomes possible since they now constitute an assembly with a common purpose.

- Third, the element of inclusion became evident, as poor women of landless families were traditionally excluded groups for priority setting and decision-making. This builds commitment to change.

- Finally, it can be expected from this process of empowerment, that accountability mechanism may emerge and are already emerging.

- The type of training imparted to women’s groups (primarily nutrition, and horticultural production including home-made food processing) meets their current needs. They often requested more training in horticultural and associated activities.

- There are early signs of successful income generation initiatives primarily based on homemade food-processing techniques acquired through the Project. In addition, crop budgets collected from selected vegetables show encouraging net returns to small shareholding farmers.

- The Project has successfully raised awareness about the importance of providing nutrition awareness in all of the HDTCs. A wide variety of vegetables is now being consumed as soups and pickles.

Training Imparted

A critical mass of manpower in the field of horticulture is being developed with capabilities to train trainers from the farming communities.  Up to December 2002, 1420 field level officials were trained in 11 different courses and 15,350 farmers were trained in 16 different subjects.

Many trained men and women farmers have already started growing mushrooms for home consumption as processed and fresh food.

The following demonstrations have been established: 1375 nutrition gardens, 7 high density banana plots, 31 high density litchi and 36 high density mango sites.

Nutrition Education/Awareness Raising

Awareness raising campaigns have been conducted on: hygienic preparation and handling of vegetables and fruits at the household level to reduce nutrient losses during cooking; and complementary low cost food associated with consumption of vegetables as soups, has been directed to housewives.

Horticultural Production Systems

As part of fruit village demonstrations, 6,030 homesteads were planted with 30,150 fruit-trees of litchi, mango, sapota, guava and lime.

A good number of Mother Tree Orchards, clonal hedges, have been established in all 15 HDTCs with recent fruit varieties.

More than 80,000 elite planting materials of fruits and quality planting materials of turmeric, ginger and vegetable seeds and mushroom spawns were produced and distributed to the farmers.

On mushroom demonstration, there were 48 on production, 48 on food preparation, 6 on post-harvest demonstrations and 45 on processing at household level.

4. 	RECOMMENDATIONS

For the Attention of Project Management

Consider the following actionable guideline to enable beneficiaries to continue enhancing their know-how in horticultural production systems and home-based food processing supported by (1) decentralized services and (2) motivated by a business approach to improve beneficiaries’ incomes. As subsidiary effect, there would be greater availability of nutritious vegetables and fruits to enhance diets in the Project area.

The Way Forward:  Business Plan for each HDTC and Decentralized Support Services

The fundamental principles are:

- The current number of existing groups should be strengthened rather than expanded.

- Technical training to beneficiaries in horticultural production systems and home-based food processing should consolidate acquired knowledge and become market oriented and marketing driven.

Business Plan for each HDTC

Within the participatory framework, each HDTC should draft a business plan centered on the needs and potential of direct beneficiaries. The plan should be managed by the farmers’ groups.

- Farmers’ needs must be assessed in detail or validated.

- Physical production potential must be determined in terms of ecological and climatic factors.

- Actual production capability, in terms of crops or produce processed, must be geared to the market and marketing arrangements should be organized in consequence.

- Based on the above, the credit requirements should be determined taking into account farmers’ groups savings.

- Taking into account the above factors, the type and length of technical assistance will be determined.

Decentralized Support Services

- For the remainder of the Project, the technical assistance must be field oriented. It should cater for the needs of 15 HDTCs and conduct its work with the participation of the direct beneficiaries and extension staff. The training manuals must be suited to convey the message to the functionally literate farmers. The pages must be laminated for lasting effect.

- Where opportunities arise, institutional collaboration should be organized with civil society, especially in the areas of crop production and marketing, credit, sustainability issues (BRAC, Milk Vita, Helen Keller, and others). Possible collaborative arrangements can defer immediate necessary expenses and consequently produce benefits at an earlier date or even provide inputs that otherwise would be unavailable such as credit funds for crop production.

- Certain HDTCs could contain horticultural farm models supported by crop budgets and marketing strategies. If the market potential of certain HDTCs is limited, income-generating activities should therefore take greater predominance.

- Consider training in literacy and numbers  for all members, not yet functionally literate, to improve their capacity in the production and marketing of produce.

- A results-oriented M&E system must be in place as soon as possible.  The results of three systems need to be monitored simultaneously

  - Activity execution in production-marketing of crops introduced

  - Activity execution in nutrition awareness-malnutrition issues

  - Management operations in 15 HDTC

  - A logical framework analysis should be conducted for each of the HDTC and the Project as a whole; and it should be updated until the end of the Project. Insufficient monitoring jeopardizes the performance of the Project and puts at risk the heavy investment by poor landless women.

The Nutrition Component

As subsidiary effect, there should be greater availability of nutritious vegetables and fruits to enhance diets in the Project area.  However, given the complexity of the causes of child malnutrition, in order to draw policy lessons, consider conducting efforts to identify the determinants of diets of children under age 5 and pregnant and lactating women. The idea is to make evident some promising points of future intervention.  To simplify the complexity of the nutrition system, it could be divided in three sub systems: crop production, processing and distribution to the consumer.

  - From standpoint of crop production, price relationships of all crops produced should be reviewed, the nutrition implications of current agricultural policies as reflected within the Project area, the workings of the agricultural credit in terms of how they affect food security and nutrition, and to what extent infrastructure considerations (physical and institutional) affect crop decisions, and other context specific issues.

  - From a processing and distribution point of view, the current mechanisms, procedures to distribute food within the Project area should reviewed, including the marketing margins and profits at each stage of the marketing chain; the nature and coverage of processed foods, if any; the cost of transportation of certain foods; and others.

  - The consumer habit subsystem should look at the food expenditure pattern within the Project area, food taboos, food consumption pattern within the family according to sex and age, and others. Seasonal variations should be detected from the sample studied.

  - Interwoven in all of the analysis should be the role of the public sector. Amounts, availability, acceptability, and effectiveness of different services related to nutrition provided by the public sector and budget analysis of different and existing programs need to be addressed such as, health and nutrition education, child feeding programs, etc.

The ultimate aim of this exercise is to develop a nutrition framework that would establish the relationship of diet to family income, to religion, to morbidity and income, to mortality and income, to educational level of parents, to use of health services, to presence of non nuclear family members, to occupation, to size of family and per capita food expenditure, to maternal employment (outside household), to safety of water supply (and other environmental hygiene factors), to awareness of nutrition, to practice of family

For the Attention of Project Management and Ministry of Agriculture

A Framework for Project Sustainability

Finally, based on the Mission’s consultations with key stakeholders, a long-term framework for sustainability purposes has been retained.

- The knowledge of enhanced horticultural production systems and home-based food processing must be embedded within the rural communities of the targeted beneficiaries. It should be patterned after the IPM clubs.

- Identify natural leaders in the rural communities of targeted beneficiaries.  These natural leaders with the support of the Project should ultimately provide an enabling environment in their communities, such that the Project results can achieve dynamic sustainability.

- The GOB through the DEA must play a catalytic role in maintaining the sustainability efforts of IPM and future Horticulture clubs. This initiative can be achieved through the organization of farmers’ days twice a year.   This platform would provide opportunities for farmers to interact amongst themselves and where new technical information could be released.

- Finally, in terms of an exit strategy, the GOB should take over full responsibility to continue the Project activities after project completion and provide necessary financial support from the national budget.

Possible Need of Additional Resources in several HDTC

The GOB should consider furnishing the Rangamati HDTC and filling several other personnel requirements and equipment for other HDTCs. For the remainder of the Project, it will be vital to ensure the continuity of the national personnel in order to ensure successful results.

For the Attention of GOB, UNDP, FAO

A Framework for Project Management

When the forthcoming UNDP guidelines for national execution (NEX) are issued and with the presence of the Horticulture Program Development Specialist and other relevant stakeholders, consider preparing a new workable management framework encompassing the management of the 15 HDTCs.

After the formulation of the 15 Business Plans for the HDTCs, as the number of activities may increase as compared to the present context, consider reviewing the budget to ensure successful results.

- Each HDTC objectives and targets for the remainder of the Project should be established. Taking into account the specific agroecologic setting, it must be oriented to increase the incomes of beneficiaries in a sustainable manner based on the technology transfer.

- An overall work plan covering the full Project horizon will be needed in terms of physical activity execution and associated cash flow. This must be supported by annual detailed work plan. A logical framework is essential supported by a results-oriented monitoring of outputs and outcomes.

- This plan should also consider overall manpower requirements and equipment until the end of the Project.

- The Project’s work plan should integrate all of the HDTCs work plans encompassing the logical framework supported by a results-oriented monitoring of outputs and outcomes.

For the Attention of UNIA

For the remainder of the Project, theUNIA management of technical assistance component should ensure greater results in monitoring consultants activities and in coordination with key stakeholders. It is vital that consultants’ reports, including backstopping visits, should circulate rapidly among end-users, no more than 10 working days after consultants’ departures.

The technical assistance for the remainder of the Project should concentrate on capacity development through situational analysis of the constraints to building this capacity within the context of each HDTC. Requests for technical assistance should emerge from end users. Therefore, the UNIA must deploy hands-on efforts to ensure that technical assistance is participatory and field oriented. All consultants’ recommendations have to be validated by consultants with end users before their departure.

The following consultants must be fielded.

Long Term:

- Senior Horticulture Program Development Expert: The project duration is 60 months but provision for a long-term international consultant is 45 months. Provided allocated funds permit, the consultant’s term should be extended to cover the Project time horizon.

Short-term

- International Consultants: The Nutrition Education Specialist has completed his/her duties. If, during the elaboration of the HDTCs Business Plans there is felt a need for further work from this consultant, an extension of his/her duties can be considered.

- Food Processing/Post Harvest Technologist, Plant Propagation & Tissue culture Specialist.  The Project will benefit, if separate consultants on each discipline could be fielded.

- Unspecified Consultants: Provision for unspecified consultants can be fixed for 6 m/m instead of 2 m/m because evidence shows that a 2m/m duty is ineffective.

Finally, with the active participation of Project management consider conducting a continous quality control of the technology proposed to beneficiaries.

- At the project level, with the active participation of management organize a committee (composed by certain members of the team of consultants, advanced farmers from Project area and  other relevant areas and other sources of experienced individuals or organizations ) to validate the recommendations proposed by consultants. And in the future, all recommendations should be validated by the same committee and others as management sees fit, before consultant’s  departure.

- FAO backstopping mission could conduct continuous evaluation exercises about the technology being introduced and the training conducted in terms of its curricula and execution. The overall purpose would be to ensure results on the ground. The Regional FAO office is in an enviable position to conduct this work because of its programmed  visits,  access to technological information and experienced personnel.

5.	LESSON LEARNED

In the search of ensuring food and nutrition security within the framework of right to survival, embedding high productivity know-how within the social structure of rural communities looms as a promising strategy. For example, IPM clubs and village nurseries appear to adapt themselves in farmers’ communities with a moderate degree of dynamic sustainability. Governmental efforts are required to continually rekindle the motivation of farmers through farmers’ days at least twice a year.  This platform would provide opportunities for farmers to interact amongst themselves and will be a venue where new technical information could be released.

Rangamathi, Kishoreganj, Mymensingh, Jamalpur, Rangpur, Nawabganj, Natore, Pabna, Meherpur, Rajbari, Khulna, Barisal, Feni Khagrachari, and Bandarban

Experience shows that there are many projects in the developing world that have increased physical productivity through technological changes but incomes have stagnated, and sometimes decreased, due to lack of institutional framework.

UN. Bangladesh: Common Country Assessment Overview. Dhaka, 2000, p. 15

See: WB. Understanding and measuring social capital. Directions in development. Washington, DC, 2002, pp 7-12

IHND. Progress report on socio-economic monitoring and evaluation component. April 2003, p 12

Krishna, A. et al. eds. Reasons for hope: instructive experiences in rural development. West Hatford, Conn: Kumarian Press, 1997. Quoted in WB. Empowerment and poverty reduction: a source book . Washington,DC: 2002, pp 7-15

It should be possible to draft a business plan applicable to a set of socioeconomic conditions and ecological setting; thus, reducing the number of business plan to a few types. There could be types containing farm models supported by crop budgets, others containing income generating opportunities. This could save time and resources.

UNDP. UNDP Results framework. Technical Note. Draft/Revision 5. New York,  December 2000, New York

Annex 4 contains the method and field procedures proposed to undertake the present evaluation.  In principle, the process moves away from assessing outputs against project objectives towards and assessment how outputs contribute together with the assistance of partners to a  change of development outcomes.

See:.UNDP. Who are the question makers? A participatory evaluation handbook. New York, 1997, pp 9-15. Also Health Canada. Guide to Project evaluation: a participatory approach. Ottawa, 1998, pp 7-13.

See: UNDP/EO (2001) Managing for results. Monitoring and Evaluation in UNDP. New York, Draft#3, p.3.

UNDP’s Results-oriented Monitoring and Evaluation Handbook  (UNDP/OESP, 1997) and Handbook on Monitoring and Evaluation for Results (UNDP/EO, 2002)  were used to achieve uniformity and coherence in data collection and analysis throughout the review of this complex Project.

Experience shows that there are many projects in the developing world that have increased physical productivity through technological changes but incomes have stagnated, and sometimes decreased, due to lack of institutional framework.

See: Prodoc, p.1-2

Rangamathi, Kishoreganj, Mymensingh, Jamalpur, Rangpur, Nawabganj, Natore, Pabna, Meherpur, Rajbari, Khulna, Barisal, Feni Khagrachari, and Bandarban

See for example: WB. The design of organizations for rural development project. Washington, 1980

UN. Bangladesh: Common Country Assessment Overview. Dhaka, 2000, p. 15

See: WB. Understanding and measuring social capital. Directions in development. Washington, DC, 2002, pp 7-12

IHND. Progress report on socio-economic monitoring and evaluation component. April 2003, p 12

It is perhaps not surprising that the 2001 Audit Report found that “financial management structure is not appropriate…monitoring , evaluation and reporting systems are absent… internal control system is not satisfactory” (section vii). The 2002 Audit Report reiterated that “monitoring and evaluation were not done by the project authority…internal control systems should be enhanced for better performance of the project.” (p 7, 14)

It should be possible to draft a business plan applicable to a set of socioeconomic conditions and ecological setting; thus, reducing the number of business plan to a few types. There could be types containing farm models supported by crop budgets, others containing income generating opportunities. This could save time and resources.

UNDP. IPM. Final Assessment Review. Annex 7. Dhaka, 2002

Krishna, A. et al. eds. Reasons for hope: instructive experiences in rural development. West Hatford, Conn: Kumarian Press, 1997. Quoted in WB. Empowerment and poverty reduction: a source book . Washington,DC: 2002, pp 7-15

It should be possible to draft a business plan applicable to a set of socioeconomic conditions and ecological setting; thus, reducing the number of business plan to a few types. There could be types containing farm models supported by crop budgets, others containing income generating opportunities. This could save time and resources.

Berg, Alan . The nutrition factor. Its role in national development. The Brookings Institution. 1973: Appendix D.