EC/FAO MID-TERM REVIEW OF THE EC-FAO COOPERATION PROGRAMME 1999 TO SUPPORT FOOD SECURITY

VOLUME I:  EXECUTIVE SUMMARY AND MAIN REPORT

JULY 2003

Table of Contents

Pages

INTRODUCTION	3

METHODOLOGY	3

STRUCTURE OF THE REPORT	4

A.  OVERVIEW OF THE EC/FAO COOPERATION PACKAGE PROGRAMME 1999 TO SUPPORT FOOD SECURITY	4

A.1  OVERVIEW	4

A.2  IMPLEMENTING ARRANGEMENTS	10

A.3  BUDGET AND DISBURSEMENTS	11

B.  OVERALL ASSESSMENT OF THE PROGRAMME	13

B.1  RELEVANCE OF THE PROGRAMME	13

B.1.1 Relevance to Country Needs	13

B.1.2 Relevance for the European Commission and the EU Sectoral Policies	14

B.1.3 Relevance to FAO	14

B.2  COHERENCE OF THE PROGRAMME DESIGN AND STRATEGY	16

B.3  EFFICIENCY OF IMPLEMENTATION	18

Programme Management and Coordination	18

Adequacy of EC Support	20

B.4  COST-EFFECTIVENESS	21

B.5  OVERALL ASSESSMENT OF OUTCOMES AND IMPACTS	21

C.  GENERAL FINDINGS	25

D.  RECOMMENDATIONS – GUIDANCE FOR THE FUTURE	28

ACKNOWLEDGEMENTS

The Review Team would like to express their appreciation for the assistance and collaboration given to them during the mission.  In particular, the Review Team would like to thank Project Managers for the useful work carried out in preparation of the mission.

EXECUTIVE SUMMARY

- The EC/FAO agreement for FAO to implement a programme to support food security was signed in March 2000 for duration of three years. It is composed of eight projects, six of which relate to food security information.

- The joint EC/FAO Mid-Term Review (MTR) was undertaken by three persons representing the EC and FAO to assess the overall results achieved under the Programme and to provide guidance for the development of a possible EC/FAO Programme 2004.

- The MTR reviewed the extensive documentation on individual projects, and undertook consultations with stakeholders at FAO Headquarters and the EC AIDCO F/5, including individual project staff, as well as short field visits in countries where the Programme had activities (Angola, Mozambique, Kyrgyzstan and Armenia). In addition, auto-evaluations prepared by individual project managers constituted a very useful tool for discussion. The MTR report is composed of an assessment of the Programme as a whole, guidance for the formulation of a follow-up EC/FAO cooperation programme, and short individual project reviews.

- With the exception of a few cases, the Programme was found relevant to the needs of countries in which it had activities. In all of these countries, food insecurity is a national issue that can only be addressed on the basis of a comprehensive understanding. The Programme is also relevant to FAO and the Commission in many ways. The Programme addresses two different areas among the EU six priority areas for development: food security and sustainable development and trade and development. It was designed to contribute to the definition and monitoring of food security interventions in line with the EC new food aid and food security policy. It aims to make recipient countries more responsible for the design and implementation of food security strategies and move from project to budget support for food security. All the projects relate to at least one or several of FAO corporate strategies defined in its Strategic Framework 2000-2015, in particular (i) Strategy A: “Contributing to the eradication of food insecurity and rural poverty” and (ii) Strategy E: “Improving decision-making through the provision of information, assessments, and fostering of knowledge management for food and agriculture” and are well integrated into regular programmes of the Organization, in particular GIEWS and FIVIMS.

- The Programme was not conceived as a whole and is perceived more as a set of projects funded under the same budget. Nevertheless, there are some common features among the projects: (i) a common theme for six out of the eight projects, i.e. support to food security information; (ii) a common approach to several projects in the Programme, building rightly on FAO’s added value and combining normative work with regional/country capacity building, and designed in such a way as to build synergy between normative and operational work. The lack of a more “programme approach” has consequences in terms of loss of opportunities for complementarity and synergy between projects, and thus the potential greater outcomes and impacts from project outputs. Most of the projects are over-ambitious in their design reflected in inadequacy between resources and expected results.

- Overall, much was achieved in terms of products and services delivered throughout the projects. This is largely attributed to dedicated and competent project staff and the technical support provided by FAO, as well as the mutual benefits derived from the synergies between the projects and other FAO programmes (e.g. with FIVIMS, GIEWS and ARTEMIS). Despite this positive overall assessment, it must be recognized that for the moment, the translation into operations and actions of normative activities and vice versa has been limited, with emphasis given to one aspect or the other in each of the projects.

- The projects are at various stages of implementation. Delays have been important for nearly all projects. Several factors impeded smooth implementation, of which the most important include: the time needed for staff recruitment; the re-design or refinement of some projects; the slow responsiveness of the EC on most matters, staff movement and consequent re-orientation of activities in some projects as well as inherent weaknesses in project design. For those projects including country-level activities, inadequate FAO support at country level and the lack of realism on the role of national counterpart agencies have been identified as major implementation constraints.

- The time and resources needed to administer the Programme was under-estimated. Furthermore, the Programme would have gained efficiency with greater technical coordination in addition to administrative coordination. This would have permitted more synergy and mutual benefit between projects as well as avoidance of duplication.

- The projects supported national capacity, mostly through training which contributed to a better understanding of food security issues and resulted in improved inter-institutional dialogue and networking in most cases. Internalization of capacity building through regional institutions was accomplished through the SADC project. Overall, capacity building was most effective when it was well-targeted, specific and not over-ambitious. The achievement in terms of institutional strengthening at country level revealed the limit of what could be achieved under the Programme given the relatively small resources and short timeframe, as well as the project management set-up which did not facilitate close follow-up. Normative materials of heterogeneous quality and design were produced throughout all the projects. Outcomes of normative outputs could be greater with more interchange among projects, in particular among those with strong similarities.

- Based on all of the above, the Review Team recommends the continuation of activities in the area of food security information for action, implemented through FAO, and defined, following a real programme approach.  More specifically, the Review Team makes a number of recommendations covering the following main areas:

- Objectives (paras 152-157): The overall objective of the Programme could take the form of “sustainable food security information systems adapted to local, regional and global usage with the capacity for flexible integration with other essential livelihoods data” and should be centred on the following three pillars: (i) regional and national capacity building in specific technical areas; (ii) provision of information for targeted usage and users; (iii) access to reference materials and tools.

- Components (paras 158-165): Components and activities should be designed on what has been attained during the current phase of the Programme, on what is available from elsewhere including the EC and FAO and what is achievable within the Programme timeframe. However, the identification of the detailed components of the Programme should be preceded by an assessment of priority uses and users, including in particular those in the countries, the EC and FAO.

- Approach (paras 166-174): The Programme should continue to build on FAO’s added-value, i.e. normative/operational synergy with a better balance between the two. Capacity building activities should be designed more efficiently, using regional institutions and groupings. This will have some implications on the criteria (among others) for the selection of countries for capacity building. More centralization of resources and services could facilitate better exchange and mutual benefits among the Programme components and allow easier customization.

- Programme duration: A 5/6-year programme with rolling annual plans would be more appropriate due to the fact that sustainable in-country implementation of food security information systems takes time.

- Programme Management (paras 177-182): Several recommendations are made with a view to strengthening the administrative and technical coordination of the Programme, including the re-location of the coordination and some components, as well as the setting-up of a steering committee.

- EC-FAO Collaboration (paras 183-185): Recommendations aim to clarify and strengthen the collaboration between the two institutions both at Headquarters and the country level.

- Other collaborations (paras 186-187): The need to ensure regular and systematic access to information from other institutions is addressed.

# INTRODUCTION

1.	On March 29, 2000, an agreement was signed by the EC and FAO for FAO to implement a Package Programme to support food security.  It was the result of a series of meetings held between FAO and the EC DG 8 Food Aid and Food Security in the course of 1999. The EC 113th Food Security Food Aid Committee, held on 16 July 1999, approved the funding of the Programme through the Food Security Budget Line. The EC took the final decision on 9 November 1999. The implementation began on 19 July 2000 with duration of three years, and a fourth year for terminal reporting and closure of projects.

2.	The Programme was designed to contribute to the definition and monitoring of food security interventions in line with the new EC food aid and food security policy, which aims at making recipient countries more responsible for the design and implementation of food security policies by moving from financial aid to budget support for sectors related to food security. After the last Commission's reforms, the EC/FAO Programme should be implemented in close collaboration with EuropeAid Cooperation Office, Food Security Unit (AIDCO F/5), and FAO Headquarters in Rome. Close cooperation was also promoted between the local/regional FAO Representations and the EC Delegations and the Food Security Units (FSU) in food security priority countries.

3.	At a meeting held in Brussels in November 2002 between FAO staff associated with the Programme and their counterparts in the EC AIDCO F/5, it was agreed that a Joint EC/FAO Mid-Term Review (MTR) of the Programme would be conducted in mid-2003. The purposes of the MTR were to assess the overall results achieved under the Programme and draw lessons from the implementation with a view to providing guidance for developing a possible EC/FAO Programme 2004.

4.	Accordingly, a three-person mission was organized and implemented during June-July 2003. Team members were:

- Etienne Bartholomé –Senior Scientist, Joint Research Centre of the European Commission.

- Stéphane Flasse – Environmental Information Systems Specialist, Consultant

- Rachel Sauvinet-Bedouin – Team Coordinator, Evaluation Officer, FAO

## Methodology

5.	The methodology for the conduct of the Review involved the use of extensive documentation on individual projects as well as consultations with stakeholders at FAO Headquarters (essentially with project staff) and the EC AIDCO F/5, including individual project staff.

6.	As per the terms of reference, short field visits in countries where the Programme had activities were carried out in a limited number of countries, i.e. Angola, Mozambique, Kyrgyzstan and Armenia. During these two-day field visits, discussions were held with project beneficiaries,  FAO Representations and staff, EU delegation and/or EC staff involved in food security activities, as well as key partners.

7.	Individual project reviews were prepared for each of the eight projects of the Programme to substantiate the overall review at programme level. This was necessary in view of the fact that the Programme to be reviewed appears as a package of separate projects with no explicit articulation among themselves, making the review of the actual Programme more difficult.

8.	Auto-evaluations had been requested by the Review Team from each project manager as part of the preparatory work for the mission. In the short time given to the mission, this constituted a very useful tool for discussion and for preparing the project reviews.

9.	The substance and detail provided for each individual project review varies according to the time the Review Team could allocate to fact-finding activities. For instance, for the CIS project two out of four countries where the project was implemented have been visited, while for the two fivims projects no country visit was made and the work was entirely based on a desk review. For the SADC project, the evaluation mission benefited from the report of the specific evaluation mission that was carried out in November 2002 in which one of the Review Team participated. For the consultancy fund, factual information could be gathered locally only for three consultancy activities, out of a current portfolio of 19 so called “baby-projects”.

10.	The project GCP/INT/736/EC “Training for ACP Countries on the Uruguay Round and Future Multilateral Trade Negotiations in Agriculture” was part of a broader programme called “the Umbrella Programme for Training on Uruguay Round and Future Negotiations in Agriculture” under which training was carried out through the same model. The project is quite distinct from the rest of the package programme and its belonging to the Programme seems to be more the result of circumstances (additional external funding needed at that time to complete the UP) rather than its thematic linkages with the rest of the Programme. For this reason, the project is not analysed in the overall assessment of the Programme. However, as all other projects, it is treated individually in Volume II – Annex 1 of the Report.

## Structure of the Report

11.	The report contains two volumes. Volume I is the main report providing an overview and assessment of the Programme as a whole and including guidance for the formulation of a next EC/FAO cooperation programme. Although it refers to individual projects, the report focuses on commonalities among projects with a view to assessing the Programme and drawing lessons for the future.

12.	Volume II contains various annexes, including eight project reviews in Annex I. For projects where the Review Team felt confident to do so, some recommendations specific to the project are made. These recommendations do not necessarily appear in the Volume I.

# A.	OVERVIEW OF THE EC/FAO COOPERATION PACKAGE PROGRAMME 1999 TO SUPPORT FOOD SECURITY

## A.1	Overview

13.	The Programme consists of the following eight projects with a total value of Euro 12.5 million:

Table 1: EC/FAO 1999 Package Programme for Food Security

| Project Number | Project Title | Budget (Euro) |
| --- | --- | --- |
| GCP/INT/736/EC | Training for ACP Countries on the Uruguay Round and Future Multilateral Trade Negotiations in Agriculture | 900,000 |
| GCP/INT/740/EC | Strengthening the Technical Capabilities of Global Information and Early Warning Systems Workstation | 1,270,000 |
| GCP/INT/741/EC | Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Less Developed Countries | 1,760,000 |
| GCP/INT/742/EC | Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Small Island States | 880,000 |
| GCP/INT/758/EC | EC/FAO Fund for Consultancy Services | 2,380,000 |
| GCP/INT/814/EC | Intensified Monitoring of Food Security in CIS Low-Income Food Deficit Countries (Armenia, Azerbaijan, Georgia. Kyrgystan, Tajikistan) | 1,130,000 |
| GCP/RAF/360/EC | Improving Early Warning and Food Security Information in Countries Subject to Complex Emergencies | 2,200,000 |
| GCP/RAF/351/EC | Capacity Building Support to SADC Remote Sensing Unit for Early Warning for Food Security | 1,980,000 |
|  |  | 12,500,000 |

14.	As stipulated in the agreement, the overall objective of the Programme “providing technical assistance and advice to a number of food insecure countries and regions is to strengthen local institutions and to build capacities critical for the improvement of food security and the management of crisis situations”.

15.	The expected results were:

- Result 1: improved monitoring of the global supply and demand situation for all basic food and facilitate access to the available information;

- Result 2: improved monitoring of food security situations in specific countries and early warning analysis;

- Result 3: reliable information on food insecure and vulnerable people in selected countries and improved design and implementation of specific action programmes to reduce food insecurity and underlying poverty;

- Result 4: strengthened developing country’s negotiating and policy formulation capacities to participate more effectively in world trade negotiations and to adapt to the changing world trade and economic environment.

16.	The fourth expected result refers specifically (and exclusively) to one project in the package, i.e. the project GCP/INT/736/EC “Training for ACP Countries on the Uruguay Round and Future Multilateral Trade Negotiations in Agriculture” which as indicated above in the section on methodology, is not analysed in the overall assessment of the Programme.

17.	The other project that differs from the rest of the Programme is the project GCP/INT/758/EC EC/FAO “Fund for Consultancy Services” with the broad purpose of making available consultancy services to developing countries/regional organizations in pursuit of “the goal of promoting national regional food security and rural development”. The funds give priority to African, Caribbean and Pacific (ACP) countries where agriculture (including livestock, fisheries and forestry) is an area of concentration for European Development Fund assistance, and to EC Food Security Prioritized Non-ACP Countries.

18.	Out of seven projects, six focus on a common theme, i.e. the further development and expansion of food security information systems, with different emphasis on the various functions of food security information systems and at different levels of aggregation (country specific, regional and global level). The following table summarizes the specific objectives, outputs and country focus as well as the thematic focus, within the broad theme of food security information of each of these six projects.

Table 2: Projects Relating to Food Security Information

| Project | Immediate objectives | Country Focus | Thematic Focus |
| --- | --- | --- | --- |
| GCP/INT/740/EC Strengthening the Technical Capabilities of Global Information and Early Warning Systems Workstation “ GIEWS project” | - Expanded GIEWS Workstation - Access to external users to info. held by GIEWS through WWW - Analytical capabilities of the individual components of the GIEWS Workstation - Continued dissemination of the GIEWS Workstation software and databases | No country specific focus Global | Early Warning Analytical tool to facilitate (and improve) GIEWS analysis |
| GCP/RAF/351/EC Capacity Building Support to SADC Remote Sensing Unit for Early Warning for Food Security “ SADC project” | - Enhanced capacity within the SADC to operate a pro-active monitoring system; - Quantitative approach to EW issues (quantitative estimate of agricultural production and grazing conditions) - Pro-active handling of broader SADC-FANR issues | Regional Countries of the SADC: | Early Warning Remote sensing tool for early warning purposes |
| GCP/INT/814/EC Intensified Monitoring of Food Security in CIS Low-Income Food Deficit Countries “ CIS project” | - maximum use being made of existing national data from the Household Budget Survey - increased capacity to analyse food security and to identify population groups most at risk of food insecurity; - an enhanced ability to make early crop forecasts and to provide warning of any potential food supply problems, - the production of coherent food security bulletins | Armenia, Azerbaijan, Georgia, Kyrgystan, Tajikistan | Methodologies and training for food security information and early warning, including food balances, household budget surveys, crop forecasting, database and production of the food security bulletin. |
| GCP/INT/741/EC- GCP/INT/742/EC: Supporting Pilot Applications of the FIVIMS “ FIVIMS project” | - Establish or improve the capabilities of national FIVIMS organizations selected pilot countries - Increase the capability of the IAWG FIVIMS Secretariat to provide enhanced project design, implementation, monitoring, and lessons-learned services to national FIVIMS and supporting regional organizations; - Provide specific lessons-learned to IAWG FIVIMS partners. | 741: in less developed countries: Kenya; Madagascar; Burkina Faso and Haiti 742: in Small Island States: Barbados, Cape Verde, Comoros, Samoa | Institutional capacity building for food security information Reference and training materials (methodological guidelines, discussion papers, best practice examples) based on lessons learned from country experiences. |
| GCP/RAF/360/EC Improving Early Warning and Food Security Information in Countries Subject to Complex Emergencies “ Complex emergencies project” | - Strengthened institutional support structures - Improved food security information system methods and techniques developed - Food security information. | Complex emergencies: Burundi, Somalia, RDC, Angola | Conceptual and analytical frameworks for food security in complex emergencies Food security information requirements in complex emergencies |

Themes and Approaches

19.	Within the broad theme of food security information, the six projects have various thematic focuses. The SADC and GIEWS projects develop tools (comprehensive interface/ analytical tool for GIEWS, remote sensing tool for SADC) for improving early warning functions of food security information system (at the global level for GIEWS, at the regional and country levels for the SADC project). The fivims projects and the CIS project have in common to improve and/or establish food security information systems with a view to improving food security monitoring (and vulnerability analysis) at the country level. The CIS project was designed around the provision for training on specific methodologies in pre-defined areas (food balances, the exploitation of household budget surveys, crop forecasting, database management and production of a food security bulletin). The fivims projects, in line with the FIVIMS principles, put much emphasis on institutional capacity building and promote a country tailor approach to country support. Finally, the complex emergencies project concentrates on the development of conceptual and analytical frameworks for better addressing food security issues in analysis and response to complex emergencies and the implications in terms of food security information.

Importance of Direct Technical Assistance to Countries

20.	The table shows that most of the projects combine direct technical assistance to countries with “normative” activities, including the development of concepts and guidelines. The importance of direct technical assistance at the country level varies among the projects.  The two fivims projects and the CIS project are the most country-level support-intensive with normative work being a result of country experiences. The fivims projects GCP/INT/741/EC and GCP/INT/741/EC are similar in their objectives, outputs and activities but cover a different set of countries. INT/741 focuses on less developed countries with a high prevalence of food insecurity and vulnerability; INT/742 provides technical assistance to small island states. The CIS project was conceived to provide support in five CIS Low-Income Food-Deficit Countries in collaboration with the EC Food Security Programme in these countries.

21.	The SADC project provides country support through the existing Regional Remote Sensing Unit of the SADC/Food Agriculture and Natural Resources (FANR) sector.

22.	The GIEWS project and, to some extent, the complex emergencies project do not provide direct technical assistance to countries. Under the complex emergencies project, country-level focus is essentially linked to the preparation of country case studies as part of the methodology for lessons learned and identifying best practices. However, with regard to the latter project, project staff provided technical advisory services albeit through other EC projects and or through FAO TCE funds.

Expected Beneficiaries

23.	Overall, the Programme documents identify the beneficiaries as “food insecure populations in a large number of countries and regions in Africa, Asia, Eastern Europe and Latin America. It will provide information and assistance to the public and private sectors to plan and implement food security operations.”

24.	Further levels of beneficiaries can also be identified.

25.	The ultimate expected beneficiaries of all the projects of the Programme are food insecure and vulnerable people. Improving the quality of and access to relevant and timely (in the case of early warning) information is expected to support better decisions and actions and therefore prevent major food crises and/or contribute to improvements in the condition of food insecure and vulnerable groups.

26.	There are several categories of expected immediate beneficiaries:

- As users of information, national policy-makers and the international aid community are expected to benefit from better quality (and timely) information products. In countries where direct technical assistance is received from the Programme, the EC Food Security Programmes and the EU delegations in those countries should also benefit from the results of the projects. Mention should be made here of FIVIMS-IAWG partners as a beneficiary target group of the fivims projects’ methodological outputs.

- More directly, technical staff in regional and national institutions is a very important beneficiary group for the projects that provide direct technical assistance since the objective at regional/country levels is to strengthen their capacity to produce improved information.

- Within FAO, GIEWS analysts, FAO staff and consultants working in the context of complex emergencies, and more broadly those within FAO working on food security information, are expected to benefit from most of the projects.

27.	Finally, the EC AIDCO F/5 itself is expected to benefit in several ways from the Programme: monitoring impact indicators for food security projects and programmes; strengthening the selection criteria of the beneficiary countries; better understanding of food security analysis methodologies (e.g. that of Crop and Food Supply assessment); and more generally, lessons learned and best practices for further application in its support to information systems.

## A.2	Implementing Arrangements

28.	The responsibilities of each party are stipulated in the implementing agreement signed in March 2000 by both parties. FAO is responsible for the execution of the Programme/projects. This includes the provision of personnel needed to execute the Programme, the supervisory and administrative support as well as appropriate backstopping and advisory services. The selection of such personnel is made in “consultation” with the Commission. This also applies to consultants hired under the consultancy funds. All projects, except the SADC project, are located at Headquarters. All the projects are operated under units of the FAO Economic and Social Department except for the SADC project (operated by the Regional Office for Africa and backstopped by the Environment and Natural Resources Service under the Sustainable Development Department) and the Trade project operated under the FAO Technical Cooperation Department.

29.	Eight project posts were established for the execution of the Programme.

Table 3: FAO Operating Unit and Project Staff

| Project | FAO Operating Unit | Project Staff I | Project Staff II |
| --- | --- | --- | --- |
| GCP/INT/740/EC GIEWS Project | ESCG: Global Information and Early Warning Service | P-4 : Technical Coordinator (GIEWS Workstation) | P-2 : Website/Database Manager |
| GCP/INT/741/EC + GCP/INT/742/EC fivims project | ESDG: Global Perspectives Studies Unit – FIVIMS Group | P-3 : FIVIMS Pilot Country Support Officer (2/3rd of cost) | P-2: FIVIMS Documentation Officer (2/3rd of cost) |
| GCP/RAF/351/EC SADC project | RAFR: Regional Office for Africa – Regional Branch + Backstopping responsibilities from HQs SDRN: Environment and Natural Resources Service | Regional Director |  |
| GCP/RAF/360/EC Complex emergencies project | ESAF: Food Security and Agricultural Projects Analysis Service | P-5: Senior Project Coordinator (Complex Emergencies) | P-2 : Database Officer |
| GCP/INT/814/EC CIS project | ESAF: Food Security and Agricultural Projects Analysis Service | P-4 : Technical Coordinator |  |
| GCP/INT/736/EC Trade project | TCAS + Regional Offices: Agricultural Policy Support Service | Consultancy only |  |
| GCP/INT/758/EC Consultancy Funds | ESDP: ES Programme Coordination Unit | Consultancy only + P3 Post created and filled in 2003 |  |

30.	In terms of reporting, FAO was to produce six monthly activity reports which, in addition of being a regular exchange mechanism between the EC AIDCO F/5 and the FAO project staff, were a condition for the annual instalment.

31.	The implementation of the Programme was planned to have a duration of three years starting from the receipt of the 80% advance of the budget for Year 1 from the Commission, with an additional year for orderly completion of any outstanding project activities and to permit final reporting and financial closure of the project. In fact, during a meeting in February 2003 between the Project Coordinator and the Head of the EC AIDCO, the EC and FAO agreed that the Programme may extend beyond July 2003 until its complete closure (operational and administrative) but not beyond July 2004. If there was a need to continue any activities beyond this latter date, they would be treated as new projects and considered accordingly.

## A.3	Budget and Disbursements

32.	The Implementing Agreement between the EC and the FAO is set in Euros. The EC pays FAO as follows:

- First year: 80% of the budget for the first year

- Following years: 80% of the budget for that year and the remaining 20% of the previous annual budget (subject to progress report approvals)

- On completion: 20% of the last year’s budget (subject to final report approval)

- 33.	At the beginning of the Programme year, the EC transfers corresponding amounts in Euros, which are automatically changed into US dollars on arrival in the FAO account, at the official exchange rate of the day. In the FAO account, interests are credited/debited depending on the balance of funds in the trust account. Consequently, the total receipts over time may vary (positively or negatively) and projects have to adjust their budgets and work plans accordingly. In fact, the balance has been positive throughout the life of the Programme and interest has accrued. Tranfers from the EC to FAO were received as schedule and in a timely manner.

34.	The total budget of the Programme amounted to Euros 12,5 million (or US$ 12,913,224 at a 1999 US$/€ rate of 0.968 as per in the Agreement).  The overall US$ budget was later reduced to $11,665,606 to take into account exchange rate losses when the first transfer was effected. Table 4 indicates the distribution of the budget among the projects.

STATUS AS OF 30 JUNE 2003

Table 4: Budget Status as of 30 June 2003

Note: The original budget (submitted in 2000) was US$ 12,913 million @ US/Euro exchange rate of 1 Euro=0,968 US$, equivalent to Euro 12,5 million.

Table 5: Funds already received by FAO

Table 6: Programme Funds available to FAO

35.	Most of the budget allocation is for expertise (project staff, consultants and technical support services), reflecting the technical assistance nature of the Programme.

COMMENTS AND RECOMMENDATIONS

36.	From Table 4, it can be seen that as of end June 2003 (39 months after the signature of the agreement, and with normally most of the projects near to completion), only 63% of the overall budget has been spent (including commitments). The budget status varies from one project to another, reflecting the different stages and rate of implementation. Budget expenditures for the Complex Emergencies project show that less than 40% of the budget has been spent and committed. On the other hand, expenditures for the Trade project (completed), SADC and GIEWS projects (almost completed) are much higher.

37.	Planned expenditure figures have been provided by project managers on the basis of a tentative work plan for the consolidation period (4th year) of the Programme. It is felt that, in some cases, planned expenditures are over-estimated taking into account the rate of implementation so far, or the actual completion of the project. The final balances are expected to be negative for two projects - GIEWS and the SADC projects – if they undertaken all planned activities by mid-2004. These over-expenditures would be offset by under-expenditure on other projects.

38.	Table 5 shows all payments received by FAO as well as the interest accrued. Table 6 shows the remaining outstanding payments, for which two scenarios of exchange rate have been considered. Overall, it can be seen that thanks to the exchange rate moving back in FAO’s favour and interest accrued, the total funds available to the Programme should comfortably cover the planned expenditures.

39.	There are three important actions to be taken for the smooth and uninterrupted completion of the Programme:

- for FAO to formally submit a set of budget revisions to the EC showing full utilization of expected available funds and any proposed reallocations between projects;

- for the EC to approve it rapidly; and

- for FAO to plan for cash flow, since the last instalment may arrive beyond July 2004, since it will only be made upon approval of the terminal project reports.

# B.	OVERALL ASSESSMENT OF THE PROGRAMME

## B.1	Relevance of the Programme

### B.1.1 	Relevance to Country Needs

40.	Overall, for most of the countries in which the Programme had substantial activities, food security is an issue of national dimension and the focus of the Programme on food security information is relevant. The Programme’s immediate objectives are particularly relevant in the CIS as they respond to the need for technical support to comply with the conditions attached to EC budget support. The selection of the fivims pilot countries was based on a broad range of political, economic and agro-ecological situations.

41.	The EC food aid/food security programme focuses action at the country level on a limited list of priority countries divided into two groups: (i) those receiving structural aid; and (ii) those receiving mainly food aid because of emergency or post-emergency situations.

42.	In 2001, the first group included 21 countries: Albania, Burkina Faso, Cape Verde, Mauritania, Niger, Ethiopia, Eritrea, Madagascar, Mozambique, Malawi, Yemen, Bangladesh, Georgia, Armenia, Azerbaijan, Kyrgyzstan, Moldova, Nicaragua, Honduras, Peru and Bolivia.

43.	The second group included 18 countries: Afghanistan, Cambodia, India, Pakistan, Laos, Liberia, Sierra Leone, North Korea, Somalia, Sudan, Democratic Republic of Congo, Rwanda, Angola, Ecuador, Palestine, Tajikistan, Montenegro and Haiti.

44.	Countries where the Programme had continuous activities (or planned to have in the project document) are in italics. Countries where only one single and short mission took place or where “marginal contacts” have been taken, mainly for fact finding activities are underlined.  In addition, the following countries outside the above-mentioned list were involved: SADC (those not mentioned above), Argentina, Kenya, Comoros, Samoa, Fiji, Burundi and Kosovo.

45.	The Review Team notes that there is only a partial matching of the countries covered by the Programme and the priority list of countries established by the EC for its food aid and food security assistance. For a few countries, justification on the basis of the importance of food insecurity is unclear (e.g., Fiji, Samoa, Barbados, in the fivims project covering small-island countries). Obviously for the latter, other criteria prevailed such as: the desire to include a broad range of situations, proximity with other countries covered in the other fivims project (Comores with Madagascar, Burkina Faso and Cape Verde), localization of FAO regional and sub-regional offices (Samoa and Barbados) with a view to using their implementing capacity to execute the project.

### B.1.2	Relevance for the European Commission and the EU Sectoral Policies

46.	Regulation n°1292/96, adopted by the Council of the European Union on 27 June 1996, defines the current legal framework of the Food Aid and Food Security Programme of the European Commission. It results from a process of reform of the food aid policy carried out since 1994, aiming to make food aid an instrument integrated as effectively as possible into the development policies and into the food security strategies of the concerned countries. The untied character of aid with respect to the management of European agricultural surpluses is formalized thanks to Article 11 of the Regulation.

47.	In April 2000, the Commission adopted a communication on the European Community’s development policy (COM (2000) 212).  Through this communication the objective of EC aid is clearly focussed on poverty eradication and sustainable development. Six areas of intervention are identified: trade and development, regional cooperation and integration, support to macro economic policies, food security and sustainable rural development strategies, institutional capacity building, good governance and rule of law.

48.	In view of the various aspects of EU development policy, the Programme as a whole is relevant and coherent with respect to EU development policies.

49.	In particular, EC action support to international early warning systems is explicitly mentioned in Regulation 1292/96. The concept of “strengthening of existing international early warning systems” is adequately represented in the objectives of the various projects focussed on food security information, both for “normative” aspects as well as implementation aspects.

50.	In crisis situations, the EC approach stresses the link between the emergency and development. Food aid provision is based on an analysis-diagnosis of the situations of food insecurity.

51.	On the other hand, reducing the vulnerability of the most vulnerable population groups means a good identification of them and a better understanding of the strategies that they implement to cope with the dynamics of the food risks.  All six food security information-related projects, as well as the consultancy fund, are meant to contribute to such assessments.

52.	Finally, the EC development policy identifies trade as a specific area of intervention (COM 2000/212, COM 2002/513). The project GCP/INT/736/EC is consistent with this orientation.

### B.1.3 	Relevance to FAO

53.	All the projects relate to at least one or several of FAO corporate strategies defined in its Strategic Framework 2000-2015. More specifically, individual project outputs were considered particularly relevant to two strategies: (i) contributing to the eradication of food insecurity and rural poverty (Strategy A); and (ii) improving decision-making through the provision of information, assessments and fostering of knowledge management for food and agriculture (Strategy E).

54.	Furthermore, all projects relate to Regular Programme entities defined in the FAO Medium-Term Plan. In this regard, in defining the implementing arrangements, the location of the project within FAO was determined by the links between the projects with these programme entities and the main responsible technical units for implementing these programme entities.

55.	The concern of relevant technical divisions to ensure the integration of projects into the regular programme of relevant technical divisions led, after its revision in summer 2001, to the transfer of the CIS project from ESCG to ESAF, traditionally supporting normative and country technical support on food security information systems.

56.	With the exception of the Trade project and the Consultancy Funds, the Programme (by its activities and/or location) relates essentially to three Regular Programme entities:

- Global Information and Early Warning System on Food and Agriculture (FAO code: 223P6). The SADC project as well as the GIEWS project are closely related to activities carried out under this programme. Furthermore, both projects are expected to improve ESCG main products (e.g. Crop and Food Supply assessment, Food Outlook, etc.).

- Food Insecurity and Vulnerability Information and Mapping System (FAO code 222A1). The fivims projects and, to a certain extent, all of the food security information related projects of the Programme, are related to the FAO FIVIMS Programme entity.

- Contribution of Agriculture to Poverty Alleviation, Rural Development and Food Security (FAO code 224P2). Less immediate are the linkages between the CIS project and the Complex Emergencies project with activities carried out under this programme entity, of which major outputs include analytical studies on food security policies, practices and options.

57.	The Complex Emergencies project, through its implementation approach (facilitating role to other units), is closely integrated with FAO’s regular programme of work on information in the context of complex emergencies as well as more broadly on FAO’s activities contributing to one of the Strategic Objectives (A3 - Preparedness for, and effective and sustainable response to, food and agricultural emergencies). It is closely linked to FAO’s Priority Area for Inter-disciplinary Action on Disaster Prevention, Preparedness, Mitigation and Post-Disaster Relief and Rehabilitation (PAIA-REHAB). Finally, due to its focus on information use, project staff maintain close relationships with staff of FAO’s Emergency and Rehabilitation Division.

58.	More generally, the relevance of the Programme to FAO’s activities lies also in the linkages with other food security information system projects.

59.	The following box shows the importance of FAO’s food security information activities in the form of direct assistance to countries and in addition to its Regular Programme activities.

Box 2: Importance of FAO’s Food Security Information Activities other than Regular Programme Activities

Current EC/FAO Collaboration in Food Security Information support outside 1999 Package: Angola: Support to the Food Security Directorate (GSA), Ministry of Agriculture and Rural Development (Phases I and II) Mozambique: Support to the Food Security and Nutrition Secretariat (SETSAN, Early Warning, FIVIMS) and Market Information (Ministry of Commerce) Somalia: Support to the FSAU (Food Security Assessment Unit), Phases III and IV Eritrea: Technical Support to Ministry of Agriculture (food security policy, information, M&E) (pipeline project) FAO Food Security Information Activities (other than EC supported) FIVIMS Asia: Phases I and II (Japan) ECOWAS: Renforcement et coordination des systèmes d’information sur l’insécurité et la vulnérabilité alimentaires (FAO) Afghanistan: Support to Food Security Surveillance, Early Warning, Nutrition and Livelihoods Analysis (USA and Germany) Eritrea: Support to the National Food Information System (Italy) Kenya: Support to Early Warning in Semi-arid Lands (FAO) Mauritania: Appui à l'Observatoire pour la Sécurité Alimentaire (FAO) Nicaragua: Support to FIVIMS/SISSA (FAO) Namibia: Support to national FIVIMS (Govt of Namibia) Vietnam: National Food Security Information System (Italy) FAO Emergency Division: Support to Food Security Surveillance under Emergency Conditions through FAO Emergency Coordination Units (including in Afghanistan, Angola, Burundi, DRC, Kosovo, Malawi, Sierra Leone, Southern Sudan and Zambia) (FAO & various donors)

## B.2	Coherence of the Programme Design and Strategy

60.	The Programme was obviously not conceived as such in the sense that no linkages were built between the projects other than a common source of funds and the very broad theme of food security. The word “package” might be more appropriate than programme to designate the set of projects.   Nevertheless, the Programme, through six of the eight projects, focuses on food security information covering various functions including: early warning, food security and vulnerability analysis, data/information management as well as advocacy and communication.

61.	Linked to the above, there is no conceptual framework behind the Programme other than the conceptual framework for food security formulated and used by FAO in different instances. This conceptual framework describes the factors at various levels (national, sub national, community, household and individual) that eventually affect the nutritional status of individuals. While being comprehensive in its coverage, nearly all FAO activities could fit into the framework. It is too broad to be useful for providing a focus and coherence in the Programme.

62.	The Programme, which is supported by an implementing agreement, is sketchily described in a two-page annex giving a summary description of the Programme and its components. Not surprisingly and consequently, the Programme has been run by FAO as a set of individual projects with limited coordination involved other than administrative. This also brought methodological issues for the present evaluation of the package as a Programme as indicated earlier.

63.	However, each project is detailed in a full-fledged project document based on a format for Trust Fund projects and including objectives, outputs, activities and inputs. One exception to this was the Consultancy Funds for which there was no project document but a mere two-page document. The lack of clear guidance as to the objectives and criteria on the basis of which consultancies could be approved under the funds, as well as the lack of procedures, seriously delayed and hampered implementation. It was only when guidelines and procedures were prepared by the Programme Coordinator in consultation with AIDCO F/5 in 2001 that the project could become operational.

64.	Neither the agreement nor the project documents provide clear indications on the terms of collaboration between FAO and the EC (EC AIDCO- F/5) at Headquarters as well as in the field, other than the legal, financial and administrative collaboration. Potential for fruitful exchanges between Headquarters but also at the country level was little exploited and essentially left to the interest and goodwill of individuals. Some projects were designed in such a way that close collaboration between the EC structure and the project was essential to the efficiency of implementation. This was initially the case of the Fivims projects with RESAL. The CIS project necessitates close collaboration between the project staff and the country EC Food Security Programme. In some instances, clarification on the terms of collaboration, including respective responsibilities, would have permitted greater efficiency.

65.	All the projects are designed in such a way as to benefit from the expertise existing in FAO, thus building on the added-value of FAO. Firstly, with the exception of the SADC project, the projects are located at Headquarters within the technical units with programmes and activities relevant to the projects, hence receiving technical support additional to that budgeted in the project.  The SADC project, however, was backstopped by the relevant technical unit at FAO Headquarters. Secondly, advisory technical services were planned and budgeted in some projects, drawing further on FAO’s expertise when and as needed.

66.	Most of the projects (except the Consultancy Funds) combine well in their approach normative and operational objectives in a way that facilitates the development of synergies between the two: lessons learned and normative materials developed from nine pilot applications in the fivims projects; and development of training materials for specific purposes in the SADC project as well as in the CIS project. This is again building on FAO’s model of cooperation (and value-added) based on normative-operational synergy so as to ensure that lessons learned from operational activities enhance normative functions while normative guidelines, methodologies and standards enrich operational work.

67.	The approach of some projects is not cost-effective.  This is the case for the fivims projects for which the geographical dispersion of pilot countries as well as the absence of a regional focus prevent economies of scale in the conduct of backstopping missions, networking with regional and international partner organizations, etc. The training approach in the CIS project (mostly one-time country workshops with few participants) was also not cost-effective.

68.	Some of the projects went through substantial revisions. This was the case for the CIS project and the Complex Emergencies project. The former was done at the request of the EC because the project, as initially formulated, did not respond to the particular needs of the EC in that region due to the termination of RESAL activities, i.e. technical assistance support for capacity building on the production of food security information associated with the EC Food Security Programme in the CIS countries. The Complex Emergencies project was revised with a view to taking into account recent relevant developments in FAO’s Medium-Term Plan as well as to increasing the normative and advisory nature of the project and facilitating the work of other in-house units and field projects on food security information. However, the project (as revised) lost clarity to a certain extent on outputs to be produced under the project with the definition of only broad “activity focus areas”.

69.	Overall and despite detailed documents, the project documents are not sufficiently clear in their immediate objectives and outputs. In particular, the objectives and outputs are spelled out in such vague terms that it can always easily be argued that they have been met, even if the actual results are clearly insufficient. The objectives should be provided with indicators of the measure of success. Among the outputs, the explicit identification of deliverables would be expected, and described in such a way that the verification of their production can be made in a more objective manner.

70.	The Consultancy Fund remains too broad in its scope, objectives and selection criteria. While the guidelines and procedures mention that “the technical fields in which the consultancy services may be used should be closely related to food security”, they include a variety of broad domains such as, inter alia, animal health and disease control; rural financial markets; trade and food security; and prevention of food emergencies.

71.	Consequently, most projects appear over-ambitious in their immediate objectives in relation to the resources provided. This is particularly true for the fivims and CIS projects. Human resources available under the projects and based at FAO Headquarters in Rome are too limited to fully support intensive project activities implemented in nine countries. This is also the assessment made in the review of the SADC project. When compared to other similar operations elsewhere, the project workplan was probably too ambitious for the human and financial resources available.

## B.3	Efficiency of Implementation

72.	Overall, much was achieved in terms of products and services delivered throughout the projects. This is largely attributed to dedicated and competent project staff and the technical support provided by FAO, as well as the mutual benefits derived from the synergies between the projects and other FAO programmes.

73.	Despite this positive overall assessment, it must be recognized that for the moment, the translation into field action of normative activities and vice versa has been limited, with emphasis given to one aspect or the other in each of the projects. The bulk of the normative work (including lessons learned from pilot country applications in the fivims projects) remains to be achieved in a number of projects.

74.	The projects are at various stages of implementation. Delays in implementation (at least six months) have been important for nearly all projects. Several factors impeded the smooth implementation of the projects, the most important ones include:

- the time needed for staff recruitment, which appeared to be a lengthy process (6 months in most cases);

- some projects were re-defined or refined either at the request of the EC (CIS project) or of FAO (Complex Emergency project, Consultancy Fund);

- the slow responsiveness of the EC on most matters: the EC approval of revised project documents took several months;

- project staff movement and consequent re-orientation of activities in some projects;

- inherent weaknesses in project design as mentioned above.

75.	For those projects which included country-level activities: inadequate FAO support at country level and lack of realism on the role of national counterpart agencies. There were also difficulties in finding Russian-speaking experts in technical areas covered by the CIS project.

### Programme Management and Coordination

Adequacy of FAO’s Management and Support

76.	The Programme Agreement of Implementation leaves “…proper implementation of the Programme/Projects…” to FAO.

At Programme level

77.	The time and resources needed for administering and coordinating such a Programme was under-estimated. The overall responsibility for coordination and management of the Programme was given to the Programme Coordinator (PC) of the Economic and Social Department. The functions of the post are such that the officer is not in a position to devote the time and resources necessary for the proper coordination and management of an additional Programme. The appointment of a staff member (not initially planned) to assist in the management and coordination of the Programme in the second year of its implementation reflected the necessity to increase FAO’s capacity in this regard and was a positive measure. The day-to-day management of project resources, decentralized at the project level, also reduced some administrative tasks of the Programme Coordinator.

Technical Support and Linkages within FAO

78.	The Review Team acknowledges the high professional quality and dedication of project staff employed by the Programme in general as well as the technical support provided by FAO. Technical support is provided in many ways, through technical assistance from other FAO units foreseen in the project documents (e.g. technical support from REUP in the CIS project) but also through the projects’ immediate working environment and linkages with other programmes.

79.	The projects are located in divisions and/or units within which they are generally well integrated and with which there are opportunities for exchanges and mutual benefits with programmes carried out by these units (Section A.2, Table 3). This is particularly true for the GIEWS project where ESCG staff are themselves amongst the primary users of information generated. Linkages are also important between the fivims projects and the FIVIMS initiative. In that case, the Programme under which the projects are placed is expected to benefit directly from outputs produced under the projects.

80.	Beyond the project locations, linkages and technical exchanges have also been significant with other major programmes managed at FAO. GIEWS workstation has well-established working relations with FAOSTAT, GEONETWORK, ARTEMIS, EIMS, AFRICOVER, and the AgroMet group. The Complex Emergencies project provides the leadership in the design and establishment of an FAO emergency database under the PAIA-REHAB.

81.	Generally, projects received appropriate technical supervision. The SADC project, which is the only project located outside Headquarters, benefited from substantial technical backstopping from SDRN. However, greater coherence could be gained if projects with many similarities (CIS project and the fivims projects) were under the same technical supervision and management. The Programme would benefit from greater overall technical cooperation between projects.

Coordination between Projects

82.	Technical coordination between projects was not formally expressed as a specific programme action. Not surprisingly, its added value for the Programme implementation and results was not considered until recently when more intensive discussion between the EC and FAO relating to the Programme required coordination. Furthermore, and despite the central role of FIVIMS on information-related work within FAO, the unit where the FIVIMS secretariat is located (including the fivims projects) did not play a particular technical coordination role among the projects. The reasons for this are essentially institutional (many locations of information related work within FAO, together with the unclear coordination function) and linked to the limited resources of the FIVIMS Secretariat.

83.	The need for greater technical coordination between projects was partially compensated by informal links through the shared interests of project staff. Examples of specific collaboration among projects of the Programme include:

- sharing of training materials between fivims and CIS projects;

- joint collaboration at country level between the Complex Emergencies project and fivims project on the application of a modified Household Food Economy Approach methodology in Kenya, through exchanges of experts;  and

- GIEWS Workstation project has collaborated with most projects, mostly in terms of technical database design.

Support at Country Level

84.	The support provided by FAO Representations at the country level is limited to logistics and local administration of some activities. The efficiency with which it is done varies widely from country to country and from project to project. The activities under the fivims projects require close follow-up that, in most cases, cannot be ensured by overloaded FAO Representations with minimal resources.

85.	The role of FAO Representations is particularly critical for the implementation of consultancies under the Consultancy Fund project. Although the Review Team could only have a very partial view, it was observed that neither the Consultancy Fund nor the implementing document (GaP) were well known.

86.	The weak and unstable capacity of national institutions designated by governments as focal points for the fivims projects was identified as a major constraint to the efficiency of implementation and was raised in several instances by the project staff.

87.	This appears to be a concern shared by other projects with activities at country level, including by the CIS project where the weakness of institutions clearly limited the impact of capacity-building activities.

88.	More successful stories took place where there were political commitment, significant external resources devoted to institutional strengthening, and thus a more solid institutional environment, and where the project activities were fully complemented by other major support. This is the case of the fivims activities in Kenya which, in addition, were closely followed up by a competent national consultant partially paid by the project. Capacity building at country level calls for realistic work planning and careful selection of interventions.

### Adequacy of EC Support

At Headquarters:

89.	Annual instalments were provided on time, according to the agreed schedule and procedures of the EC.

90.	Implementation does, however, suffer from inefficiencies in the EC administration of the Programme. Considering the limited importance of the Programme within the overall volume of activities (and budget) managed by the EC AIDCO/F5 (food security unit), the Programme is obviously not given high priority. This was reflected, among other things, in delays in approving revisions to annexes of the EC-FAO implementing agreement (i.e. project documents). These delays had a direct impact on the start of activities of projects which were re-designed (Complex Emergencies project as well as the CIS project). In both cases, FAO eventually started activities without having received official approval. Numerous delays were also reported in the case of the Consultancy Fund project. Approvals of both the individual consultancies and the consultants were excessively slow (up to one year in a few cases). This was partly due to inadequate procedures for the implementation of the fund such as the double ranking and selection process (EC and FAO) for any consultant recruited under the fund.

91.	Technical collaboration happened in the case of the GIEWS project which benefited from cooperation between FAO and two different units at JRC (GVM and MARS) in the framework of a specific agreement.

92.	However, the Programme would have benefited from greater involvement and interest from EC technical staff. Project staff rarely, if at all, received feedback on project progress reports although they are a condition for the EC to provide the annual instalment. Their content is generally thorough and highlights, among other things, issues of implementation. They could have formed a good basis for discussion between the EC and FAO, as well as more generally an adequate instrument for the joint management of the projects and the Programme including joint search for solutions when issues occurred.

93.	The technical dialogue between EC officers and project staff could be facilitated by direct line of communication between them as demonstrated by the regular consultation taking place under the Complex Emergencies project. Such a dialogue could be implemented at the Programme level through more regular meetings between AIDCO F/5 and the Programme Coordinator/core group.

At Country Level:

94.	The only project where interaction with the EC delegation is explicitly mentioned is the Consultancy Fund project: consultancy request must be endorsed jointly by the FAO Representative and the EU Delegate to the beneficiary country.

95.	In the absence of a clear identification and definition of roles and responsibilities from the EC staff, support provided was left to the individual. Linkages have been particularly important in the case of the CIS project which, by design, implied close collaboration between the EC-FSP in the country and the project. In other cases, the level of interaction and support depends very much on the overall volume of cooperation between the two institutions in the country. It should be made clear in both FAO and the EC that country-level collaboration should be the norm for related work especially that funded under the Programme.

Visibility and Recognition of the EC

96.	Most projects created/adapted/distributed materials such as guidelines, reference material, user guides and software. The various documents/CD carry logos which lack obvious homogeneity between them. While FAO is generally noted, the EC logo is regularly missed. FAO and the EC should establish in the Programme agreements guidance on the visibility to be accorded to FAO and the EC as well as disclaimers. In general, materials should not be copyrighted.

## B.4	Cost-effectiveness

97.	Overall, the Programme was implemented in a cost-efficient manner (in part due to its location at FAO Headquarters and integration with other FAO programmes).  Some factors did, however, generate cost-ineffectiveness.

98.	As already mentioned in the above section, the geographic dispersion of the countries selected under the fivims projects prevented economies of scale and, combined with limited resources, led to reduced effectiveness.

99.	The implementation of training activities in the CIS project does not appear to be cost-effective. One-off training centrally organized from FAO, with flying visits from international experts and with limited follow-up, has a high cost with limited impacts.

100.	In reviewing and comparing the capacity building/training approaches of the various projects of the Programme, including that of the Trade project, efficiency gains seem to result from greater regional focus for capacity-building activities, including the organization of regional workshops, the use of regional networks and institutions such as the CILSS and the SADC as relays for training at the national level (including training of trainers approach) and a better integration with information-related work of other organizations (e.g. with FIVIMS partners’ institutions present and active at regional level).

101.	At the same time, the Review Team recognizes the need for capacity-building including customized training at the national level. Whether it is done by regional trained trainers, or by the Programme itself, capacity-building at the national level necessitates on-the-job and follow-up training. In addition, if carried out under the Programme, it should be done so in countries where a number of conditions are met, including political commitment and strong or supported institutional environment.

## B.5	Overall Assessment of Outcomes and Impacts

102.	The difficulties in assessing the Programme outcomes and impacts in the absence of a Programme concept should again be underlined. Outputs were produced on an individual project basis without much interaction among the projects (or only in very limited cases as noted in Section B.3). As a result, the Programme’s outcomes and impacts tend to be the sum of outcomes and impacts of individual projects. In addition, while the MTR comes at the end of the Programme’s life, it is still “work in progress” for most of the projects, all at different stages of implementation. For example, the SADC project and the GIEWS project are near completion while at the other extreme, the Complex Emergencies project has just started the ball rolling.

103.	As indicated in Section B.2, the Expected Results described in the Implementation Agreement of the Programme are very broad, and include short-term outcomes and longer-term impacts, as well as overlapping areas between them. It is thus difficult to use them for assessing what has actually been achieved and its impacts. The latter can be viewed from different perspectives. While there are visible project achievements in terms of capacity-building, they are far from having built strong and sustainable capacities.

104.	On the other hand, if one considers the Programme with a long-term perspective and with the ultimate goal of improved food security and nutrition, these projects achieved an invaluable and essential path/fact finding work, as well as laid down strong basic foundation blocks, only waiting to be built upon.

105.	For assessment purposes, it was found useful to re-define generic expected outcomes and impacts of the Programme. The generic expected outcomes of the Programme were based on the Implementation Agreement and the individual project documents. The expected impacts of the Programme are generally not defined in the Programme or in the project documents. They are essentially those associated with the uses of better food security, vulnerability and early warning information and analysis, the ultimate objective of the Programme being seen as improved food security and nutrition.

106.	Table 7 below summarizes these new definitions.

| Ultimate Impacts | Table 7: Improved Food Security and Nutrition |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ##### Impacts | - Improved understanding of food security and vulnerability - Better household food security and nutrition monitoring - Better prevention, preparedness of food crisis - Timely and appropriate emergency response - Appropriate policy formulation/programming for food security |  |  |  |  |
| Outcomes/ Results | Strengthened Capacity at regional/ country-level for FS and vulnerability monitoring and EW | Strengthened capacity at country level for designing and implementing specific action programmes to reduce food insecurity | Expanded Global Monitoring and EW | Access to reference material | Intensified EC/FAO Collaboration |
| Project & main activities | SADC Project (technology transfer + training) CIS Project, Fivims projects & Complex Emergencies project (training) | Consultancy Funds through Specific interventions | GIEWS Project (development of an analytical tool: GIEWS Workstation) | SADC, CIS, fivims, GIEWS projects, Complex Emergencies project | All projects |

107.	The next part of this section attempts to synthesize from all individual project reviews, what, at the programme level, was achieved by identified outcomes. Expected and actual impacts are underscored to the extent possible.

Strengthened Capacity at Regional and National Levels for Food Security and Vulnerability Monitoring and EW (SADC, fivims, CIS project and Complex Emergencies projects)

108.	This is one of the main areas with significant outcomes. Substantial capacity was built, mostly through training (from workshops to on-the-job training), in many areas relevant to food security information, such as Household Consumption Surveys, Food Balance sheet, crop forecasting, drought forecasting, as well as on the concept of food and nutrition security.

109.	Internalization of capacity-building through regional institutions was accomplished through the SADC project, hence setting the ground for sustainability in the future. As indicated in Section B.3, national capacity is built through training carried out by SADC project staff independently of international experts.

110.	There are several factors that limited achievements in terms of capacity-building, including among the main ones:

- the limited resources available for capacity-building for each country covered by the Programme combined with the dispersion of actions: both in terms of countries – in the fivims projects the geographic dispersion of selected pilot countries led to scattered and relatively small actions in each country - and in terms of subject areas – in the CIS project, the number of technical areas to be covered in each of the countries limited the depth of capacity-building activities and thus of achievement in this regard;

- the under-estimation of the weakness of institutional capacity at country level, thus limiting the achievable within the timeframe and resources;  and

- the insufficient policy environment for receiving food security information reflected in the difficulties in identifying uses and users.

111.	Overall, and not surprisingly, capacity building was most effective when it was well-targeted, specific and not over-ambitious. Institutional strengthening at country level was very limited and not highly successful so far (fivims projects). This reveals the limit of what could be achieved under the Programme given the limited resources, the relatively short timeframe of the Programme, as well as the project management set-up preventing a necessary close follow-up.

112.	To date, the Complex Emergencies project achieved limited capacity-building beyond FAO itself. This is mainly due to the fact that the project is not designed with capacity building objectives and the priority was given first to the needed conceptual work.  However, the project was catalytic in promoting conceptual and analytical frameworks on food security and crisis amongst FAO staff.

113.	The impacts of these outcomes are modest but not insignificant. The Review Team mainly identified the following:

- A better understanding of food security issues and in particular of the multi-sectoral dimension of food security (mostly through the CIS and the fivims projects).

- Creation and/or improvement of inter-institutional dialogue (CIS) and network (fivims projects).

114.	Given the multi-disciplinary and multi-sectoral nature of food security, these two aspects will likely generate positive changes of attitude which constitute the essential foundation to best tackle food security issues.

- An uptake and improvement in practice, when the training was appropriately focused and dimensioned.

- New/improved information products have been generated, some are one-time food security reports, others are periodic reports.  The main value-added is generally in terms of multi-sectoral integration and analytical content. The extent to which the production of such new/improved information is sustainable was difficult to assess.

115.	Based on a restricted number of observations by the Review Team, impacts in terms of actual usage of the new information, when produced, still appear to be limited. This is largely the result of a poor identification of usage and their users’requirements in the first place. While, in the SADC project, capacity was built to produce information, there is little evidence of the use of that information at country level. Another illustration is the bulletin produced (though improved) under the CIS project, the use of which seems very much limited to the EC. It must be noted, however, that most diagnostic and assessment work and documents proved to be of great value to the target users in several cases in the fivims projects.

116.	Within the Programme’s short timeframe, sufficient capacity to ensure sustainable impacts could not be achieved. Consequently, long-term impacts of capacity building will require further consolidation, adapted and continuous training, as well as a greater focus on the usage and users’requirements for food security information.

Strengthened Capacity at Country Level for Designing and Implementing Specific Action Programmes (Consultancy Funds project)

117.	Based on a small sample of observations, the Review Team found the outputs produced under the Consultancy Funds well integrated in the broader context within which they were produced and useful. They contributed to a process, though minimal capacity-building was achieved.

Expanded Global Monitoring and Early Warning (GIEWS Workstation project)

118.	The main achievements towards this outcome have been:

- the completely re-designed GIEWS workstation, in order to provide a series of new analytical tools, flexibility for customization, and access to archived newly-generated information on food security;  and

- the expansion of a series of databases (administrative boundaries, base map information, crop information etc.), at the national level, for a selection of countries.

119.	The GIEWS workstation, with its ambitious re-design, will most likely bring long-term flexibility and adaptability of the platform and, therefore, ensure greater sustainability. However, the limitation in resources necessitated focusing on very specific areas of development, initially the core/modular platform, the provision of analytical tools for the GIEWS analysts, and it has improved information on a limited number of countries.

120.	The GIEWS Workstation is expected to generate greater quality information flows and more efficient working methods. It should be operational in the very near future.

121.	In the short term, when the current version of the station becomes operational, major impact on the working process of FAO/GIEWS food security analysts can be expected. However, it is anticipated that it will very much depend on the full institutionalization of the tool within FAO. In the longer term, when the system will be adapted and transferred to individual countries, it is expected to provide countries with a tool to analyse all kinds of food security information, both at national and sub-national levels. However, this will depend on the adaptability of the system to country needs, as well as its appropriate design for data transfer and exchange at a more central level (FAO).

Access to Reference Materials (SADC, fivims, CIS project, Complex Emergencies and GIEWS Workstation projects)

122.	These projects have provided/produced/gathered a substantial amount of materials (mostly training materials such as reference documents, exercises and demonstration software), but also adapted software (CIS), case studies (Complex Emergencies) and pilot countries assessment (fivims). Some benefited from informal interactions between projects and FIVIMS. It must be noted that the quality and user-friendliness of such material appear to vary greatly.

123.	Some of the material is normative in nature because it is compatible and is/can be used in several countries. However, the Review Team has only found a few examples of real effort to render the material produced more generic, say in an off-the-shelf format easily accessible to other potential users. This has partly been due to the lack of resources and therefore balance between the various activities.

124.	The diversity of languages (English and French for the fivims projects, Russian and other local CIS languages for the CIS project, and English, French and Portuguese for the SADC project) is clearly a barrier to access to reference material, as well as to successful training, day-to-day communication and uptake. It must be noted, however, that substantial material and training were provided in Russian in the CIS project, making a visible impact.

125.	The Review Team is of the view that outcomes could be greater with more cross-fertilisation of ideas and experiences among projects in particular among those with strong similarities, and with improved quality and user-friendly material. Some kind of centralization and standard in the production of the normative material would probably benefit the Programme, which, as indicated elsewhere, would also very much benefit from Programme technical coordination.

Intensified EC/FAO Collaboration at Country Level (all projects)

126.	Overall, a sustainable intensification of EC/FAO collaboration at the country level has been very modest. It is mainly in the cases where the project design included, at least implicitly, some collaborative arrangements. The intensification of the EC/FAO collaboration is most visible through the CIS project, though remaining at the level of the project.

127.	Some outputs produced under the Consultancy Fund generated further collaboration with the EC (project documents prepared under the Consultancy Fund led to an EC/FAO/country agreement).

128.	However, in general, the other projects did not particularly foster further collaboration at the country level between the two institutions as project activities and amounts involved were small compared to the overall existing volume of EC/FAO cooperation in the country.

# C.	GENERAL FINDINGS

Relevance

129.	Overall, for most of the countries in which the Programme had substantial activities, food security is an issue of national dimension and the focus of the Programme on food security information is relevant. The Programme’s immediate objectives are particularly relevant in the CIS countries as they respond to the need for technical support to comply with the conditions attached to EC budget support. The selection of the fivims pilot countries was based on the consideration to have a broad range of political, economic and agro-ecological situations. However, the Review Team notes that there is only a partial matching of the countries covered by the Programme and the priority list of countries established by the EC for its food aid and food security assistance. For a few countries, justification on the basis of food security consideration is unclear.

130.	The Programme addresses two different areas among the EU six priority areas for development defined in its Communication of April 2000: food security and sustainable development and trade and development (Trade project). The programme is compliant with EC regulation 1292/96 defining the legal framework for the implementation of the Food Aid and Food Security programme.

131.	All the projects relate to, at least, one or several of FAO corporate strategies defined in its Strategic Framework 2000-2015. More specifically, individual project outputs were considered particularly relevant to two strategies: (i) contributing to the eradication of food insecurity and rural poverty (Strategy A); and (ii) improving decision-making through the provision of information, assessments, and fostering of knowledge management for food and agriculture (Strategy E). Finally, all projects relate to Regular Programme entities defined in the FAO Medium-Term Plan. In particular, the Programme is well integrated with FAO GIEWS and FIVIMS.

Programme Design

132.	The Programme was not conceived as such and is perceived more as a set of projects funded under the same budget. Nevertheless, there are some common features among the projects: (i) there is a common theme for six out of the eight projects (or nearly three quarters of the total Programme budget), i.e., support to early warning and/or food security information; (ii) there is a common approach to several projects in the Programme (five out of eight), combining normative work (including knowledge of  lessons learned, best practices, standards and procedures of wider applications) and regional/country capacity building, and designed in such a way as to build synergy between normative and operational work. The lack of a more “programme approach” has consequences in terms of loss of opportunities using complementarity and synergy between projects, and thus on the potentiality for greater outcomes and impacts of projects outputs.

133.	Projects are designed building rightly on FAO’s added values, including cross-fertilization between the projects and FAO regular programmes, the combination and synergy between normative and operational work, as well as drawing from FAO’ s expertise for multi-sectoral backstopping. The projects’ immediate objectives are generally relevant, but also quite broad. However, the outputs and deliverables are often weakly formulated and no measurable indicators of success are contained in the project documents. Consequently, expected results and modalities of implementation have been left to a large extent to individual interpretation.  The latter being generally ambitious, leads to an inadequacy between resources and expected results in most projects. In a few projects, the approach is not cost-effective (e.g., CIS project & fivims projects). One case in point is the geographical dispersion of selected countries under the fivims projects.

Efficiency of Implementation

134.	Overall, much was achieved in terms of products and services delivered throughout the projects. This is largely attributed to dedicated and competent project staff and the technical support provided by FAO, as well as the mutual benefits derived from the synergies between the projects and other FAO programmes (e.g. fivims projects with FIVIMS, GIEWS and ARTEMIS).

135.	Despite this positive overall assessment, it must be recognised that for the moment, the translation into operations and actions of normative activities and vice versa has been limited, with emphasis given to one aspect or the other in each of the projects. The bulk of the normative work (including lessons learned from pilot country applications in the fivims projects) remains to be done in a number of projects.

136.	The projects are at various stages of implementation. Delays in implementation (at least six months) have been important for nearly all projects. This is accounted for by the time needed for staff recruitment which appeared to be a lengthy process. Some projects were re-defined or refined either at the request of the EC (CIS project) or of FAO (Complex Emergency project, consultancy funds). This indubitably impeded the pace of implementation of these projects. The slow responsiveness of the EC on most matters also created further delays in implementation (e.g. approval for project revisions came very late when they came).  Other factors that impacted negatively on the smooth implementation of the projects relate to changes in staff and consequent re-orientation of activities in some projects as well as the inherent weaknesses in project design as mentioned above.

137.	The time and resources needed for administrating such a programme was under-estimated and the appointment of staff (not initially planned) for assisting in the management and coordination of the Programme in the second year of its implementation reflects the necessity to increase FAO’s capacity in this regard. The Programme would have gained efficiency with greater technical coordination in addition to administrative coordination. This would have permitted more synergies and mutual benefits between projects as well as avoidance of duplication. It should be noted though, that the lack of coordination was partially compensated by informal links essentially based on individual interest between project staff. Greater coherence would also have been gained if projects with many similarities (CIS project and the fivims projects) were under the same technical supervision and management.

138.	From the EC side, the budget was provided according to the agreed schedule and procedures. At the technical level, the Programme would have benefited from greater involvement from the EC technical staff. At the country level, and in the absence of a clear identification and definition of roles and responsibilities from the EC staff, support provided was left to the appreciation of individual. Linkages have been particularly important in the case of the CIS project which, by design, implied close collaboration between the EC-FSP in the country and the project.

Outcomes and Impacts

139.	It is difficult to assess the Programme’s outcomes in the absence of a programme concept. Programme outcomes and impacts should essentially be seen as the sum of outcomes and impacts of individual projects. Another methodological difficulty lies in the various stages of implementation of the projects. In fact, while the MTR comes at the end of the Programme’s life, it is still “work in progress” for most of the projects.

140.	The Review Team defined the following five expected generic outcomes, resulting from outputs of one or several projects of the Programme. This was done on the basis of those stipulated in the Programme agreement (where they are in a more aggregated manner):

- strengthened capacity regional and national levels for food security and vulnerability monitoring and early warning;

- strengthened capacity at the country level for designing and implementing specific action programmes to reduce food insecurity;

- expanded global monitoring and early warning;

- access to reference materials; and

- intensified EC/FAO collaboration.

Strengthened Capacity at Regional and National Levels for Food Security and Vulnerability Monitoring and Early Warning (SADC, fivims projects, CIS project, Complex Emergency projects)

141.	Substantial capacity was built, mostly through training (workshops as well as on-the-job training). It is undeniable that training carried out contributed to a better understanding of food security issues and of the multi-sectoral dimension of food security, in particular through the CIS and the fivims projects. Capacity building activity further resulted in improved inter-institutional dialogue and network in most cases. Internalisation of capacity-building through regional institutions was accomplished through the SADC project. To date, the complex emergency project achieved limited capacity building outside that within FAO. This is mainly due to the fact that the project is not designed with clear capacity building objectives and that priority was given first to the needed conceptual work.

142.	There are several factors that limit achievements in terms of capacity building, including among the main ones: the dispersion of actions combined with limited resources, the under-estimation of the weakness of institutional capacity at country level, the insufficient policy environment and, in a few cases, the relatively poor linkages between the information products and the target user groups (SADC and CIS projects).

143.	Overall, capacity building was most effective when it was well-targeted, specific and not over-ambitious. Institutional strengthening at country level was very limited and not highly successful so far. This reveals the limit of what could be achieved under the Programme given the limited resources, the relative short timeframe of the Programme, as well as the project management set-up preventing a necessary close follow-up.

Strengthened Capacity at Country Level for Designing and Implementing Specific Action Programmes (Consultancy funds)

144.	Based on a small sample of observations, the Review Team found the outputs produced under the consultancy funds well-integrated in the broader context within which they were produced, and useful. They contributed to a process, though minimal capacity building was achieved.

Expanded Global Monitoring and Early Warning (GIEWS Workstation)

145.	The GIEWS Workstation is expected to generate greater quality information flows and more efficient working methods. Its impacts will depend on the full institutionalisation of the tool within FAO as well as the adaptability of the system to country needs.

Access to Reference Materials

146.	Normative materials were produced throughout all the projects. Overall, the design and quality of these materials are heterogeneous. The Review Team is of the view that outcomes could be greater with more inter-action among projects in particular among those with strong similarities. One recognised barrier to access to reference materials was the lack of such material translated into country official languages.

Intensified EC/FAO Collaboration at Country Level (all the projects)

147.	EC/FAO collaboration at country level was indeed intensified in cases where the project design at least implicitly included collaborative arrangements. The EC/FAO collaboration was the most effective through the CIS project that. Some outputs produced under the consultancy funds generated further collaboration with the EC (project documents prepared under the consultancy funds led to an EC/FAO/country agreement). However, in general, the other projects of the Programme did not particularly foster further collaboration at the country level between the two institutions as activities and amounts involved were small compared to the overall volume of EC/FAO cooperation in the country.

# D.	RECOMMENDATIONS – GUIDANCE FOR THE FUTURE

General Recommendations

148.	Overall, the Review Team recommends the continuation of activities in the area of “food security information for action”, implemented through FAO, with the definition of a new programme, for the following reasons:

- Relevance: the Programme is relevant to EC development policy, to the FAO mandate, strategy and programmes, and to countries facing food security issues;

- Outcome and impacts: significant impacts will only be possible through the long-term continuity of the activities, and therefore it is important to build on the substantial fact-finding work that has already taken place in the first programme (an important investment), in addition to the strong willingness of local recipients.

149.	Based on all the above findings, the Review Team strongly believes that the outcomes and impacts of a next phase would significantly benefit from a real programme approach, rather than from the mere packaging of a number of separate, although loosely, connected projects.

Scope of the Recommendations

150.	Given the timeframe and the mandate of the Review, the recommendations below are not exhaustive and do not provide a detailed description of a new Programme. Based on the assessment of the current EC/FAO Programme and key lessons drawn, this section aims to give broad directions and principles on the basis of which a future Programme should be based. It also highlights more specific recommendations where the Review Team felt confident enough to do so.

151.	The recommendations below assume that the Programme will be formulated on the basis of commonly-accepted sound design principles, including in particular the definition of clear objectives, deliverables and measurable indicators of success/impact. Furthermore, it assumes that the formulation will follow a logical sequence, some of the key steps being summarised in Box 3:

Some key steps in the formulation of a Programme - Define the long-term context and goal within which any programme and its component will be placed: - define a conceptual framework - define the ultimate goal - Define a programme framework (i.e. for the duration of the EC-FAO agreement) with identification of general objectives. - Define the programme components, activities and approaches. Operational linkages between components’ activities must be identified together with the activities themselves: interfaces/links are as important as activities. - Define resources and allocation of resources based on the above. - Define rolling annual work-plan, adapted to the dynamism and evolution of the programme.

Programme Focus

152.	The Review Team suggests to formulating the new Programme around a “food security information for action” theme. A conceptual framework describing the information provision and uses/users chain is illustrated in the graph below.

153.	Taking into account the importance of the FIVIMS initiative in FAO and its overarching role with regard to food security information-related work, a Programme focusing on food security information should be coherent and in line with principles developed under the initiative.

154.	The overall objective of the Programme could take the form of “food security information systems adapted to local, regional and global usage with the capacity for flexible integration with other essential livelihoods data, for food security interventions, policies and programmes”.

155.	Within that context, the Programme should be centred on the following three pillars:

- Regional and national human capacity building in specific technical areas

- Provision of information for targeted usage and users at various levels

- Access to reference materials (norms and standards) and tools

156.	The rationale for giving priority to these three “pillars” relates to the following main concerns:

- keeping close to the ultimate beneficiaries (food-insecure populations)

- responding to the immediate needs of users, in particular those of the EC

- ensuring better and continuous linkages between the information and its usage and users

- complying with FAO’s mandate and using its added-values

- integration with the rest of FAO’s programme

- building synergies among the different Programme components made possible by the linkages between the immediate objectives (e.g. the provision of information can be a tool for capacity-building)

- taking into account what is realistically achievable given the volume of resources, the time-frame of the Programme and the receiving institutional structure at country level.

157.	In this regard, it should be noted that “institutional strengthening” (understood as the adaptation of institutions and their structures to improve their effectiveness and efficiency) is not mentioned as a core objective of the Programme, although, obviously human capacity building is part of it and will contribute to it. This acknowledges the limit of what is achievable within a Programme and the fact that full-fledged support to institutional strengthening is time and resource-consuming, highly contextual and thus, requires sustained country-level support that will be difficult to allocate within the resources and time-frame of the Programme.

Programme Components

158.	The Review Team is of the view that the present Programme’s components (“individual projects”) focusing on early warning and/or food security information should continue in a future Programme. However, the Review Team is not in a position to make specific proposals on their dimension within the whole Programme and the exact form under which these components should remain/evolve in the next Programme. In some project reviews (Annex 1), the Review Team was able to make specific recommendations.

159.	For reasons explained in the above-section on “ Methodology”, the Review Team believes that the Trade project should not be part of a future programme focusing on food security information. However, considering the development of a specific programme on “Trade and Development” by EC, and the FAO programmes of work in this domain, capacity building on multilateral agreements and trade in general should continue to be a high priority in the overall EC/FAO collaboration.

160.	Still in general terms, the approach towards the Programme formulation should be pragmatic and build components and activities on what has been attained during the previous phase, on what is available in general and what is achievable within the Programme timeframe.

161.	The identification of the detailed components of the Programme should be preceded by an assessment of priority uses and users. The Programme’s relevance and impact will be greater if, ultimately, information products (and thus all activities) respond to well identified uses and their users’ requirements. A clear identification of uses requires not only an explicit identification of the users/decision-makers but also an evaluation of the environment (including policy, strategy and programme environment) within which the information is produced. This will facilitate during the course of programme implementation the gathering of users’feedback to ensure improvement of the adequacy of information products.

162.	The Review Team suggests below some areas that deserve increased focus and/or should be further explored in relation to information needs and requirements of three major user groups of the Programme outputs: the countries, the EC and FAO.

163.	For the first category, it is undeniable, that proper identification of uses and users and information requirements are best defined at the country level. However, it is important to note the need for greater attention to the linkages between food security and poverty and the implications in terms of food security information and linkages of the programme activities with poverty alleviation programmes. The evaluation team believes that this issue is particularly relevant in CIS countries. Furthermore, advocacy work on the food security concept and its multi-sectoral and inter-institutional dimensions, as well as its implications on food security information systems, should still be given high importance.

164.	At the EC level, at least three areas of action have been identified as Programme uses: (i) contribution to the update of the list of priority countries of the food policy programme ; (ii) identification of needs at country / sub-country level for the provision of food aid, (iii) support to the operational implementation of the LRRD concept (e. g. identification of information priorities, etc.).

165.	At FAO, it is recognised that some of the components of the present Programme benefited or will benefit FAO staff eventually if objectives are met (e.g. GIEWS workstation and conceptual work carried out under the complex emergency project). It is felt that in formulating the new Programme, attention should be given to the possibility of establishing linkages (through normative activities) between the Programme and a number of initiatives and programmes of international dimension and for which FAO has a central monitoring role, among which: the monitoring of the WFS Goal, MDG relating to hunger and poverty and the right to food. Direct link with the FIVIMS initiative (using the FIVIMS umbrella as a channel for disseminating normative materials) should also be maintained and strengthened.

Programme Approach

- Normative/Operational Balance

166.	A future Programme should continue to build on FAO’s added value, namely the synergies between normative and operational work. However, the right balance should be set based on the considerations mentioned above and on the three Programme pillars. In particular, resources and relative costs should be carefully and explicitly assessed separately for operational actions on the one hand, and normative activities on the other. Particular attention should be given to the need to bring to full operational stage methods and principles conceived during the current phase.

- Capacity-building

167.	Efficiency gains could result from more regional focus for capacity building activities, including the organization of regional workshops, the use of regional networks and institutions (such as the CILSS and the SADC as relays for training at the national level (including training of trainers approach) and a better integration with information-related work of other organisations (e.g. with FIVIMS partners’institutions present and active at regional level).

168.	However, some capacity building will have to be carried out at national level. Whether it is done by regional trained trainers, or by the Programme itself, training at national level should focus on frequent on-the-job and follow-up training. In addition, priority should be given to an appropriate policy environment (food security is a recognized policy priority) with an adequate infrastructure (existence of concrete actions and projects at country level).

  - Tools, Materials and Methods

169.	Some centralization (e.g. repository) of resources and services (e.g. normative approaches, generic training material and ICT support), organized in a modular way could facilitate better exchange and mutual benefits among the Programme components and allow easy tailoring and customization. The place for such a centralization of normative materials could be the FIVIMS umbrella.

170.	For efficiency and visibility reasons, efforts for Internet pages should be concentrated at programme rather than project level. Moreover, all software applications under development should be consolidated into one single package/user interface (not only for early warning, but also for complex emergency management and structural information). This will permit to avoid duplications, to look for complementarities and homogeneity, and to reach a necessary critical mass for increased visibility and sustained development and maintenance. Ultimately, FAO should provide official recognition to those tools as the FAO standard to be used in-house and to be promoted outside.

  - Selection of Countries

171.	The Review Team had neither the mandate nor the time to acquire the information needed to formulate specific recommendations regarding geographic focus for activities at country level. The above-mentioned requirement for impact maximization should in principle lead to countries already identified in EC and/or priority lists for concentration of action, as well as those countries where building blocks have already been implemented. However, the Review Team thinks that the new Programme should not exclusively focuses on countries currently identified by the EC for its food aid and food security assistance programme. There should be room for the selection of countries not listed, providing there is a good justification from an FAO (or another) perspective. More specifically, the needs of countries subject to sudden political instability, large-scale natural disasters, or complex emergencies should be considered, especially since the occurrence of food insecurity and vulnerability, as well as information needs, under such circumstances are very high and require specific attention.

172.	It is believed that a regional approach would, in addition to efficiency gains, facilitate cross-fertilization among countries facing similar and common problems. Consequently, regional affinity should be an additional criterion for selecting countries.

173.	The Review Team recognises the difficulties in building/strengthening human capacity within a context generally characterised by weak institutions. In fact, one of the main lessons from the fivims projects is the weakness and instability of FIVIMS-related national institutions as one of the key causes of poorly performing national fivims in most pilot countries. Other criteria will have to be defined to select countries, depending on the specific objectives of  the Programme component(s). The Review Team suggests to adopt a pragmatic approach, taking into account again what is realistic to achieve within the timeframe and resources of a Programme. The Programme will be designed in such a way that human capacity buidling will have the greatest impact taking into account the institutional context. In general terms, the Review Team believes that another criterion which should carefully be considered is the existence of parallel institutional strengthening projects/programmes that are relevant to the human capacity building areas of the Programme.

  - Optimising the Impact

174.	A new Programme should include actions to connect with relevant and complementary external programmes/projects on food security (e.g. poverty alleviation programmes in the context of MDGs and, at national level, UNDAF/CCA and PRSP processes). Much value would be added by building on those opportunities and potential synergies. In particular, ensuring endorsement of the programme’s outputs by these Programmes would probably bring more opportunities, but more importantly would significantly increase the Programme impacts.

  - Adapting the duration

175.	Given the nature of the Programme, the Review Team believes that a rolling 5-year programme would be more appropriate, because sustainable in-country implementation of food security information systems takes time. This does not imply that the budget should be increased of the same magnitude.

176.	The Review Team recognised however that the duration of the rolling EC/FAO agreement may not easily be changed for various institutional reasons. It would therefore be strongly suggested that a new programme proposition would be built on a 2 x 3-year basis.

Programme Management

177.	In addition to administrative coordination, the management of the Programme requires continued technical oversight and coordination. The latter should be carried out in the technical division/service that has the most inter-sectoral approach to food security information. In this respect, and subject to careful examination of capacity, the Food Security and Agricultural Projects Analysis Service (ESAF) may be appropriate to carry out technical coordination functions of a food security information programme. The technical coordination tasks would involve among other things, coordination of Programme formulation (this is currently underway), the setting-up of mechanisms for communication and exchange (e.g. ad-hoc/across-projects working groups), the monitoring of progress, the coordination of activity planning (annual detailed programme), the identification of issues to be submitted to the steering committee and whenever it applies, the coordinated production of outputs leading to common outcomes.

178.	Because of the central role of FIVIMS on information-related work within FAO and the above-suggested repository role of FIVIMS secretariat, the Review Team would see advantages in FIVIMS and the Programme technical coordination being institutionally located together.

179.	The Review Team recommends that a steering committee be formed to assist in the continuous programme monitoring and directions. It should be composed of senior staff not involved in projects, but with a good understanding of activities. Its size should be sufficiently large to ensure a significant range of different perspectives on the Programme, and small enough to be operational and useful (typically 4-6 members). It should include 1-2 members from the EC (with one with a technical profile).

180.	For practical reasons, administrative and technical coordination should be located in the same unit. With regard to the budget holding, its current decentralized management is efficient because each project has a manageable budget. On the other hand, centralized budget holding would facilitate coordination in a straightforward manner. The Review Team does not have a strong view for one or the other option but the decision in this regard should be based on a proper assessment of capacity vis-à-vis the recognized heavy administrative requirements of such a function.

Programme/Components Location

181.	Because of the normative nature of a large part of the Programme and its approach building on FAO’s added value, the Programme should essentially remain at FAO Headquarters with support ensured and relays established with regional and sub-regional technical officers in particular for the capacity building component.

182.	It is believed that coherence, cooperation and linkages among the components could be further strengthened if components with strong similarities were managed under the same technical division. In the present Programme, this is the case of the fivims projects and the CIS project. Because of the long-standing experience and programmes of ESAF and its capacity in FAO Regional and Sub-Regional Offices, the latter seems better equipped to be responsible the projects/components that will have an important capacity building component. However, attention should be paid to the possible adverse impact that concentration of only one part of the various activities could have on the other activities that would remain scattered.

EC-FAO Collaboration

183.	The terms of collaboration between EC and FAO at Headquarters and at regional and country levels should be strengthened and explicitly defined, from the design to the implementation, and monitoring and evaluation.

184.	It would be mutually beneficial to develop regular technical exchanges in order to better identify specific information needs of the EC and partners (e.g. national authorities) and share experiences on normative aspects (indicators, etc.) for the various components of the food security policy. In this regard, the Review Team highly recommends direct communication links between the Programme staff and responsible technical staff at the EC. The Programme Coordinator, having substantive technical and adminsitrative roles, should retain overall responsibility for liaison with AIDCO F/5. Furthermore, the same direct links should also be facilitated with the EU delegation in the countries.

185.	In return, FAO could take full advantage of a number of activities developed by the EC, also through instruments other than the food security policy. This is for instance the case in particular of the GMES programme implemented as part of the EC space policy. EC Commissioner in charge of the development policy has recently expressed his interest for the reinforcement of  i.e. the “food security watch” component as part of the GMES action plan. A number of activities are already being developed, where links with the EC-FAO Programme on food security information for action could be reinforced.

Other Collaborations

186.	The Review Team believes that it is critical for operational activities as well as for normative development, to access high quality data and information in support to food security analysis. These data and information are typically produced by external (i.e. non FAO) institutions. Access to these data and information is often restricted (not in the public domain) and/or provided on commercial bases. Without such data and information, the production of relevant bulletins on food security situation is difficult if not impossible. This is a permanent need.

187.	It is thus important that the Programme specifically addresses this issue by establishing and implementing a proper strategy to establish long-term agreements with these institutions so as to ensure continued access to these inputs.  Such a strategy would, in addition, favour the development of customized input data for the Programme by these institutions.

Acronyms

ACP		African, Caribbean and Pacific Group of States

AIDCOF/5 		EuropeAid - Cooperation Office, Food Security Unit, European Commission

AMESD	 	African Monitoring of Environment for Sustainable Development

ARTEMIS		Advanced Real Time Environmental Monitoring Information System

CIS		Commonwealth of Independent States

COM		European Commission (in references from EC communications to the Council of Ministers and the European Parliament)

DG AIDCO 	EuropeAid - Cooperation Office, European Commission

DFID		Department for International Development (UK)

DG DEV	 	Development Directorate General, European Commission

DG RTD 		Research Directorate General, European Commission

EC 		European Commission

EW		Early Warning

FAO		Food and Agriculture Organization of the United Nations

FIVIMS		Food Insecurity and Vulnerability Information and Mapping System Initiative

fivims		A generic food insecurity and vulnerability information and mapping system or network of systems

FNS		Food and Nutrition Security

FS		Food Security

FSIS		Food Security Information Systems

FSP		Food Security Programme – EC

GaP		Guidelines and Procedures

GeoNetwork	FAO spatial data and information infrastructure

GIEWS		Global Information and Early Warning System (FAO programme)

GMES		Global Monitoring for Environment and Security

GTZ		German Technical Cooperation (Deutsche Gesellschaft für Technische Zusammenarbeit)

GVM		Global Vegetation Monitoring unit (JRC)

HBS		Household Budget Survey

ICT		Information and Communication Technology

IES		Institute for Environment and Sustainability (JRC)

IPR		Intellectual Property Right

IPSC		Institute for the Protection and Security of the Citizen (JRC)

JRC		Joint Research Centre (EC)

IMF		International Monetary Fund

IPR		Intellectual Property Right

LDC		Least Developed Countries

LIFDC		Low-income-food-deficit-countries

LRRD		Linking Relief, Rehabilitation and Development

MARS		Monitoring Agriculture with Remote Sensing unit (JRC)

MDG		Millennium Development Goal

MTR		Mid-Term Review

PAIA-REHAB	Disaster Prevention, Preparedness, Mitigation and Post-Disaster Relief and Rehabilitation (FAO)

PRSP 		Poverty Reduction Strategy Papers

RESAL		European Network for Food Security (Réseau Européen de Sécurité Alimentaire)

SADC		Southern African Development Commission

SPFS		Special Programme for Food Security (FAO)

TCP		Technical Cooperation Programme (FAO)

TEM		Terrestrial Ecosystem Monitoring action (JRC)

UNDAF		United Nations Development Assistance Framework

UNHCR		United Nations High Commissioner for Refugees

VAM		Vulnerability Analysis and Mapping Unit (WFP)

WB		World Bank

WFP		World Food Programme

WFS		World Food Summit

WHO		World Health Organization

WMO		World Meteorological Organization

Abbreviations used for Individual Projects

| Project Number Project Title | Abbreviations |
| --- | --- |
| GCP/INT/736/EC Training for ACP Countries on the Uruguay Round and Future Multilateral Trade Negotiations in Agriculture | Trade project |
| GCP/INT/740/EC Strengthening the Technical Capabilities of Global Information and Early Warning Systems Workstation | GIEWS project |
| GCP/INT/741/EC Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Least Developed Countries | fivims project |
| GCP/INT/742/EC Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Small Island States | fivims project |
| GCP/INT/758/EC EC/FAO Fund for Consultancy Services | Consultancy Fund project |
| GCP/INT/814/EC Intensified Monitoring of Food Security in CIS Low-Income Food Deficit Countries (Armenia, Azerbaijan, Georgia. Kyrgyzstan, Tajikistan) | CIS project |
| GCP/RAF/360/EC Improving Early Warning and Food Security Information in Countries Subject to Complex Emergencies | Complex Emergencies project |
| GCP/RAF/351/EC Capacity-Building Support to SADC Remote Sensing Unit for Early Warning for Food Security | SADC project |

Council Regulation (EC) No 1292/96 of 27 June 1996 on food aid policy and food aid management and special operations in support of food security.

The Terms of Reference are contained in Volume II – Annex II of the Report.

The quality, clarity and organisation of the documents provided (or not) to the Review Team varied greatly throughout the Programme.

The Angola case study, for instance, is a useful background document, reviewing existing information work in the country. However, the report is expected to feed discussion and debate outside the country itself.

The Trade project relates to the FAO Regular Programme entity: “ Commodity and Trade Policy Support to Developing Countries” (FAO code: 224A2)

The conceptual framework was recently used for the formulation of the FAO-Netherlands Partnership Programme – Food Security Component.

COM (2000) 212

Food security information system is understood here in a broad sense, covering various information functions including, among others, food security and vulnerability analysis, early warning, sectoral analysis, data and information management, advocacy, etc.

Regulation 1292/96

Ibid.

COM 2000/153

This is the case for instance of the African Observatory developed in the TEM action (JRC/IES/GVM unit), the Crop Monitoring for Food Security action (JRC/IPSC/MARS), the GEOLAND Integrated Project (DG RTD/GMES programme) and the AMESD project under identification by DG AIDCO.

Data and information providers exist at country as well as at transnational scale.  In this last case, it is well known that a number of UN agencies (i.e. WHO, WMO, UNHCR, WFP), within the framework of their mandate, ensure the collection in a structured manner of relevant information and include ad hoc services for that purpose. Other organizations have an operational mandate to collect and distribute data and information of relevance to the programme such as EUMETSAT, or the European Centre for Medium Range Weather Forecast (ECMWF).