EC/FAO MID-TERM REVIEW OF THE EC-FAO COOPERATION PROGRAMME 1999 TO SUPPORT FOOD SECURITY

VOLUME II:  ANNEXES

JULY 2003

TABLE OF CONTENT

ANNEX I	PROJECT REVIEWS

ANNEX II	TERMS OF REFERENCE

ANNEX III	BACKGROUND ON EC FOOD SECURITY POLICY AND RELATED MATTERS

ANNEX IV	ITINERARY

ANNEX V	LIST OF PERSONS MET

ANNEX I

PROJECT REVIEWS

| Project Number | Project Title |
| --- | --- |
| GCP/INT/736/EC | Training for ACP Countries on the Uruguay Round and Future Multilateral Trade Negotiations in Agriculture |
| GCP/INT/740/EC | Strengthening the Technical Capabilities of Global Information and Early Warning Systems Workstation |
| GCP/INT/741/EC | Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Less Developed Countries |
| GCP/INT/742/EC | Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Small Island States |
| GCP/INT/758/EC | FAO/EC Fund for Consultancy Services |
| GCP/INT/814/EC | Intensified Monitoring of Food Security in CIS Low-Income Food Deficit Countries (Armenia, Azerbaijan, Georgia. Kyrgystan, Tajikistan) |
| GCP/RAF/360/EC | Improving Early Warning and Food Security Information in Countries Subject to Complex Emergencies |
| GCP/RAF/351/EC | Capacity Building Support to SADC Remote Sensing Unit for Early Warning for Food Security |

PROJECT REVIEW

| Project Symbol GCP/INT/736(EC) | Title Training for ACP countries on the Uruguay Round and Future Multilateral Trade Negotiations on Agriculture |  |  |
| --- | --- | --- | --- |
| Operating Unit TCDX | Lead technical Unit TCAS | OED- date Sept. 2000 | NTE-date Dec. 2002 |

Methodological Note

This brief Project Review was prepared on the basis of documents related to the project, in particular on a comprehensive review of the Umbrella Programme (FAO) prepared during the summer 2001. FAO staff who coordinated the Programme and those who participated actively to the workshops were interviewed by the Review Team. During the country visits in Angola and Mozambique, the Review team met with a few trainees. However, the very limited number of trainees met (three in total) did not permit to make any generalisation.

Project Summary

The Plan of Action of the World Food Summit commits FAO to assist developing countries on trade issues and, in particular, "in preparing for multilateral trade negotiations including in agriculture, fisheries and forestry inter alia through studies, analysis and training." The Committee on Commodity Problems at its Sixty Second Session urged FAO to continue its programme of work in this area, in particular with the aim of ensuring that developing countries are well informed and equal partners in the new multilateral trade negotiations on agriculture. The Committee's recommendation in this regard was endorsed by the 30th FAO Conference.

Following these recommendations, FAO formulated an Umbrella Programme (“UP”) for Training on Uruguay Round and Future Negotiations in Agriculture which entailed the implementation of between14 and 19 sub-regional training courses in the various economic development and transition regions.  The programme was co-financed by FAO, various donor countries and the European Commission through the project GCP/INT/736/EC.  The main purpose of this project was to enhance the capability of the ACP countries to:  (i) understand the existing WTO Agreements that affect agriculture and food security; (ii) analyse new issues that are likely to arise in the negotiating process; (iii) take up and debate special issues of regional/sub regional concern. Approximately 330 agricultural policy makers and specialists from 70 ACP countries were planned to be trained, using a comprehensive resource manual on multilateral Trade Negotiations on Agriculture prepared by FAO staff for the workshops.

Assessment

Project Relevance

Developing and transition countries are in great need of fruitful incorporation to the ongoing globalisation process and this very much depends on their ability to take advantage of the existing MTA.  It also requires their active participation in the forthcoming negotiations, in order to ensure that the new and updated agreements take into account their particular structures and stages of development. The Umbrella Programme appears to be relevant to the needs of developing countries which are members of WTO or countries considering WTO accession as it addressed a technical assistance area of clearly high priority for developing and transition countries for which there are substantial gaps that affect their ability to participate in trade negotiations, take advantage of trade opportunities and thus, to cope with the new challenges of globally integrated markets.  The project approach further reinforced its relevance by using regional and sub-regional groupings to the extent possible, thus permitting addressing specific issues of common interest in each group. However, the relevance of training could have been further enhanced if the workshops had been more timely vis-à-vis the timetable of international trade agreements (the Lusaka workshop took place after the WTO Doha Ministerial Meeting).

FAO’s assistance programme to member countries on trade-related matters has a two-prong focus: (i) immediate, directly related, support to member countries for the multilateral negotiations; and (ii) capacity building in the area of institutions and human resources so as to enhance trade over the medium and long term.The project is relevant and complementary to several FAO regular programme work including that carried out under the Priority Area for Inter-disciplinary Action (PAIA) on Trade Priority Area for Interdisciplinary Action (PAIA). The project is very much in line with several regular programmes of the Organisation, including  programmes 2.2.4 dealing with the linkages between Agriculture, Food Security and Trade Policy;  3.1.2  Policy Assistance to Various Regions;  2.3.4.  Fisheries Policy;  2.4.3.  Forestry Policy and Institutions; 3.1.3 Legal Assistance to Member Nations; 2.2.1 Nutrition, Food Quality and Safety; 2.1 Agricultural Production and Support Systems.  The table attached to the present Review gives an overview of FAO’s technical expertise in relation to current WTO agreements of relevance to food, agriculture, fisheries and forestry and to areas covered by the UP.

Trade and development is one of the six priority areas of interventions defined by the EC communication on the European Community’s development policy (COM(2000) 212) adopted in April 2000.  The latter underlines the need for coherence of the various aspects of EC external policies. Developing countries need to be integrated into the world economy. On the other hand the EU is the first donor and the first trading partner of the EC priority countries. As such, it has to maximise its capacity to act within the various pillars of the international economic system, with a view to ensuring coherence between trade liberalisation (WTO), assistance and financial co-operation (Bretton Woods Institutions) and normalisation aiming at sustainable development (Environment, ILO, Codex Alimentarius, etc.). The Commission further promotes the gradual and harmonious integration of developing countries into the World economy. In this respect, the project is fully in line with EC cooperation objectives relating to trade.

Adequacy of the Project Design

The approach was designed to meet the UP’s objectives within the limit of the foreseeable resources, one-week standard sub-regional workshops were organized:  day 1 (plenary session) to introduce general agricultural trade and GATT/WTO topics; days 2, 3 and 4 to analyse the main agriculture-related UR agreements (AoA; SPS and TBT; TRIPS, in three parallel seminars); and day 5 to discuss cross-cutting issues, including the participants’ evaluation and recommendations. The approach was also cost-effective. The organisation of workshops on a sub-regional basis permitted to give particular attention on the food and agriculture policy issues specific to each region.

Project Linkages with other Projects of the Programme/ with other FAO Programmes

The project was part of a broader programme, the UP under which training was carried out through the same model. In fact, the project is quite distinct from the rest of the package programme on food security 1999 and its inclusion in the PP 1999 seems to be more the result of circumstances (additional external funding needed at that time to complete the UP) rather than its thematic linkages with the rest of the PP 1999.

The project has established effective linkages among eight different units dealing with: policy assistance and capacity assistance in policy (TCA);  trade negotiations and policies (ESCP), standards for food safety and quality (ESNS) in animal health (AGAH) in plants (AGPP);  trade issues in forestry  (FOP) and  fisheries (FIIU); intellectual property rights related to plant genetic resources (LEG).  In addition, activities were implemented with the direct support of TCA decentralised policy assistance branches in Africa, in the Caribbean and the Pacific. These linkages were concretised in the collaboration made during the (i) preparation of the Manual (though not strictly under the project as it was funded by RP funds) and (ii) the active participation of staff from these various divisions to the training workshops.

Project Implementation

The fact that the project was a contribution to an ongoing programme facilitated its smooth implementation and no major problem was encountered.

The project envisaged the organization of six workshops.  The last workshop (4th to be organised in Francophone Africa) did not take place because by the time the project became operational, the Government of France through the project GCP/INT/591(FRA) funded the regional workshop for French-speaking West African countries.

The project (and more generally, the Umbrella Programme) has been a model of excellent coordination within FAO, thanks to the dedicated and highly qualified staff involved in the Programme. The institutional framework utilized for the preparation and implementation –an existing interdivisional Task Force, to guide and supervise the Programme, under which a Training Core Group was entrusted of its overall management and backstopping– permitted an unusual combination of technical and administrative inputs originating in several FAO Headquarters and decentralized units.  The arrangement proved to be efficient for the delivery of integrated, complex training and seems to be a useful model for other training areas.  The direct cost of the workshops (total US$2.29 million, or US$2,000 per participant) is comparatively low if compared with other events of international level.

Project status

The Umbrella Training Programme terminated in July 2001.  During the period August 2001-June 2002, there have been no further training activities under this Programme.  There has been, however, the preparation of the second phase of the Umbrella Training Programme drawing from the recommendations made by participants and the review of the Programme conducted by FAO as well as the organisation of a distance-learning course (by Internet) and a workshop which will be held in Panama from 25 to 29 August 2003.

Project Results and Impacts

Under the project, five sub regional workshops on the Uruguay Round Follow-Up and Multilateral Trade Negotiations have been organized:

Kingston (Jamaica), 23-27 October 2000

Yaoundé (Cameroon), 4-8 December 2000

Addis Ababa (Ethiopia), from 15 to 19 January 2001;

Lusaka (Zambia), from 8 to 12 January 2001;

Nuku’alofa (Kingdom of Tonga), from 9 to 13 July 2001

A total of 312 government officials have been trained on WTO agreements and multilateral trade negotiations on agriculture. Technical reports for each of the workshops have been produced covering the technical issues discussed and the recommendations made by participants.

As mentioned above, a comprehensive review of the Umbrella Programme has been carried out by FAO. The evaluation and recommendations contained in the report mainly reflect the comments provided by the participants at the end of each workshop and several months later, in a post-workshop questionnaire. The following paragraph is extracted from the Review and summarises the views of participants.

“The overwhelming majority of the participants agreed that the major objectives of the Programme were successfully fulfilled; the different parts of the workshops were also positively evaluated with regard to the coverage of their various subjects, the clarity of the presentations and the usefulness of the training material.  In their March/April 2001 follow-up assessment, they indicated that most of them continue to be involved in MTN (close to 90%), the information received was pertinent and useful for their work (over 90%) and the collaborative work and partnership among institutions dealing with MTN in their countries increased as a consequence of the workshops.

Moreover, information available in FAO indicates that the Programme contributed to better informed and formulated proposals to the new WTO negotiations by many developing countries.  It should also be noted that, though the focus of the Programme was on WTO Agreements, national capacities were also enhanced on trade-related issues of importance on their own, inter alia, food safety and quality, protection of human, animal and plant life or health, and intellectual property rights.”

Interviews held with some participants in countries visited by the Review mission as well as with FAO staff/trainers from different divisions (FAO Headquarters) corroborate this overall positive assessment.

General conclusion

- The project made two major achievements:  (i) officials informed/trained on most critical agriculture trade issues resulting from WTO membership or WTO accession; (ii) widely disseminated background materials which were assembled in a Reference Manual on Multilateral Trade Negotiations on Agriculture praised by member governments and by other organizations like World Bank and WTO.

- The project approach was cost-effective in various ways including economies of scale and greater relevance linked to the sub-regional focus of the workshops, the use of a variety of expertise within FAO, and building-up on existing FAO relevant programmes.  The project benefited from the capacity building approaches, knowledge and information materials of the various FAO technical programmes that effectively participated to the UP.

- The regional dimension is a positive aspect of the programme. However, more homogeneous groups would permit a better identification of the common issues and dealing with them in a more detailed and practical way.

- It is well recognised that a workshop of five-day duration (and of such a general awareness nature) is only the starting point of a broader institution and capacity building strategy to ensure sustainability. Furthermore, an average of 5 participants from each country is a low number which would need to be increased to arrive at a critical mass of informed/trained officials at different levels.

- In addition to regional workshops, the Programme to be more effective should also include (i) national activities, preparation with national expertise of analytical work of direct interest to the country or group of countries, (ii) training of trainers in institutions dealing with trade policies; (iii) preparation of background/reference/training materials consolidating knowledge following the example of the Reference Manual on Multilateral Trade Negotiations on Agriculture.

List of abbreviations

AoA: Agreement on Agriculture

MTN: Multilateral Trade Negotiations

SPS: Sanitary and Phytosanitary Agreement

TBT: Technical Barriers to Trade Agreement

TRIPS: Trade-Related Intellectual Property Rights Agreements

UR agreement: Uruguay Round agreement

UP: Umbrella Programme

WTO: World Trade Organisation

Table 1: FAO areas of technical assistance related to relevant WTO Agreements

|  |  | WTO Agreements relating to food, agriculture, fisheries and forestry |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | AoA | SPS |  | TBT |  | TRIPS |
| FAO areas of technical expertise | Food | Implementation issues relating to the AoA and issues in the context of the multilateral trade negotiations, including impact assessments on trade, food security and rural development. | Risk analysis | Food safety (Codex) | Food quality and Labelling (Codex) | Trademarks Geographical indications Patents Genetically Modified Organisms |  |
|  | Agriculture – Crops |  |  | Plant health Environment, etc. | Eco-labelling Organic farming | Breeders’ rights Farmers’ rights Access to genetic resources Patent protection for agricultural chemical products |  |
|  | Agriculture – Animals |  |  | Animal health | Animal welfare, Traceability |  |  |
|  | Fisheries |  |  | Fish safety Codex | Fish quality and Eco-labelling Codex |  |  |
|  | Forestry |  |  | IPPC | Eco-labelling |  |  |
|  | National Legislation and International Instruments | Trade and environment law | Sanitary and phyto-sanitary law |  | Import and export legislation Customs law | “Sui Generis” Patents Geographical indications Breeders’ rights Farmers’ rights Access to Genetic Resources for Food and Agriculture; Genetically Modified Organisms |  |

PROJECT REVIEW

| Project Symbol # GCP/INT/740/EC | Title Strengthening the Technical Capabilities of Global Information and Early Warning Systems Workstation |  |  |
| --- | --- | --- | --- |
| Operating Unit ESCG | Lead technical Unit ESCG | OED- date July 2000 | NTE-date July 2003 |

Project Summary (from project document)

The project will further improve the information base and analytical capabilities available to GIEWS and other early warning units through improvements and updates to the GIEWS Workstation software and associated databases, and will provide users with access to the GIEWS Workstation information bases via the Internet on the World Wide Web. Expected outputs will be:

- Expanded GIEWS Workstation to include information for developed countries, other major foods, and newly available real-time information

- Access to external users in the field of food security and early warning to information held by GIEWS through WWW

- Analytical capabilities of the individual components of the GIEWS Workstation, and

- Continued dissemination of the GIEWS Workstation software and databases to other food security and early warning units.

Note: this project was not subject to a formal revision of its terms of reference

Assessment

Project Relevance

The project is fully relevant both from FAO and EC points of view.

At FAO, GIEWS is a well-established structure providing key information on per-country food production and availability situation at global scale. This information gathering, evaluating and disseminating service is central to the FAO institutional mandate.

Through the Council regulation EC/1292/96 the European Union has explicitly chosen to rely on existing information systems and to reinforce them (title III, art. 6: The Community may support existing national early-warning systems and help to strengthen existing international early-warning systems concerning the food situation in developing countries and, in exceptional and duly substantiated cases, it may operate such systems, in accordance with the procedure laid down in Article 27.)

The GIEWS is explicitly mentioned as part of one of the six EC horizontal axes of intervention in support to food security, under “support to crisis prevention systems” (EC annual report on implementation of EC external assistance, p 32).

Even before this regulation the development of a computer-assisted GIEWS working environment has been seen as a strategic field of cooperation between FAO and EC through projects GCP/INT/534/EEC started in 92, followed by GCP/INT/619/EC (started in 1996).

Although developed centrally the project is also relevant at country level: the analysis work produced at global scale by GIEWS is also carried out at national level by national early warning units. By using similar tools normalised procedures are progressively put in place and information exchange between national and trans-national levels are facilitated.

Adequacy of the Project Design

Project design is adequate in general terms.

Project design focuses on 4 key objectives: 1) expansion of GIEWS database, 2) expansion of access to data through web-based interface, 3) improvement of analytical capabilities of the GIEWS workstation, 4) dissemination of GIEWS sw and databases at various institutions involved in food security

The mission notes that:

- These four objectives give a complete framework of where the project should support the improvement of GIEWS, from extension of data input to improvement of analytical methods and tools to dissemination of information and tools

- Objective 1 complements the mandate of other FAO services, activities and projects (e. g. statistical databases are managed by FAO statistical service (FAOSTAT), the GIS service is responsible for digital reference maps, etc…). Project’s ToR involve not only interaction, but also sometimes specific actions that could have been carried out by these services under their normal mandate.

- Objective 2 partly complements other on-going actions at FAO (e. g. GEONETWORK)

- Objectives 2 and 3 require different skills (i. a. software development) than objectives 1 and 4

- Information technology is evolving very rapidly, at a much higher pace than project implementation cycle. It is thus appropriate to define objectives and output / deliverables, rather than to specify technical details of the implementation

- Project design does not prioritize the main objectives: they are thus implicitly on an equal footing. In actual fact the bulk of the effort in terms of manpower seems to have been dedicated to objectives 2 and 3

Project Linkages with other Projects of the Programme/ with other FAO Programmes

## With PP 99 Projects

In the project document there is little attention to this dimension: only FIVIMS is mentioned under activities 1.2.3.

Nevertheless the mission could observe elements of specific cooperation with the SADC RRSU (RAF/351).

Cooperation is also mentioned with FIVIMS (INT/741 & 742), complex emergencies (RAF/360) and CIS countries project (INT/814), in particular for what regards access to specific databases.

In turn these projects should benefit from the new developments of the GIEWS workstation and increased integration of their specific needs should be taken into consideration

## With other FAO programmes

The project contributes to FIVIMS & WFS follow up, and to FSAU in Somalia

It has well-established working relations with FAOSTAT, GEONETWORK, ARTEMIS, EIMS, AFRICOVER, ESCB, AgroMet group. The projects contribute to the PAIA on “Spatial Information Management and Decision Support Tools”. Further developments are expected with EMPRES.

## With EC services & Projects

Working contacts are established with two different units at DG JRC: MARS (Monitoring Agriculture with Remote Sensing): organisation of joint workshops and collaborative work on methodological development; and GVM (Global Vegetation Monitoring): access to remote sensing data from the VEGETATION instrument, incorporation of the Global Land Cover 2000 map.

Contacts have been established with DG AIDCO, they didn’t result so far in concrete collaboration actions

Project Implementation

The project officially started in January 2001 under the responsibility of the previous project leader who started concrete project activities only in July 2001. The current project leader started on the project in September 2001.  Thus the project had so far less than two years of real active life.

The project was implemented following the initial version of the project document without any formal revision. Nevertheless significant technical changes were made, in particular with respect to objective 2 “expand access to information on the Internet’s WWW”, in order 1) to overcome a number of difficulties met with the operation of the system developed under the previous projects, and 2) to take into account evolution in Information Technology.

This change will have far-reaching impacts on the day-to-day work of GIEWS analysts. Indeed, while the previous version was mainly conceived as a web interface to a number of databases assembled, for specialised analytical capacities, in particular in the field of remote sensing data, thanks to a separate module, WINDISP, the new GIEWS station under development will also serve as the analysis and reporting interface. Hence, the “original” GIEWS report being the digital one and not the paper one anymore. Thus, while until now the analyst used to prepare a report with paper and a pen, the new workstation aims at digital generation of information and reports and implements the necessary tools to do this.

This specific task has involved a complete software design and development, rather than just an update of the previous tools. Such a huge task couldn’t have been carried out in a shorter time frame than actually observed (i. e. less than 2 years as indicated above).

This had for sure an impact on the prioritisation of the various tasks under the 4 objectives and on task scheduling. Indeed the new GIEWS workstation is becoming available this Summer 2003, and thus tasks under objective 4 “dissemination of the GIEWS workstation software and databases” could of course be implemented only by relying so far on the previous tools, in particular WINDISP. In practical terms this means that the concrete task of workstation installation, debugging, training among users both in beneficiary countries and in international institutions (I. a. FAO and EC DG’s) will occur only after formal project’s end.

Besides this key action, the project continued supporting the updating, maintenance, distribution and training on the use of the WINDISP freeware, and ensured acquisition and formatting of data to be used by GIEWS (re. VEGETATION data, vector files of administrative boundaries, etc…)

Project status

At this stage all tasks foreseen by the project document have been addressed but not all have been completed. By end of June 2003 the new GIEWS workstation had not yet been put into operation. It is thus expected that the bulk of the effort for the coming months will focus on installation among the various user communities, software debugging, user training and ad-hoc database customisation.

Project Results and Impacts

The results expected from the terms of reference of the project document have been obtained, or will be achieved in the near future.

This project already has a major impact in particular at national and regional levels in many countries of Africa, but also in Latin America. In particular it was observed, during the evaluation mission, as well as recently during the mid-term evaluation mission of the FAO-SADC RRSU project (351/EC) or through other contacts, that the WINDISP freeware is broadly used everywhere, in particular by operational agrometeorologists, and in countries where agromet services do not benefit from specific external support.

The new workstation, by design, is expected to have a major impact on the working process of food security analysts. The question at this stage will be the reaction of the analysts: although they have been involved in the design of the system, no indication is available yet on their acceptance of the new way of working in practical terms. For the impact of this result to be significant, a number of steps have still to be passed through: 1) implementation of the workstation among the GIEWS analysts at FAO, 2) final debugging, 3) formal endorsement by FAO of the workstation as “the” official analysis environment, 4) distribution among the early warning analysts community at country level.  It can be anticipated that continued support will have to be provided for the years to come to support these steps and to take full advantage of the investment done through this phase.

General conclusion

- The overall implementation of the project is satisfactory, even if some key results will become available only after the nominal project end.

- Further investment will be needed to consolidate the results obtained during this phase and take benefit of the current investment

Recommendations for the future (in case of a new phase)

For the future attention should be paid to the following points:

- WINDISP is technically not anymore central to the new system. Nevertheless it has become a reference tool, and in many cases the only available one because it is freely distributed. Unless there is an equivalent alternative solution, attention should be paid at least to support continuation, and if possible to capacity expansion.

- Once the new station will be available and will be considered as sufficiently stabilized it should explicitly become the FAO reference system (as part of FAO’s normative role)

- Appropriate efforts have to be programmed to keep on consolidating the workstation to ever better responds to the specific needs of the GIEWS analysts and GIEWS as country based food security report generating service.

- The effort required in identifying and implementing the adaptations needed for use at country / regional level should be properly dimensioned: local working conditions are completely different to the FAO GIEWS environment.

- Appropriate expansions should be considered to accommodate needs and specific requirements of other users such as FIVIMS, ESAF, complex emergencies,… , in order to avoid duplication of tools and efforts

- Efforts to ensure integration of development efforts within FAO should be continued

- A particular attention should be given to acquisition and access to input data, in order to, as far as possible coordinate and take benefit of and complement actions which are on-going or planned, both within and outside FAO. This is the case in particular for space-based information. It should be noted that a number of actions are being developed at European level in that matter which are very relevant to the Workstation philosophy and structure, such as GMES (both ESA and EC/RTD & JRC components), AMESD geared towards African countries, PUMA – Meteosat transition in Africa (EDF-funded project), EUMETSAT ”Land” satellite application facility, ECMRWF, etc… In the same way the project has developed networks downstream with users, it should reinforce connections upstream (possibly in cooperation with other FAO services) to ensure continued access to high quality information at global scale as it was initiated with the access to the data of the VEGETATION instrument.

- A particular attention should be given to ensure smooth access to, and tailoring of, GIEWS information and tools by EC staff when and where required (i. e. both at headquarters and in delegations)

Addendum: Project results (provided by project leader)

Objective 1: Expand the GIEWS Workstation database to include information for developed countries, other major foods, and new real time information.  In addition, update and maintain the Workstation database with current year information for the reference databases and the near real-time monitoring databases.

Output 1.1

An expanded version of the GIEWS Workstation databases which will include information on developed countries, as well as information on other major foods. The improved database will include current and historical reference data on agriculture and commodity prices, major cropping zones, textual reports concerning agriculture, meteorological phenomena affecting agriculture, and information derived from crop and agro-meteorological models.

The databases of the workstation have been expanded and updated. Details are to be found in the progress reports.

Globally, administrative maps have been updated and amended up to the second level. It has to be stressed that the project (not only the current, but already since its predecessors) has been the main active source for keeping administrative boundary files up to date for the whole of FAO. Artemis copied regularly the whole GIEWS data sets to make them (more centrally) available to FAO. This focal distribution group should now be the GIS Unit, but still the project is the main source within FAO for updated data. The project therefore contributed substantially to the SALB project (UN Second Administrative Level Boundary project).

For more then 25 countries crop maps and sub-national crop statistics have been updated or created.

We would like to point out at this stage that the planned mandate for the project, as outlined in the project document, to globally expand and keep updated the workstation’s sub national level statistics database is a huge, nearly impossible, and very unsustainable task. The complete working time could be spent on this objective without even reaching complete or satisfactory results. Therefore the project tried to re-initialize a number of contacts and linkages. Another initiative linked to the purpose of keeping databases up to date, was the organizing of regional partnerships between countries, with FAO as active partner, in view of harmonizing and exchange of data and methodologies. The idea is that national ownership is crucial and sensitive but that technology (tools and methods) exchange and transfer can foster a network of people and institutes through which the partners, including FAO-GIEWS, get access to each others data and results. This creates a partnership which is at the basis for a more correct and sustainable access to data. The input from the project to the network is based on the provision (on research level) of satellite based information and transfer of the Workstation application when finished. For the realisation of these networks, the project organized jointly with the MARS Unit of the JRC, two regional workshops, one in the MERCOSUR area and one in the East Africa area. Participants are getting active to provide data and for the MERCOSUR area, a complete set of statistical data along with updated and detailed crop maps and calendars were put at the disposal of the project for incorporation in the workstation databases.

Needless to say that other relevant data organized by the other projects, such as the CIS and Complex Emergency project, is (or will be – in the new database structure) incorporated.

There is cooperation with the AFRICOVER project to extract useful layers out of their database to update the current workstation crop maps.

It is planned to use the JRC produced GLC to create similar extractions, albeit at a smaller scale, to reflect main areas of agricultural use.

Output 1.2

An expanded version of the existing GIEWS Workstation database to include new tabular and digital map databases and data available at higher sub-national administrative levels.

Products produced by the FAO AgroMet group, now still intermittently and with limited area coverage, are included in the ‘product’ databases. More regular products are expected in the future. An agreement has been reached with the FEWS unit at the Eros Data Centre to receive the archive on the global soil moisture and rainfall estimated data as produced by the Climate Prediction Centre. The purpose of getting these archives is not to put them completely at the disposal of the public (the CPC already provides that service) but to serve the early warning analyst, apart from the recent data required for their work, with the time series data extracted from this full data archive.

A complete new set of tabular data available in the renewed Workstation consists in fact of extracted statistics to provide time series analysis of all products offered. This means that statistics are extracted from satellite based imagery and products at province level, crop map level and the combination province/crop map. A graphing applet is used to offer these data to the user in a very interactive and easy way.

The introduction of higher sub-national level data was considered not appropriate in view of the already marginal use of province (first) level data due to the rigid access and the incompleteness of the datasets.

Another new database consists of the historic archive of all Food Emergency and Bad Crop Prospect tables as published in the Foodcrops and Shortages reports. The archive contains the country, data, category and main reasons of emergency. In the renewed Workstation, the analyst will be able to introduce the classification himself. This database now allows for historic analysis in order to better understand the various types of Food Emergency Crises. The project performed a first analysis which was presented to the Committee on World Food Security and which will be published in the SOFI 2003 document.

The renewed workstation will link directly into the ESCB basic commodities database to offer enhanced viewing and manipulation of these data.

Output 1.3

New real-time satellite images and derived products to be made available through the GIEWS Workstation and over the Internet's WWW.  This will included satellite data from the new SPOT-4 VEGETATION sensor  (global coverage and 1km resolution), as well as evaluation products from the new NOAA/GOES, TERRA and MODIS satellites.

The new SPOT VEGETATION data has been successfully introduced into the workstation. However, the access and evaluation will be more user-friendly in the renewed version.  A strong price reduction has been negotiated with the SPOT Steering Committee, providing some savings on the project’s budget.

It is considered inappropriate to introduce evaluation products in an operational system considering the already difficult threshold the user need to surpass for actually using the system (the renewed version however is designed to dramatically lower this threshold). MODIS data has been looked at and together with some staff of SDRN some test data has been processed, especially over Pakistan. It was concluded that these data have serious drawbacks for visual as well as for statistical analysis due to problems related to the compositing method and to the atmospheric and view angle interferences. Moreover it is estimated that at this stage the advantage of using 500m data over 1km is not outweighing the effort and cost of operational introduction of such data.

As specified above the project focused on getting processed products available, such as the CPC soil moisture products or post-processed SPOT NDVI products such as resulting from the work performed under contract  by the University of Cordoba, Argentina.

Output 1.4

An up-to-date GIEWS Workstation database/archive as a result of continuous updates and maintenance of the existing data in the GIEWS Workstation database including agricultural statistics and livestock, digital maps (with special emphasis on recent changes in sub-national boundaries), and an update of all metadata in the GIEWS Workstation database.

At the end of the project, the database on agricultural statistics will be updated for a number of key countries. Two regional networks will have been initiated to ensure such data can be obtained in the future. The project also put efforts in trying to convince the GIEWS Service to institutionalise the data collection part, which is up to now exclusively done by the project, by assigning a regular programme staff to this task. In fact the project promoted the proposal for establishing a “Data and Information Group” within the GIEWS Organigram to better deal with data issues.

Objective 2: Expand access to information held in the GIEWS Workstation database, as well as other GIEWS Information bases, to external users on the Internet's WWW.  Three levels of access should be maintained providing for the protection of copyright restricted and sensitive information.

Output 2.1

An expanded version of the current version of the GIEWS Workstation Internet module GeoWEB, which will provide Internet wide access to the GIEWS Workstation Information base.  Three levels of access to information will be implemented: public, partner and analyst.

This is fully taken care of within the development of the renewed Workstation (see below).

Objective 3: Continue with improvements in the analytical capabilities of the individual components of the GIEWS Workstation.

Output 3.1

An improved version of the GIEWS Workstation module WinDisp.

WINDISP has always been the most important module of the workstation. WINDISP is a desktop application dating from the late eighties which underwent several upgrades. The GEOWEB internet application used WINDISP to run the map-on-demand requests. This, however is superseded technology and caused a lot of problems. WINDISP is not to be used for the workstation any more. However, for detailed analysis of satellite based imagery, WINDISP is a phenomenal programme and is very applicable for use at country level. It was therefore decided to continue to improve the product, upgrading it to a full 32 bit application.  Some new functionality was introduced, such as simultaneous zooming, statistics extraction, colour table editing, etc. With three months of consultant work, an upgraded WINDISP version 5.2 was made available.

To further estimate what the actual use at country level is, before investing more effort for further improving WINDISP (even if this is highly desired by some key users) a user-survey has been launched by attaching a questionnaire to the ARTEMIS global user survey.  Based on the outcome it will be decided where to go from here for WINDISP. Another counterweight for the decision is that together with WFP, it was considered that a clustering programme such as ADAPIX would be extremely useful when adapted to some specific capacities to deal with food security parameters. WFP would be ready to participate in the funding. A cost estimate is underway.

Output 3.2

An improved version of the GIEWS Workstation Module CCBSx.

The CCBSx has been developed to ‘computerise’ a traditional economic balance calculation method. This application was added to the shell under the old desktop workstation (GeoFile). It is currently used by the country analysts in its ‘raw’ Excel format as GeoFile does not provide the proper tools. The application is so specific that improving it is nearly impossible. However the project looked at introducing the full CCBSx application within the internet based renewed version. The project looked at the data and product flow and organised actions to streamline these and to include the core CCBSx dataset in the Workstation database. This will help to reduce redundancy and errors occurring while having to copy numbers from one location into another. The Workstation will also offer visualisation of CCBSx data, not only for  a single country but at regional scale, in the form of interactive mapping and graphing of selected fields.

Output 3.3

An improved version of the GIEWS Workstation Internet module GeoWEB.

Output 3.4

An enhanced version of the digital mapping capabilities of the "maps on demand" system in GeoWEB.

These two outputs can be covered jointly.

The project analysed the use of the workstation web application, GEOWEB, by discussing with the GIEWS analysts how they valued the system operationally  for their work. It was found that although useful the system remained underused for a number of reasons. Fairly late within the project (related to staff issues), the decision was taken to take the opportunity to redesign the application with specific attention to the user while upgrading it to the newest technologies, rather than performing a simple transfer of the GEOWEB structure to a standard FAO database.

Building further on the vast experience of the earlier Workstation and GEOWEB, a summary of the main drivers and criteria which were considered for redesign is as follows:

- two way interaction: User-Use based;

analysis based accessibility

analytical tools integrated

drafting and internet posting tools integrated

scalable

- easy transportability of the application

packaged data extraction possibilities

- flexible

adaptable

expandable

By redesigning the system and optimizing the development work by using, adapting, and updating  existing modules, along with developing some specific modules according to the current technologies, the renewed system covers more than the anticipated improvements planned in the project document. Moreover, it is completely designed with three user groups in mind: (1) GIEWS analysts; (2) field mission consultants; (3) Country Early Warning Units (even other thematic use can be expected).

A more detailed discussion on the background and issues of the redesign can be found in a separate project report.

Objective 4: Continue to disseminate the GIEWS Workstation software and databases to other early warning units, and provide training on the GIEWS Internet GeoWEB system at various institutions involved with food security.

Output 4.1

A mechanism to enable the external use of the Workstation and its associated database by other early warning units, and to provide access to the GIEWS Workstation database via the Internet.

Also this output is completely incorporated and addressed by the current renewal of the workstation.

PROJECT REVIEW

| Project Symbol GCP/INT/741/EC GCP/INT/742/EC | Title Supporting FIVIMS Applications in Less Developed Countries and Small Island Developing States |  |  |
| --- | --- | --- | --- |
| Operating Unit ESDG | Lead technical Unit ESDG | OED- date 01/08/2000 | NTE-date 31/07/2003 |

Methodological Note:

This review is based on various documents related to the projects, including detailed progress reports, internal papers as well as interviews with Project staff. None of the countries visited by the Review team is covered by the projects 741 and 742 (called the “project” thereafter). It is therefore a “desk review”, using extensively the well-detailed auto-evaluation prepared by the Project staff for the Programme review. In view of this, it appeared important to the Review team to document substantially results achieved by the project. To this effect, a table presenting outputs produced vis-à-vis planned outputs and prepared by Project staff is attached to the present annex.

Project Summary

The two projects are similar in their objectives and outputs and aim at supporting FIVIMS pilot applications in a number of developing countries. The project 741 supports FIVIMS national programmes in four less developed countries: Haiti, Kenya, Burkina and Madagascar. The project 742 focuses on four small island developing states, Barbados, Cape Verde, Comoros and Samoa to which was added later on Fiji. The development objective of the project is to improve food security, in particular for the most food insecure and vulnerable population groups at country level, through (i) improvement in the quality of the food security information collected by national FIVIMS organisations and through (ii) enhanced use of that information to improve the performance of action programmes dealing with both transitory and chronic food insecurity. The project was designed around three immediate objectives as follows:

- Establish or improve the capabilities of national FIVIMS organisations in four larger ACP pilot countries to collect and disseminate critical food security information;

- Increase the capability of the IAWG FIVIMS Secretariat, in collaboration with the Inter-agency Working Group (IAWG) members and national governments, to provide enhanced project design, implementation, monitoring, and lessons-learned services to collaborating national FIVIMS and supporting regional organisations; and

- Provide specific lessons-learned from the pilot experience to assist the personnel of the EC RESAL and other IAWG FIVIMS partners (international and national) through a variety of training and internet dissemination channels.

As RESAL formally finished operations in August 2001, the latter objective and related outputs were modified to refer to all IAWG partners (and excluding RESAL), which is in keeping with the original objective.

The core of the project implementation strategy involved three phases to the work in each pilot country:

Phase 1: Diagnosis and Assessment

Phase 2: Pilot Production of Improved Information Products

Phase 3: Rolling Redesign of the National FIVIMS to Promote Sustainability

Assessment

Project Relevance

The project’s overall relevance lies in the magnitude of food insecurity and the needs to address food security issues on the basis of reliable and adequate information in most of the countries selected for pilot application. Kenya, Madagascar, Haiti are classified among the countries that have the highest proportion of undernourished (over 35% of the population), followed by Burkina Faso (26%). While similar figures are not available for Comoros and Cape Verde, the high proportion of the populations living under the poverty line gives an indication of  food security problems in these food import dependent economies. Among the selected countries, (western) Samoa and Barbados do not face food security problems to the same extent as other countries. In this respect, the relevance of project’s objective for these countries may likely be lower.

The project, through its tailor-country need approach, is expected to be relevant to country priorities. In each pilot country, activities have been first of all identified on the basis of country priorities with regard to improving information on food insecurity and vulnerability (FIV) and on-going programmes/ projects (looking for complementarity and synergy).

The general approach adopted at country level has been to identify one or more intervention areas (with corresponding set of activities), based on an assessment of: (i) availability and quality of relevant information in the country; (ii) strengths and weaknesses of existing information systems and of inter-institutional coordination and information sharing mechanisms, and (iii) information needs for decision-making and identification of information gaps to adequately meet information needs of target user groups.

Adequacy of the Project Design

Overall, the project was too ambitious in its objectives and outputs, given the inputs and the Programme timeframe. The projects combine support to country institutional capacity building, requiring extensive field work and technical and operational management as well as substantive normative work in support to the FIVIMS-IAWG secretariat and partners.

Human resources available under the projects and based at FAO HQ in Rome (basically 2 project staff) were too limited to fully support project activities implemented in 9 countries (originally 8 countries but resources “allocated” to Samoa were shared with Fiji, where levels of poverty and under-nutrition are significantly higher).  The pilot nature of the project combined with dispersion of the pilot countries over three continents contributed to high levels of pressure on the human resources available under the projects.

The project was conceived to test and refine methods, tools, software, etc. developed under the FIVIMS Initiative. But there has been very little material specifically developed with the FIVIMS stamp (one guidelines document, one software package (KIMS), FIVIMS Tools and Tips) and therefore very limited inputs from the FIVIMS Initiative has been available to feed the normative process being carried out under the project. Therefore, normative activities should have been given more priority (and allocated a larger share of resources) in project design (vs. operational activities).

The criteria for selecting countries for pilot application are not clearly stated in the project document. The relevance of the project vis-à-vis the needs at country level is expected to vary depending, among other things, on the importance of food insecurity and the expected political commitment to address food security issues. In fact, the selection of pilot countries turned out to be a very important factor since the major constraints to successful outcomes of pilot activities are found to be largely, external to the project’s design.  In addition to the importance of food insecurity issue, country selection should have taken into account two key criteria given the pilot nature of the project and its focus on strengthening national institutions, namely: (i) (demonstrated) political commitment for the production of better information and (ii) capacity of the national institutions designated as focal point (which to some extent reflects political commitment).

The contribution of national focal point institutions to projects' implementation, in particular the preparation of outputs, is also considered central to the project strategy to strengthen the existing capacity in a sustainable way. In most pilot countries, focal point institutions were too weak (in some countries, there is no capacity at all) to meaningfully play this role.

Pilot countries included countries with two working languages (English and French: work in five of the eight original pilot countries is carried out in French).  Most reports, normative and reference material prepared in the context of the project have been produced in English, adopted as the project working language, which makes it difficult to share with French-speaking partners (including EC partners in Brussels and in country delegations in French speaking countries where staff is not always fluent in English).

Project Cost-effectiveness

The project’s cost-effectiveness is negatively affected by the geographical dispersion of pilot countries as well as the absence of a regional focus preventing economies of scale in the conduct of backstopping missions, networking with regional and international partner organizations, etc.

Project Linkages with other Projects of the Programme/ with other FAO Programmes

With other FAO Programmes and Projects

The project is linked to varying degrees with various relevant programmes within FAO.  This ranges from highly complementary and participatory involvement with some direct assistance in implementing activities to more superficial involvement through ad hoc sharing of information.

The most active links are with the FNPP Project “Food Security Cluster” (FNPP/GLO/001/NET) funded by the Netherlands Government, a component of which (Integrating FIVIMS into the CCA/UNDAF Process”) is implemented by the FIVIMS Secretariat.  This project which seeks to integrate FIVIMS into the CCA/UNDAF and now PRSP processes includes Kenya and Bangladesh as pilot countries.  The three projects are run in a highly complementary fashion to maximise the leverage obtained from the total resources through sharing of experiences, consultants and key documents and a joint workplan.  The Asia FIVIMS project funded by the Japanese Government is another very active partner in FAO, with a high degree of interaction and support.

Various technical divisions have been involved with the implementation of the project.  This also reflects their involvement in the wider FIVIMS Initiative.  Involvement includes participation in taskforce meetings, development of software, technical support to project activities and sharing of relevant new methodologies and approaches. While valuable, these cross-departmental/divisional partnerships need to be further strengthened to explicitly recognise this activity as a core function of all groups.

With the other projects of the Programme:

There is regular collaboration and frequent exchanges with other projects staff of the Programme regarding the methodologies, approaches and tools being used or developed in the context of the projects. However, this collaboration is taking place on an informal and ad hoc basis, depending on good will and personal interest.

Some collaboration, although limited, took place with project 814 (CIS Countries) with the participation of the project staff in task force meetings.

Conversely, staff from other projects participate in task force meetings (involving also staff from relevant FAO divisions), organized to review progress and discuss methodological and implementation issues in pilot countries. Collaboration also takes place through the sharing of training material (material used for training in SADC and CIS countries), outputs (Briefing Note for policy-makers in Madagascar, Food Security Bulletins in Georgia), lessons, findings, etc., especially again with Project 814 and 360;

While there is potential for more complementarity and synergy with other EC-supported projects, (in particular Projects 360 and 814), the collaboration remained insufficient. The absence of a clear definition of the areas of collaboration at Programme level at the design stage as well as a well-defined mechanism to do so and time and resource constraints faced by project staff prevent full exploitation of these complementarity and synergies.

Project Implementation

The Project became fully operational in January 2001 when the project staff (Country support officer and documentation officer) were recruited. The overall implementation of the project has been good considering the complexity of the project operational management with nine countries to support and monitor on a day-to-day basis in addition to the technical management and tasks to be carried out. There has been a considerable amount of expertise (project staff and consultants) in each pilot country. However, there have been some delays in the delivery of outputs and progress towards objectives is expected to be slow.

The implementation of normative activities and the production of normative outputs are slower that initially envisaged. The Project approach (lessons learned from country experience) itself implies a sequential implementation to a certain extent from country application to lessons learning. Nevertheless, the normative component of the project has suffered from the overwhelming burden of the operational management of country work.

A number of factors that hamper Project implementation deserve to be mentioned:

- The lack of a minimal and stable capacity of national institutions appears to be the overwhelming constraint to project implementation.   The poor capacity of national agencies prevents FIVIMS focal points from effectively carrying out their coordination and monitoring duties. Furthermore, national FIVIMS focal points are often ineffective because they don't have a clear mandate, nor a mandate that is recognised and supported by their superiors. They are thus not in a position to coordinate activities within their own institution, much less even among institutions. The preparation of guidelines for countries regarding the FIVIMS focal points is an attempt made by the Project to address such an issue.

- Weak institutional capacity also limits the types of FIVIMS activities that can be implemented, as well as the speed at which implementation can porceed. This constraint could have been partially addressed through a two pronged regional and national capacity building effort. But the fact that pilot countries were not grouped by region prevented the formation of significant partnerships with regional organizations and capacity building efforts were exclusively focused on national institutions.  This prevented any real support from, and strengthening of, existing institutional capacity at regional level to help build capacity at national level e.g. through development of a training capacity at regional level.

- In such a context, keeping in line with FIVIMS priority to institutional capacity building appears to be a real endeavour and requires much more sustained support and resources than the projects can provide.

- The lack of FAO implementing capacity is a major constraint to provide adequate support to the 9 pilot countries and carry out normative activities: In most pilot countries, activities are directly implemented by the FIVIMS Secretariat in Rome.  Assistance from national and regional/sub-regional FAO offices is usually limited to basic logistical support during missions, as the FIVIMS Secretariat has no outposted officers.  The assistance provided by FAO in-country representations tends to be also limited, largely because of their own limited capacity to provide such assistance. It may also reflect unclear understanding of FIVIMS initiative or low national priority afforded the fivims activities.

- Partnerships at country level is insufficient, reflecting a more general lack of commitments of FIVIMS partners. Support from FIVIMS IAWG Member Institutions at country level is limited to participation in meeting and informal consultation (on a voluntary basis) but there has been no real buy-in into the project. It must be recognised that the FIVIMS Initiative is still relatively unknown amongst national and regional level offices of the IAWG partner institutions.

- As mentioned above, little material from FIVIMS available to support country work added to the tasks to be performed by the project staff.

- The project was designed (and inputs planned accordingly) in support of RESAL activities at country level and in turn, RESAL structures at country level were expected to provide support and follow-up to country-level activities. Joint project/RESAL missions were planned. However, RESAL was dismantled during summer 2001, a few months after the project became operational, leaving the project with a resource gap and adding further work to already stretched human resources.

Project Results

Considering the ambitious project design, the limited human and financial resources and the weak support provided to the project, considerable achievements have been made under the project within the time frame.

A detailed list of  project outputs together with their uses and a short assessment is given in appendix.

Regarding Objective 1 (Strengthening the capacity of national institutions), the outputs are country-specific and, to the extent feasible, produced by national focal point institutions (in collaboration with national and international partner institutions) with support from the FIVIMS Secretariat Staff (complemented by national and international consultants’ expertise) in line with the principles defined in the “Guidelines to national FIVIMS” (see FIVIMS Guidelines).  The degree of involvement of national institutions varies from country to country, depending on the existing institutional capacity (from almost nil in Comoros to maximal in Cape Verde and Haiti). Best results, in terms of capacity building (but with sometimes important trade-offs regarding the quality of the outputs), are expected in countries where the process is handled by national institutions who retain ownership for the outputs.

Regarding Output 1.1. (Diagnostic and Assessment of national information systems related to food insecurity and vulnerability within a broader context of poverty reduction and sustainable development). Diagnostic and assessment work has been carried out in all countries (except Barbados) as a start up activity leading to the identification of priorities to improve information in the country and project activities. The work has been done with more or less depth, depending on country specific circumstances, interest and priority attached to this type of work bystakeholders. In some countries, there was a full assessment with a more formal document while in others, the findings are contained in a number of trip and consultants’ reports and information products.

The diagnostic and assessment work led to the identification of priorities to improve national and sub-national information systems and promote a more effective utilization of information, based on (in line with the recommendations included in FIVIMS Guidelines) the analysis of the existing situation in regard to FIV information, internal strengths and weaknesses and potential external opportunities and threats. It includes an inventory and evaluation of data available and information systems, a user-needs assessment, an analysis of existing inter-sectoral and inter-institutional coordinating mechanisms.The depth of diagnostic work was very much dependent on pre-existing work. In some countries, RESAL had carried out a full diagnosis of food security systems and there was therefore no need of a new full assessment.

The diagnostic and assessment work proved to be an excellent entry point activity in most countries and raised much more interest than expected with important benefits in terms of collaboration and coordination at country level (lack of coordination is probably the main problem at country level, creating dispersion, confusion and non-rational use of resources). The output was used by national institutions, partner organizations and decision-makers as a reference document to coordinate with each other and to decide on strategic priorities and allocation of resources. This type of activities could become a major activity under the FIVIMS Initiative, fitting very well with the FIVIMS mandate (promotion of collaboration and coordination and consensus building on best practices). A guidelines document is being prepared for national multidisciplinary teams (Guidelines to conduct an assessment of a national fivims leading to the definition of a strategy and operational workplan) to take advantage of the lessons learned in the pilot countries (regarding both results and process).

Regarding Output 1.2. (Improved information products):  considerable emphasis has been given to the production of information products, as a way of building a dialogue with target user groups and supporting/ encouraging the use of information for improved decisions leading to the reduction of FIV. The nature of these improved or new information products has ranged widely. Some are one-time food security reports, others are periodic reports.  The main value added from the project is usually in terms of analytic content, in particular multi-sectoral integration (most products are based on secondary data/ information), also some products include newly collected information with the support of the project in Kenya and Cape Verde.

Regarding Output 1.3. (Redesign of information systems).  In some countries, the design or redesign of national information systems is a main output per se (Burkina Faso, Cape Verde, Samoa, Fiji) while in others recommendations for changes from a technical or institutional perspectives are included in other outputs (for instance in the Bilan de l’insécurité alimentaire in Haiti).

Objective 2 (Strengthening the capacity of FIVIMS Secretariat). A number of outputs are associated with the production of methodological guidance and training materials (with normative contents) which are expected to reinforce the capacity of the Secretariat to provide support to national and international partners. These outputs are crucial for the projects and the FIVIMS Initiative as well, with intended benefits beyond project life for countries not directly targeted by the projects. First lessons are now being drawn from the country experiences and various draft documents are now available on a number of issues.

Objective 3 (Sharing of lessons-learned with IAWG FIVIMS partners): Progress, findings and lessons from country experiences have been continuously shared with national and international partners through the dissemination of mission reports and technical reports, participation in meetings and workshops inside and outside FAO and the preparation of briefs, newsletters and other documents as appropriate. In general, there was a lot of interest expressed by national and international partners in countries in particular for the FIVIMS framewor (the latter is usually found very relevant to identify problems and solutions to improve fivims), the results of the diagnosis work and the activities carried out in other countries. However, there was no real buy-in for several reasons including the lack of incentives for collaboration and coordination from top management of partner institutions, which is essential because coordination is time consuming and requires trade-offs.

In addition, the FIVIMS Website is now fully operational and offers improved opportunities to inform and provide national and international partners with a wide access to an enormous amount of reference documents.

Expected Impacts and Prospects for Sustainability

In pilot countries where focal point institutions have a minimal and stable capacity, some activities initiated under the projects that are expected to be continued beyond the life of the current project phase include: in Haiti (preparation of annual and quarterly Food Security Reports, these activities are now part of a new dissemination strategy of the focal point unit established following the priorities identified with project support with backing from EU), in Cape Verde (collection of information within the context of the decentralized information system, publication of the results in the monthly publication Flash Info), in Kenya (use of HFEA for food security reporting in semi-arid districts).  In other countries, very limited activities are expected to be pursued without external support due to the lack of a minimal capacity (see last progress report for details) but the project outputs are expected to have an impact on decision-making (e.g. Barbados, Comoros, Samoa).

The lessons drawn from the pilot country experiences and guidance and training material with a normative content are expected to be useful to the pilot countries, other developing countries interested in improving their food insecurity and vulnerability information and development partners (including IAWG partners) providing support to national institutions. The projects have also contributed to strengthen the FIVIMS Secretariat’s capacity to provide relevant support to national fivims.

The projects are also expected to have a lasting impact on national institutions and associated partners in terms of changing attitudes in areas such as information sharing, networking, cross-sectoral analyses, regular dissemination of information etc. but this the extent to which this happens is difficult to measure.  The institutionalisation of FIVIMS concepts into national strategies and approaches in some pilot countries (Kenya, Samoa, Cape Verde and Haiti) should hopefully contribute to longer term political support for similar activities.

General conclusion

- The projects’ key objective (improve the information available for  decisionmaking) responds to a real need in many countries with high prevalence of food insecurity and vulnerability. Project efforts to assist with ascertaining information needs of decision makers and development stakeholders contribute to prioritising the information that is collected, analysed and disseminated.

- The approach adopted by the project at country level is valid to improve national fivims (although requires adjustments to improve its impact based on lessons learned), in line with FIVIMS philosophy and principles in countries where focal point institutions have a capacity (even if very limited) to contribute to project implementation, with positive results in terms of strengthening institutional capacity, ensuring national ownership of outputs, improving collaboration and coordination of partners and networking, and therefore an expected positive impact beyond project time horizon.

- The project’s implementation is slower than expected due to many factors, among the most important ones being, the weak national capacity and the lack and/or insufficient support from all sides. The project ended up working pretty much on its own: limited support from FAO (internal HQs), from FAO regional/sub-regional/national offices, from the FIVIMS (no materials), from RESAL (which disappeared, though the project built on the work already carried out by RESAL in some countries.), limited support (if any?) from FIVIMS partners at country level.

- The project needs to find the right balance in its two objectives: (i) Operational objective  (country level): Improve capacity of national/sub-national institutions in 9 pilot countries to produce & use better information to reduce food insecurity and vulnerability (FIV) and (ii) Normative objective: Develop reference and training materials (methodological guidelines, discussion papers, best practice examples) based on lessons learned from country experiences

- Despite all the difficulties and complexities of project’s implementation, the project achieved a great deal in the timeframe, not only in terms of output but also (awareness building, institutional building) processes that it generated. However, most of the latter will need further consolidation. No significant improvements can realistically be expected by the end of the project in terms of achieving sufficient capacity to ensure sustainability of project activities being given the projects’ short time-frame and limited resources.

Main lessons learned:

- A minimal and stable institutional capacity is essential to carry out pilot activities in a way which ensures a lasting impact in terms of improved information for decision-making.

- Institutional capacity building at country level requires intensive and continuous follow-up in-country that can not be carried out by punctual visits of international consultants.

- Selection of countries appears determinant in: (i) ensuring greater cost-effectiveness through for instance regional groupings (ii) relevance of the project (iii) more effective lessons-learning process. (Geographical dispersion of pilot countries prevents benefits expected from regional grouping in terms of training, capacity building, backstopping, networking, etc.)

- Essential to tailor project activities to country priorities but risk of dispersion of efforts and limited impact of project but need of a tradeoff between "a la carte" support and standardized activities because of risk of dispersion.

- FIVIMS-specific Reference material (guidelines, examples, discussion papers) is key to the provision of efficient support

- Lessons learning, best practices based on field experience are time and resource consuming that need to be carefully planned.

PROJECT REVIEW

| Project Symbol GCP/INT/758/EC | Title FAO/EC Fund for Consultancy Services |  |  |
| --- | --- | --- | --- |
| Operating Unit Variable according to “baby project” | Lead technical Unit ESDP | OED- date 17/07/2000 | NTE-date 17/07/2003 |

Project Summary (from Project Document)

The provision for consultancy services in support of food security programmes and activities financed under the food security/food aid budget line will be in specific fields, such as:

- pest control

- integrated pest management

- post-harvest losses

- seed development

- soil fertility and productivity

- animal health and disease control

- rural financial markets

The total amount for this framework contract is EURO 2,380,000.  An annual amount will be earmarked for this exercise. The consultancy services will include missions for such different purposes as technical advice, evaluation, monitoring, sector studies.  The costs to be covered under this framework contract refer to salaries and emoluments, travel daily subsistence allowances, equipment, insurance as described in the tables in annexes IV, V and VI.

Note: the specifications of the project document were later on completed by a document called “Guidelines and Procedures” (GaP) whose content was agreed by EC and FAO. This in particular defines the limitations in using the facility: i. a.  it excludes equipment and defines a maximum envelope by consultancy of € 100,000. The GaP also defines the procedure for implementing the consultancy services, called “baby projects” in FAO jargon.

Assessment

Preliminary remark

The evaluation mission was not in a position to review in a systematic manner each consultancy work carried out under this project. In total the mission had the opportunity to access partial information for a total of 4 out of 19 on-going or completed consultancies. Focus was thus set on 1) the adequacy of the procedure put in place, 2) the perceived usefulness of the consultancy work.

Project Relevance

The principle of this project is to provide a facility whereby limited support actions can be put in place in a more flexible manner from the implementation point of view than what happens for a full-scale project, in particular for what regards the approval process.

Discussions with field staff both from FAO and EC have confirmed this view by providing concrete examples.

Adequacy of the Project Design

The Review Team recognises its limited knowledge regarding EC financial regulations. In view of the current developments put forward by investigations at Eurostat, and given some apparent similarities between the practices under examination there and this project, i.e. the principle of creating a financial reserve lodged under an umbrella contract, the principle itself of this project might be questionable. The issue here is not the way the fund is managed by FAO according to their standard financial rules and with their own auditing procedures, but whether the principle itself of an open consultancy fund provided by EC to a third party is consistent with EC financial regulations.

The project document was not sufficiently detailed to allow direct implementation of this project. FAO thus drafted a document entitled “guidelines and procedures” that was submitted for approval to EC services. This process took quite some time, so that the first date of approval of a consultancy service is end of February 2001. The GaP was found to be an appropriate tool, although for sure some refinements should be included based on the experience gained.

Project Linkages with other Projects of the Programme/ with other FAO Programmes

The linkage of this project with other FAO and EC projects and activities is not explicitly mentioned as a selection criterion. From what could be observed from the 4 case studies, linkages with on-going or future EC and FAO projects were always evident. In Angola and Mozambique, the facility was used to obtain consultant support in the framework of projects financed by EC on the food security budget line and for which FAO provides the technical assistance.

Project Implementation

A large number of comments have been collected about the implementation of this project. Moreover a number of specific observations have been made by the evaluation panel.

On the “guidelines and procedures”

The purpose of the facility is rather broad as well as the user base and the candidate countries. On the other hand budget is limited. Although the GaP was circulated among FAO HQ departments and representations at regional and country level, as well as in EC delegations, its existence is apparently not known by all potential users.

The Gap provides a list of EC prioritized countries. From regulation 1292/96 it is understood that the list evolves with time. For transparency and coordination reasons, it would thus be useful for EC to provide updates of the list as well as the rationale behind insertion or removal of specific countries.

Regarding self evaluation, it is correct to ask the applicant to provide argumentation. However the grading system is of dubious usefulness, and can be self-promotion rather than self evaluation. It is up to EC and FAO evaluators to verify and where justified to confirm project’s compliance with each criterion.

It is noted that the compliance matrix does not include all the criteria mentioned in the text of the GaP document (e. g. p. 3: limitations on use of the facility, “the facility may not be used…”). Moreover there are indications that in some cases exceptions to the agreed rules are negotiated among the parties.

On the consultancy implementation

The comments collected among interested persons can be summed up as follows: “it is an interesting tool that provides real services, but the administrative process is too slow”.

On the positive side of the consultancy fund system, EC staff members mentioned the possibility to hire highly qualified experts with know-how specifically attuned to the consultancy needs, which seems to be a problem with the EC framework contract system, an internal EC procedure whereby one or several companies are selected and contracted to provide equipment and/or services on a case-by-case basis through a simplified administrative procedure.

FAO staff members indicate that no equivalent administrative and financial tool is available in their institution to carry out on-demand consultancy services. As a result, positive feedback was received from EC, FAO as well as from senior staff of national administrations for the already completed consultancy activities.

On the negative side, the procedure is quite complex. It significantly slows down the start of technical activities as well as the final administrative closure of each consultancy contract. It should be noted that when the mid-term review started, only 2 projects had been completed to the last step of the process.  As mentioned later on under “project status” the situation has slightly improved at the time of report writing.

Each proposal must be approved by EC (either headquarters or local delegation), FAO (either headquarters or local representation), and national authorities. When the principle of the “baby project” has been approved, it can take up to one year before the consultant can start working.

Administrative procedures to implement the “baby projects” follow FAO standard operating procedures for all technical assistance projects implemented by the Organization. These procedures are intended to ensure the highest quality of technical support and backstopping (and hence technical quality and relevance of outputs produced) while maintaining efficient and effective financial management and control as well as reporting to parties concerned. (The technical unit designated to backstop a mission is responsible for clearing the final reports - not the FAO budget holder, who is not competent to make such technical judgements. The budget holder is responsible for ensuring that all parties involved perform their specific tasks in a responsible and timely manner.)

In application of title V of the GaP, under title “processing and approval of requests”, “FAO budget holder forwards to EC headquarters (AIDCO/F5) at least three CVs for each expert post, and EC will make an assessment that will be communicated to FAO”. This specific point is seen by FAO as an additional complexity that fails to recognise FAO technical competence and rigorous internal selection procedure.

On the project management

The GAP document agreed upon by EC and FAO requires the intervention of a large number of stakeholders in the administrative process before and after the execution of the technical tasks. The budget holder of the consultancy project at FAO has a clear understanding of the whole procedure, as he drafted personally the GaP, but the time he can personally dedicate to the task is quite limited. As a result, the management started improving when FAO decided to dedicate a part-time staff to the administrative management of the project. This was not foreseen at the time of project formulation, but is for sure the only way to ensure smooth implementation. Indeed, the mission noted that not many people among EC and FAO staff have a clear understanding of all the various steps through which the consultancy request has to pass through. It is thus important to strengthen the one-stop shopping approach already in place.

Project status

So far, 19 projects have been approved for a total figure of US$ 1 514 430, out of a budget line of US$ 2 458 678.

The first date of approval is 26.02.2001. It should be noted that this corresponds to the date when the selection process of the consultant could start.

Nine projects are comprised in the range US$ 90 000 – US$ 100 000, i.e. close to the maximum allowed by the GaP, while only 3 projects are smaller than US$ 50 000. Among the 19 on-going projects, only 5 have an end of consultancy work before 1st Jan. 2003.

In terms of geographic distribution, 11 are in Africa, 4 in Latin America, 3 in the Near East and 1 in CIS countries. All fit in the EC food security list of priority as well as in the FAO country membership.

Twenty additional project proposals have been rejected. Fourteen other proposals for a total budget in the order of 1 280 000 US$ are waiting for a decision, while available budget is in the order of US$ 700 000. On 10 July, a priority list was given to the evaluation team: 4 projects were given priority A with hard commitment planned before end of 2003, and 4 more are planned for approval in 2004. These 8 projects are worth about US$ 696000 in total. It should be noted that among the remaining proposals a number of them are above the agreed threshold of US$ 100 000, and thus should have been rejected on this criterion.

Project Results and Impacts

Results

The evaluation team found it almost impossible to assess and synthesise in a sensible manner the results of this project, for a number reasons: 1) the number of consultancies is very large and detailed factual information could be collected during the evaluation mission for only 4 of them 2) there is most often no link at all between the various consultancies, thus there is no way to build a technical synthesis of the work carried out, 3) the evaluation team was not given a chance to consult all the available reports at the time of the mission. It had thus access only to fragmentary information.

Impact

The mission tried as much as possible to assess the impact of the consultancies that were analysed as case studies. In these specific cases the impact was judged positively to very positively by the interviewed persons. However, it could be noted in Angola that the lack of final clearance had a negative impact on the use of the results because they were not seen as an official FAO input.

General conclusion

At the time of evaluation about 2/3 of the budget have been committed.  By mid July 2003, 5 consultancies have reached their final stage and draft reports of two more projects had been received.

From the technical point of view the facility provided by the project is very much appreciated by EC, FAO as well as beneficiary countries

From the administrative point of view the system is best characterised by the adjective “slowness”. Situation is improving since a part-time FAO staff was allocated to project management.

Recommendations

If a consultancy fund facility is to be included in a new programme, then it is recommended that AIDCO formally receives confirmation from EC ad-hoc services that the financial procedure of this activity is compliant with EC standard financial regulations and practices.

In case of renewal of the project Guidelines and Procedures document should be reviewed jointly by FAO and AIDCO to take into account the observations mentioned earlier in the text, as well as the experience gained through actual project implementation. Particular attention should be given to the timeliness of procedures. Reference timing could be specified for each step as a guideline. Where acceptable a priori by both parties a procedure of implicit approval could be set up: “if no answer is received from the partner within a given timeframe, then the proposal / request of the other partner is considered to be approved”.

EC should provide FAO with updates of priority countries whenever this list is updated.

Regarding the selection of candidates, insofar as FAO has got the technical responsibility of project implementation, expert technical qualification should be assessed only by FAO. On the other hand it can occur that, for various reasons, some candidates are not welcome on EC-funded projects. EC staff should thus keep a right of veto on the list submitted by FAO.  Alternatively, it could be envisaged that CVs are jointly assessed at country level by staff of EC delegation and FAO representation during a joint meeting.

Project administrative management requires adequate staff allocation. It is thus recommended that, in case of continuation of the consultancy fund in a new phase, FAO continue dedicating adequate staff time of one person to ensure practical coordination and administrative management of the baby projects.

Appendix: status of project implementation (provided by FAO)

## PROJECT REVIEW

| Project Symbol GCPS/INT/814/EC (formely GCPS/RER/012/EC) | Title Intensified Monitoring of Food Security in CIS Low-Income Food Deficit Countries (Armenia, Azerbaijan, Georgia. Kyrgyzstan, Tajikistan) |  |  |
| --- | --- | --- | --- |
| Operating Unit # ESAF | Lead technical Unit # ESAF | OED- date 19.7.2000 | NTE-date 18.7.2004 |

As indicated in the terms of reference of this Mid-Term Review of the EC/FAO Package Programme on Food Security 1999, the review team briefly visited Kyrgyzstan and Armenia.

Project Summary

The initial project aimed at strengthening the capacity of Armenia, Azerbaijan, Georgia, Kyrgyzstan and Tajikistan in the collection and analysis of information on food security situation to provide a better base for the FAO Global Information and Early Warning System (GIEWS) and the Commonwealth of Independent States (CIS) to monitor and improve food security, and minimise the impact of emergencies in these countries.

At the request of the European Commission (EC) in February 2001, and because of the termination of the European Network for Food Security (RESAL) activities, the project was redesigned to focus specifically on the support to the local Food Security Programmes (FSP) of the EC, and in particular to the Food Security Observatories, also called Food Security Information Systems (FSIS). Redesigned project documents were ready in July 2001, but have still to be officially approved by the EC.

This review focuses on the redesigned project.

The redesigned project aims at building the capacity of staff of the national Food Security Information Systems (FSIS) in Armenia, Azerbaijan, Georgia, Kyrgyzstan and Tajikistan to monitor, assess and report on food security in their respective countries. The project immediate objectives are (from the project documents):

- To review the current survey methodologies to assess agricultural production and food security.

- To strengthen the capacity of the FSIS to carry out food security analysis.

- To improve the ability of the FSIS in the 5 countries to report on food security problems in a clear and timely manner.

- To develop a food security database for use in analysis.

This is achieved by a series of expert in-country assessments and training, focusing in the following six main areas:

- Understanding the concept of food security in a market economy

- Improving the construction of the national food balance

- Developing a food security data base for use in analysis

- Improving food security analysis using Household Budget Survey (HBS) and national food balance

- Developing crop forecasting and early warning capability

- Improving the ability to report on food security in a clear and timely manner.

Assessment

Project Relevance

By its objective, the project is very relevant to the needs of the CIS countries in building capacity in the production of adequate food security information, which in turn is very relevant, in principle, to national Poverty Reduction Strategies Papers (PRSP) currently being elaborated by the CIS countries (under the promotion of the World Bank (WB) and the International Monetary Fund (IMF)). Food and nutrition insecurity being closely related to poverty, improving information on food security should support the identification and targeting of the food insecure/poor, as well as provide essential tools for the monitoring of the PRSP implementation.

More immediately, the project is very relevant to the European Commission Food Security Programme (EC-FSP) in individual CIS countries. The EC-FSP provides budgetary support to CIS governments, attributed to specific sectors, and sets a series of conditionalities (e.g. the creation of operational Food Security Information System unit – FSIS, the production of food security information bulletins) to secure a coherent reform process in the specific sectors.  These conditionalities need to be met by the country to secure the EC budgetary support. In this framework, the project supports the capacity building in meeting food security information conditionalities.

Adequacy of the Project Design

In order to meet the request of the EC, the project was redesigned to focus on support to the EC-FSP in-country, while staying within the budget of a project initially intended for other outputs. While the reasons for this re-focus can be understood, it is clear that such process has negative consequences, such as delays and shorter time for the implementation of the project, and a project designed to fit a given budget rather than the contrary.

In order to re-design the project, the project leader and a consultant shared fact-finding missions in the four countries to identify the EC-FSP and countries main areas of requirement. This re-designing period was long (5 months) because, while already fully attached to the project, the project leader was requested by FAO to continue part-time at her previous affectation.

### Overall

The result of the redesigned project, which objectives are summarised above, is a very ambitious project, well targeted towards helping CIS countries in the food security information areas, aiming at helping countries to reach their conditionalities in the framework of the EC-FSP, starting with what exists. Consequently the project design embraced training, analysis and presentation of information in many areas (e.g. food availability, access and early warning, inc. food balances, household surveys, food and nutrition security, crop forecasting). Overall, the Review Team thinks that the project design is over-ambitious given the wide objectives, the large number of areas covered and the number of countries, for the given budget and timeframe.

### More specifically

Dealing properly with starting with what exists is obviously very difficult with budget constraints, and consequently the project planned to simultaneously investigate further the detailed needs (restricted to FS information) required by each country, as well as to already give some training, in order to help the countries to move one step further in the right direction in all areas identified.

The question is whether it was reasonable or at all possible to kill two birds (assessment and training) with one stone. While it is recognised that much knowledge on the real local needs can sometimes only be appreciated in the daily running of activities, implementing assessment and training simultaneously (or near-simultaneously) takes the risk to lead to trainings that are not always provided at the appropriate level. In addition, doing so, for a fixed budget, in multiple areas obviously reduces the depth or completeness of the training/follow up in each area.

In particular, the choice/priority (and corresponding budget allocation) of the training interventions could have reflected better local food security situation (e.g. more real needs for information on economic access to food rather than food availability) and technical capabilities (e.g. Hydromet generally very poorly equipped and knowledgeable in information, technology and communication equipment). Consequently the Review Team questions the priority given to the crop forecasting training and the Internet FS data base training and development.

Another essential point that would probably have helped focusing and prioritising the project is the consideration of the end-users of the FS information. With an objective to overall improve in-country sustainable capabilities in the area of the EC-FSP, the redesigned project would have benefited of the following:

- A fact finding mission in more depth;

- Better focus/prioritisation within a long-term support and sustainable strategy, e.g. fewer areas of support and/or countries, but with continuous and deeper involvements, adapted to the country needs (production and uses of information, on-the-job training);

- Clearer (more targeted) immediate outputs, placed in the long-term strategy, with verifiable indicators and deliverables (in order to better measure the project success in outcomes and impact. This will also very much help any review taking place!);

- A project mid-term review taking place at mid-term, with budget clearly allocated (programme vs. project review).

In addition, the project design should have provided a more detailed description of the FAO backup expertise that the project would have benefited from, indicating clearly the areas and sources of funding (FAO own resources vs. contracted by the project).

All the above issues resulted in difficulties in running an effective and efficient project.

Project Linkages with other Projects of the Programme/ with other FAO/EC Programmes

This project complements and had informal contacts with two projects of the Programme:

- GCP/INT/740/EC: The project interacted with the GIEWS workstation project on technical matters.  In the long run the project outputs should become very useful to provide appropriate information the GIEWS workstation, when both ICT level will be sufficient in-country and when the GIEWS workstation will be designed to receive directly and operationally information from individual countries.

- GCP/INT/741/EC: The project incorporated FIVIMS material in their training in food and nutrition security material. The aim of the quarterly FS bulletin being produced by the FSIS is to provide decision makers with better information on which to base policy decisions designed to improve food security, therefore supporting the Food Insecurity and Vulnerability Information and Mapping System (FIVIMS) Initiative.

Project Implementation

As indicated above, project re-design and late recruitment and availability of staff (project leader recruited fully in January 2001, but only available part-time for the first 5 months of the project), reduced considerably the time available to undertake project activities.

Given the project design indicated above, the overall implementation of the project has been relatively good and has been able, thanks to the high dedication of project staff, to adapt well according to the difficult field conditions such as diversity of expertise and local conditions, Russian experts low-availability, languages, diversity of technical capabilities, etc., and to produce substantial outputs.

However there is a series of important points to be noted. Many of these issues (only few of them applying to the Food and Nutrition Security – FNS – training) would probably have been avoided with an improved project design.

EC-FSP involvement: The EC-FSP interpretation of their role in the project has varied substantially between countries (and even within country), resulting in various levels of collaboration and commitments. It goes without saying that assistance in-country requires permanent knowledge of the evolving local situation. The project would have greatly benefited of i) a clear definition of EC-FSP role and responsibilities towards the project, ii) a close collaborative relationship throughout the design, implementation and running of the project.

EC feedback: The project should have benefited from regular feed back from EC-Head Quarters, at least on the very good six-monthly progress reports produced by the project.

Intellectual Property Right – IPR – & visibility: This project created/adapted/distributed training materials such as guidelines, reference material, user guides, software etc. The various documents/CD carry logos without obvious homogeneity between them. While FAO is generally noted, the EC logo is regularly missed, while consultants affiliation not. In addition, InWEnt (a German Governmental Development Agency specialising in training), which provided some reference training material that was built upon and translated in the course of the project, is now also using the improved/adapted material for its own purposes. Except from a basic Memorandum of Understanding between the parties, no apparent agreement or procedures exist.

It is essential that the FAO and the EC establish clearly, between them and with the consultants, the rule of IPR and visibility in order to avoid any subsequent conflicts, as well as to ensure allocation of appropriate funding for training material preparation.

Cost effectiveness: While overall, and given the project design, the efficiency of the project has been good, several points need highlighting:

Regarding the FNS training (2 so far: Kyrgyzstan and Azerbaijan), good collaborative work with InWEnt and GTZ has allowed good usage of staff and existing training material for a reasonable cost to the project. However the ratio “participants” / “support-facilitator staffs” is low (on average 3/1). This average is slightly higher when considering all project training. While this can probably be accepted for on the job training, given the “awareness” nature of the FNS workshop, this ratio could have been higher.

- Substantial developed material (e.g., Crop forecasting training and user friendly FNS data base, Website) was developed from scratch, requiring substantial resources, whereas none of the subjects are actually completely new, even if needing adjusting. The Review Team could see little evidence that the project actually attempted to look for and adapt existing material (except for the Food and Nutrition Security). For example, the EC organised workshops on food security in the late 90s in the CIS countries, or the World Bank organised household balance survey and interpretation training. While the target of these may not have been the same, there must have been useful material to use. If the project considered these, there is no clear evidence to why they were not used.

- Most project activities required external expertise, and the project leader attended most in-country inputs (at least partly). The project would probably have been more efficient would the expertise of the project leader been closer to the project activities (or the project activities less diverse), and the EC-FSP been much more involved in organisation and follow-up activities.

- However, the project benefited from substantial (but not quantified) self-funded input from FAO, through a Task Force of about 14 persons, representing each division with an interest in FS, as well as individual appropriate expertise, providing, in a multi-sectoral project, pragmatical support with all the complementary skills the project could not all actually have directly on board. In addition the project had very substantial administrative support from FAO.

Training timing: The timing of the workshop has mostly been driven by the availability of Russian experts (already trained, or to be trained), in addition to the time constraint and the understanding of the actual demand/requirements. This has led to an apparent non-logical sequence of training delivery. Most notably, the workshop on awareness and definition of the improved FS bulletin is taking place at the end of the project.

Training content: The high competence of the training staff/consultants has consistently been reported by the training recipients. Most on-the-job trainings have been well tailored to local conditions, practical and very well received. However most general trainings have mostly been designed on a generic template, i.e. for all countries. While their delivery was adapted on-the fly, the general trainings would have benefited from a better knowledge of the country/participants requirements, and therefore appropriate customisation. In addition, provision/training of software should have been carried out only when local staff was technically capable to receive it, and when software has been fully tested, in Russian, and with appropriate users’guide (unlike AgroMetShell for example).

Training follow-up: All trainings were the result of an expert coming in & out of the country, with most follow-up via email. While this approach as allowed many subjects to be addressed by appropriate experts, this has also meant too little time for essential in-country/on-the-job follow-up.

Training reporting: Generally the project leader reported very clearly and comprehensively on her missions, often with the help of the consultants. These are valuable documents for the future, since they report on the participants, their evaluations, the success and impact of the training, while providing a useful summary of the work undertaken.

Contracting local authorities: Several Hydromet services were contracted by the project to ensure delivery of agro-meteorological data essential to the improved FS bulletins. Given that Hydromet services are very low in resources in the CIS countries, it can be understood that such contract can help starting things going. However, such action should take place in a clear strategy to ensure long-term sustainability.

Project status

Given the loose definitions of the outputs, the project can always do more. However all output areas have already substantially delivered. Two FNS workshops (Armenia and Georgia) will still take place during the end of 2003. Most remaining activities are some tidying up and follow-up/support to keep the ball rolling in-country, while waiting for phase II of the project, expected in July 2004.

Project Results and Impacts

Because of the delays in appointing the project leader (see above) and the reformulation of the project, all the project results have really been obtained in only two years time, which must be noted as being remarkable.

The project achievements summary that is presented here follows the outputs as presented in the new project documents.

No input was provided to Tajikistan because the country has not an operational FSIS yet, an EC-FSP conditionality.

Output 1.1  A review of the methodology in use for assessing agricultural production using the existing survey and data processing techniques and proposals to strengthen data collection/processing if necessary.

In agreement with the EC, this component was to be covered by another project of the programme under the Consultancy Fund, GCP/INT/758/EC.  For no obvious reasons this did not happen, and FAO agreed on some TCP projects under its own funds to fill the gap. Some are already underway. Nevertheless, this project still collected and translated a lot of basic information (survey questionnaires and methodologies) and forwarded them to FAO - ESSB.

Output 1.2. : An assessment of and training in improvements in the methodology in use for carrying out food security analysis using existing Household Budget Survey data (HBS) and proposals for improvement.

This on-the-job training was provided very successfully to the four countries, and very well received by the participants (3-4/country) of the statistical departments. Local staff is using the new approaches, which already has had a very positive impact in the information available for the FS bulletin. Recommendations for improvement by the expert have been compiled but for some unknown reason not released by FAO yet.

Some technical problems which cannot be solved in a training course have been identified, such as within the HBS and food balance methodologies

Output 2.1:Development of the crop forecasting and early warning capability of the FSIS.

While varying between the countries, the local political interest in crop forecasting/monitoring appears to be low, as well as the local technical ability to do so. One-week crop forecasting workshops were provided in each country to participants (6-16/country) from the Ministry of Agriculture, Hydromet and Statistics departments. They were generally well received, but also with mixed feelings due to the fact that either the notions presented were already known or they were state-off-the-art techniques far beyond the local capabilities. This is also linked to the difficulty in choice/selection of participants, particularly with the low-interested and highly conservative Ministries of Agriculture and the extremely weak national funding of the Hydromets.

However, the project has established a Crop Forecasting Working Group in Georgia, Azerbaijan and Armenia which does produce, an agrometeorological report/quarterly forecast to the best of their abilities.

Output 2.2:  Familiarity with a harmonised methodology for constructing national food balances which will enable the FSIS to make an appraisal of the current and prospective food supply situation in country at the aggregate level.

One-week training in the above was provided in each country mostly to participants from the FSIS Statistics Departments (4-14/country). These included customised software greatly simplifying the work of local staff, and therefore that were very well received. All four countries have drawn up food balances for the major commodities (covering between 87-95% of food intake) for the years 1996-2001. Overall these balances are coherent and in reasonable shape, given the quality of the data available. The capability acquired by the FSIS appears to be sustainable.

Output 2.3: An understanding of the concept of food security in a market economy and the ability to analyse it using economic indicators, information from the HBSs and from the food balances.

There is great need for FNS understanding and awareness. This understanding has been growing slowly, and is being reinforced with a 2-week participative interactive workshop (so far in Kyrgyzstan and Azerbaijan), with participants from various ministries and other organisations (13-17/country). From all the participants met by the review team, these participatory workshops have been exceptionally good, both in terms of form and content, and have resulted in ”FS benchmark bulletin” consensus based on the information available in the country which they feel comfortable using.

Output 3.1: Coherent bulletins reporting on developments in, or likely to affect, food security and including regular updates on the outlook for crop and livestock production.

Thanks to substantial on-the-job training and supervision, bulletins are being produced regularly and are visibly improving in content, coherency and layout (but to various degrees in different countries). By the end of 2003 all FSIS will have developed a “benchmark bulletin” with indicators and analysis covering all 4 dimensions of FNS –availability, access, utilization and stability of the preceding 3.

Output 4.1: A database, accessible via Internet and easy to maintain for use in analysis and early warning, for each of the project countries.

Two staff from FSIS of each country has been trained in Rome to FS database, which has been developed and customised as needed. Three of the four countries have taken ownership of the database and are compiling it. While not a priority, countries do generally accept its long-term usefulness, both for the country itself, as well as for the international community. Substantial supervision will probably be required for the continuous compilation and updating of the database. The access of the database on the Internet will only become an operational reality when Ministries will have the willingness and appropriate capabilities to do so.

*

Overall: In most cases, this project has allowed countries to make a step forward in knowledge and practice in several areas of FS information. Since the overall project input has been scattered in many areas of FS information, the project impact represents a series of stable building blocks to support the countries to improve their FSIS. However, given the project design, effective follow up has only been successful to various degrees, sometimes reducing the real benefit of these trainings.

Sustainability: For the building blocks to be used and built upon sustainably, and for the collaborations to become reality, to mature and to flower, time, incentive, technical support and effective orders from ministerial heads will be necessary.  It must be noted here that it is only when officials can see the benefits of new and improved methods in their work that they will take them up. In many areas this does require sustained on-the-job training.

Training documentation: Most trainings have been accompanied by plenty of training materials, usually in both English and Russian, very appreciated by the participants met by the Review Team. Those will be good basis for other CIS and transition economies. However the quality and the homogeneity of the material varies very much between the trainings, which in general would have benefited of a much more user-friendly dimension, particularly for the Russian versions.

Inter-ministerial work: The project played an important role of trigger and catalyst for the start of essential inter-ministerial dialogue and work in the FS domain.

FS information usage: Last but not least, the Review Team could not see clear evidence of who are the actual users (particularly in-country) of the newly produced FS information (e.g. improved bulletins), nor evidence for potential users of newly promoted information (e.g. crop forecasting information). This reduces the potentially important impact of such a project.

General conclusion

Despite a difficult start (project redesign, over-ambitious given the budget and time frame, with wide objectives and little prioritisation, see above), this project managed to establish, in four CIS countries, very useful, but scattered, new basic building blocks for the awareness and for the delivery of useful information on food security. It has been instrumental in helping some countries to reach their EC-FSP conditionalities. Two additional bonuses from the project are i) the very beginning of inter-ministerial dialogue/collaboration, and ii) an increased understanding on local issues and requirements.

An important issue has been the adequacy of the capacity building approach, i.e. external experts going in and out of the country, whereas the real needs appeared to be for on-the-job training.

For sustainable impact to be visible, it is obvious that this project should be the beginning of long-term actions, focusing on the production of information to and for the users.

Consequently, substantial work is still required to reach full yield of the investment as well as to reach sustainability. While mindset and habits of a lifetime die slowly, in particular in former centrally planned economies, openings for improvements are clearly visible, but new understandings need to be refreshed and built upon regularly.

Recommendations

Given the nature of this review, the Review Team can only make limited specific recommendations.

Overall the Review Team recommends for the actions in CIS to be continued, on the basis that they are relevant to the countries, and that an invaluable path finding and block building has prepared the ground for potential real long-term impacts.

In the CIS countries the need for capacity building is very large, and the institutional capacity to receive it varies greatly. It is therefore very difficult to focus when nearly all needs to be done. In addition, it is only when officials can see the benefits of new and improved methods in their work that they will take them up. This will work best with sustained on-the-job training and follow up. However this is resource consuming.

Consequently, future actions must be prioritised to maximise the impacts of the inputs. The main recommendations therefore are:

- As much as possible, to identify some regional body that could be used as a centre for resources. As seen in other places (e.g. SADC project), this can work well, efficiently and sustainably to serve individual countries in a region. If it means working in fewer/different countries, it is still worth it in the long term.

- To prioritise actions (i.e. do not do it all) on subjects where results are achievable and will bring most potential impacts. For example, the Review Team feels that food and nutrition security awareness at all staff levels, food balances or household budget analysis, the organisation of food security data and their interpretation, and the production of bulletins are, in the short term, the most promising areas.

- To work not only on the production of the information, but, in parallel, on the usage and users of the information (the users do not always know exactly what information they want/need/is potentially available, this is why it must be in parallel. This is a very dynamic process).

- To build further on recent project activities, i.e. to place activities into a broader policy context and to design them accordingly, for example to better serve the PRSP purposes, and ensure endorsement of activities for maximum impact.

- Provide clear objectives, with defined outputs, deliverables and measurable indicators of success.

A series of additional points will have to be taken into account when designing a new phase, of which many are generic or related to the programme dimensions and are covered in the general recommendations for the programme.

PROJECT REVIEW

| Project Symbol GCPS/RAF/360/EC | Title Improving Early Warning and Food Security Information in Countries Subject to Complex Emergencies |  |  |
| --- | --- | --- | --- |
| Operating Unit ESAF | Lead technical Unit ESAF | OED- date 1 August 2000 | NTE-date 30 April 2004 |

Project Summary

The project aims at improving the quality of and access to crucial information relating to food security and nutrition of vulnerable population groups in complex and protracted emergencies. This would allow local institutions, donors, NGOs, UN agencies and others to respond to emergencies in an informed way, and to design appropriate rehabilitation and recovery programmes for affected populations. The immediate objectives, as specified in the project document, are:

- strengthened institutional support structures and linkages at national and international levels for improved information systems in complex and protracted emergencies, and well-functioning networks amongst national and international stakeholders established in four selected countries;

- improved food security information system methods and techniques developed for wider application in the context of complex and protracted emergencies;  and

- food security information on areas and population groups vulnerable to complex emergencies assembled and disseminated.

The project document was revised (revision endorsed by the EC in October 2001) with a view to:

- taking into account the establishment of the outputs and activities planned in the PAIA on Disaster prevention Mitigation and Preparedness and Post-Emergency Relief and Rehabilitation established in the context of FAO’s MTP 2002-2007;  and

- increasing the normative and advisory nature of the project and facilitating the work of other in-house units and field projects on food security information.

The revision implied the upgrading of one of the project staff from P2 to P4 level, giving up of the four national country coordinators in the four case study countries, placing country case studies at the centre of project implementation and giving up one major output, i.e. a baseline databank for areas that are prone to emergencies.

Assessment

Project Relevance

With regard to its objectives, the project is very relevant to the needs of humanitarian actors who are the prime potential beneficiaries of the project and of others, though to a lesser extent, who are concerned by LRRD issues.

In Angola (post-conflict – still many complex emergency features) and Mozambique (rehabilitation, high malnutrition compounded by a series of disasters such as drought, flood and long-term emerging HIV-AIDS crisis) visited by the Review Team, the loss and paucity of data and analysis remain a major constraint to policy and programming.

As to the relevance to the ultimate potential beneficiaries, this depends very much on the effectiveness of the information-action chain, in which the provision of reliable coordinated information and analysis is one element.

The project continues to be highly relevant to FAO’s priorities. There is an active debate/ strategic thinking process within the Organization on its emergency-related work. One sign of the importance given by FAO to emergency-related work has been the evaluation of the SO A3....requested by the Programme Committee (Governing Body).

Adequacy of the Project Design

Overall, the project was well designed. The participatory approach to concept and strategy development defined in the project revision is well suited to the project’s normative and advisory nature in the FAO environment. Such an approach was indeed appropriate to tap FAO’s multiple expertise, to use FAO’s experiences and to build upon existing activities.

However, and linked to the above, the project (as revised) lost clarity to a certain extent on outputs to be produced under the project. The project revision defines only broad “activity focus areas”. This has consequences on the way the project has operated so far (lack of focus) and on the achievements (see below).

The initial project document appears to be too ambitious with regard to expected achievements at the country level. This is particularly true in countries where very few information infrastructures were developed (eg. Burundi, RDC). The establishment of well-functioning networks amongst national and international stakeholders in four selected countries (specific objective 1) did not take into account the time needed for capacity-building and the need to have a minimum of existing information related infrastructures upon which to build the network. Country level operational objectives are to be seen as the ultimate rationale for project activities but, given the current availability of human resources, substantive follow-up at country level would need to be sought through other additional mechanisms. In this respect, the project’s approach as outlined in the revision giving up country applications and strengthening support to existing field projects, is more adequate.

Project Linkages with other Projects of the Programme/with other FAO Programmes

Up to now, the project has had limited relationships with other projects in the package programme.

The project’s implementation approach (facilitating role to other units) makes the project’s activities closely integrated with FAO’s regular programme of work on information in the context of complex emergencies, as well as more broadly on FAO’s activities contributing to one of the twelve strategic objectives (Strategic Objective A3). To a large extent, the close link of the project with FAO’s Regular and Field Programmes has been its strength and weakness (see below in results).

It is closely linked to FAO’s Priority Area for Inter-disciplinary Action on Disaster Prevention, Preparedness, Mitigation and Post-Disaster Relief and Rehabilitation (PAIA-REHAB). Under the framework of the PAIA-REHAB, the project is providing leadership on the design and establishment of an FAO emergency database. It is also linked to food security information system work of various FAO units involved in the FIVIMS initiative. Due to its focus on information use, project staff maintain a close relationship with staff of  FAO’s Emergency and Rehabilitation Division.

Project Implementation

Partially as a result of a change in the project strategy but also due to delays in the FAO recruitment process, the Project Coordinator was appointed only on 1 October 2001. The P4 Food Systems Economist was recruited in mid-December 2001. These recruitment delays have resulted in late implementation of project activities and an under-delivery on budgetary expenditures. However, in the absence of a full-time project staff, a consultant (later on the FS economist) was recruited for much 2001. This greatly helped the project take off more quickly once the Project Coordinator came on board.

A new Project Coordinator was appointed on 15 October 2002, just one year from the appointment of the first Project Coordinator, who was transferred to a full-time FAO Headquarters post in June 2002.  Given the change of management, a further revision of the work plan and priorities in the implementation of activities was undertaken, defining a new work plan (see the attached document). In the meanwhile, a new Division Director and a new Service Chief were appointed during the latter half of 2002, further impacting on the overall project strategy in view of changing divisional strategies and priorities.

Some activities started on the production of outputs and then seemed to have been neglected: ex. The idea of complex emergency briefing sheets was in fact implemented only for Sierra Leone.

Project Results and Impacts

Because of the delays at the start of the project, the project is only half-way through implementation. Consequently, the project is not at a mature stage on most of its expected outputs. This should be kept in mind while examining the project’s achievements and (potential) impacts.

As progress reports give on achievements by “focus area” as defined in the project document revision, the project results are reviewed and assessed using this categorization.

FAO’s platform for managing food security information in complex emergencies

Under this focus area, institutional issues have been examined within the specific context of FAO’s own in-house structure, with a view to contributing to a strategic planning process for FAO’s information strategy for complex emergencies. This includes both the organization by project staff of a series of in-house events or a contribution by the project staff to relevant events organized by other FAO units. The project has been instrumental in the formulation of the work plan under the PAIA-REHAB, through its conceptual and analytical contribution during the planning process (MTP, PWB 2004-2005), and continues to play a central role in the development of one of the major outputs under the PAIA REHAB (disaster data base). While recognizing the substantial analytical contribution from project staff to the in-house thinking and strategic planning process, the activities are (by definition) in-house/inward- looking and mostly benefit FAO staff. The current setting-up and development of an internal portal on complex emergencies for improving access to information will likely participate to bring the benefits of FAO’s platform role outside the Organization.

Tools and Methods

Substantial work was carried out including the testing and evaluation of some methods and tools such as vulnerability profiling in Afghanistan, the use of the food economy approach in a complex emergency context, and the use of GIS tools for broad farming systems mapping in complex emergencies, etc. While all these activities are relevant to the project’s objectives, there is a need for consolidating existing materials and lessons learned into concrete outputs for wider use (including an inventory of existing methods and tools, lessons learned/guidelines/manuals/best practices/etc.) and to make them accessible. In this respect, the portal will hopefully facilitate accessibility.

Case studies

Case studies are at the core of the project’s approach. A methodological guide was prepared for the conduct of a series of case studies. As of today, three case studies are either under way or in the process of finalization, looking at various aspects and issues of food security and vulnerability information in Angola, Somalia and Afghanistan.  Each of the documents is recognized to be of good quality, although the process to finalize the documents seems to be taking time (Angola case study, carried out last year, is still a draft). The case studies will feed the discussion in the planned international meeting in September. Similarly to the tools and methods-related activities, case studies are only intermediary outputs. It is not clear how the case studies will lead to some generalization other than feeding the discussion at a meeting. Lastly, the documents produced seem to have only marginal use at the country level (e.g. Angola).

Collaboration with other international organizations (UN/Bilateral/NGOs)

The project established relationships with relevant initiatives (eg. ODI sustainable livelihood approaches in situation of chronic conflict and political instability). The project also made some attempt to promote the application of FIVIMS principles (based on inter-agency collaboration) in the case of Afghanistan through the development of a proposal along this line for a joint FAO/WFP support to the food security surveillance and assessment activities.  However, collaboration with other international organizations is not yet translated into a joint programme of work.

Context definition: complex emergency

Under this focus area, various contributions (through preparation of papers and/or review) have been made on the following themes:

- Linkages between HIV/AIDS and Food Insecurity (CFS paper)

- Addressing the common causes of conflict and food insecurity and conflict (SOFI paper)

- Gender Perspectives in Emergency Programmes (comments)

Technical advice to FAO’s Regular and Field Programme activities are also part of the project’s contribution to a better understanding of food security in complex emergencies (information and analysis).

Although these contributions are highly valued by those benefiting from them (the paper on HIV/AIDS and Food security is recognised in FAO to be a reference paper), the project seems to stretch its scope beyond the limits of its specific objectives as well as its resource capacity. In particular, technical advice to RP and FP activities is time-consuming and ad-hoc based but is not systematically integrated into a set of clearly-defined activities leading towards the production of outputs.

General conclusion

- The project is very relevant to the needs of the prime expected beneficiaries, i.e. those involved in humanitarian action and, more broadly, the international community having to deal with complex and protracted emergencies.

- While appropriate and sound in its overall approach, the project is designed in such a way that it does not provide sufficient guidance for its implementation, with too much unclarity on the project’s boundary (scope) and outputs to be produced.

- The project efficiency has been hampered by the late recruitment of project staff as well as the change of project coordinator within a short period. Furthermore, the use of project staff for Regular Programme activities of the division in which it is located, did not help the project staff to closely follow a work plan. The project is not sufficiently independent from the Division in which it is located. The project is only half-way and much remains to be achieved.

- The key strength of the project lies in its full integration into FAO Regular and Field Programmes which provide many opportunities for cross-fertilisation and synergies as well as potential mechanisms for disseminating project results at all levels (e.g. through the CFS at the international level, through projects at the country level, etc.).

- At the same time, these strong linkages (also reinforced by the location of the project into the ESA division) have two negative (risky) implications: (i) the project tends to be very much inward-looking; the project benefited mostly FAO staff up to now (technical advice to activities of other divisions); and (ii) the project staff is very much absorbed into FAO Regular and other Field Programme work which diverted project staff from the production of project outputs.

- The project staff provided (and continue to provide) well-recognised and sound analytical support in a number of fora on various themes relating to food security in crisis situation. However, it is felt that activities are too dispersed and lack focus. The project has expanded its scope beyond “information in complex emergencies” to broader structural issues such as HIV/AIDS and food security or the broad theme of LRRD. Despite the high quality of analysis and the needs for such analytical work in principle, these again contributed to disperse efforts and divert the project thread from its core themes (outputs).

- Furthermore, the project stand-alone “products” (e.g. case studies, some of the work carried out under methods and tools) are not yet transformed into consolidated products ready for dissemination and useful for a wide range of beneficiaries. While this was too early to expect so, it is felt that the work plan does not reflect a clear road map (time, resource allocation, approach and mechanism) to produce these (e.g., learning – best practices, FAO’s information strategy for complex emergencies) outputs.  In building the work plan, a more systematic output-oriented is needed to achieve project objectives. Limited impacts are expected within FAO and even less outside if more effort is not given into the preparation of lessons consolidation/best practices outputs.

- By design, there is a broad range of potential beneficiaries, including primarily the various groups in the international aid community. By the topics it covers (information); the project should bring important benefits to practitioners at the country level. However, the Project impacts at the country level are expected to be limited by the end of the project. The design of the project (in particular in its revised form) is not country-focused. When there was a support provided at the country level (e.g. Afghanistan, RDC), the time and resources allocated were insufficient to generate substantial impacts. It is also felt that there was insufficient effort so far to exploit some of the work done at the country level to the benefit of the country (again this was not planned in the project document). There is a need to think of mechanisms (beyond a portal...) to ensure the dissemination as well as the operationalisation (use) of project outputs at all levels, including by practitioners at the country level.

PROJECT REVIEW

| Project Symbol GCP/RAF/351/EC | Title Capacity Building Support to SADC Remote Sensing Unit for Early Warning for Food Security |  |  |
| --- | --- | --- | --- |
| Operating Unit RAFR | Lead technical Unit SDRN | OED- date 19/07/2000 | NTE-date19/07/2003 |

Project Summary (from revised project document)

- The project will: consolidate the use of remote sensing and agrometeorological and GIS techniques to support early warning for food security in the SADC Regional and National Early Warning Systems, including required technological upgrading.

- Quantitative estimation of agricultural and rangeland production will be refined and operationalised where suitable, through collaboration with other institutions.

- The user base will be extended to incorporate the requirements of the public and private sectors through consultative fora. Training in monitoring and analytical techniques will be further enhanced, consolidated, and integrated into SADC FANR activities.

- This phase of the project will put emphasis on promoting SADC ownership of the project activities with a view to ensuring sustainability of operations beyond the project, within the established SADC infrastructure.

Note: the project document was revised with no substantial impact on the project’s objectives.

Assessment

Project Relevance

In general terms the project is relevant. SADC early warning activities were triggered in the late eighties by the occurrence of droughts that had negative impact on crop production and food security and which is again actual in the region at present. By that time the lack of a regional monitoring and reporting tool was felt and led to the implementation of a Regional Early Warning System as one of the instruments of SADC’s food security strategy. The strategic priority of REWS has been confirmed by SADC at the occasion of its restructuring.

Recurring effects of drought in some SADC countries as well as of tropical cyclones in others during the past cropping seasons have reinforced the perception that early warning is a critical issue. SADC’s assessment of the current crisis is that close to 13 million people from 6 different countries are exposed to severe starvation risks.

The key objective of improving the use of agrometeorology, space-based information and GIS techniques in SADC’s early warning system is highly relevant. These techniques are successfully used in Europe for the EU Common Agricultural Policy, in the United States both for national and foreign policies, at FAO (GIEWS and related activities such as ARTEMIS), but also elsewhere in Africa, such as at the AGRHYMET Regional Centre for CILSS countries in West Africa.

Adequacy of the Project Design

Project design is adequate in its general objectives.

Nevertheless when compared to other similar operations elsewhere the Project work plan was probably too ambitious for the available human and financial resources.

In particular, as already pointed out by the project evaluation mission, “technological upgrading” and implementation of “quantitative estimation of agricultural and rangeland production” require different technical and project planning skills as well as resources than the day-to-day routine operation of an existing system (i. e. “consolidation” as mentioned in the first objective).

Moreover when objective #2 is taken literally then one can understand that there was some overstatement. Indeed if yield estimates can be produced in a centralized manner from a combination of agromet models, space-based observation and point weather measurements, surface assessment require 1) the operation of enumerators on the field 2) the application of statistically valid sampling methods 3) if possible access to and analysis of high resolution satellite imagery. No means were foreseen in project design to achieve production of acreage figures.

For what regards the user base, it can be noted that, because of the crop production situation at project definition time, no explicit attention is given to key stakeholders in case of crisis, i.e. national authorities and the donor community.

Too little attention is paid to high resolution data acquisition, a pre-requisite to carry out the monitoring activities.

Project Linkages with other Projects of the Programme/ with other FAO & EC Programmes

FAO

Working contacts are documented in particular with GIEWS, ARTEMIS and the AGROMET group. This was done mainly through short term missions and regular e-mail contact.

EC

RRSU staff participated in a workshop organized jointly by FAO and JRC. Besides this the project evaluation mission noted that no EC service was mentioned as addressee of the bulletins produced by RRSU. A further workshop on the AgrometShell software development and utilization is scheduled for mid-September 2003 at FAO HQ with RRSU participation a.o.

The overall assessment is that there were contacts both with EC and FAO, but no real continued working relationship was established.

Project Implementation

Note

This project is the only one of PP99 which benefited from a full-scale mid-term evaluation. . The mission thus limited its evaluation task to information update, and not to the verification of actual implementation of the recommendations made by the previous evaluation team.

The project document was substantially revised with the objective of enhancing SADC ownership of the project and accepted by FAO and SADC in early 2001. Final approval was given by EC by May 2001. As a result staff could only be fully deployed from July 2001.

The Project was then normally implemented through the Operations Service of the FAO Regional Office in Accra, Ghana.

As pointed out in the evaluation report activities were carried out towards achieving most of the immediate objectives. However, the Remote Sensing & Modelling specialist left for personal reasons in early 2003. By that time the objective of methodological improvements and production of quantitative production figures had not been reached.

The project has been successful in particular in two domains:

- the production of regular crop growing situation bulletins  distributed to a growing number of users at technical and decision-making level in the countries of the region in various ways: paper, email and through a web site;

- the interaction with national agromet specialists through training sessions, technical workshop, exchange of data, tools and information.

For what regards the production of bulletins, it should be noted that emphasis is put on the analysis. Indeed, as pointed out before the project did not really succeed in upgrading their capacity. Thus so far, with the exception of the cold-cloud duration product jointly prepared with the Zimbabwe Meteorological Department, most pre-processed data are prepared elsewhere. This however is not to be seen as a shortcoming of the project as various data acquisition arrangements, e.g. with FAO ARTEMIS, were included in the project design.

Information on institutional restructuring started circulating during the second half of 2001. This is expected to impact the project’s life in two ways: 1) transfer to Gaborone, Botswana; 2) institutional re-positioning, possibly up to complete integration of RRSU, Regional Early Warning Unit, Database project and Drought Monitoring Centre. Uncertainties about the process, more than the process itself, have created some difficulties in the implementation of the current project.

Project status

The project has been working regularly so far. Further to the project review a number of steps have been taken so as to ensure continuation of key monitoring capacities during the season 2003-2004.

A tri-partite meeting was held between SADC, EC and FAO in Gaborone in March 2003. SADC expressed their wish to benefit from a new phase, while EC indicated their availability to consider its funding. It was announced that the transfer of RRSU wouldn’t occur before end of 2003. There is still no indication of any progress towards the articulation to be established among the four above-mentioned REWS components.

Project Results and Impacts

Detailed observations collected during the project’s evaluation mission and structured by objective are annexed.

This mission had the opportunity to collect some additional feedback from a number of persons interviewed.

- EC delegations in Angola and Mozambique confirm they now receive the bulletins. Distribution to Brussels headquarters is missing.

- Although bulletins have been regularly produced, disseminated and posted on the project’s web site, it is interesting to note that the only information accessible from the main SADC portal is the one provided by DMC. Neither REWU nor RRSU inputs are mentioned and no link is proposed

- In Mozambique the national food security officer commented that information was not really useful for his needs, while the regional food security officer was complaining about 1) lack of sufficiently detailed information at sub-national scale in particular in countries where such information is not available from national sources, 2) lack of quantitative production assessment

- Both in Angola and in Mozambique the language barrier is seen as a major hindering factor for training sessions as well as for day-to-day technical communication

- In Angola regional products are known but not used among other things because of telecommunication problems. It should be noted that because of the current situation in the country space-based information is for a number of areas the only possible source of information for a regular monitoring during the growing season. As national capacities are not yet sufficient to carry out locally data acquisition, processing and analysis, it would be most useful that the regional capacities take a pro-active role to ensure targeted and detailed analysis and on-time delivery of the information.

General conclusion

As a whole the project is a good example of ownership transfer, it has been operated without the continued support of non-SADC technical assistance, starting from a situation where it benefited from the support from two senior expatriate experts in the previous phase. All routine tasks could be carried out.

On the other hand the expected technology upgrading was not achieved.

The project has been successful in its crop monitoring and reporting activities as well as in the activities related to training and regional coordination of national points of contact.

While regular interaction was established by the project with national agromet services and, in some cases to a lesser extent with national early warning systems, this project is still weak in its outreach component, with no apparent visibility at SADC’s headquarters, and little or no visibility among the donor community.

Recommendations for a new phase proposal

The PP99 evaluation team recommends that in a project proposal

- institutional arrangements

The experience at national level, in particular in Mozambique, demonstrates the need to set up food security information systems in the appropriate institutional framework in order to ensure genuine cooperation between services and long term efficiency and sustainability. A pre-condition for successful implementation of a new phase is the finalisation of SADC’s restructuring, in particular the connection / integration to be established among the REWS components (REWU, RRSU, Dbase, DMC). This issue should thus be addressed with no delay by SADC as it may affect infrastructure costs related to relocation.

- ownership

Currently only one RRSU staff member is a regular SADC staff member. A demonstration of the actual ownership, a condition for system sustainability, will only be given when the core technical staff needed for routine operations is covered by regular SADC budgets and not by projects anymore. SADC should indicate how and when they plan to pass from the current project situation to a routine operation mode

- transfer from Harare to Gaborone

If the project is to cover part or all of the relocation costs, as discussed during the tri-partite meeting, then SADC should identify office / laboratory space, and infrastructure needs in detail (e. g. stabilized power supply for computers, local Internet connection, international connection to Internet, access to Meteosat data, etc…)

- operational aspects

It can be expected that efforts will have to be pursued to improve agricultural quantitative analysis and forecast capacities. A specific plan should be drafted, separately from routine activities

- product definition

As indicated elsewhere information generated does not necessarily satisfy the needs of real users. The various user categories should be identified, also beyond the current REWS distribution lists, and for each category specific needs should be identified, current products should be compared against these needs, and guidelines should be defined. User feedback should then be collected on a regular basis. Long term sustainability of RRSU will be guaranteed only if users are satisfied.

Attention should be maintained to all aspects of food security, i. e focus should not be limited to crop production, but also to rangeland resources, and other aspects of environmental monitoring useful to assess the level of food security.

- Input data

Access to useful input data for operational needs should be identified, and their access cost should be assessed. Whenever possible the project should establish arrangements with external providers who can guarantee long-term data provision at low or no cost.  Particular attention should be paid to European sources of data that are being set up with EC support, such as Meteosat-MSG (EDF is financing the installation of new reception equipment throughout Africa: Meteosat Transition in Africa under the PUMA Project), SPOT-VEGETATION through FAO-ARTEMIS with support from the EC (50% of the VEGETATION programme was financed by the EC), as well as other actions in development (ESA – GMFS project, AMESD initiative supported by AIDCO and EDF). This should not of course prohibit the project to access other sources of information when appropriate.

- Information Management and Analytical Capacities

The formulation of a future phase should take due account of the current developments in FAO in the area of standardized information management and access under GeoNetwork and the analytical and indicator tracking capacity of the new GIEWS Workstation and AgrometShell. These software capacities, which are currently being integrated, have the potential of assisting the RRSU, as well as SADC, to undertake its technological upgrading, improve its general information management and enhance its analytical capacity for generating more value-added products for food security early warning.

ANNEX II: TERMS OF REFERENCE

Terms of Reference for a Mid-Term Review

of the

EC/FAO Package Programme on Food Security 1999

1. Background

On March 29, 2000, the European Commission (EC) and the Food and Agriculture Organization of the United Nations (FAO) signed an agreement for FAO to implement a Package Programme to support food security (EC/FAO PP 1999).  The programme was designed to contribute to the definition and monitoring of food security interventions in line with the EC new food aid and food security policy, which aims at making recipient countries more responsible for the design and implementation of food security policies by moving from financial aid to budget support for sectors related to food security. After the last Commission's reforms the EC/FAO PP 1999 should be implemented in close collaboration between EuropeAid Co-operation Office, Food Security Unit (AIDCO F/5), and FAO HQ in Rome. A close co-operation was also promoted between the local/regional FAO representations and the EC Delegations and the Food Security Units (FSU) in food security priority countries.

The EC 113ts Food Security Food Aid Committee, held on 16 July 1999, approved the funding of the 1999 PP through the Food Security Budget Line. It consists of eight projects with total value of Euro 12.5 million (see Annex 1). The EC took the final decision on 09 November 1999. The implementation began on 19 July 2000 with duration of three years, and a fourth year for terminal reporting, closure of projects, etc.

The overall objective of the programme, which provides normative studies combined with technical assistance and advice to a number of food insecure countries and regions, was to develop new concepts and guidelines, strengthen local institutions, and build capacities critical for the improvement of food security in the longer term and under crisis situations.

The expected results were:

- improved monitoring of the global supply and demand situation for all basic food and facilitate access to the available information;

- improved monitoring of food security situations in specific countries and early warning analysis;

- reliable information on food insecure and vulnerable people in selected countries and improved design and implementation of specific action programmes to reduce food insecurity and underlying poverty;

- Strengthened developing country’s negotiating and policy formulation capacities to participate more effectively in world trade negotiations and to adapt to the changing world trade and economic environment.

The package was conceived as a programme in the sense that most individual projects (six out of eight projects) focuses on a common theme, that is, the further development and expansion of global and country monitoring and early warning systems. Two other projects were broader in their scope and included the provision of training and consultancy for a number of specific policy and thematic issues. Another significant common area among individual projects (at least among five projects) was the intensification of EC-FAO collaboration in food security in a number of selected countries.

Furthermore, the programme was designed to build on FAO long-standing experience in the field of food security information systems, food security strategy and policy, and FAO’s role in strengthening its developing member countries’ capacity in these domains.  All the projects relate to, at least, one or several of FAO corporate strategies defined in its Strategic Framework 2000-2015. More specifically, individual project outputs were considered particularly relevant to two strategies: (i) contributing to the eradication of food insecurity and rural poverty (Strategy A) and (ii) improving decision-making through the provision of information, assessments, and fostering of knowledge management for food and agriculture (Strategy E). The Programme was also designed following the Council Regulation (EC) N° 1296/96 of 27 June 1996, specially its Title II Operations in Support of Food Security. Individual projects, thus, were integrated into FAO existing programmes, in particular GIEWS, the FIVIMS initiative and FAO support to SADC in the field of food security information. The information systems projects and that on Complex Emergencies in particular, are fully integrated into the Priority Area for Inter-disciplinary Action (PAIA) on Disaster Prevention, Mitigation and Preparedness and Post-Emergency Relief and Rehabilitation. As such, much synergy was expected between the EC/FAO PP individual projects and other FAO programmes with which they related.

To the exception of two projects which started implementation late, all of the others are now completed or near completion. Already, some significant achievements are noticed on both the normative and operational aspects of individual projects.

An FAO mission visited Brussels, 21-22 November 2002, to review the programme with counterparts in the EC, namely, the Food Security and Food Aid Programme of the EuropeAide Cooperation Office (AIDCO F/5).  Feedback from the Commission was positive. It was agreed that a Joint EC/FAO Mid-term Review of the 1999 PP would be conducted in March/April 2003. The MTR would serve as guidance for the formulation of a new EC/FAO PP 2004 along major themes and within a clearly defined conceptual framework and a strengthened programme approach.

On 6-7 February 2003, the FAO technical officers associated with the PP 1999 visited the EC, Brussels, and made a presentation of progress achieved on the individual projects and discussed opportunities for developing a more unified programme approach (PowerPoint presentation available).

On 27-28 February 2003, EC officers made a return visit to FAO, Rome, for further technical discussions on issues of commun concern (PowerPoint presentation available), which focused on methodology for conducting crop and food supply assessment, early warning systems in Latin America, and linkages between disaster rehabilitation and development.

2. Objective

The objective of the MTR is to assess the overall results achieved under the EC/FAO Food Security Package Programme 1999 and draw lessons from the implementation with a view to providing guidance for developing a possible EC/FAO PP 2004.

3. Scope and issues to be addressed

The MTR will provide an overall assessment of the extent to which the EC/FAO PP 1999 has contributed to its overall food security objectives and will identify strengths, weaknesses and other opportunities for the development of a new EC/FAO PP 2004. In this respect, the focus of the MTR is on strategic evaluation and on the operational capacity of the programme as a whole rather than on individual projects.

More specifically, the MTR will analyse strengths and weaknesses of the EC/FAO PP against the following criteria and issues:

- Continuing relevance of the programme to the policy, priorities and needs of main stakeholders, including:

- the extent to which the programme was relevant to the institutional strengthening and capacity building needs of selected developing member countries for promoting food security information systems;

- its relevance to the development aid priorities (objectives, strategies and approaches) of the EC, in particular in the field of early warning and food security information systems, linking rehabilitation and rural sustainable development;

- its relevance to FAO’s priorities as set in the MTP 2002-2007; and

- its relevance to EC’s priorities set out in the Food Security Annual (2003-04-05) Programmes.

- Coherence of the programme design and strategy including:

- the extent to which the Package constituted a well-integrated programme with common objectives, linkages between outputs and consistency in approaches, methods and tools developed in the various individual projects; and,

- the complementarity/duplication with other agencies’ work in particular in the field of food security information systems;

- The effectiveness of linkages and synergies with other related FAO programmes (normative and operational at Headquarters as well as in the countries/regions), including the extent to which the programme has taken advantage of FAO’s technical and institutional strengths and, thus, the value-added of FAO as the implementing agency of the programme;

- The adequacy of inputs vis-à-vis the programme’s normative and country-level operational objectives;

- The results achieved by individual projects and by the EC/FAO PP 1999 as a whole against expected results, in particular in relation to the following areas:

- institutional strengthening and capacity building for the development and expansion of global and country-level monitoring and early warning food security information and analysis as well as for the design and implementation of specific action programmes to reduce food insecurity;

- provision of training and consultancy for a number of specific policy and thematic issues

- capacity building for member countries on the world trade negotiations on agriculture;

- normative studies leading to policy guidance, standards and procedures of wider applications;

- intensification of EC-FAO collaboration in food security in a number of selected countries.

The MTR will draw lessons from the analysis covering the above criteria and issues and will make recommendations for guiding the formulation of a new EC/FAO PP 2004. In doing so, particular attention will be given to the need for strengthening a programme approach to the Package and to building on the added-values of FAO implementing the Projects..

4. Proposed Methodology

As mentioned above, the MTR will focus on the strategic aspects of the programme’s performance vis-à-vis its overall approach and design. However, the MTR will be based on individual desk project review profiles prepared by project managers prior the start of the Review.

The MTR will be based on interviews with Project staff at FAO Headquarters, based on the project review profiles prepared by Project Managers and using existing project documentations extensively. The MTR will be highly consultative, in particular with staff involved in project implementation. It will use in particular the recently carried out evaluation of project GCP/RAF/351/EC and other assessments that have included activities relating to the EC/FAO PP 1999.

It will also include field missions, which will focus on end-beneficiary perspectives and to what extent collaboration between the EC and FAO has increased at Headquarters and field levels. Operations with a particular regional or more specific country focus concern: Southern African Development Community (SADC) countries, Horn of Africa countries, Sahel countries, Small Island Developing State countries and Countries in Eastern Europe/Central Asia. Among those, the following four countries will be visited: Armenia and Kyrgistan, Mozambique and Angola. Criteria for selecting countries include:

- Countries where assistance has been provided through one or desirably several projects of the EC/FAO PP 1999;

- Activities related to the EC/FAO PP 1999 in the country have not been evaluated yet.

It is important that within the four countries to be visited, two at least present results on which positive lessons can be drawn for guiding the formulation of the EC/FAO PP 2004.

5. Team Composition

The team will be composed of three evaluation experts: two from the EC to be nominated by EuropeAid F/5 (AIDCO F/5) and one from the FAO to be nominated by the FAO Evaluation Service. All; the three experts will have expertise in food security and food security information systems. Good familiarity of the strategies and policies of their respective agency will be essential. The team leader will be appointed by mutual consent of the two parties.

The Review Team will be assisted by a resource person (FAO staff) who will provide general advice for the conduct of the Review and assistance for organising the field work.

6. Timing

The total duration of the review will be 37 days, strating the 2nd of June. The detailed schedule of the Review is as follows:

| 02/06 Briefing | Brussels | 1 day |
| --- | --- | --- |
| 03 – 06/06 Documentation review – 1st interviews with Projects staff | Rome | 4 days |
| 07- 11/06 Field mission | Kyrgystan | 5 days |
| 12 – 17/06 Field mission | Armenia | 6 days |
| 18 – 23/06 : Interviews with Project Staff + Second field mission preparation | Rome | 4 days |
| 24/06 – 02/07 Field mission | Angola - Mozambique | 10 days |
| 03 – 11/07: Final consultation and Report writing and finalisation | Rome | 7 days |
| Total number of days |  | 37 days |

7. Budget

The FAO will cover the costs of the Review.

8. Reporting

The final report will be written in English and will be the co-responsibility of the team and will be submitted to both FAO and the EC within two weeks from the end of the mission.

Annex 1 - EC/FAO 1999 Package Programme for Food Security

| Project Number | Project Title | Lead Officer | Budget (Euro) |
| --- | --- | --- | --- |
| GCP/INT/736/EC | Training for ACP Countries on the Uruguay Round and Future Multilateral Trade Negotiations in Agriculture | Quieti, TCAS | 900,000 |
| GCP/INT/740/EC | Strengthening the Technical Capabilities of Global Information and Early Warning Systems Workstation | Cherlet, ESCG | 1,270,000 |
| GCP/INT/741/EC | Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Less Developed Countries | Immink, ESDG | 1,760,000 |
| GCP/INT/742/EC | Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Small Island States | Immink, ESDG | 880,000 |
| GCP/INT/758/EC | FAO/EC Fund for Consultancy Services | Hughes, ESDP | 2,380,000 |
| GCP/INT/814/EC | Intensified Monitoring of Food Security in CIS Low-Income Food Deficit Countries (Armenia, Azerbaijan, Georgia. Kyrgystan, Tajikistan) | Drysdale, ESAF | 1,130000 |
| GCP/RAF/360/EC | Improving Early Warning and Food Security Information in Countries Subject to Complex Emergencies | Smulders, ESAF | 2,200,000 |
| GCP/RAF/351/EC | Capacity Building Support to SADC Remote Sensing Unit for Early Warning for Food Security | Hielkema, SDRN | 1,980,000 |
|  |  |  | 12,500,000 |

Annex 2: Contribution of Individual Project Outputs to the Stated Four Programme Outputs

| EC/FAO PP 1999 Expected Results: R1: Improved monitoring of the global S/D situation facilitate access to information R2: improved monitoring of food security situations in specific countries and early warning analysis R3: reliable information on food insecure and vulnerable people in selected countries and improved design and implementation of specific action programmes to reduce food insecurity and underlying poverty R4: strengthened developing country’s negotiating and policy formulation capacities to participate more effectively in world trade negotiations | R1 | R2 | R3 | R4 |
| --- | --- | --- | --- | --- |
| GCP/INT/736/EC Training for ACP Countries on the Uruguay Round and Future Multilateral Trade Negotiations in Agriculture - 900,000 Euros -Training Materials and kits on UR agreements and agriculture - Government officials trained on various world trade and agriculture issues |  |  |  | X |
| GCP/INT/740/EC Strengthening the Technical Capabilities of Global Information and Early Warning Systems Workstation – 1,270,000 Euros - An expanded version of the GIEWS Workstation - Access to infor. By external users - Improved analytical capabilities of the workstation - Continued implementation of the GIEWS workstation software + databases by other FSEW units. |  | X |  |  |
| GCP/INT/741/EC Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Less Developed Countries – 1,760,000 Euros GCP/INT/742/EC Supporting Pilot Applications of the Food Insecurity and Vulnerability Information Mapping System Initiative in Small Island States – 880,000 Euros - diagnosis/assessment of national food security information systems - improved information products (national FIS) - Lessons-learned documentation - Refinment of FIVIMS model - Training module and country applications and Technical materials - Exchange materials (approaches, methodology) |  | X | X |  |
| GCP/INT/758/EC FAO/EC Fund for Consultancy Services – 2,380,000 Euros - Country and regional food security strategies, poverty reduction strategies, etc. - sectoral studies, policy decision papers, constraints analyses, etc. - identification and formulation of investment projects - identification and formulation of technical cooperation projects, incl. monitoring and evaluation. |  |  | X |  |
| GCP/INT/814/EC Intensified Monitoring of Food Security in CIS Low-Income Food Deficit Countries (Armenia, Azerbaijan, Georgia. Kyrgystan, Tajikistan) – 1, 130,000 Euros - Review of methodology for assessing food production - Government staff trained in methodology - Crop forecasting and EW capacibility in FSIS - Capability developed on FS analysis - coherent bulletins on FS situations - A database easily accessible |  | X |  |  |
| GCP/RAF/360/EC Improving Early Warning and Food Security Information in Countries Subject to Complex Emergencies 2,200,000 Euros - Review of activities relating to information system work in complex emergencies - Institutional capacity in case study countries to collect and disseminate information - Local experts trained in the use and application of field-tested methods and techniques for the collection and dissemination of information - A forum of experts and users of food security, nutrition and vulnerability information - Comprehensive review of methods and techniques - Assessment and identification of potentially relevant methods and techniques for the collection and dissemination of information to be field-tested - A set of methods, techniques and systems for the collection and dissemination of information tested in four country cases - Technical group of experts established for monitoring the testing and implementation of selected methods and techniques - Comprehensive analysis of lessons learned from case studies - A set of guidelines relating to the application of methods and techniques - A baseline databank for areas that are prone to emergencies - Incorporation or linking and use of the database in the FIVIMS Common International Database - A databank maintenance procedure |  | X | X |  |
| GCP/RAF/351/EC Capacity Building Support to SADC Remote Sensing Unit for Early Warning for Food Security 1,980,000 Euros - Improved and documented processing and communications system for dissemination of data and products - Extended user-base for FSTAU products to include both public and private sector users. - Improved inflow and use of current and new satellite data streams to SADC RRSU - Extended availability and use of agrometeorological data - Operationally implemented methods for early estimation of agricultural production - Enhanced data holdings and availability within SADC FSTAU - Regularly disseminated information products |  | X |  |  |

ANNEX III: BACKGROUND ON EC FOOD SECURITY POLICY AND RELATED MATTERS

Annex III:  Background on EC food security policy and related matters

In April 2000 the Commission adopted a communication on the European Community’s development policy (COM(2000) 212).  Through this communication the objective of EC aid is clearly focussed on poverty eradication and sustainable development. Six areas of intervention are identified: trade and development, regional cooperation and integration, support to macro economic policies, food security and sustainable rural development strategies, institutional capacity building, good governance and rule of law.

The regulation n°1292/96, adopted by the Council of the European Union on 27 June 1996, defines the legal framework of the Food Aid and Food Security Programme of the European Commission. It results from a process of reform of the food aid policy carried out since 1994, aiming to make food aid an instrument integrated as effectively as possible into the development policies and into the food security strategies of the concerned countries. The untied character of aid with respect to the management of European agricultural surpluses is formalised thanks to Article 11 of the Regulation.

EC food aid policy is targeted on priority countries. They are divided into two groups: those that receive structural aid and those that are in a crisis or post-crisis situation. The first group includes countries classified as: least developed countries (LDCs), low-income food-deficit countries (LIFDCs), with a high food insecurity index and where the government is keen for a coherent, long-term food security strategy. The second group includes countries in a crisis or post-crisis situation (linking relief, rehabilitation and development: LRRD). Interventions in these countries are less structural and mostly involve supplying food aid, tools and seeds, together with additional technical and financial support to prevent the risk of famine or help rebuild the economic and social fabric damaged by political or ethnic conflict.

In 2001, the first group included 21 countries: Albania, Burkina Faso, Cape Verde, Mauritania, Niger, Ethiopia, Eritrea, Madagascar, Mozambique, Malawi, Yemen, Bangladesh, Georgia, Armenia, Azerbaijan, Kyrgyzstan, Moldova, Nicaragua, Honduras, Peru and Bolivia.

The second group included 18 countries: Afghanistan, Cambodia, India, Pakistan, Laos, Liberia, Sierra Leone, North Korea, Somalia, Sudan, Democratic Republic of Congo, Rwanda, Angola, Ecuador, Palestine, Tajikistan, Montenegro and Haiti.

Concentrating operations on a limited number of countries means a critical mass can be achieved in each country, thereby increasing the impact of aid on improving food security.

The list is subject to revision, based on the assessment of indicators on a) poverty and food insecurity, b) national food security policy, c) EC food security policy vis-à-vis de country, d) possibility to activate other EC cooperation instruments

The EC Food Security budget line is in the order of 450 M€ /yr, out of a total EC development assistance of around 9 700 M€/yr. By comparison the annual European Development Fund budget (ACP countries) is in the order of 1 500 M€/yr. From the above-mentioned list 15 countries receive EC assistance from the food security budget line for an annual amount comprised between 10 and 30 M€ per country.

EC food aid is trans-sectoral: its elements come from the fight against poverty, from the support to the agricultural sector, to trade, to environment, to transport, to support to the private sector and to the civil society, to the crisis prevention, etc.

In crisis situation, the approach stresses the link between the emergency and development. Reducing the vulnerability of the most vulnerable population groups means a good identification of them and a better apprehension of the strategies that they implement to cope with the dynamics of the food risks. The multidimensional character of food security, just like the one of the fight against poverty, requires a good articulation between the various sectors (agriculture, trade, infrastructures, health, etc.) and the various intervention levels (local, national, regional, international).

EC Food aid provision is based on an analysis-diagnosis of the situations of food insecurity and on co-operation with the various participants and partners of the Community policy.

Regarding food security and sustainable development the Commission adopted in April 2001 a communication on linking relief rehabilitation and development (LRRD) COM(2001) 153 final of 23.4.2001). In this framework particular attention is paid to, i. a.: attention to preparedness in regions prone to natural disasters, due consideration to economic, social and political context and on the link between relief and development in conflict situations, refocusing of ECHO on its core mandate, emergency assistance to be designed to be consistent long term development objectives and sustainability.

Besides relief and rehabilitation assistance in the field of rural development is part of the strategy for poverty alleviation. Activities to be implemented must comply with six guidelines: promote quiet, fair, open and democratic rural societies, set up more efficient and reliable rural institutions, support economic activities leading to rural growth, improve living conditions of rural populations, promote sustainable management of natural resources, improve consistency between development policy and other EC sectoral policies. Rural development policy implementation will require appropriate information for action formulation, which is defined as rural development country profile.

The regulation n°1292/96 foresees in its article 6 that  “The Community may support existing national early-warning systems and help to strengthen existing international early-warning systems concerning the food situation in developing countries and, in exceptional and duly substantiated cases, it may operate such systems, in accordance with the procedure laid down in Article 27.” This is the legal basis i. a. for the support provided by the EC to FAO in the framework of the package programme under review, as well for assistance to national and regional early warning systems.

Regarding trade and development, the communication on the European Community’s development policy (COM(2000) 212)  notes that it is a key lever for development (§2.1) and underlines the need for coherence of the various aspects of EC external policies (§2.2). Developing countries need to be integrated into the world economy. On the other hand the EU is the first donor and the first trading partner of all these countries. EU trade policy can have a positive impact on development by contributing to a fair and equitable multilateral system and thereby facilitating the integration of developing countries into the world trading system. This involves taking into account the interests of developing countries and of economies in transition in international bodies regulating the framework of trade and investment, in particular the WTO. The EC can furthermore, through cooperation in all relevant areas relevant for trade (sanitary and phytosanitary measures, health standards, etc.) enhance the capacity od developing countries to handle all these issues and thereby remove unintended obstacles to developing countries exports  As such, the EU has to maximise its capacity to act within the various pillars of the international economic system, with a view to ensure coherence between trade liberalisation (WTO), assistance and financial co-operation (Bretton Woods Institutions) and normalisation aiming at sustainable development (Environment, ILO, Codex Alimentarius, etc.). The Commission will soon put forward an action plan to use its external policies to improve the coherence and the international economic governance, to further promote the gradual and harmonious integration of developing countries into the World economy.

References:

The European Community’s development policy – Communication from the Commission tot the Council and the European Parliament – COM(2000) 212 of 26.4.2000

La politique de développement de la Communauté européenne – déclaration du conseil et de la commission- DE 105 – dec. 2000

Politique et approches communautaires pour le développement rural – lutte contre la pauvreté en milieu rural – DG DEV – développement rural & sécurité alimentaire 15 juin 2000 (no ref)

EC food aid and food security programme Food security at the heart of poverty reduction – bi-annual report 2000 – 2001

Guidelines for the design of a rural development profile and strategic framework Final Document - December 2000 DG DEV – développement rural & sécurité alimentaire

Integrating environment and sustainable development into economic and development cooperation policy. Elements of a comprehensive strategy - Communication from the Commission tot the Council and the European Parliament COM (99) 499

COUNCIL REGULATION (EC)No 1292/96 of 27 June 1996 on food-aid policy and food-aid management and special operations in support of food security

Linking relief, rehabilitation and development – an assessment- Communication from the Commission tot the Council and the European Parliament  COM (2001) 153

External aid programmes – financial trends (1989-2002) – EuropeAid cooperation office

Annual report 2001 from the Commission to the Council and the European Parliament on the EC development policy and the implementation of the external assistance- Communication from the Commission tot the Council and the European Parliament  COM(2002) 490 12.09.2002

Annual report 2001 on the EC development policy and the implementation of the external assistance – ISBN 1683-3457

Annual report on the implementation of the European Commission’s external assistance situation at 01.01.2001 – ISBN 92-894-0766-2

ANNEX IV : ITINERARY

03 June:		Brussels – Interviews with EC AIDCO F/5

04- 06 June:		FAO Headquarters – Rome – Interviews with Programme/ Project staff

09 – 13 June: 		Country Visit – Angola (Luanda)

14 – 18 June: 		Country Visit – Mozambique (Maputo)

20 -23 June: 		FAO Headquarters – Rome – Interviews with Programme/ Project staff

24 – 27 June:		Country Visit – Kyrgyzstan (Bishkek)

29 June – 02 July: 	Country Visit - Armenia (Yerevan)

14 – 18 July: 		FAO Headquarters – Rome – Review Team Meeting

17 July:		FAO Headquarters – Rome – Debriefing

21 – 31 July:		Draft Report finalisation

### ANNEX V:  List of people met

DG AIDCO - Brussels

Jean-Claude Esmieu

Administrateur principal

Unit coordinator

AIDCO-F5 Food security unit

jean-claude.esmieu@cec.eu.int

Jose-Antonio Munaiz-Samperio

Relations with international organizations

AIDCO-F5 Food security unit

Jose-Antonio.Munaiz-Samperio@cec.eu.int

Maria Van Dunem

Food aid programmes in S. Africa

AIDCO-F5 Food security unit

MARIA.VAN-DUNEM@CEC.EU.INT

Mandeep Bains

Food aid programmes in S. Africa

AIDCO-F5 Food security unit

Mandeep.baines@cec.eu.int

FAO Headquarters

Nicholas Hughes, Senior Programme Coordinator, ESD

Pansy Tsang, Project Coordinator

GCP/INT/758/EC

Margarita Flores, Chief ESAF

Henri Josserand, Chief ESCG

Mark Smulders, Senior Food Systems Specialist, ESAF

Andrew Nadeau, GILW

Cristina Vertucci, GILW

GCP/INT/741/EC + GCP/INT/742/EC

Maarten Imminck, ESD

Françoise Trine, ESD

Jenny Riches, ESD

GCP/RAF/360/EC

Luca Alinovi, Project Manager, ESAF

Gunter Hemrich, ESAF

GCP/RAF/351/EC

Jelle Helkema, SDRN

René  Gommes, SDRN

Jeroen Ticheler, SDRN

GCP/INT/740/EC

Michael Cherlet Project Manager

### Claude Roy, ESCG

Mima Pippa, ESCG

GCP/INT/736/EC

Maria-Grazia Quieti, TCAS

Jean-Pierre Chiaradia-Bousquet, LEG

Cristina Devorshak, AGPP

Dr Lahsen Ababouch, Chief FIIU

Auden Lem, FIIU

GCPS/INT/814/EC

Marijke Drysdale, Project Manager, ESAF

David Sedik, REUP

#### Angola

Susan Mills,

FAO Representative

Paulo Vincente,

FAO National Programme Officer

Robert Steinlechner,

Second Secretary,

EC Delegation,

rsteinlechner@uniao-europeia.netangola.com

Roberto Calza,

EC Food Security Project

MINADER/GSA

Roberto.calza@netangola.com

David Tunga,

Director

GSA (Food security Dept)

MINADER (Min. Agric. & Rural Dev.)

davidtonga@hotmail.com

Fernando Andre,

NEWU, MINADER

Santos Felix,

GSA, MINADER

Laurinda Fernando,

Chief

Plant protection department,

MINADER

Adelino Rodrigues,

Animal health Department,

MINADER

Jean-François Dontaine,

Projectos the emergencia

FAO/UCPE

Consultor.fao.ucpe@angonet.org

Giovanni La Costa,

GIS officer

VAM unit

World Food programme

Giovanni.Lacosta@wfp.org

Mozambique

Boaventura Nuvunga,

Deputy National Director,

Nat. Dir. Of Agriculture

Min Agric & Des. Rural

bnuvunga@map.gov.mz

Mario Ubisse

Early Warning Department

Nat. Dir. Of Agriculture

Min Agric & Des. Rural

Raul Cumba,

Early Warning Department

Nat. Dir. Of Agriculture

Min Agric & Des. Rural

Jacintho Da Graça

Early Warning Department

Nat. Dir. Of Agriculture

Min Agric & Des. Rural

Paolo Machunga

Early Warning Department

Nat. Dir. Of Agriculture

Min Agric & Des. Rural

Joana Madime

Reg. Coordinator SETSAN Project / Tete.

Jeff Marzilli

CTA UTF/MOZ/071/

Raul Valera,

Consultant FAO/SETSAN

Marcella Libombo,

SETSAN Staff

Carlos Mucavele,

National Director

Directorate of Economy,

Min Agric & Des. Rural

cmucavele@map.gov.mz

Frans Van de Ven,

Chief Technical Advisor

FAO MarketingManagement Assistance project

MIC (Min. Industry & Trade)

faodnci@tropical.co.mz

Olga Munguambe

Deputy National Director of Trade

MIC (Min. Industry & Trade)

Maren Elise Bachke,

Marketing & Trade Research officer

FAO MarketingManagement Assistance project

MIC (Min. Industry & Trade)

faodpc@teledata.mz

Filipe Freires Lucio,

National director

INAM – Nat. Institute Meteorology

flucio@inam.gov.moz

Jafar Ruby

Technical assistant, FINAM Finnish coop project

INAM – Nat. Institute Meteorology

jafar.ruby@inam.gov.mz

Selma Honkanenn

Counsellor

Embassy of Finland

finemb@vircomm.com

Jean Risopoulos

Food security officer

Deleg. European Commission

jean.risopoulos@cec.eu.int

Bernard Lyonnaz-Perroux

Regional food security officer

Deleg European Commission

bernard.lionnaz@cec.eu.int

H.E. mr. Joao Carrilho

Deputy Minister of Agriculture

Peter Vandor

FAO Rep.

Peter.vandor@fao.mz.org

Armenia

# National Statistical Services

Stepan Mnatsakanyan

President

Gagik Ananyan

Member of the State Council on Statistics

Hrachya Petrosyan

Member of the State Council on Statistics

Armine Karapetyan

Main specialist

Internal Statistical Co-operation Division

# Ministry of Agriculture

Khradrik Tspnetian

Head of Agrarian Policy Department

Petrossyan Artur

Chief Specialist

Agrarian Policy Department

# Gagik Manucharyan

Chief Specialist

Development of Agricultural Sectors Department

Avetik Nersisyan

Team Leader

Agricultural and Rural Development Unit (UNDP)

Hydromet

Mayilyan Armen

Head of Agrometeorology Forecasting Department

# Food Security Programme – European Commission

Yiannis Hadziyiannakis

Technical Assistant

Ministry of Finance

Irina Grigoryan

Assistant

Ministry of Finance

Mane Tapaltsian

Assistant, Ministry of Agriculture

# The World Bank

Gohar Gyulumy

Economist

Poverty Reduction Strategy Programme

# World Food Programme – United Nations

Muzaffar Choudhery

Country Director

Sarah Gordon-Gibson

Programme officer

##### Kyrgyzstan

# National Statistical Committee

Muktar Minbaev

Head

Sample Survey Department

Ibragimova Shamsia

Deputy head of Sample Survey Department

Head of Household Budget Survey Statistics Division

Janibek Esengeldiev

Food Balance Division

Larissa Praslova

Sample Survey Department

# Administration of the President

Leonid Komarover

Deputy Head of Economic Policy Department

Head of the CDF Secretariat

# Ministry of Agriculture and Water Resources

Jumabaev

Head

Analysis and forecasting unit

Tzykalova

Chief specialist

Analysis and forecasting unit

# Hydromet

Inna Mayatskaya

Head

# KAMIS – Kyrgiz Agriculture Market Information Service

Elebes Rayapov

Head

# Food Security Programme – European Commission

Khadidja Kadri

Technical Assistant

Ministry of Finance

Arndt Von Stein-Lausnitz

Technical Assistant

Ministry of Agriculture

Alexander Kolposhilko

Assistant

Ministry of Finance

Galia Gukasian

Assistant

Ministry of Finance

Marina Klabukova

Assistant

Ministry of Agriculture

# The World Bank

Shamkanov

Operation officer

Rural Sector and Development and Environmental management unit

Umbrella Training programme on the Uruguay Round Follow-up and Multilateral Trade Negotiations on Agriculture – Review and Results – August 2001 FAO, Rome.

Ibid

FAO, State of Food Insecurity in The World, 2002.

We had initially planned to organise KIMS training sessions in countries under the projects but finally decided not to do it as the development of the software had not reached a sufficient level

The Annex 2 shows how expected outputs of individual projects contribute to the four stated Programme outputs.

FAO/EC Fund for Consultancy Services, and Training for ACP Countries on the Uruguay Round and Future Multilateral Trade Negotiations in Agriculture

EW and Food Security Information in Complex Emergencies and the FAO/EC Consultancy Fund.

The Mission was composed of  M. Nicholas Hughes, Programme Coordinator, ESDP, M. Mark Smulders, Senior Economist, ESAF, and Ms. Pansy Tsang, Programme Officer, ESDP.