ANNEX 1

Terms of Reference for the Mid-Term Evaluation of the Sustainable Fisheries Livelihoods Programme (SFLP)

### GCP/INT/735/UK

Joint Evaluation Mission by the UK Government’s Department for International Development (DFID), the Food and Agriculture Organization (FAO) of the United Nations, and the Department of Fisheries, Benin, on behalf of the 25 West African partner countries

##### Contents

- Terms of Reference

- Annexes 1, 2, 3

##### 1. Purpose of the Evaluation

1.1 The SFLP began in October 1999, initially for a planned period of five years, but has now been extended by an additional two years with an expected completion date of October/November 2006. As a result, the Programme is currently at its mid-way point. The evaluation is therefore primarily intended to be formative and to guide the remainder of the Programme activities during its last three years. This requires considerable vision but implementation of recommendations will be aided by the process approach, further output to purpose reviews and programme steering committees.  Its recommendations must focus on desirable and necessary changes to improve activities during the remainder of the Programme.

1.2 However, the evaluation will also have two other tasks. Firstly, given the SLA and process-orientated approach to the Programme Workplan, the mid-term evaluation will also be expected to comment on the success of the approach itself and of the SLA in contributing to poverty reduction. Given the flexible nature of the Workplan, the evaluation will need to make recommendations on how the SLA/process-approach can be improved.

1.3 Secondly, it is expected that the assessment of Programme results will itself use a livelihoods impacts assessment methodology (see below). The evaluation will therefore provide valuable lessons on how such methodologies can be improved for future use.

1.4 As a result, the development of the evaluation process itself is seen as part of the participatory and process-orientated approach adopted by the Programme and could have implications for further evolution of evaluation techniques within FAO as a whole.

##### 2. Scope of the Evaluation

2.1 The mission will assess the following:

2.1.1 Relevance of the Programme, and its approach, to development priorities and needs. The evaluation will consider the most pressing constraints and strengths of primary beneficiaries, and make an assessment of whether:

- the SLA and the CCRF (as guiding principles of the Programme) are appropriate tools for tackling such constraints and building on strengths and whether their use can be expected to result in the Programme’s expected achievements and meaningful contributions to poverty reduction;

- activities undertaken comply with the principles of the SLA and the CCRF;

- activities undertaken specifically address the strengths and opportunities of the Programme beneficiaries and can show achievements to demonstrate these.

These tasks will require a review of background data and information on Programme beneficiaries, a review of how the SLA and the CCRF have been applied, and consultation with beneficiaries on whether they see Programme activities addressing their most pressing development priorities and opportunities.

2.1.2 Clarity and realism of the Programme’s development and immediate objectives, including specification of targets and identification of beneficiaries and prospects for sustainability. Further to the assessment (above) of whether the Programme is attempting and succeeding in tackling key development problems and opportunities, the evaluation will also be required to assess whether the Programme can realistically expect to make a meaningful contribution to the resolution of such problems and opportunities. In particular the Project Document will be reviewed to consider the Programme’s objectives. Project objectives are often assessed in terms of the “SMART” framework, i.e. are the objectives Specific/Specified, Measurable, Agreed, Realistic, and Time-dependent. The evaluation will comment on whether such a framework is appropriate for assessing the objectives of projects incorporating the SLA.

2.1.3 Quality, clarity and adequacy of Programme design, including:

- Clarity and logical consistency between inputs, activities, outputs and progress towards achievement of objectives (quality, quantity and time-frame). This will require the evaluation: i) to review both the original Logical Framework presented in the Project Document and its revised version and ii) to assess whether the budgets/human resources/inputs allocated in project design and subsequent implementation were realistic in terms of timely and efficient achievement of required outputs, contributing to the programme purpose and objective. Were the inputs, activities, and outputs well-specified? Given the participatory and process-orientated approach used in the Programme, it will be appropriate for the MTE mission to consider the effectiveness of using these approaches to achieve the given purpose and objective. Has leaving the Workplan flexible to allow for beneficiaries to promote their own ideas for adoption by the Programme, resulted in Programme inputs and activities which are not supporting progress towards stated Programme objectives? Should the Programme design have been more specific? Does the Programme design contain a coherent strategy to guide, with flexibility, the implementation process within a realistic Workplan given the budget available? In particular, given that small projects are ongoing and that one pilot project has already been designed, the evaluation will consider the quality and methods of design used for these activities. Lessons to be learned and incorporated into the detailed design of the remaining two pilot projects and future small projects will be highlighted.

- Realism and clarity in the specification of prior obligations and prerequisites (assumptions and risks). It will be necessary for the evaluation to review the Logical Framework presented in the Project Document for the stated Assumptions, to consider whether those assumptions included have been clearly specified, and whether other assumptions and risks should have been included. Are the assumptions about the requirements for the Programme’s success realistic, and to what extent, if any, are the assumptions about hindrances to Programme activities and outputs actually just statements of fact, rather than risks? The evaluation should be mindful that project design can be considered defective if guaranteed problems are just stated as possible risks.

- Realism and clarity of external institutional relationships, and in the managerial and institutional framework for implementation and the Workplan. The evaluation will assess the logistical and managerial strengths and weaknesses arising from the Programme management and organisational structure as described earlier in this mission brief. Are the respective functions appropriate and realistic for the PSC, PCU, RSU and NCUs? Were specific relationships between institutions clearly and appropriately defined in the Programme design? Was the institutional setting and external linkages (i.e. PIPs) that might have a bearing on the Programme objectives and results adequately considered? How well-defined in the Programme design were the necessary links between Programme institutions and others, such as national government departments, associations of beneficiaries, local government etc.?

- Likely cost-effectiveness of the Programme implementation (in terms of the “least cost method” of achieving results). Could the design have allowed for the same level of expected benefits, but at a lower cost? And could the Programme design have been different, with the same cost, but with greater effectiveness? For example, could the same results have been achieved by using more national/regional expertise?

2.1.4 Efficiency and adequacy of Programme implementation including

- Availability (amounts and timeliness) of funds compared to the budget for both donor and national components. The evaluation will assess whether budget allocations specified in the Programme design have been made available as expected, and in a timely manner, and in particular, whether national country governments have demonstrated commitment to the Programme by providing financial input (unspecified in Prodoc).

- The quality and timeliness of input delivery by both FAO, including backstopping support, and the national partners/countries. The evaluation will review project documents, and consult with secondary beneficiaries to make an informed judgment about the quality of inputs provided by the Programme. This will involve an assessment, particularly of the perception by beneficiaries, about how well prepared the Programme staff were (especially to apply an innovative approach). The evaluation team will also consider the timing of inputs to the Programme. Were there any activities, the success of which could be expected to be dependent on the season or time of year? If so, were such activities implemented during this optimal time? If the timing of key planning decisions was known in advance were Programme activities which were intended to feed into the planning process through improved governance, completed prior to such decisions being made? And were the Programme inputs of sufficient quality likely to result in recommendations being adopted? The evaluation will also consider the performance of the Programme delivery against the anticipated timelines (milestones?) specified in the Prodoc, reasons for Programme delays, and any remedial action taken.

- Managerial and work efficiency. The evaluation mission will assess, through interviews with the various levels of the Programme management chain (e.g. PSC, PCU, RSU and NCUs), the perceived effectiveness and managerial efficiency at different levels of programme management.  Beneficiaries will also be questioned about their perceptions of Programme management. Relevant questions may include: were requests/questions promptly dealt with? Were activities/answers provided which were appropriate to the requests/questions? Were staff seen to be readily available and approachable? Are the PCU, RSU and NCUs fulfilling their stated functions? Have Programme responsibilities been delegated as far as possible?  The advantages and/or disadvantages to date of operating within FAO and FAO-FI?

- Implementation difficulties. An assessment of implementation difficulties is considered to be especially important in terms of formative recommendations of the evaluation. Programme staff and beneficiaries will be consulted and questioned to assess in particular questions relating to: 1) the geographical and holistic scope of the Programme and whether more focused activities would have reduced implementation difficulties, 2) the ability of the Programme to generate participatory agreement about which activities should be included 3) any problems relating to issues of the politically and economically powerful in beneficiary communities taking control of Programme activities for their own benefit, 4) the involvement of appropriate people from external institutions in Programme activities, which may be important for Programme outputs and results 5) the extent to which national stakeholders find the SLA and the CCRF accessible and useful tools, and the degree to which beneficiaries understand the Programme process and objectives.

- Adequacy of monitoring and reporting. The evaluation will assess the monitoring and reporting requirements as laid out in the Project Document and the Monitoring/ Evaluation study, to consider whether such requirements and recommendations have been followed or otherwise developed, and to what effect. The evaluation will thoroughly review the Programme Output to Purpose Reviews which have already been completed, and will also consider: 1) the level of detail required in monitoring and reporting, 2) the frequency and quality of monitoring and whether it has been sufficient, 3) whether progress towards Programme objectives is being sufficiently reported on, 4) has monitoring information been adequately used, and importantly, 5) the extent to which the participatory and process-orientated approach to the Programme has been successfully applied to monitoring and reporting.

- The extent of national support and commitment and the quality and quantity of administrative and technical support by FAO Programme staff. The evaluation will consider how experienced and skilled Programme staff are, and whether their skills match the activities being undertaken. And whether they will continue to match envisaged future activities.  Were project inputs felt by beneficiaries to be sufficient in length, quality and frequency to make material progress towards Programme objectives? It will also assess, through extensive consultation, the level of participation and sense of ownership felt in the Programme by national participants. An assessment will also be made of host country and participating country support for the Programme.

2.1.5 Programme effects and impacts and their sustainability. The evaluation will assess the progress of the programme in achieving effects and impact and the potential for effects and impact by programme completion. Where possible, effects and impacts will be quantitatively assessed and in all cases qualitative judgments will be made. In making its assessment of actual and potential effects and impacts, the evaluation team will make use of the SLA framework supplemented by other criteria as they find appropriate.

2.2   The evaluation will make a comprehensive assessment of the Programme’s impacts on livelihoods, disaggregated at community and household level to identify who, directly or indirectly, is a beneficiary, is bypassed or is negatively affected, along lines of gender, age, ethnicity, etc., and in terms of:

- Incomes (cash and in kind)

- Employment

- Food security

- Vulnerability

- Assets

- Policies, Institutions and Processes (PIPs)

- Learning and Livelihoods Strategies used by communities and households.

- Empowerment for more participatory governance

2.3 Given that livelihood impacts assessment methodologies are still evolving, the current evaluation mission will clearly define the methodology it uses for the assessment of the Programme results, and comment on the lessons learned using a livelihoods impact assessment approach in the evaluation.

2.4 The cost-effectiveness of the Programme. The assessment of cost-effectiveness, i.e. the best use of given resources for achieving the planned objectives, can clearly not use a quantitative measure such as an internal rate of return, as is common for investment projects. Given the nature of many of the project inputs and outputs, the assessment of cost effectiveness will need to be largely qualitative. Relevant questions will include whether the balance of Programme expenditure could have been used on different Programme activities to achieve greater results, and whether costs could have been reduced without reducing the positive impacts of the Programme e.g. could more local/regional expertise have been used, would the Programme have benefited from a greater degree of delegation of authority or are FAO procedures overly cumbersome applied in a SLA context.

2.5 Findings and Recommendations. Based on the above analysis (points 1-6), the mission will draw specific conclusions and make proposals for any necessary further action by specific parties to ensure sustainable development and improved livelihoods. This may include a re-definition of inputs and/or processes that are already planned to ensure that they have a greater impact, or specification of the need for any additional assistance and activities of the Programme prior to its completion. The mission will also draw attention to any lessons of general interest. Any proposal for additional assistance should include precise specification of objectives and the major suggested outputs and inputs.

##### 3. Composition of the Mission team

3.1 The mission team will comprise the following:

One person representing DFID

One person representing FAO FI (Fisheries Department)

One person representing FAO PBEE (Office of Programme, Budget and Evaluation)

One person representing the host country, Benin, on behalf of the other 24 participating countries

Between them, the mission membership will assure expertise in the following areas:

Evaluation, SLA, small-scale fishing communities of West Africa; small-scale fisheries and commercialization of their aquatic products.

3.2 The decision on who will assume the role of Mission Leader will be made on the basis of the experience and background of the experts suggested by the three parties, and subsequent agreement between all parties.

##### 4.   Organisation and management of the Mission

4.1 In discussion with the members of the team, the Team Leader will have the ultimate authority and responsibility for the work of the mission, including the allocation of tasks between team members and the production of the evaluation report.

4.2 The mission will be assisted with logistics by the PCU, the RSU, and by NCUs in all countries to be visited.  Travel arrangements of the Mission will be coordinated by the SFLP PCU in consultation and with full assistance of the RSU in Cotonou, Benin.

4.3 The PCU and RSU will ensure that all Programme staff and any information that they have are readily available to the Mission.  The PCU and RSU will try to facilitate the work of the Mission with prior preparation and presentation of key information.

4.4 At the specific request of the Mission the RSU will provide a professional staff member to travel with the mission for its duration in the region or to specific sites.  In each country the Mission will have contact with FAO country representatives and be supported by the NCU.

4.5 Staff in FAO-FI Rome will be available to the Mission as required.

4.6 The mission will be responsible for the final decisions about the schedule that it is to follow, within the confines of budget and possibilities of countries and FAO to support the work.

4.7 Since the number of countries involved in SFL is large, it will not be possible to visit them all and to consult with all beneficiaries. It is expected however, that the following arrangements would be appropriate:

- An initial briefing in Rome with the PCU, DFID and FAO, to take place early in June 2003. Time will also be spent in Rome with the PCU to prepare for the Mission, in contact with the RSU to arrange logistics of travel and accommodation in the West African region during field visits, to read background documents, and to allocate specific tasks to Mission members. The Mission Leader will spend slightly longer in Rome than the other three members of the mission. The time in Rome will also be used for specification of information and activities which the evaluation mission would like countries in the region to prepare before its arrival, so as to ensure efficient use of time. Requests may include evaluation questionnaires to be sent to all participating countries, or just a state of readiness to be achieved in the countries to be visited (with some specification of activities which the mission would like to complete during their visit). To allow for such a state of readiness to be achieved (and possibly for questionnaires to be completed), the mission will travel to the region at the beginning of July 2003.

4.8 Information to be provided to the evaluation mission by the PCU and RSU will include:

- Briefing material on the SLA

- The SFLP Project Document

- SFLP Output-Purpose Reviews

- SFLP reports and publications

- SFLP budget reports

- Information on primary and secondary beneficiaries

- Information on all Programme activities (completed, current, and already planned)

- Logistical information that may prove useful for the mission team

- Information is also available on the SFLP website:  www.sflp.org

- The evaluation mission will then travel to Cotonou, Benin, for a period of approximately one week. Time spent with the RSU is considered vital for further familiarization with the Programme, its approach, discussions with RSU Team on methods, activities and achievements to-date, as well as future vision of Programme development. During the time spent with the RSU, the representatives from all 25 countries will be invited to Cotonou to meet with the evaluation team. This will provide an opportunity for resolving any irregularities with questionnaires (if used), for all participating countries to discuss with the mission team aspects of the evaluation and contribute to the team’s investigations, and also for the participating countries to comment on the choice of individual countries to be visited.

- The evaluation mission will then visit at least four countries. Based on a review of Programme activities completed to-date, and the proposed pilot projects, it is recommended that the following countries be selected for visits: Guinea (Northern region), Ghana (Central region), Burkina Faso (Landlocked region) and Cameroon (Southern region). The evaluation mission will discuss the final choice of country visits during the initial briefing meeting in Rome. The whole mission could visit initially two countries and then split in two groups, to visit one country each. If Ghana will be one of the chosen countries, arrangements should be such as to allow necessary meetings at FAO Regional Office.

- Following visits to countries in the region, a further 5 days will be spent in Cotonou, Benin, to discuss preliminary findings with the RSU and to prepare the Draft Evaluation Report.  This will be sent by e-mail to the PCU, FAO-Rome and DFID, and discussed with the RSU before leaving Benin.

- The evaluation mission will then travel back to Rome and having received  comments on the Draft Report will make necessary amendments in Rome and present the final report.

4.9 The proposed itinerary is summarised in Annex 3 (weekends should be taken in consideration, either for field visits or travelling between countries

##### 5. Consultations

5.1 The mission will maintain close liaison with the Representatives of DFID, FAO and the concerned national agencies, as well as with national and international project staff. Although the mission should feel free to discuss with the authorities concerned anything relevant to its assignment, it is not authorized to make any commitments on behalf of the host government, DFID, or FAO.

5.2 The evaluation mission will be expected to consult thoroughly with the following groups:

- In FAO HQ, including  Fisheries Department (FI), Evaluation Service (PBEE), Field Programme Development Service (TCAP), Rural Development Division (SDA) and Project Coordinating Unit (PCU)

- Project Steering Committee (PSC) members

- Regional Support Unit (RSU)

- In countries visited, Government institutions and National Coordinating Unit (NCU), FAO Representative and if appropriate, DFID Representative. Primary and Secondary beneficiaries

##### 6. Reporting

6.1 The mission will be expected to produce a Draft Evaluation Report, before returning to Rome. A Final Report will be submitted at the completion of the Team Leader’s debriefing in Rome and will incorporate any changes and recommendations found acceptable by the mission which have been made during discussions and correspondence on the draft. The report will be simultaneously submitted by the evaluation mission to the RSU, PCU, DFID, FAO and the host country. The mission will also complete the FAO project evaluation summary questionnaire.

6.2 The mission is fully responsible for its independent Final Report, which may not necessarily reflect the views of the host government, DFID or the FAO. The Evaluation Report will follow in general the indicative headings and content shown below. It should be prepared in MSWord and have a sub-numbered paragraph format for ease of reference:

6.2.1 Executive Summary (Main findings and recommendations). The Executive Summary should be no more than 5 pages. It should contain a summary of the project objectives, structure and methodology followed, the reasons for the evaluation, and the composition and timing of the mission. Most important, it should include major findings, recommendations and lessons learned.

6.2.2 Introduction. Reasons for conducting the evaluation mission (terms of reference to be annexed to the report) and its composition. The mission itinerary with main visits made and persons met, and list of documents consulted by the mission should be presented in the annexes to the main report.

6.2.3 Background and Context. Brief description of the Programme rationale, including the development issues and constraints to be addressed by the Programme. Using a SLA framework (where information allows on vulnerability, assets, PIPs and livelihood strategies), baseline conditions should be described at the time of the Programme’s approval.

6.2.4 Project Relevance, Objectives and Design. In particular, this section should highlight the relevance and importance of the SLA and the CCRF as guiding principles of the Programme, and provide a critical analysis of the justification for the Programme. Other material to be included should cover all aspects mentioned in points 2 and 3 of the Scope of Evaluation described above.

6.2.5 Project Implementation, Efficiency and Management. Material to be included will cover all aspects mentioned in point 4 of the Scope of Evaluation described above including a summary of the scheduling of the project and expenditures to date against budget by country and main purpose.

6.2.6 The process approach followed by the Programme including major activities and outputs

6.2.7 Assessment of sustainable effects and impact.

6.2.8 Cost-effectiveness of the Programme .

6.2.9 Conclusions and Recommendations. This section should present a concise synthesis of the main findings of the preceding sections of the report, and should present a rational basis for the recommendations. Recommendations should be as specific as possible with necessary actions required by different parties, with suggested time-periods where appropriate. Given that the Workplan is flexible within the SFLP, recommendations will be made both about the envisaged activities, but also about the process used for guiding the Workplan and approaches employed for the remainder of the Programme i.e. the process approach.

6.2.10 Lessons Learned. The Final Report will pay particular attention to the importance of lessons learned, not just for the rest of project, but also for a) the use of the SLA and the CCRF for food security, poverty reduction and sustainable natural resource management, and b) the use of livelihoods impacts assessment methodologies.

6.2.11 Annexes

Terms of Reference.

List of places visited and key persons met.

List of documents and other reference materials consulted by the mission.

Notes on methodology used for assessment of the sustainable effects and impact of the programme on the livelihoods of fishing communities and their cost-effectiveness.

The logframe and Objectively Verifiable Indicators (OVIs) were revised in consultation with the SFLP PSC 6-7 December 2001

It is noted that such methodologies are still evolving,