SUSTAINABLE FISHERIES LIVELIHOODS PROGRAMME

(GCP/INT/735/UK)

- Joint Mid-Term Evaluation Mission

- FINAL REPORT

- September 2003

James Muir

Soulé Abdoulaye Manigui

Richard Chamberlain

Tullia Aiazzi

Acknowledgements

The Mid-term Evaluation Mission of the SFLP wishes to thank all those who have contributed to its implementation and full success. We are grateful to all staff of the SFLP Programme Coordination Unit in Rome and of the Regional Support Unit in Cotonou for the time devoted to organise the logistics for the Mission, their contributions and their patience in answering our continuous questions and requests for material and information. We would also like to thank the NCUs staff and members in the countries visited, for their kind support and time.

The Mission particularly wishes to thank the people in the communities visited, who gave their precious time to meet us and answer patiently and with good humour and spirit our many hundreds of questions, while accepting that we could not alone respond so quickly or completely to their own questions and requests.

Table of Contents

Acknowledgements	ii

Table of Contents	iii

Acronyms	iv

Executive Summary	v

1	Introduction	1

2	Background and Context	2

3	Project Strategy, Relevance, Objectives and Design	5

3.1	Project strategy and relevance to development needs	5

3.2	Programme objectives	6

3.3	Programme beneficiaries and participatory approach	8

4	Project Implementation, Efficiency and Management	10

4.1	Activities and Outputs	10

4.1.1	Overview	10

4.1.2	Set-up and institution building for the NCUs	10

4.1.3	Training on SLA and CCRF	12

4.1.4	Policies, Institutions and Processes	13

4.1.5	Poverty profiling	14

4.1.6	Small/community projects	15

4.1.7	Pilot projects	17

4.1.8	Organisation Development	18

4.1.9	Monitoring, reporting, information and communication	19

4.2	Government Support	20

4.3	Project Management	20

4.3.1	Structure and operation	20

4.3.2	Steering Committee	21

4.3.3	Task Force	21

4.3.4	Management and implementation	22

5	Assessment of sustainable effects and impact	23

5.1	Effects and Impact	23

5.1.1	The application of the SLA and CCRF	23

5.1.2	Strategic technical issues	23

5.1.3	Wider impacts	24

5.1.4	Partnerships	25

5.1.5	Regional and inter-regional impacts	26

5.2	Environmental Impact	26

5.3	Social and Gender Equity in Project Implementation and Results	27

5.4	Project budget, rate of expenditure and cost-effectiveness	28

6	Conclusions and Recommendations	29

6.1	Conclusions	29

6.2	Recommendations	30

7	Lessons Learned	33

ANNEXES	35

Acronyms

CBO	Community-Based Organizations

CCRF	Code of Conduct for Responsible Fisheries

CP	Community Project

DFID	Department for International Development

DSSM	Fisheries Department Senior Staff Management

FI	FAO Fisheries Department

FIPL	Fisheries Policy and Liaison

IDAF	Integrated Development of Artisanal Fisheries

MOV	Means of Verification

OD	Organization Development

OPR	Output to Purpose Review

OVI	Objectively Verifiable Indicators

NCU	National Coordination Unit

PBEE	FAO Evaluation Service (Programme, Budget and Evaluation)

PCU	Programme Coordination Unit

PIPs	Policies, Institutions and Processes

PPRC	Project and Programme Review Committee

PRA	Participatory Rural Appraisal

PRSP	Poverty Reduction Strategy Paper

PSC	Project Steering Committee

PP	Pilot Project

ProDoc	Project Document

RSU	Regional Support Unit

SIFAR	Support for International Fisheries & Aquatic Research

SLA	Sustainable Livelihoods Approach

SFLP	Sustainable Fisheries Livelihoods Programme

TCP	Technical Cooperation Project

TF	Task Force

ToR	Terms of Reference

Executive Summary

- The Sustainable Fisheries Livelihoods Programme (SFLP) was established in 1999 as a DFID/FAO partnership, originally completing in 2004, but extended to October/ November 2006. Notable for its geographical spread and development ambitions, it seeks to improve policy relating to artisanal fishing communities within its 25 partner countries, test, prove and promote its approach amongst partners, including FAO and its Fisheries Department. Key elements are the FAO Code of Conduct for Responsible Fisheries (CCRF) and the Sustainable Livelihoods Approach (SLA), strengthening community and institutional capacity and influencing the wider policy environment.

- This Mid-Term Evaluation was carried out between 31 June and 1 August 2003 to assess progress, and consider how well the SFLP’s higher aims (Goal and Purpose) were being realised. The team, James Muir (Department for International Development/DFID, Team Leader), Soulé Abdoulaye Manigui (Benin, representing the 25 countries), Richard Chamberlain (FI, FAO) and Tullia Aiazzi (PBEE, FAO), based its findings on discussions at a range of levels, on participation in programme management meetings, with representatives of 23 countries, interviews with key staff and informants, review of project documents, and on visits, community meetings and discussions in five selected  partner countries, Benin, Mali, Guinea, Ghana and Congo.

- The CCRF and the SLA provide respectively guidance for good practice in fisheries resource use, and a framework for using grass-roots procedures to influence policy issues, institutional environments and processes. Programme objectives are to be met through capacity building, advocacy, Community Projects (CP) and three Pilot Projects (PP) each involving 4 countries. Main beneficiaries are to be the fishing communities, whose self-realisation and empowerment would link with meso level awareness raising and capacity building, and at national policy (macro) level, greater inclusion and support for their needs. The SFLP would also inform other development agents on best practice, and offer new perspectives on social, technical, institutional and policy interventions.

- Three development hypotheses are implicit within the programme:

- Management of complex, traditionally common property-based natural resources under decentralised government requires locally devolved and internally motivated management structures. Traditional sectoral agencies and processes, using strategic, technocratic and top-down planning cannot do this effectively.

- It is only by describing and addressing household and community needs in a holistic manner, that poverty can be alleviated.

- Policy change and its practical application are the most effective and wide-reaching mechanisms for longer-term development delivery. This can only arise through awareness raising and through interlinked communication.

- Three operational hypotheses are that public sector fisheries institutions are the primary agents for cross-sectoral processes involving fisheries dependent people, that long term changes can be effected by focusing primarily on building human and social capital, and that general principles can be derived and applied from localised processes and experience. The logical framework (logframe) broadly reflects these developmental and operational issues. However, whether the true and immediate impact will be for the primary beneficiaries (fishing communities) or the secondary beneficiaries (government institutions) in the shorter term is not clear.

- A Project Co-ordination Unit (PCU) attached to FIPL in Rome, has strategic oversight, administrative and managerial responsibility. Operations are handled by a Regional Support Unit (RSU) in Cotonou, and local actions promoted by National Co-ordinating Units (NCUs) in each of the 25 countries. The project liaises with the FAO Regional Office in Accra, and FAO Representatives provide minor administrative services. The plan to manage pilot projects from the PCU, and site PP Coordinators in one of their participating countries, adds to the SFLP's structural, operational and managerial complexity.

- Over three and a half years, the Programme has carried out a number of activities:

- Set up and institution building of 25 National Coordination Units (NCU);

- Training and capacity building on SLA and CCRF;

- Policies, Institutions and Processes (PIP) analyses, awareness raising and inclusion of the artisanal fisheries sector into a number of Poverty Reduction Strategy Papers (PRSPs), as well as into FAO COFI concerns;

- Poverty profiles in 12 countries, quantitative and qualitative, and poverty studies;

- Fifty-two Community Projects in 20 countries;

- One Pilot Project launched in April-May 2003 and two in final preparation;

- Organisation Development;

- Monitoring, reporting, information and communication;

- Links developed with organisations such as the World bank, the EU, IFAD, etc.;

- Contributions to international thematic overviews on small scale fisheries, links with poverty HIV/Aids in fishing communities, fish trade;

- The CCRF and SLA have been taken up broadly, and their language is understood and expressed. The use of participatory tools, stakeholder analysis and livelihoods diagnoses, has been adopted, and the SLA’s holistic nature widely described if less commonly applied. The Mission’s major concern is the lack of connection between human and social capital development on which the SFLP focuses, and real processes of change, involving both sustainable management of the resource and economic opportunity development, on which poverty alleviation depends.

- Progress has been made in developing capacity of NCUs, widening cross-sectoral membership, involving a range of stakeholders. Women are usually but not always represented. Many NCUs can now identify and develop community projects, and can understand the role of policy. Together with studies on PIPs they have also contributed to raising wider awareness. However, their institutional position and membership do not often allow sufficient breadth of vision and scope to influence national policies. Without wider political will and clear strategies, few will themselves enable the SFLP to attain its more strategic goals.

- Ministers, Senior Cabinets and Fisheries Directors are commonly aware of the SFLP’s approach, but their engagement so far is partial, perhaps awaiting validation of its principles and methodologies. Progress has been made in engaging with PRSPs processes in some countries, but will need further effort to describe and activate alleviation strategies. In particular, practical and substantiated policy lessons from local/community level processes need to be developed to connect with national strategies and policy development.

- Local to national connections through meso level institutions (local and district government, line ministries, NGOs) are needed for livelihoods to be improved and sustained on a broader base. In several countries, other national and international partners, and other donor programmes are now working with fishing communities, engaging them in meeting needs identified during livelihood diagnostic exercises. These include issues of water supply, sanitation, health and education, not met directly by the programme. However, with a few exceptions, these links appear to arise incidentally rather than by intent, and where other resources are commonly lacking, this can unfortunately leave target communities without practical means of development, though “organised and empowered” by the SFLP.

- Community Projects cover a variety of issues, and many have mobilised community groups and engaged them in processes of self-realisation. Women are often involved and in some cases take a leading role, but gender is not often a key feature. Many issues have been simple and practical, but the SFLP offers little beyond limited initial inputs, with little to address longer-term change. In some cases, wider options including micro-finance have arisen but this has not been an explicit aim. However while human and social capital is important, it cannot be isolated from daily concerns for food and income. Without financial and physical capital, people cannot create the changes they desire, nor the SFLP reach its aims.

- In achieving wider programme objectives CPs have been relatively undervalued. Initially intended to give experience to RSU and NCU staff, and develop practical concepts, the issues, their importance to communities, and the expectations raised, have emphasised their broader significance. Given that in 13 out of 25 countries these will be the SFLP’s only field level activities, there is considerable scope for strengthening on-going projects, for replication of successful experiences and for their use to inform policies at national level, and formulate future investment.

- The Pilot Projects focus on broadly important thematic grounds. They involve a range of stakeholders and aim to build regional partnerships and perspectives, and two of them are oriented towards resource management and more general fisheries management on a participatory or co-management basis. These also conform broadly with the SLA and the CCRF principles. However, the Mission has broad concerns on the quality of the project designs and regional justifications.

- Links within FAO, including the Fisheries Department, have been rather poor. Missed opportunities for exchanges with relevant services limit the potential to influence policy development and normative work. This has also affected the morale of RSU professional staff and the quality of programme outputs. Without a clear mandate, the SFLP’s in-house Task Force (TF) has been relatively ineffective. Though many FAO Representatives have been supportive, their potential for national impact has not been realised, nor have TCP (Technical Cooperation Project) options been well explored.

- Regional and inter-regional links are yet to be developed fully, though a number of functions have promoted collaboration. There have been useful contributions to CECAF and CIFA, and discussions with the regional programme of Worldfish, and a valuable policy engagement in the 2002 COFI meeting. However, little so far suggests a genuinely strategic supranational perspective. Partnerships at all levels are a critical need and show useful leads, but there is little evidence of proactive engagement. This is especially urgent given both the need for development investment to achieve the programme’s main objective, and because of the time required for engaging with other donors’ programme processes and securing their funding commitment.

- Gender and poverty targeting, though mentioned in SFLP documents, are much less evident in practice. Very few institutional stakeholders seem aware that both need to be addressed concurrently to realise holistic livelihood gains. In particular, the programme has commonly missed the opportunity to contribute to empowerment of women through simple and inexpensive literacy courses. However, though still to be used fully, the poverty profiling initiative is an excellent example of how FAO can interact to establish key knowledge and normative strength. This is valuable in developing methodologies for identifying the significance and nature of poverty amongst fishing communities, and for recording changes associated with the programme or other developments.

- Market, trade, resource and policy interactions with industrial fisheries, essential for sectoral perspectives, have been largely unexplored, and justify more attention. Regionally, aquaculture is insignificant, but is changing, and has targeted roles in food security, livelihood diversification and income generation. Potential interactions and opportunities in production and markets will need to be noted.

- Co-management in inland and coastal waters has been promoted within the SFLP. While there can be valuable potential, many issues need to be addressed, though these appear little recognised, in spite of a growing body of international work, where both DFID and FAO have played leading roles. To engage in this without foreknowledge and practical approaches could be risky and even potentially destructive of the interests of those who the SFLP aims to support.

- The importance of communication is appreciated by the SFLP but insufficient thought is given to its purpose and targeting. The absence of livelihood impact and of strong engagement in wider development processes so far has limited the value of much that has been produced to date. These issues can be addressed but need a clearer perspective and more practical outcomes, as few can be convinced by records of process alone, without real and sustainable changes in livelihoods.

Conclusions

- While recognising the importance of the SFLP’s approach and the great potential of adopting a wider perspective to poverty alleviation, the Mission has concerns for its overall effectiveness. This is also reflected in documentation underpinning its process approach and in concepts and priorities shown amongst key actors, with a lack of structure and rigour in strategy and implementation. This extends to approaches for monitoring and reporting, which appear both burdensome and uninformative. It has been difficult to avoid attributing many of these and other constraints to management approach. Though some issues may relate to the way the programme has been structured, and terms of reference set out and interpreted, senior management should be expected to take more strategic responsibility.

- Unless changes are made, the SFLP’s quality as a development investment may be jeopardised. While benefits of more effective policy can greatly exceed programme costs, policy changes have to lead to outcomes, and there are many risks. Reliable processes of change need to be implemented, effective connections made between stakeholder levels, wider investment and development partnerships promoted, and the lessons learned based on evidence and debated widely. The balance of expenditure in the partner countries also needs to be adjusted. Nevertheless, the SFLP has real potential to demonstrate significant impact, and could stand as a landmark initiative, reflecting well on key partners and offering valuable gains in development understanding and impact, addressing relatively complex areas of natural-resource linked poverty alleviation. Though not every partner country can benefit in similar ways there are excellent opportunities at most levels. However, current constraints must be removed.

Recommendations

- The next phase needs to shift increasingly from activity and output level to immediate and development objectives (purpose and goals). Management and stakeholders alike need to understand the nature and type of challenge this brings. The programme needs to deliver real and substantiated outcomes, and will need a well developed approach and institutional partnership. Long-term impact will arise through wide ownership, with development partners and within countries. The SLA should not be dogma, but applied with skill and insight in a range of contexts, within definable development processes. This will also generate far more useful development knowledge. The SFLP needs to be open and participative, with wider networking, and links with other multilateral and bilateral initiatives in development and related research.

- The initially intended thrust for the SFLP to interact with the Fisheries Department and FAO wider normative aims, and its potential to fulfil this role, argue clearly for shift to a different position inside FI. A possibility could be at the ADG co-ordination level, with senior FI staff in greater contact, and opportunities to gain mutual benefits during this stage. The FI and FAO RAF technical advisory role should be enhanced, in particular to provide support to the RSU team. FAO Country Representatives should have a specific role in upper level national co-ordination and policy advice.

- The SFLP Task Force interactions need to be revitalised. The ToR it developed are still relevant, and should be activated for a more open process of collaboration and interaction. Opportunities should also be sought to create open sessions and seminars to allow wider access to the perspectives, issues and findings of the Programme. TF membership could also be reviewed where appropriate to ensure that it is widely representative and well motivated.

- The PCU should rationalise administrative functions, with a far clearer communication and advocacy role, promoting debate in development ideas, sharpening focus on key issues and developing wider links to share outcomes. New ToRs should be drafted for the Programme Coordinator, to reflect these changes, including more pro-active involvement of the FAO Fisheries Department in implementation and monitoring. The RSU and its remit should be developed, with ToRs for staff revised, linking with FI and FAO-RAF staff. The two other Pilot Projects should be coordinated from Cotonou, to maintain the RSU’s capacity and ensure effective backstopping.

- The SFLP needs to build on its positive proactive experience, at a range of levels, linking these effectively, with flexibility in adding value, to improve connections and impact. It should work with NCUs and other national agents from local to higher policy level, ideally in conjunction with PRSP implementation strategies, to develop national sectoral approaches with defined poverty alleviation outcomes. No uniform solution is expected, with detailed institutional analysis required and specific recommendations formulated for each. As part of this, the current and future role of NCUs should be developed, and investment strategies defined. In this respect also, greater interaction with FAO Representatives could be valuable not only in developing strategic perspectives, but also in making better use of TCP and other funding opportunities.

- New Community Projects should be developed, and promising on-going projects strengthened with partners’ contributions or where necessary direct programme funding. Projects should be grouped to establish a comparative/lesson-learning framework, and whenever possible connected with other development partners. In all cases, measures should be improved to avert social exclusion and support strategic empowerment, in particular along lines of gender, poverty and age.

- The quality and coherence of the three Pilot Projects should be upgraded improving measures to avert social exclusion and supporting empowerment processes, in particular along lines of gender, poverty and age. Regional focus should also be enhanced, clarifying thematic issues and outcomes, and logframes developed more accurately. This should be done in collaboration with FAO HQ (e.g. with the Task Force) as a learning process with RSU and NCU partners.

- There is an urgent need to clarify where knowledge is to be developed, and how lessons are to be learned, so that policy is evidence based and impacts of CCRF/SLA processes can be described. This does not require a rigid quantitative framework but should use current best practice. Links should be made with other areas of knowledge and with research agents in the region and elsewhere. Monitoring should be carefully developed to ensure it is efficient and meaningful, and administrative reporting reduced to the minimum consistent with needs. It is important also to establish primary indicators of programme progress with suitable milestones. A consultancy input is recommended.

- A clear strategy should be developed for information and communication identifying which stakeholders the programme needs to reach, what messages it needs to convey, and how these are to be conveyed. Materials and processes can then be developed more effectively. Further links should be sought with other agents in these areas. Strategic policy inputs from an external specialist or institution could also be considered.

- A more rigorous system of linking Programme strategy and goals to the implementation level needs to be established, to identify opportunities and constraints, steer agreed changes, provide specific action dates and monitor their adoption. This should be incorporated into routine PSC and Task Force procedures. As proposed for monitoring, independent external advisory support could be considered and agreements established with a highly reputed external consultant or with a suitable institution.

# Introduction

- In October 1999, the Sustainable Fisheries Livelihoods Programme (SFLP), commenced through a partnership agreement between the Department for International Development of the United Kingdom (DFID) the financing agency, FAO the executing agency, and the Department of Fisheries of Benin, the representative of 25 coastal and land-locked partner countries in North, West and Central Africa. The Programme was initially planned over a five-year period, and a final tripartite evaluation mission was foreseen at the end of the fourth year. In December 2001 the Steering Committee (SC) responsible for SFLP overall implementation, in assessing its state of advancement by then, agreed on a two year extension within the initial budget allocation, postponing the closing date to October/November 2006.

- The extension notwithstanding, there was general agreement that a joint external evaluation mission, primarily intended as a formative exercise, would contribute to guide the remainder of the Programme activities during its last three years. A Mid-Term Evaluation (MTE) team was therefore fielded in July 2003, when the Programme was at its mid-way point, composed of Mr James Muir, representing DFID, Mr Soule Abdoulaye Manigui, representing the Programme host country, Benin, on behalf of the other 24 partner countries, Mr Richard Chamberlain, representing FAO Fisheries Department (FI) and Ms Tullia Aiazzi, representing FAO Evaluation Service (PBEE). A first briefing took place in FAO HQ with the Programme Coordination Unit (PCU) at the beginning of June 2003, to allow the team to get a first overview of the Programme, decide which countries to visit for the field work and agree on major methodological aspects. Selected countries were Mali, Guinea, Ghana and Congo, together with Benin as the host country of the Programme’s Regional Support Unit (RSU). The team met again in Rome at the beginning of July, for a full briefing with the different HQ Services involved in SFLP implementation. On completion of four-week field work, the Mission held one debriefing session in Cotonou and two in Rome, with the Fisheries Department Senior Staff Management (FI-DSSM) and with the SFLP Task Force (TF) respectively, to present its first draft findings and recommendations. Also, a final debriefing took place at the beginning of September, once the final draft of the report had been circulated among all concerned. Many of the observations stemming from all these discussions were taken into account into the present document.

- The Mission had two other tasks. A key and in many respects distinguishing feature of the SFLP is its application of the Sustainable Livelihoods Approach (SLA) and its structuring in a process-oriented form, in which more specific elements of the Programme were to evolve during its implementation. The Mission was firstly required to comment on the success of the process approach itself and of the SLA in contributing to poverty reduction, and to make recommendations on how both could be improved. Secondly, it was expected that the assessment of Programme results would itself use a livelihoods impacts assessment methodology. The evaluation was therefore requested to provide lessons on how such methodologies can be applied and improved for future use.

- The methodology adopted by the MTE Mission was based on systematic analysis of the Programme processes and results at the intended and actual institutional levels, and of the experiences and opinion of the different stakeholders, to the extent possible in all visited countries and within the time available. Countries were selected to be visited by the review on the basis of community and resource issues, political and institutional characteristics, project activity and practical access, with the aim of providing a good cross section of features, potential, and progress. An SLA approach was adopted insofar as the Mission could assess the potential impact of the Programme on the eradication of poverty in relevant fishing communities. The SL framework was used to judge the relative significance of elements of the SFLP, whether in terms of livelihood capitals of communities, vulnerability, policies, institutions and processes, or in development outcome. More specifically, the Mission focus was on how activities implemented were likely to bring longer term, tangible and sustainable benefits to the targeted and other beneficiaries, or on the contrary affect any of them negatively. Its findings are based on discussions at a range of levels, on participation in Programme management meetings, including representatives of 23 countries, interviews with key staff and informants, review of project documents, and on field visits, community meetings and discussions in the five selected SFLP partner countries.

# Background and Context

- From 1983 to 1998, FAO implemented the Integrated Development of Artisanal Fisheries (IDAF) project funded by the Danish agency DANIDA, involving 20 West African countries, from Mauritania to Angola. Through this wide-ranging programme, the Regional Network for Artisanal Fisheries was established and capacities enhanced in all participating countries. The IDAF network was also instrumental in training and informing participating countries on the adoption and application of the Code of Conduct for Responsible Fisheries (CCRF), proposed by the FAO Secretariat and approved by FAO member countries in 1995.

- Participatory methodologies had been used successfully in IDAF and in other FAO executed fisheries development projects during this period (e.g. Yeji in Ghana and Shenge in Sierra Leone) resulting in substantive initiatives in artisanal fishing communities. This included identification and implementation of alternative or complementary revenue earning activities, empowerment of socio-professional groups within the fishing communities and had encouraged at least at the local level, a degree of community level management of facilities and infrastructures.

- In November 1997, DFID officials contacted FAO Fisheries Department and expressed interest in setting up a partnership to promote FAO’s normative functions in the application of the international CCRF. In 1998, for internal and organisational reasons, DANIDA had intimated its withdrawal from assistance to the Network. Subsequently, DFID informed the Fisheries Department that it would be ready to support partnership activities in West and Central Africa, and requested that four land-locked countries (Burkina Faso, Chad, Mali and Niger; Central African Republic joined at Programme start-up) be included in an enlarged network. In January 1999, DFID provided approximately US$ 640.000, under GCP/RAF/365/UK for the preparation of a 5-year programme. A detailed Project Memorandum was prepared by DFID in collaboration with the Fisheries Department and with contributions from the FAO Regional Office for Africa (FAORAF) and from representatives of fisheries sector stakeholders from the participating countries. A participatory planning workshop took place, with 90 representatives, 25% of whom were women, from government, non-government, fishing and fish-processor groups in the 24 countries. This enabled the incorporation of lessons learned from the earlier FAO-supported work and other projects in artisanal fisheries in the region, into a project concept acceptable to all. An FAO Project Document (ProDoc) was then developed and signed by three parties: DFID, FAO and Benin, host country of the Programme and representative of all partner countries.

- Marine and inland fisheries resources are the main source of livelihood for over 5 million people in West and Central African countries, and represent up to two thirds of the animal protein content of the average diet throughout the whole region, playing a very crucial role in national and local food security and food safety. The positive economic and employment creation impact of an active fishing sector also extends well beyond the actual fishing communities, directly involving a range of functions, from fuel (including wood) and gear supply to marketing, processing, transport and boat construction. While a substantial part of this is related to the artisanal sector, which has typically contributed strongly to the livelihoods of poorer communities and households, these fisheries have been neglected for a long time in relation to their contribution to national GDP, in terms of policy approaches, and with respect to the recent national Poverty Reduction Strategy Paper (PRSP) exercises.

- It is also widely recognized that the fishing resources accessible to artisanal fishermen have been declining over the last decade, due to excessive and illegal exploitation by industrial vessels and to some extent to wider environmental processes, including contamination, spawning and nursery habitat destruction, and climate change. Changing patterns of demand and trade, and relatively open access to many coastal and inland water has also led to increasing pressure of exploitation in many artisanal fisheries. In particular, the continuous and transboundary characteristic of the marine fisheries and the cross-cutting issues of coastal surveillance and sustainable management of both marine and inland resources, all require a regional approach if any substantial long-term improvement is to be achieved.

- Although precise data are lacking, there is widespread recognition and broad evidence that fishing communities are among the poorest in many of the partner countries, especially in relation to lack of physical, financial and human capital. For a number of reasons, including physical isolation and seasonal migration, fisheries communities tend to have limited access to basic services and infrastructure such as safe drinking water, clean sanitation, medical facilities, education and roads. Though natural capital may not in broad terms be so limiting as in some other communities, it is clearly sensitive to external factors and to the actions of the communities themselves. It also creates routine exposure to risks. These may be contributing factors to the social solidarity and cohesion usually noticed in fishing communities in the region and hence their potential for building on social capital to promote development. These features are indeed quite complex and articulated, in particular in terms of economic and decision-making power, because of the sometimes skewed access to means of production – where investments required to purchase gears and boats can limit ownership to a few - and because of the marked gender-based division of tasks which can give women fish processors and traders a much stronger visibility and independence than in neighbouring farming societies. In fact, throughout the whole region, though varying according to country and type of fisheries, women are dominant in post harvest activities and often also in financing the capture phase.

- At household and community level, the SLA aims to describe both the interconnecting needs and vulnerabilities to which people are exposed and the resources from which development can be defined and promoted. According to needs expressed during community level participatory assessments carried out by the SFLP at its inception, the basis of all constraints as seen by the beneficiaries had been the lack of disposable income. Most initial requests for assistance were for inputs: fishing gear, outboard motors for the fishers; micro-finance to expand working capital or other inputs for post harvest activities. This in itself could be seen as an informal baseline to measure changes in attitude once wider perspectives were to be introduced by the project.

- In the socio-political and economic environment at the time of project design, the SLA could also be seen as an enabling and empowering tool for communities and citizens in the context of democratisation processes evolving towards devolution of decision-making power, decentralized administration, and the development of local accountability vis-à-vis grass roots voting constituencies. This process has become a reality in some participating countries and is in its infancy in others, but there is growing acknowledgment that it is a crucial - and possibly inescapable - prerequisite for any sustainable development process in Africa. This is further accompanied by aims to rationalise public sector investment and promote private sector and civil society endeavour, in which development is increasingly seen as a shared responsibility, requiring effective partnerships. Indeed, present policy circumstances at the regional level seem to offer a fertile ground for the SFLP to be a useful learning experience and to develop lessons relevant also at a wider scale.

# Project Strategy, Relevance, Objectives and Design

## Project strategy and relevance to development needs

- The goal of the SFLP is “to reduce poverty amongst coastal and inland communities in West Africa through sustainable use of aquatic resources” and its purpose is “Livelihoods of artisanal fisheries communities improved”. The Programme seeks to achieve its objectives through the strengthening of social and human capital and the development and adoption of appropriate and widely-replicable policies based upon the application of the CCRF, for sustainable and equitable fisheries. Harnessing the social capital and developing it together with the human capital through organizational development and capacity building at the community level would permit communities to participate in the key areas of resource management and effectively articulate their needs at the higher levels of governance. It would also contribute to improved ability to react at the community level and within their various socio-professional groups to find solutions to problems, assuming that complementary economic or physical inputs can be found and/or partnerships developed. A similar level of sensitization and possibly capacity building or organizational development at the district or other meso levels of governance, would also be pursued, especially where the decentralization process is only just beginning

- Implicit within the Programme are three development hypotheses:

- The management of complex and traditionally common property-based natural resources under decentralised government requires locally devolved and internally motivated management structures. Traditional sectoral agencies and processes, using strategic, technocratic and top-down planning cannot address or support these demands effectively.

- It is only by understanding community strengths, and addressing their needs in a holistic manner that long term processes of poverty alleviation can be successful; needs must be expressed at the local level, and also understood clearly at the national policy level.

- Policy change and its practical application are the most effective and wide-reaching mechanisms for longer-term development delivery. This can only arise through awareness raising and through interlinked communication.

- Three other operational hypotheses are that public sector fisheries institutions are the primary agents for initiating cross-sectoral processes involving people engaged in the sector, that long term changes can be effected by focusing primarily on building human and social capital, and that general principles can be derived from localised processes and experience and applied elsewhere. The application and testing of these development and operational hypotheses are the primary function of the Programme. This requires impartial assessment of process and impacts, and effective communication between and beyond primary Programme stakeholders.

- The Programme’s reference at the sectoral policy level is the CCRF, which sets out a series of guiding principles covering inter alia resource management, its exploitation, processing and marketing. This is promoted to ensure long term sustainability for those directly involved in the sector, consumers and future generations. It aims to achieve this in a participatory way at the local, national and international levels through sensitisation, dialogue, clear and transparent strategies and fisheries management plans. In post harvest activities, the Code outlines the need for improved and environmentally sound methods of processing, transporting and storage of fish. This includes maximising value addition in the processing chain where improved returns will filter back to the primary producer thus improving disposable income and therefore livelihoods at all levels. Better quality products would then be available to the consumer. The integration of fisheries into wider frameworks such as coastal and watershed or catchment management is also included.

- The acceptance of the Code at the national level and indeed the dissemination of the priority concerns to community level in partner countries have created an awareness of issues that need to be addressed internationally, but which up until now had often been thought only to concern individual communities, and not be relevant for policy makers at any higher level. However, the need for a strong link between micro and macro levels of decision making in natural resources management, among other sectors, is by now widely acknowledged and the SFLP has correctly focused attention on the needs and scope for action and improvement in this direction. Further, potential links with specific issues of poverty, its characteristics and mechanisms provide an important strategic focus for development practice in poverty alleviation.

## Programme objectives

- Project goal, purpose, strategy and the concerns and issues discussed above are broadly reflected in the logical framework (logframe) reported in the ProDoc and in the Memorandum between FAO and DFID. The Programme Outputs (Objectives) as stated in the ProDoc and after the revision in December 2001 are as follows:

- National fisheries plans and policies improved through incorporation of adapted CCRF. Revised: National fisheries plans and policies improved through adoption of relevant CCRF principles, and national poverty alleviation planning takes account of fisheries communities needs.

- Capacity of communities to participate in fisheries planning and management improved. Revised: The capacity of communities and their partners to participate in fisheries planning and management for improved fisheries livelihoods improved.

- Community-based co-management systems established and functioning. Revised: Co-management systems established and functioning.

- Ecosystems and the resources they support enhanced and/or protected. Unchanged.

- Economic and social benefits from the artisanal sub-sector enhanced. Unchanged.

- Policy informed by dissemination of project experience and knowledge. Revised: Policy, institutions and processes informed by dissemination of project experience and knowledge

- Effective institutional network for programme implementation established.

- Out of these seven outputs, two (4 and 5) envisage straightforward contributions to purpose and goal. Four of these (1, 2, 3 and 6) contribute to purpose and goal insofar as one of the basic premises mentioned above, “policy change and its practical application are the most effective and wide-reaching mechanisms for longer-term development delivery” holds true. The 2001 revised version strengthens the institutional focus of the Programme, further away from its intended primary beneficiaries, i.e. the fishing communities. Last, programme network establishment (7) is commonly classified as a start-up activity no matter how complex the institutional set up of a Programme may be. Its wording and position among outputs raises the question of whether the sustainability of livelihoods is the core concern of a programme that looks at its own institutional set-up as an output/result, or whether a network is supposed to be seen as a requirement for longer-term processes beyond the programme period.

- The Mission notes two further issues in relation to the Logical Framework. First, there seems to be some confusion about outputs, Objectively Verifiable Indicators and Risks and Assumptions. Outputs are often classified as OVIs, and valid indicators are commonly missing. Risks and assumptions, on the other hand, often simply indicate the possible failure of project activities, without adequate analysis of potential external threats to project implementation. Secondly, perhaps due to the poorly structured development of the logframe, this was in effect set aside by the RSU in its operational practice and in presenting its activities to the MTE Team, using instead seven thematic issues: Changing Policies and Institutions; Code of Conduct for Responsible Fisheries; Capacity Building; Gender; Organizational Development; Participatory Monitoring; Information and Communication. While such practical modifications can be useful, and may be appropriate within a process approach, it is important contractually, in guiding staff and stakeholders, and in measuring progress, performance, impacts and lessons learned, to establish and maintain a clear and coherent management framework.

- Finally, the Project Review Sheet approved by the PPRC on 19/8/1999 included an additional output to those listed above, namely “FAO normative functions strengthened and capacity for contributing to international development goals enhanced”. Although it does not feature as a Programme Output in the eventually approved ProDoc, the concept of close collaboration with FAO FI, the use of its human resources to support Programme implementation and the feed-back of results and lessons learned into normative work, are raised a number of times in  project documents, minutes, etc. Indeed, the siting of the PCU in Rome HQ was largely aimed at facilitating this, in effect making a case-study of the Programme, for wider dissemination and information of policy-makers. While FAO’s constitutional issues of independence and impartiality require to be observed, it is important for Programme structure and operation to be clear about such expectations. Successful Programme’s results and effective partnerships should enable all stakeholders to strengthen their capacity, and FAO’s strategic and influencing role in particular could be validated and reinforced.

## Programme beneficiaries and participatory approach

- The ProDoc identifies the SFLP beneficiaries in the following sequence:

- Primary beneficiaries: the resource users in the artisanal fisheries communities, particularly the poorer groups: small scale traders and processors (mostly women) and consumers.

- The secondary beneficiaries include: Fisheries departments of member countries and other related government departments, NGOs, the national and regional sectoral planners and others who have overall responsibility for the proper management of the fisheries sector at global level through “enhanced normative functions of FAO”.

- A case can also be made for defining a third group of beneficiaries, i.e. the development community, including FAO and DFID themselves, together with a range of direct partners such as IFAD and others. Indeed, if a holistic perspective is proposed, in which agents at a range of levels are involved in development processes, a distinction into different levels of beneficiaries loses partly relevance. Still, the evidence of Programme implementation suggests that intended primary beneficiaries have been neglected so far in terms of both focus and resources.

- A gender analysis was carried out at the time of project formulation, 25% of the participants to the workshop to discuss the SFLP were women, and the role of women in artisanal fishing communities is widely mentioned in the ProDoc. However, the ProDoc mentions the word “gender” only twice, always in relation to the tasks and ToRs for the Community Organization/Gender Officer.

- The Programme relies upon the adoption of a participatory process approach, through which potential beneficiaries “will be encouraged to progressively and in a participatory manner, identify, implement and evaluate development activities which correspond to their own needs and aspirations”. Also, it should lead beneficiaries to establish and to enhance their own influence and control over planning and management of resources. Though not explicitly stated in the ProDoc but frequently reiterated in Programme Steering Committee (PSC) and other working documents, further coherence is pursued with the adoption of a “demand-driven” approach: beneficiaries will identify activities to implement at community/field level, which therefore cannot be prescribed or planned in advance.

- However, the Programme implementation strategy does not really meet all these principles. For needs and aspirations related to human and social capital, the SFLP expects to offer specific inputs. But needs and aspirations for physical, financial, and possibly also natural capital, are to be met, according to the Programme, through support from local development agents such as NGOs and other institutions, the development of partnership agreements with other donors, or through enhanced access to national funds for sector development: “it is envisaged that there will be many opportunities to establish close collaboration with other partner organisations during the implementation of the programme”. However, although participatory exercises have indicated that needs and possible ways to improve livelihoods sometimes relate to improvement of social and human capital, and that hitherto unrealised resources in human and social capital could be engaged in addressing development aspirations, they mostly identify the lack of financial and physical capital as the real bottleneck to sustainable livelihoods. In practice, it is only if these are in place, or imminently available while human and social capital is being activated and/or developed, that the combined impact can be effective and sustainable. Given the lack of resources at the national and local levels, the legitimate existence of other donors’ different agendas, or at best the very lengthy procedures to have access to their funds, the Mission considers this implementation approach to be quite naïve and unrealistic.

- Linked to this point is the core meaning of the demand-driven approach. In fact, the discrepancy between expressed needs and Programme’s response raises two possibilities. One, the communities do not understand and do not see “their wider constraints” and they miss the real causes of their poverty. This might imply also that the participatory assessments are not a suitable tool to identify problems and trigger a locally-centred development process, or that the assessments are not properly carried out. Two, the communities are correct in their diagnosis, and therefore it is the Programme that misses the point. On one hand, it is true that sometimes communities might tend to provide stereotyped answers to external agents, but these however should be averted through careful and accurate participatory assessments. Still, the Mission considers that the Programme tends to underestimate the importance of getting engaged in the practical processes of addressing the management of fisheries resources, generating local economic value, and developing wider livelihood opportunities, so as to offer wider lessons, and promote well developed policy.

- Some further doubts are also legitimate about the Programme’s capacity to reach its intended beneficiaries. Though the Programme “is not expected to provide funds to improve the access to resources”, the poorer groups in fishing communities would benefit “from the improved management and social organization”, as the latter would stimulate more funds flowing into the communities. In spite of the strong solidarity ties which may exist in fishing communities, this assumption again seems to rely upon a rosy picture of communities where access and control of resources are open and equal for everyone and no mechanisms of power, control and exclusion exist. Evidence of the review at the operational level suggested that these questions were either simply not raised, or if inescapable, were not analysed and addressed, and were therefore not brought forward into national awareness and policy processes.

- Finally, the Programme’s thrust and ambition ask for a lot of “intelligence”, exchange and openness to steer implementation in a flexible and effective way, adjusting it without losing sight of objectives and constraints. The Programme design provides reasonable guarantees in principle for wider technical and methodological support and monitoring, though possibly it does not provide enough details on mechanisms to foster participation at all levels and among all stakeholders, FAO Fisheries Department in primis among these. While the priorities of establishing networks and operating procedures have necessitated more of an internal focus in the earlier Programme stages, there is increasing evidence of ideas and approaches being unnecessarily limited or hampered by a lack of wider communication and lesson-learning from others.

# Project Implementation, Efficiency and Management

## Activities and Outputs

### Overview

- Over three and a half years of implementation, the Programme has carried out a wide range of activities, as bulleted below. The complete list of these, based upon the “Thematic Brief” prepared for the Mission by the RSU is found in Annex 4. Specific activities on gender issues are further detailed in the related subsection in Results and Impact. Here, to avoid over-detailed and repetitious itemisation and explanation of each of the very many individual activities, main clusters of activities are highlighted and commented upon, based on direct evidence obtained by the Mission:

- Set up and institution building of 25 National Coordination Unit (NCU);

- Training and capacity building on SLA and CCRF; national planning assistance, inputs to national training curricula in selected countries;

- Policies, Institutions and Processes (PIP) analyses, awareness raising and inclusion of the artisanal fisheries sector into a number of Poverty Reduction Strategy Papers (PRSPs);

- Poverty profiles in 12 countries, quantitative and qualitative, and poverty studies;

- Fifty-two Community Projects (CPs) in 20 countries;

- One Pilot Project launched in April-May 2003 and two Pilot Projects under finalisation at the time of the Mission. These cover a total of 12 countries;

- Organisation Development;

- Monitoring, reporting, information and communication;

- Links developed with organisations such as the World Bank, the EU, IFAD, etc.;

- Contributions to international thematic overviews on small scale fisheries and poverty (Willman FIPP), ACFR, CECAF/CIFA working group on small scale fisheries, FAO-SD review on HIV/Aids in fishing communities, contribution to Norwegian funded fish trade study (Kurien-Murray);

- Support to boost FAO-FI input to COFI in raising the profile of small scale fisheries and its links with poverty.

### Set-up and institution building for the NCUs

- Each country participating with the SFLP agreed to set-up a National Coordination Unit to represent the Programme in the country, coordinate activities and different in-country stakeholders and supervise and monitor the implementation of Community Projects and Pilot Projects, where this would be the case. The NCUs, set up and trained for the purpose by the Programme, should become the primary agents for change in each of the target countries, though for the time being they are primarily the SFLP national counterparts, representatives and promoters. In all countries, the NCUs are attached to the Ministry/Department of Fisheries, at different hierarchical levels, following internal decisions, though a number include representation from other Ministries, e.g. Rural Development, Environment, Forestry, Agriculture, Finance, etc. Some were set up through a specific decree, others are clearly perceived simply as the SFLP structure in the country, to be cancelled once the Programme was closed. This of course has a direct impact on the NCUs’ leverage and their capacity to influence policy makers at the higher levels. In a number of countries but not everywhere, appointed Coordinators are seconded full time to the NCU work.

- The Mission visited 5 NCUs in their localities, intended to represent a reasonable range of strength and activity, met 23 out of 25 National Coordinators in Cotonou, and discussed a range of issues concerning their organisation, processes, progress and aspirations. Members and National Co-ordinators were open and frank about their perceptions of the development issues, the Programme and their role, and were generally realistic about expectations. There is strong evidence of the Programme’s intensive training effort to strengthen NCU staff, both through seminars and workshops held at sub-regional level, and subsequent follow-up from RSU staff at each country level. Useful though rather uneven progress appears to have been made in developing their capacity. Many NCUs now include wider cross-sectoral membership, and represent a range of stakeholder levels, according to the implementation set-up and needs of the on-going community projects. Women are usually but not always represented, though in two cases (Ghana and Burkina Faso), National Coordinators are female. This profile of NCU membership is generally relevant to the Programme’s aims and is usually adequate to identify, formulate and implement community projects, and to identify potential entry-points and processes for influencing national policies.

- Recently, the RSU prepared the “Profile of a Model NCU”, which reflects views on what an NCU should become and do (see Box 1). The future of each NCU will depend on the SFLP’s capacity to support them to define a role for themselves in each country’s institutional environment, but also on higher political decisions not easily influenced and informed by the SFLP. Informally, discussions with RSU staff and others identified which NCUs had made particular impact at various levels, which were in a positive process of development, and which, for structural, national political or security reasons, were not able to participate in the Programme to the extent appropriate to deliver its development aims. The Mission’s evidence at this stage is that many NCUs are still tied up with SFLP processes and specific implementation tasks, and only a few are really beginning to think and operate strategically.

Box 1 - The Ideal NCU

Under the SFLP the basic responsibilities of each National Coordination Unit are:

- To maintain links with the National Government in order to facilitate changes in Policies and Institutions

- To establish and maintain a mechanism for the identification, examination and approval of proposed community projects.

- To establish links with local government bodies, community-based organisations, NGOs and donors in order to identify opportunities for poverty reduction.

- To inform decision-makers on best practices and lessons learned to influence policies and institutions.

- To assume any other responsibilities identified by the NCU, depending on the national context.

The essential features of an NCU should be as follows.

- The composition of an NCU should take account of the diverse nature of the institutions and stakeholders involved in the small-scale fisheries sector

- The NCU should be made up of active people who have the ear of decision-makers, and who effectively represent the various institutions which have an impact on the livelihoods of fisheries communities.

- The NCU should have a holistic outlook.

- The NCU should define a clear approach and establish the rules for participatory action.

- The NCU should expand awareness-raising and training activities to all NCU members, not only those from the fisheries administration.

- The NCU should create and promote working relations with technical departments, institutions and structures specialising in the fisheries and rural development allied sectors.

- The NCU should establish and build up broad contacts with grass-roots communities in order to encourage their real participation and ensure that they gradually take over responsibilities.

- The NCU should develop a lobbying strategy to inform partners, donors and decision-makers about the lessons learned from the implementation of NCU activities in the country.

From: Thematic Brief, RSU, Cotonou, June 2003

### Training on SLA and CCRF

- Training for RSU and NCUs staff and partners in participating countries on SLA and the CCRF has been one the major areas of action of the Programme so far. On the whole, 305 people of both sexes were trained on the SL approach in three languages, in relation to the methods of livelihood analysis at the community and individual level and subsequent identification of development activities and associated needs together with the means of implementation, monitoring and evaluation of results.

- The Mission sought to ascertain how the concepts of the CCRF and the SLA had been taken up within partner countries, and how their language, complementarities and synergies between them, are understood and expressed. The fundamental ideas of the CCRF are relatively straight forward and easy to explain practically, and encourage those in the sector to employ and develop locally a range of good practices to ensure sustainable and equitably distributed benefits from the resource, including where appropriate, agreements for trans-boundary resources. The CCRF was translated into a number of national languages and distributed at all levels, including fishing communities, and there is evidence of the positive impact of this in particular among fisher folk, where it connects well with people’s own sense of the appropriate ways to look after their resources and activities, and to develop stronger local responsibility. However, it does not appear to be seen as providing solutions to the very real problems experienced locally in poor catches, market constraints, conflict, and social deprivation. The visually compelling systems diagram of the SLA appears to have translated into widespread conceptualisation and understanding of livelihood capitals, vulnerability, policy, institutions and their inter-relations. The use of participatory tools, stakeholder analysis and livelihoods diagnoses, has also been adopted by the Programme’s partners and agents.

- The holistic nature of the SLA is widely expressed, though in practice less commonly applied, and this is associated with some confusion amongst practitioners and advisers about how the SLA would be applied in practice, and used as a development tool rather than simply a useful descriptive method and diagnostic tool. There also appears to be potential confusion in the way that the SLA and CCRF were presented, particularly in the Training Manual on SFLP prepared by the Programme, where descriptions and details are unnecessarily complicated, developing ‘compare and contrast’ ideas, and conveying the impression that it is necessary for key practitioners and indeed target communities to be fluent in the minutiae of the concepts. This risks losing the potential for explaining complementary and synergy between the Code, which is a globally recognized set of principles for policy making and action in fisheries, and the SLA, which is a framework for analysis and action in the context of development. It also creates the danger of establishing and/or reinforcing elite jargons, separating more educated service providers from poor and much less literate communities.

### Policies, Institutions and Processes

- Under this heading, two pilot and two targeted PIPs studies were carried out, together with a number of workshops on PIPs. This appears to have contributed very usefully to raising awareness at macro level, including government institutions, other donors and NGOs, on the importance of PIPs on livelihoods and on the links between micro-meso-macro levels. In some cases, PIPs were also addressed through community projects (Ghana and Senegal).

- Most importantly, the PIPs studies, together with the poverty profiling exercise discussed below, have had a significant impact at national government level in a number of countries, in raising the initial awareness of the level of poverty in the artisanal fishing communities and ensuring the inclusion of the artisanal fisheries sector into PRSP processes. In the long run, and assuming this leads to identification of the means to address these communities' needs, this achievement alone will be highly significant in focusing attention and channelling additional development funds to artisanal fishing communities.

Box 2 - Policies, Institutions and Processes

The term is defined within the SLA and describes the local and national context in which household and communities, their access to resources, their opportunities for activity, and their scope for economic and social welfare are influenced by socio-political and structural characteristics.  The process of change at the PIPs level is considered to be critical in developing and applying effective policy and in widening the scope of influence of specific development approaches, whether technical or social.

The purpose of the PIPs study within the SFLP is mainly to raise national awareness on interactions between policies and institutions and dynamics of poverty in fisheries, and to initiate a process wherein institutions and donors can go beyond their hitherto sectoral views in addressing poverty in rural areas. Within this framework, the NCU should play a catalytic role.

SFLP pilot PIPs studies aimed at testing and developing an SLA-based methodology to understand which policies and institutions impact most upon livelihoods and identify major PIPs entry points in Ghana and Senegal using SFLP possibilities.

Targeted PIPs studies, on the other hand, were carried out in Congo and Niger by conducting a participative institutional analysis in the context of improved SFL, to identify critical entry points to support concrete change in policy and institutions, including better integration of fisheries into PRSP processes.

However, PIPs studies are only a first step towards concrete changes in policies and institutions. In the countries where they were carried out, they raised many expectations, but close follow-up is necessary to accompany the process lest it will not be sustainable. A case in point is the integration of fisheries into PRSPs in Congo and Niger: respective NCUs will have to be supported to formulate the artisanal fisheries programme to be included in the national PRSP.

### Poverty profiling

- The goal of the SFLP being to reduce poverty, as well as to develop normative methods and tools to understand what and where poverty in artisanal fishing communities is, resources have been allocated in collaboration with the Support Unit for International Fishery and Aquatic Research (SIFAR) “to inform cost-effective beneficiary targeting and monitoring and evaluation within the programme”. The work has mainly centred upon the assessment of poverty levels in artisanal fishing communities and on efforts to ensure that such communities are included in national poverty alleviation strategies, fishery development plans and sector strategies. These activities use the SLA in their analysis and aim also at the inclusion of the artisanal sector into fisheries policies and strategies commensurate with the principles of the CCRF.

- A good number of useful outputs have already been generated, ranging from quantitative and qualitative poverty profiles for those countries participating, to a series of key-sheets and policy briefs on small scale fisheries and poverty, to relevant methodological guidelines and papers. However, the Mission has some doubts on the extent to which the outcome of the poverty profiles were actually taken in consideration in the formulation of the Pilot Projects, and whether the insights developed by the exercise have been properly taken up into practical approaches by the RSU and the NCUs. This is a very critical issue, as it is only by incorporating these perceptions into the SFLP process that credible and effective approaches can be defined and tested for alleviating poverty.

- In spite of these concerns, the poverty profiling initiative appears to be an excellent example of the ways in which FAO can interact with the SFLP and its partners to establish a key area of knowledge and normative strength. This is equally valuable in developing good methodologies for identifying at district and national level the significance and nature of poverty amongst artisanal fishing communities, and for recording changes associated with Programme or other development initiatives. Current plans to extend these exercises to develop comparative understanding of poverty processes in and outside the region will also have important potential.

### Small/community projects

- Since Programme formulation, a small-project fund was foreseen “to be used for low-cost, small scale poverty-focussed initiatives, some of which may later develop into pilot-project proposals”. In the practice of Programme implementation, what have been called for some time “Small Projects”, have been initiated to i) allow hands-on training in SLA for RSU and NCUs; ii) commence the process of interaction between communities and other agents and iii) in a number, trigger a local process of sustainable development and empowerment. Following the suggestion of an Information/ Communication (I/C) consultant, their name was changed to “Community Projects”, which more accurately describes their focus and helps to define their longer-term role. However, it remains necessary to ensure that the purpose of these projects is clear, as they are not simply about development support for specific communities, but about stimulating community-linked processes which can offer wider lessons. More specifically also, Institutional Support (IS) or capacity building projects are supported.

- By July 2003 fifty-two Small/Community Projects were under implementation. These operate in 20 of the SFLP partner countries, and one covers 5 countries (Study of the contribution of fish marketing to livelihoods in the countries of the Chad Basin). According to their thrust, they can be classified as follows: six on Institutional Support, including the above mentioned study; twelve on Organizational Development (training and capacity building at community level); twenty on Resource Use (small investment on fishing, post-harvest or diversification activities); fourteen on Resource Management (training on fishing, post-harvest, co-management issues). Budgets range from US$ 4,000 (institutional support in Nigeria) to US$ 25,600 (resource management in Ghana) and duration ranges from 6 to 18 months, with the possibility of extension or second round funding.

- Community Projects are identified and decided at the community level, through the use of the SL approach and conform to CCRF principles. IS or capacity building projects are more targeted towards specific objectives improving the effectiveness of institutions in addressing SL processes. At this level financial means or physical inputs are put at the disposition of the primary beneficiary by the SFLP or identified through other partners, to permit concrete results to be achieved which correspond to their key concerns and constraints. The NCUs elaborate the project documents and the Letters of Agreement (LoA), and identify partners with the support of the RSU. Implementation is usually entrusted to local NGOs, and communities participate to the budget with their own labour or contribution of local materials. The RSU Team Leader is responsible for the financial and technical endorsement/signature of the relevant LoA and their technical annexes. In general terms, quality of the project documents is weak, with very limited ideas about measuring change and impact, or use of key indicators, and efforts should be devoted to improve this.

- At the local level, the CPs cover a wide variety of issues (see Box n.3), and many appear to have been successful in mobilising community groups and engaging them in processes of self-realisation and the expression of needs, as well as linking these to the IS initiatives. Women are often involved and in some cases take a leading role in interactions, but gender is not often per se a key feature. Many project issues have been simple and practical, but the Programme has until relatively recently offered little practical support beyond limited initial inputs, with little foreseen to address longer-term processes of change. In some cases, access to wider options including micro-finance has taken place but this has not been an explicit aim of the SFLP, and its role in promoting this has not been significant.

Box 3 – Community Projects

Akpéyédjé marine fishing community, Benin

In this relatively isolated community on the Benin West coast, two CPs are presently under implementation. The first one is called “Regulation of beach seine mesh size” and its objective is to test at users’ level in Benin, Ghana and Togo, the performance of larger mesh-size beach seines and its impact on resource conservation (lesser pressure on juvenile stock) and on short and medium term economic returns to fishermen. Indeed, this CP was launched as a pilot experience to test possible alternatives to the radical banning of beach seine in Ghana, this being envisaged out of resource conservation concerns. SFLP provides the new beach seine to a group of fishermen in each selected community. Quantitative and qualitative harvest data are recorded with the help of a surveyor from the Ministry of Fisheries. Results so far are mixed: on one hand, only more adult fish is caught, with a positive impact on stock reproduction capacity. On the other hand, the lighter beach seine speeds up hauling work and allows a second trip per day, increasing thereby stock exploitation. At the same time, present catch seems to sell better because of the larger size of fish, and overall income has not changed, but supposedly this might not hold true for more remote markets where purchasing power is very low and buyers cannot afford paying more for fish.

The second CP in the community is “Support to development of alternative activities” and aims at starting alternative income generating activities in and out of the fisheries sector. Alternatives under testing are oyster raising and sale of coconuts, and both are under the responsibility of women in the community. A revolving fund was set up with financial support from SFLP, as start-up seed money. Activities have just begun and no other analysis or conclusion is possible so far.

Overall, the two CPs are tackling resource conservation and poverty alleviation issues in a complementary way. In both, activities are still at a too early stage to draw more definite lessons or conclusions, but there is undoubtedly potential for bringing other partners into the picture to solve other problems in the community (lack of fresh water, difficult access to the community, etc.). Also, scaling up experience should be feasible, in particular for the beach seine to inform future policy at the sub-regional level on resource conservation.

Total funds for both projects amount to almost US$ 34,000, and beneficiaries’ contribution corresponds to 13% approximately.

Box 3 - cont.

Moree fish processing: women’s oven construction and community woodlot initiative, Ghana

In this relatively important town on the Ghanaian coast, the Programme has been working with fish processors members of an already existing group within the community. The objective was to secure access to fuel wood and increase the working capital of the women’s group. Activities included the cultivation of a woodlot, the construction of energy-saving Chorkor ovens and providing credit through the local rural bank to expand fish processing and marketing activity. The Programme assisted also with the technical assistance for oven construction, and with inputs and transport cost to plant the woodlot.

- The Mission feels that the Programme management tended so far to undervalue the community projects in their potential for achieving wider Programme objectives. They are indeed small and dispersed and to date whilst using some as success stories, efforts to promote, fund or identify resources for replication do not seem to have been prioritised. However, the Programme has now invested considerable human and time resources to identify, design and implement the CPs, and the quality of approaches appears to be steadily improving, with far greater attention to developing local partnerships in the early stages. Given also that in 13 out of 25 countries these will be the only SFLP activities aimed directly at the intended Programme primary beneficiaries, there is considerable scope for strengthening on-going projects, for replication of successful experiences, for widening the range of issues and themes critical in policy development, for their use to inform policies at national level, and to formulate future investment.

### Pilot projects

- By the time the Mission was fielded, the first Pilot Project (Improvement of the Policies and Institutions for Co-Management in Inland Waters in Burkina Faso, Mali, Ivory Coast and Ghana) had already started (April 2003) with the transfer of the Coordinator from the RSU to Burkina Faso. The other two PPs, one on post-harvest activities and one on coastal management, were submitted in draft to the Programme Steering Committee (PSC) on July 9th meeting, to which the Mission took part as observers. These were approved after minor discussion and with some recommendations proposed to be incorporated. The budget for each PP is approximately US$ 3 million, and they are planned to last 3 years.

- The Pilot Projects focus on broadly important thematic grounds. They involve a range of stakeholders and aim to build regional partnerships and perspectives, and two of them are oriented towards resource management and more general fisheries management on a participatory or co-management basis. These also conform broadly with the SLA and the CCRF principles. However, whether the true and immediate impact will be for the primary beneficiaries or the secondary beneficiaries in the shorter term is not clear, and the Mission has broad concerns on the quality of the project designs. While the consultation processes and the ownership of the projects by partner countries and their institutions is very important, and indeed a significant and potentially very positive departure from much previous practice, this does not remove the need to ensure clarity and focus.

- Pilot Project documents made available to the Mission appeared to have a number of deficiencies with respect to aims, structure, processes and normative value, with limited prospect of generating either effective and sustainable capacity, or significant evidence-based policy lessons. The regional justifications were also poorly developed, though there is obvious scope for improvement. Regarding the Pilot Project on Post Harvest, the Mission had not seen the overall strategic framework, and therefore was able to develop only a partial understanding of the overall coherence and purpose of the initiative, as well as of regional justification and normative value. A first impression is that as a large proportion of activities and desired results of the project concern Ministries other than Fisheries, and their commitment and involvement is not specifically apparent, they may prove harder to achieve in the project timeframe. While such a cross-institutional approach may well be valuable, a strategy should be evident for its achievement.

- As noted earlier, the promising CPs could also have evolved into pilot projects, and while not every opportunity could have been taken up in these, some apparently promising directions seem to have been missed. An example would appear to be the  Participatory Coastal Surveillance initiative in Guinea, which showed promising results at the level of one community. Given the importance of this problem along most of the regional coastal line, and the impact that tackling this issue could have on sustainable fisheries management, on developing effective co-management plans and on fishing communities livelihoods, it was surprising that this was not further strengthened and up-scaled through the Coastal Management Pilot Project. Alternatively, had there been constraints to doing so, it was equally surprising that these were not set out and addressed, as the example is currently represented as being a success.

### Organisation Development

- This sector of intervention has been included into the SFLP implementation strategy once the need was acknowledged for a methodology approach and relevant training on this topic. Organisation Development (OD) is defined by the Programme as a process approach in which “a client system and a consultant/accompanying organisation system engage with community organisations working towards social and developmental change that will assist organisations to strengthen themselves and improve their performance.”

- Activities consist of on-the-job training for NCUs and partner organisations, elaboration of an OD guide, exchange visits between NCUs, and integration of OD into the implementation of CPs. Results at community level are apparently encouraging, though the guide is still at a very preliminary draft level. There is no clear evidence however, possibly due to the recent inclusion of this field of activity into the SFLP plan of action and its preliminary stage of implementation, that indicators have been identified to measure the intended outcome of this area of action or to consider how changes would impact in practical terms on the function and performance of the various agents within the SL context.

### Monitoring, reporting, information and communication

- Monitoring in the context of the SFLP was apparently among the first concerns of the Programme, through the support of a consultant and a guide on this topic to the RSU at the end of 2000. However, monitoring and reporting appear to be developing in ways which are both burdensome and uninformative, and this trend appears to be increasing as new projects come on stream. The RSU meets DFID quarterly reporting requirements somewhat in excess, with the production of over-detailed and lengthy reports. A large and complex work-load appears to have been placed on Programme staff, without necessarily guaranteeing that the key issues of the Programme’s impacts and wider lessons will be defined in the process.

- At the same time, NCUs interpret monitoring as the production of activity reports, often in addition to NGOs activity reports, which however do not provide useful information on the results, not to mention impact. In spite of the amount of information produced by the Programme, its overall relevance to monitoring of results and impact is very doubtful.

- The absence of livelihood impact – though admittedly perhaps too early for this to be measurable - or indeed of a strong engagement in wider development processes, leads in much of the Programme’s current products to rather sterile accounts of meetings or alternatively rather unsubstantiated claims of success. These issues can be addressed but need a clearer perspective and more practical outcomes, as few development partners can ultimately be convinced of impacts measured primarily by process and much less by real and sustainable changes in livelihood.

- Participatory monitoring is for the time being only at the stage of lip-service, and there appears to be considerable uncertainty about how this is to be carried out and for what purpose. Only recently has the Programme started introducing the concept of community/group level self-evaluation and re-planning sessions, and apparently only in one country (Nigeria). There may again be substantial risk of these exercises generating a lot of work for both the communities and the project and its associates, without any practical outcome beyond being able to say that it is being done.

- The importance of communication is appreciated by the Programme: the activities under the Information and Communication (I/C) component range from planning workshops, the elaboration of a communication strategy, the regular production of InfoFlash and Liaison Bulletin, the set-up of the SFLP web-site, etc. There is evidence that both InfoFlash and the Bulletin reach different and widespread audiences and are well appreciated, though more thought should be given to the nature of the messages conveyed and their immediate and consequent impacts.

- Overall, in spite of the support provided through a specific consultancy on communication strategy, there seem to be insufficient attention to identify priorities and focus in terms of targeting and contents. As a case in point, the Programme has not invested so far in the production of information material to be used at the level of fishing communities, though there seem to be plans to start activities on this aspect. Furthermore, there appears to be little strategic sense of what specific messages need to be applied, and with what evidence base, to influence key changes at national and regional levels, and amongst partners and development investors.

## Government Support

- The requested national financial contributions consist mainly in providing basic logistical support as and when required, including staff to operate the National Coordinating Units and the Project Management Committees in the case of Pilot Projects. The Government of Benin committed to and made available office accommodation in Cotonou for the RSU.

- Good levels of government support were broadly observed through the Programme, though constrained in some instances by political and economic difficulties. In many cases the NCUs received positive support in the form of allocating staff time and access to facilities, and in some cases providing budgetary inputs.

## Project Management

### Structure and operation

- The SFLP is an international programme, according to FAO definition and geographical divisions, as participating countries are under the responsibility of two different Regional Offices (the Regional Office for Africa, responsible for 24 countries, and the Regional Office for the Near East, responsible for Mauritania). In consideration also of its ambition and potential to contribute to FAO normative work, it was agreed that it should be based in FAO HQ, so as to facilitate exchanges of lessons learned and feed back into policy development. In the Fisheries Department, the SFLP comes under the Fisheries Policy and Liaison Service (FIPL) inside the Fisheries Policy Division (FIP).

- The Programme is structured in that strategic development methodology and associated institutional change is to be addressed by a Project Co-ordination Unit attached to FIPL, practical programme development and co-ordination roles is carried out by a Regional Support Unit in Cotonou, and national processes are to be promoted by National Co-ordinating Units in each of the 25 countries. A Senior Officer at the FAO Regional Office in Accra holds a liaison role with SFLP and FAO Representatives are in principle only involved with the SFLP through provision of minor administrative services in the countries concerned. The planned administrative management of pilot projects from the PCU, and the siting of PP Coordinators in one of their participating countries, will potentially add to the Programme’s structural, operational and managerial complexity.

- However, in spite of the initial mandate and the institutional siting of the Programme, the involvement of FAO and FI in the SFLP, in their respective roles of facilitator for informing national policies, source of expertise and backstopping, or as a recipient of SFLP experience, has been very weak so far. This is an important concern as it impacts on a significant area of the project’s potential and on the longer term effectiveness of future partnership arrangements.

- This lack of communication with FAO has also had a direct effect on the morale and performance of the RSU staff. Although they perceive themselves as FAO staff, they feel they are not receiving from HQ what they consider to be a necessary and potentially enriching backstopping support. There also appears to be conflict between their experienced and personal understanding of the needs of communities and their policy environment, and the constraints imposed within the Programme, which cannot be resolved through wider discussions, whether with FAO counterparts, or in the wider development community.

### Steering Committee

- The performance of the Programme Steering Committee (PSC), as determined by its record of activity and decisions made, appears to be acceptable, but delays in Programme implementation, including staffing decisions, particularly since the latter part of 2002 must be questioned. This is perhaps a result of an apparent absence of mechanisms for agreeing action points and timelines, and for monitoring progress by the PCU and RSU, but this also points to operational deficiencies. The Mission’s observations of the PSC’s actions in practice in Cotonou, at least on the occasion concerned, suggested that engagement was more formal than participatory, with little in-depth discussion of key areas. This applies also to the missed potential contributions for example from the FAORAF representative in the PSC.

- It is expensive in time and resources for the SFLP and its contributors to have these meetings, and thus it is important to make sure they represent good value. It is important to note that they can also be a valuable learning ground for participants, and a prime opportunity for structured engagement in discussion and debate. Future approaches should operate with clearer agendas, with much more stimulus for discussion, and opportunities for RSU, NCU and/or others to make key presentations and seminars. The current observer status of FAORAF could also be changed to a more active role, and other individuals invited as observers or resource providers. Development partners such as IFAD, international and national NGOs could also take part, in a wider open sessions for communication, while small closed session can easily be set aside for truly confidential purposes.

### Task Force

- The Task Force was established according to normal FAO Field Project procedures, and in a departure from more traditional approaches, applying the principles of participation and process, it was given the opportunity to develop its own specific terms of reference and mode of operation to meet its expected generic responsibilities. That apart, however, it appears that communication and interchange with Programme has subsequently been very limited, and a degree of mutual disregard appears to have developed, fostered on one part by the view that the Task Force was primarily assembled for mandatory reasons and has neither the time or interest to get involved in the Programme, and on the other, that the Programme wishes to restrict access and information, and would not accept much debate of its approaches or priorities, or practical engagement with FAO expertise and normative initiatives. Considerable frustration appears to have built up on both sides. This view was reinforced by the circumstances of the MTE itself, but very positive feedback during the debriefing presentation showed clear evidence both of the benefits of the TF if it is properly engaged, and the very real prospects for using it as an important mechanism for testing and mainstreaming Programme approaches and findings.

### Management and implementation

- An underlying element for many of the deficiencies in the practical aspects of project management and implementation is the lack of structure and rigour in the strategy and implementation of the Programme and projects themselves. While it is admitted by SFLP staff that ‘participation and process approach does not mean laissez-faire’, there appears to be either a reluctance to introduce good practice in the process of problem formulation and development response, or perhaps more worryingly, a lack of awareness of quality, perhaps reinforced by too isolationist an approach. To accept either of these is however to betray the interests of the community the Programme claims to serve.

- These observations cannot be separated from issues of the Programme’s management. A combination of over-rigid interpretation of aspects of the SFLP's approach, a reluctance to engage partners in communicating and debating areas of development within the Programme, an over-dependence on describing process rather than outcomes, and a lack of critical perspective on the Programme’s development has not served the Programme well. There have also been substantial and unexplained delays in completing key documents and clearing various reports and Programme outputs, including OPRs. It has been difficult for the Mission to avoid attributing much of this to management approach and style. While some aspects of this may relate to inconsistencies between the Programme strategy and the terms of reference of senior management, there is a definite weakness in terms of strategic vision in Programme implementation.

# Assessment of sustainable effects and impact

## Effects and Impact

### The application of the SLA and CCRF

- The SL approach is a refined analytical approach, encouraging reflection and expression of opinion on all factors, issues and opportunities influencing the day-to-day and future existence of individual and community livelihoods. This takes into account, and encourages, discussion and dialogue on policy and institutional matters emanating from national government, issues over which communities felt they had no control, nor indeed any real right to intervene in the past. Effectively this opportunity to intervene, as opposed to just discuss, is also the result of the democratisation process, which is evolving within the region, and the willingness of the policymakers to listen. Thus whilst the SLA is an appropriate tool, if it is not fully integrated at the policy making level and if resources are not available to satisfy the needs and aspirations of primary beneficiaries it could prove counter productive.

- The importance of building capacities and strengthening national institutions and Community Based Organisations (CBOs) cannot be overstressed, and the SFLP has the potential to perform an important role in this respect, by filling a too long neglected aspect of fisheries management and fishing communities’ livelihoods. The application of both SLA and CCRF and the focus on human and social capital development, are proving already visible positive achievements at different levels. Still, the Programme is coming short of expectations in connecting these changes with the wider processes of livelihoods improvement and poverty alleviation, which require involving both sustainable management of the resource and economic opportunity development.

### Strategic technical issues

- While the Programme has identified many of the technical issues directly impacting artisanal communities and their resource access, a number of issues require to be further addressed. Strategically, market, resource and policy interactions with industrial fisheries, though essential in the sectoral perspective, have been largely unexplored. The significance of markets and international trade issues is particularly important in understanding the dynamics of the sector at all levels, and justifies more attention. Regionally, the role of aquaculture is relatively insignificant, but is changing. It also has targeted roles in enhanced fisheries, food security, livelihoods diversification and income generation. It will therefore be important to recognise potential interactions in supply, livelihood opportunities, post-harvest and market implications.

- Co-management in inland and coastal waters has been widely promoted as an element within both Community and Pilot Projects, and within wider policy discussions. While the ideals are beyond doubt, and there is valuable potential in the right circumstances, there are many practical and biotechnical issues to be addressed, though very little apparent recognition within the SFLP of their existence or importance. There is a growing body of work in this area internationally, within which both DFID and FAO amongst others have played leading roles, and there appear to be few connections. To enter this critical area without foreknowledge and practical approaches could be considered irresponsible and even potentially destructive of the interests of those who the SFLP aims to support.

### Wider impacts

- Wider awareness has been raised through NCUs by the Programme, and targeted studies on PIPs have been influential in this process. At the level of Ministers, Senior Cabinets and Fisheries Directors, knowledge about the Programme and its approaches is typically present, but engagement is at best partial, not surprisingly perhaps in awaiting evidence that the SFLP is generating real change, and its principles and methodologies are well enough validated. In particular, practical and substantiated policy lessons from local/community level processes need to be developed to connect with national strategies and policy development. Valuable progress has been made in engaging with the PRSP in some countries, but it would need to be more targeted to ensure not just that sectoral poverty was acknowledged but that alleviation processes could be described and activated. Economic valuation studies concerning the resource and its use, covering market and non-market goods and services would be important, have been drafted but currently seem to be stuck, with little input either from the considerable body of work in these areas being generated elsewhere. However, other links such as the FAO-FIP-SFLP macro-economic modelling of poverty and small-scale fisheries are extending awareness more widely.

- At the same time, whilst fisheries and staff of other ministries, NGOs and resource persons participating in the NCUs are fully supportive of the approach and have been trained in its use, it is not clear to what extent they are in a position to influence the Ministers themselves, or their senior advisors, on strategy and other policy issues. In many cases this seems unlikely, as often NCUs’ location within the Fisheries institution, as well as their present capacities, do not allow the necessary breadth of vision and scope to influence national policies, which should be their thrust for the next Programme phase. This is precisely the level of influence that has been missing in early development strategies, including those using PRA at the community level, but with no further linkages. It is therefore a key element if this Programme is to have the desired impact and long term sustainability. Further, unless political will exists and precise strategies are defined, it is difficult to see how some NCUs will ever have much potential to transcend a fairly narrow and institutionally constrained range of functions. Thus it will be essential to ensure additional and higher levels of intervention during the remaining project period to ensure sufficient impact of the Programme and its PIP component on policies.

- Intermediate connections between the macro level and communities, passing through meso level institutions (local and district government, line ministries, NGOs) are required for livelihoods to be improved and sustained on a broader base and the need to develop these links is recognised and well understood within the SFLP and its stakeholders. SFLP is clearly now devoting many efforts to the development of these links. This process is clearly facilitated in those few countries where decentralization processes are on-going or are well advanced, in particular for the micro-meso link. However, it should be noted that in most partner countries it is invariably not a question of re-allocating resources, financial or otherwise, to satisfy the basic needs, re-defining policies and strategies required to improve livelihoods and provide basic facilities and infrastructure, but a question of finding the resources, possibly externally, drawing up policies and strategies which had not existed before, approving them and then implementing them. In real terms these demands risk going substantially beyond the time frame of the present Programme before tangible and widespread improvements to livelihoods will be seen.

- The development of micro-macro level links is more difficult and there is not always too much direct scope for doing so. However, there seem to have been some missed opportunities for influencing the macro/policy level, by not pursuing more attentively and thoroughly some promising local level activities and deriving key lessons (e.g. MCS in Guinea, women’s group wood-lot in Ghana), though the Mission recognizes that many CPs are just now starting to show results. Here of course, a critical body of evidence, accurately defined, monitored and reported, is necessary to properly inform and influence policies. However, so far, the Programme does not seem to have established an effective strategy for doing so, and at this stage there is little evidence in the Pilot Projects, with the possible exception of the Inland Fisheries project, that they will be able to provide the relevant information.

### Partnerships

- Development partnerships at all levels, from local CBOs with national and international NGOs, to wider agreements with bilateral and multilateral donors such as IFAD, AfDB, EU, are a critical need and show promising leads in some cases. In a number of countries, other partners, including national and international NGOs and other donor funded programmes (e.g. AfDB in Guinea, community social infrastructures) are now working with fishing communities, until then largely ignored, and engaging them in meeting needs identified during livelihood diagnostic exercises. These mostly include household and community issues of water supply, sanitation, health and education, not met directly by the Programme. However, with a few exceptions (e.g. World Vision in Ghana and Oxfam Québec in Benin), these links often appear to arise more incidentally than by intent. Without such links, and where conventional public sector resources are commonly lacking, this can unfortunately result in communities of poor people, without more tangible means of development, being “organised and empowered” by the SFLP and expected to gain the strength, confidence and resources to promote changes by themselves.

- It is critical and urgent to re-orientate the Programme to tackle these problems, given both the need for development investment to achieve the Programme’s main objective of policy development linked with tangible livelihoods improvement, and because of the length of time required for engaging with other donors’ strategic Programme formulation and securing their funding commitment. If no action will be taken the SFLP, through the absence of support to meet concrete and practical needs of individuals and groups in fishing communities, such as access to finance and inputs, will come short of its mandate and of the expectations it raises at all levels. This unfortunately concerns mostly the intended primary beneficiaries, the fishing communities, as Programme implementation so far has privileged institutions over communities, and with a few exceptions, government institutions have become the present primary beneficiaries, both in terms of activities and budget.

- As earlier noted, links within FAO, in particular at the level of the Fisheries Department, have been poor, and notable primarily for inadequate communication and missed opportunities on both sides to develop fruitful reciprocal exchanges with relevant technical services. As a consequence, the Programme is also coming short of its ambitions to influence FAO policy development and normative work, with a negative impact also on both the morale of the RSU professional staff and on the quality of a number of the Programme’s outputs to date. The in-house Task Force has never been able to develop effectively, even as a forum for information exchange. Lastly, though some FAO Representatives have been supportive in practice, their potentially significant scope for impact does not seem to have been realised, and neither have the TCP funds been properly explored as a means to complement activities at country level.

### Regional and inter-regional impacts

- Finally, the regional and inter-regional strengths of the SFLP are yet to be developed fully, though pilot projects, steering committee meetings, and regional workshops are useful vehicles for promoting interchanges and wider collaboration. There have been useful contributions to CECAF and CIFA, and discussions have been held with the regional programme of Worldfish, the CGIAR institute for fisheries and aquatic resources, with which there are important potential synergies. A particularly notable achievement is the feedback from SFLP experience to date in the FI paper “Strategies for increasing the sustainable contribution of small scale fisheries to food security and poverty alleviation”, which was presented at the 2003 COFI meeting and was endorsed by this Conference. However, in terms of practical policy development, there appears little at this stage to suggest a genuinely strategic perspective on supranational issues.

## Environmental Impact

- It is too early to consider environmental impacts in a broad sense, though the SFLP’s objectives relate clearly to the more effective management of aquatic resources. As well as addressing direct issues concerning fishery stocks and their management, related elements such as the supply and conservation of brush and mangrove wood supply, and representations to limit impacts of external sources of water pollution, might also be expected to provide positive environmental impact. The programme also supported an APO position to assist the RSU in awareness-raising for effective environmental monitoring amongst the National Coordinators in relation to the SFLP monitoring framework. However, in other areas, the Programme appears not to have considered wider implications of its activities. Thus where increasing beach seine mesh size may reduce the catches of smaller species and under-sized stocks, their greater ease of use may significantly increase fishing effort. In other aspects, a focus on fuel efficiency in smoking operations does not seem to be accompanied by particular concerns for handling and hygiene practices, or by general maintenance of landing and processing areas, thereby increasing risks of poor waste management, contamination, food safety and wider public health impacts.

- The Programme’s ultimate directions are towards policy that will in itself create sustaining processes and ensure in doing so that natural resource and environmental issues are appropriately addressed. However, as in other areas the Programme aims to develop, much more will depend on policy implementation, and hence the effectiveness of linkages between community activities and national perspectives. Unless communities see the potential for access to better livelihood inputs, they may have no choice but to persist in activities which they know to be damaging in the longer term but which at least provide for essential current needs.

## Social and Gender Equity in Project Implementation and Results

- The Mission has no clear evidence of the Programme capacity so far to involve and give voice to the different social groups through SL analysis at community level, or about its capacity to avoid discrimination or reinforcement of present inequalities in the context of the Community Projects. The Poverty Profile Study provides in principle the baseline data against which the Pilot Projects performance and impact will be measured, but it is too early to assess this aspect.

- Indeed, gender and poverty targeting, though mentioned in various SFLP documents, and clearly essential elements in overall development performance, appear to be much less prominent in the Programme’s practical engagement and partnership influence. Very few institutional stakeholders appear to be aware that both require to be identified, and then addressed concurrently if wider goals are to be achieved and more holistic livelihood gains are to be realised.

- Gender is so far the single aggregated element taken in consideration by the Programme. As noted earlier, in West Africa, women have the full responsibility for post harvest fish handling and in some cases also, for financing fishing activities. Though this gives them more visibility, in most countries this does not imply a corresponding recognition of women’s voices and needs in local decision making processes and in national legislative frameworks. This means that targeting women in such a programme should not be difficult in terms of activities aimed at improving the sub-sector, but also that support to the different socio-professional groups might risk endorsing or strengthening the actual patterns of unequal access to resources or burden with extra activities only one of the two groups at stake, if a gender analysis framework is not used and applied.

- The Programme has recruited so far two female professional staff: one Associate Professional Officer, expert on coastal management who also worked on poverty profiling, and one of the two Project Officers. The latter also took the responsibility for the elaboration and follow-up of both the gender strategy and the Organization Development strategy for the SFLP.

- RSU staff claim that the SLA does not explicitly include gender analysis, and this has been the main cause for its neglect. However, the marginal level of attention paid to gender issues in the whole of SFLP, from formulation to implementation, is very surprising exactly because of the focus of SLA on people, on strengthening their assets, capabilities and social capital and on their empowerment at large.

- The two OPRs (2001, 2002) had both called attention to gender issues, among others, as being a particular weakness and recommendations were formulated. A gender study was carried out from November 2002 to March 2003, and a guide is under preparation. However, few initiatives so far in the context of CPs and PPs, aim at tackling strategic gender needs, such as literacy courses, which however are widely asked by women in most communities the Mission visited. Some allocations for literacy courses are included in the Pilot Projects, although without clear specification about who the recipients will be, and in some cases even subject to the identification of partners for funds.

## Project budget, rate of expenditure and cost-effectiveness

- DFID contribution to SFLP as per the MoU between DFID and FAO is set at UK ₤ 21,547,660, which at the time of signature corresponded to US$ 35,324,033. Due to fluctuating exchange rates, this figure is currently revised to US$ 33,311,021. At the end of 2002, total SFLP disbursement was US$ 11,169,455 corresponding to 32% of the total budget. Detail of budget allocation is as follows.

- The Pilot Projects will absorb US$ 3 million each, 16% of which (500,000 US$/project) is earmarked for coordination purposes. Therefore, 22% and 4% of the total Programme funds will be used respectively for PP implementation in 12 countries (US$ 7,5 million) and for their coordination. Differences in presentation of budget breakdown do not allow a comparison among the three budgets, or a clear distinction between field activities, running costs, etc., with the sole exception of the PP on Coastal Management.

- Field activities other than Pilot Projects, including community projects approved by the RSU and managed by the NCUs, are allocated US$ 4,044,902, or 12% of the total Programme budget. Training is earmarked US$ 856,363, or 2% of the total.

- Other sub-programme entities approved and managed by the PCU amount to US$ 1,481.806 or 4% of the total Programme budget. This figure includes among others the Poverty Profiling exercise, and other normative and policy activities. The PCU also disburses funds to NCUs for their own management and other contracts, for a total of US$ 1,078,652, or 3% of the total Programme budget.

- Staff, consultancies and travel expenses absorb, as expected, a large part of available resources: US$ 14,773,449 or 43% of total budget (respectively 28%, 5%, 10%). The figure for travel includes staff, consultants and NCUs travel costs, with the latter absorbing about 60% of all travel expenses. It should be however reminded that all coordination, training and backstopping activities carried out by the SFLP are paid for through salaries, fees and travel costs.

- Running costs and equipment, including vehicles, computers for NCUs, etc., absorb US$ 1,116,722, or 3% of the total budget, and FAO support costs correspond to 7% of total budget.

- The Mission notes the discrepancy between the Programme expenditures to the end of 2002 (US$ 11 million), and the value of investment reaching so far the intended primary beneficiaries, in the order of US$ 920,000 (8%). This indeed reinforces the Mission’s concern about the shift between primary and secondary beneficiaries mentioned earlier. At the same time, it recognises that as a regional Programme covering 25 countries, the SFLP requires important resources for its coordination and overall management, especially during its initial years, but has also allowed attaining a level of sensitization, awareness-raising and capacity building at the regional scale which could not be reached through smaller sub-regional, not to mention national, projects.

- Finally, the Mission acknowledges that financial reporting for the SFLP is a complex issue, as it involves budget reporting from 25 countries plus two coordination units, transfer of data from FAO Field Administration System to Oracle, a different reporting system for DFID, etc. Thus, a more detailed breakdown is not available, distinguishing funds allocated for regional coordination and PCU/RSU equipment, and initiatives of no direct and immediate benefit to partner countries (e.g. SFLP brochure) from funds accruing directly to the primary and secondary beneficiaries in the partner countries. Only for PP is this in principle feasible, as 16% of each PP budget is earmarked directly for regional coordination. At the same time, it could be argued that all coordination activities are sine-qua-non investments for the SFLP to attain its goals. This means that member countries will benefit on the whole of a figure ranging between 44 and 52% of total Programme budget.

# Conclusions and Recommendations

## Conclusions

- The SFLP has made a useful organisational impact at this stage of its development, and has made progress in raising awareness at community, CBO, NGO and public sector level concerning the principles and practices of the SLA, and in setting out the broad objectives of the CCRF. A good number of activities have been carried out, and many more are on-going. Several national PRSPs in the region have now included artisanal fisheries in their scope of concern. More than 50 Community Projects are now under implementation and may provide good evidence on how to improve livelihoods of fishing communities, and three Pilot Projects have been formulated through a participatory process and have a good potential to provide useful lessons on issues of regional relevance.

- However, while recognising the conceptual and methodological importance of the Programme’s approach and indeed the great potential of adopting a wider perspective to poverty alleviation, the Mission has practical concerns for the SFLP's strategic effectiveness, in both structural and operational terms. This is reflected both in the documentation underpinning the process approach employed to develop the Programme, and in the concepts and priorities shown amongst the Programme’s key actors. The Mission is not convinced that the SFLP as it currently stands will attain all its stated outputs, and on the contrary, it risks coming very short at least of Outputs 4 and 5, which aim directly at the improvement of fishing communities’ livelihoods. As a consequence in turn, its purpose/development objective would not be effectively attainable, and its potential for wider influence would be seriously compromised.

- It is simple to suggest in the Programme's economic evaluation that benefits of more effective policy, in avoiding declining output, will greatly exceed costs. While such benefits (and possibly also enhancing value delivered to communities) can indeed do so, changes in policy need to lead to outcomes before benefits can arise, and many risks attend the process of policy change and effective implementation. These risks need to be clearly expressed and the means to avoid or mitigate them identified. It will be essential to ensure that reliable processes of change can be implemented, that effective connections can be made between stakeholder levels, that wider investment and development partnerships are promoted, and that the lessons learned are based on evidence and debated widely.

- Nevertheless, the SFLP has real potential to demonstrate significant impact, and if well developed could stand as a landmark initiative, reflecting well on its key partners and offering valuable gains in development understanding and impact, addressing relatively complex areas of natural-resource linked poverty alleviation. Though not every country can benefit in the same way or to the same extent there are excellent opportunities at most levels. There is much that is good about the Programme, and clear opportunities to make it much better. However, current constraints must be removed.

## Recommendations

- The next phase of the SFLP will need to shift increasingly from activity and output level to immediate and development objectives (purpose and goals). Management and stakeholders alike need to understand this and reflect on the nature of challenges that this brings. The Programme needs to deliver real and substantiated outcomes at community level, and will need a well developed approach and institutional partnership to do so. The greatest long-term impact of the SFLP will arise through wide and full ownership, with development partners and within countries. The SLA should not be dogma, rather applied with skill and insight in a range of contexts, within definable development processes. This will also generate far more useful development knowledge. In order to be applied through a wider forum, the SFLP needs to be genuinely open and participative, with wider networking, and links with other multilateral and bilateral initiatives, including DFID and other programmes, CG centres, EU programmes, plus investment agents.

- The initially intended thrust for the SFLP to interact with the Fisheries Department and FAO wider normative aims, and its potential to fulfil this role, argue clearly for shift to a different position inside FI. A possibility could be at the ADG co-ordination level, with senior FI staff in greater contact, and opportunities to gain mutual benefits during this stage. The FI and FAO RAF technical advisory role should be enhanced, in particular to provide support to the RSU team. FAO Country Representatives should have a specific role in upper level national co-ordination and policy advice.

- The SFLP Task Force interactions need to be revitalised. The Terms of Reference developed by the Task Force are still relevant, and should be activated for a more open process of collaboration and interaction. Opportunities should also be sought to create open sessions and seminars to allow wider access to the perspectives, issues and findings of the Programme. Task Force membership could also be reviewed where appropriate to ensure that it is widely representative and well motivated, and separate working groups, with participants outside the Task Force if appropriate, could be considered to support and interact with key implementation areas such as individual Pilot Projects.

- The PCU should rationalise its administrative functions and its leadership should have a far clearer communication and advocacy role, promoting debate in development ideas, sharpening focus on key issues and developing wider links to share outcomes. The two other Pilot Project coordinators should be based in Cotonou, to avoid diluting the RSU’s capacity and provide stronger backstopping from the RSU team. ToRs for PCU and RSU staff should be revised as soon as possible, linking with FI and FAO-RAF staff, with subsequent adjustment of staff, according also to their availability up to the end of the Programme.

- The SFLP needs to build on the successes of its proactive initiatives, at a range of levels, linking these as effectively as possible. There is a need for flexibility in adding value, to improve connectivity and impact. Applications range from strengthening and widening community processes, improving micro-meso-macro linkages, exploring and developing policy issues, to engaging with development investors from local to international levels to enter planning and programme cycles. In particular, attention could be given to develop links with micro-finance institutions and propose specific credit packages suitable for artisanal fishermen and fish-processors, as well as with the private sector for identifying and developing national and international marketing ventures.

- National strategies and NCUs are a key priority. The SFLP should work with NCUs and linked national agents, including higher level agents and processes, ideally in conjunction with PRSP implementation strategies, to develop national level sectoral approaches with defined poverty alleviation outcomes. As part of this, the current and future role of NCUs should be developed, and investment strategies defined. Greater interaction with FAO Representatives could also be valuable not only in developing strategic perspectives, but in making better use of TCP and other funding opportunities.

- New Community Projects should be identified, formulated and implemented, and promising on-going projects strengthened with partners’ contributions or where necessary with direct funding from the Programme. Projects should be grouped in one or more clusters to simplify administrative demands and establish a comparative/lesson-learning framework, and should whenever possible be connected with other development partners. In all cases, measures should be improved to avert social exclusion and support strategic empowerment processes, in particular along lines of gender, poverty and age.

- The quality and coherence of the three Pilot Projects require to be upgraded, building from successful experiences from community projects; improving measures to avert social exclusion and supporting strategic empowerment processes, in particular along lines of gender, poverty and age. The regional focus should also be improved, clarifying key thematic issues and outcomes, and logframes should be developed more accurately. This should be done in collaboration with FAO HQ (e.g. with the SFLP Task Force) and carried out as a learning process with RSU and NCU partners. To avoid delaying start up of the Pilot Projects and curtailing their duration, this should be carried out immediately in their inception period.

- There is an urgent need to clarify the areas where knowledge is expected to be developed, and how lessons are to be learned so that policy is evidence based and impacts of CCRF/SLA processes can be described. This does not require a rigid quantitative framework but should pick up current best practice in related fields. Connections with other areas of knowledge should be better established and wider links made with research resources in the region and elsewhere. Participatory monitoring and indicators should be carefully developed to ensure they are relevant, efficient and meaningful, and administrative reporting should be reduced to the minimum consistent with good practice. It is important also to establish primary indicators of Programme progress with suitable milestones. Given the complexity and the importance of this issue, the Mission recommends that a highly qualified support be made available to the RSU. This could be in the form of a 6-8 months consultancy, to be organized with three to four field visits distributed over 12-24 months, or through an overall agreement with an international level research institution which can offer similar services.

- An operational strategy should be developed for information and communication identifying which stakeholders the Programme needs to reach, what messages it needs to convey, and how these are to be conveyed. Indeed, I/C should be the mechanism for diffusion of the experiences and lessons learned through Programme activities and identified through both the participatory and “classic” programme monitoring activity. Materials and processes can then be developed more effectively. Further links should be sought with other agents in these areas, and whenever necessary, also external support for specific aspects. Proposals to involve an external specialist during 2003-04 to develop and communicate policy analyses should be considered in this light.

- A more rigorous system of linking Programme strategy and goals to the implementation level needs to be established, to identify opportunities and constraints, steer agreed changes, provide specific action dates and monitor their adoption. This should be incorporated into routine steering PSC and Task Force procedures. As proposed above for monitoring, the use of independent external advisory support could be considered and adequate agreements could be established with a highly reputed external consultant or with a suitable institution.

# Lessons Learned

- The Programme is still at an early to intermediate stage in many of its output areas, and so it is too early yet to determine the more complete range of lessons learned which would be anticipated in its design. Nor in some cases is there a robust enough methodology approach available to determine specific causal or associative links in the issues concerned. However, a number of organisational, institutional and policy development areas can be identified where lesson learning potential exists. In a number of other areas, too, the MTE Mission itself learned lessons from the process of the Programme in its engagement with specific challenges, and in identifying practical elements of a participatory approach in its own assessment.

- A primary lesson is simply that the artisanal sector, its links with other sectors, and with its resource systems, its value and its income/poverty characteristics, is very poorly understood in practical development terms. Information from the SFLP will have immediate potential in informing policy at a range of levels, though this could be strengthened by linking with work in related projects and fields. The position of artisanal fishing also needs to be seen more clearly in the wider fishery sector, and in other large-system perspectives.

- The organisational context of the Programme, and the issues generated from this, have created several useful lessons. Applying a broader development approach to a traditional production subsector involving traditional public sector agents results either in a mismatch of understanding and priorities, and sometimes disengagement, or a genuine shift in perspectives and institutional responses. To achieve this however, requires wide influence, negotiation, and evidence. Within this framework, the creation and use of NCUs has proven to be of variable effect, and most notably, a need commonly exists for higher level cross-sectoral engagement in national policy.

- In spite of many obvious constraints, there appears to be considerable potential for the artisanal fishing sector and its communities in most partner countries, though these are subject to a complex mix of conditions, and require relative stability for the social and political mobilisation. At the same time, opportunities of entering in post-conflict phases, when there is a real dynamic for change and a strong desire for reconstruction can be very positive. By contrast, processes of change can be more complex when there is already a strong donor presence, and a number of competing initiatives.

- It is clear that although part of a generic socio-political change, decentralisation, and the often associated processes of public sector rationalisation, acquire different meaning and practical consequence in different national economic and policy contexts. Many of these processes are still to work through, but development approaches need to be flexible and interactive to ensure the most effective outcome.

- The project’s primary emphasis on social and human capital development has been important, but without equivalent development in other areas, has commonly created frustration, as mobilisation without a practical outlet for action or change can become futile, not to say neglectful by those responsible. By contrast, linking this with real development change can become extremely rewarding. In this context also, traditional scientific and technical knowledge has great importance, and in its appropriate form needs to be reintroduced into the process. The most fruitful developments can occur when local communities can interact with external sources of skill or knowledge, in open and egalitarian processes of problem identification and resolution.

- Local level uptake for community projects, and specifically for the SLA and CCRF has been very positive, and attests to the evident practicality of many of the approaches. This emphasises again the importance of using these as practical tools, above all else, and using the holistic perspective in a rational manner. However, too theoretical and specialised an approach can stimulate a danger of elitism, with small numbers of individuals exercising power through their favoured knowledge.

- The SLA is not always seen amongst RSU and national staff as a dynamic and interactive approach, but rather as a static and definitive structure. As a consequence, social and economic exclusion processes, including issues of gender, poverty and age, important in the SFLP’s development context and having important bearing on poverty and its alleviation, are not always brought into view or traced more specifically. This suggests two main possible lines of analysis: first, the way SLA is diffused and utilised, which might call for more skilled trainers and possibly better information/training material. Second, the apparently inadequate focus of the SLA on social and economic exclusion processes, and therefore the need for an adjustment of the approach.

- The wider application of SL however offers valuable potential for linking poor rural communities with national processes, and provides a practical means to ‘reinvent’ the policy processes in developing democracies. There are nonetheless important limitations with respect to its application in that complex analyses are too cumbersome and expensive to be applied at every level and in every context. Rather it needs to be used selectively to screen options, identify priorities, and target actions, clarifying which kinds of specialist inputs may be most relevant.

- Finally, applying a participatory approach to the evaluation itself has been a challenge, firstly in defining how that might differ from conventional methods, and secondly in carrying it out. Time and resource constraints inevitably prevented a wide and discursive, open-ended approach to assessments, with wide contributions from many voices, and the team still had the task of controlling and selecting information. The consultative approach adopted, involving stakeholders at all levels, was not really different from that employed in good evaluation practice, with a major difference being the use of the SL context to structure the enquiry and determine the position of the project. Initial findings were also widely discussed, to gain feedback and presentations made at all Programme levels, which the Mission believes adds significantly to the ownership of this exercise by all stakeholders.

ANNEXES

This term is used by the RSU throughout its documents and language.

There is however a high frequency of requests for literacy courses for women, which the programme could have easily tackled but in many cases went unheeded (see below)

Formerly ICLARM, the CGIAR institute responsible for fisheries and aquatic resources research

Participating countries are: Angola, Benin, Burkina Faso, Cameroon, Cape Verde, Central African Republic, Chad, Congo, Cote d’Ivoire, Democratic Republic of Congo, Equatorial Guinea, Gabon, The Gambia, Ghana, Guinea, Guinea Bissau, Liberia, Mali, Mauritania, Niger, Nigeria, Sao Tome and Principe, Senegal, Sierra Leone and Togo.

The SC is composed of one representative each for DFID, FAO, one National Coordinator for each of the four sub-regions on a rotational basis, and the Programme Coordinator. The Fishery Planning Officer from FAO RAFI and the SFLP Team Leader participate as resource persons, and a Benin DoF representative as observer.

Details of ToRs, itinerary and meetings are given in Annexes 1-3

Project Review Sheet, August 1999, FAO FI.

The Logical Framework Table in the ProDoc reports the following Goal “Widely-replicable policies for sustainable and equitable fisheries adopted”. However, this contradicts the text of the ProDoc and the second OPR. The logframe revised at second PSC, Dec 2001, currently understood within the SFLP is “Poverty amongst coastal and inland communities in West Africa reduced through sustainable use of aquatic resources”, though it is not clear that this change has been formally recorded.

This type of confusion seems to exist also in the logical frameworks elaborated for the Pilot Projects.

Featured also in OVIs 6.1 and 6.7 (old logframe) 6.1 – 6.3 (revised logframe). Note also the ProDoc, page 21: “A specific budgetary allocation is made for policy studies and/or global dissemination of information from the SFLP to be organized by FAO HQ by FAO Regular Programme officers”.

Italic used for quotes from the ProDoc.

It is important to note that women in the communities ask in particular for literacy courses, when talking about improvement of human capital, as they correctly perceive literacy as a very powerful empowering tool. However, the Programme appears to have taken a long time to realize this, and has so far done little to respond.

This term is used by the RSU throughout its documents and language.

Briefing sheet for SFLP Mid-Term Evaluation Mission, Fabio Pittaluga, SFLP-SIFAR Liaison, June 2003.

Thematic Brief, RSU, June 2003

To place in perspective, the originally suggested Task Force for CCRF mentioned in Prodoc has never functioned during SFLP life, FISHCODE has no task force and FI Gender group is long moribund.

As already mentioned, there is however a high frequency of requests for literacy courses for women, which the Programme could have easily tackled but in many cases went unheeded (see below)

The two posts for Project Officers were created in 2002 following recommendations from the first OPR, to cope with the amount of work required for the identification, formulation, management and monitoring of the Community Projects.

This analysis is based upon figures provided by the PCU to the mission, updated on 22/8/2003.

See Annex 5 for outline TORs. These should be developed and ratified as soon as possible.