## Annex 1. Terms of Reference for evaluation

Joint Evaluation Mission by

FAO and Host Government of Mongolia

# Background

The Project is a bilateral project between the Netherlands and Mongolian Governments. It is implemented by FAO over a five year period (13 February 2007 to 31 January 2012) with a budget of USD 4,686,686.

The problem to be addressed by the Project is to stop and reverse the ongoing degradation of the forests of Mongolia and to contribute to poverty alleviation through the development of a model for local level forest ecosystem management at soum level which can be replicated to other sites in the forested aimags of Mongolia.

The development objective of the Project is “the maintenance and improvement of the existing forest cover of Mongolia in order to ensure the sustainable livelihoods of the rural population”.

The immediate objective is “the implementation and integration of participatory forestry in rural development in pilot areas through capacity building of the main stakeholders and through the development of enabling institutional frameworks at local, regional and national levels”.

The Project was designed to deliver five major Outputs that collectively should lead to the achievement of the immediate objective and contribute towards the development objective:

Output 1: 	Functional local organizations/entities (Nukhurlul) for forest management established in pilot sites.

Output 2: 	Adapted management planning for local sustainable forest use, 	reforestation and conservation.

Output 3: 	Adequate legislation and regulations for local level forest resources use, reforestation and conservation.

Output 4: 	Adequate institutional framework at national level for local forest resources use and conservation.

Output 5:	Improved knowledge on integrated and sustainable natural resources utilization and conservation.

At the end of the project, it is expected that a system of local level forest-based natural resources management and administration will have been tested in four different aimags and in at least one soum in each aimag and that field activities in the selected soums will demonstrate:

- what type of local organizations are best functioning for forest management;

- the results of sound practices in forest-based natural resources management: e.g. forest management planning, sustainable harvest and marketing of forest products;

- what local government institutions, laws and regulations are required to create an enabling framework for participatory forestry

- the management of soum forest resources by soum authorities and its impact on poverty alleviation.

A Project Mid-Term Review (MTR) has been carried out from August 11th to 28th, 2010. The MTR concluded “that overall progress has been very good, in fact much better than one might expect in such a short period of time. This good progress can be attributed to several factors.

- The Project is addressing a real need in Mongolia;

- There is good support at all levels in government and among the targeted rural populations.

- The Project design has been appropriate to the political, economic and social situation in the country.

- The implementation of the Project has been efficient and effective.

The MTR acknowledged that PFM is becoming a major, if not the major, form of active forest management in Mongolia, with demand for support increasing rapidly from both herder communities and government officials at aimag and soum levels.

An important conclusion from the MTR is that the approach taken by the Project is in accordance with global best practice and is achieving results that, subject to two caveats that need to be addressed by the Government and the project, are likely to lead to the achievement of the Project’s objectives. These two caveats are:

1.	There needs to be a continuing evolution of the regulatory framework to make it much less enforcing and more enabling for PFM so that FUGs can derive significant economic benefits from forest utilization, and

2.	An institutional “home” needs to be established in the Forestry Agency, staffed by sufficient people and supported by an adequate budget to take on the mandate to manage the PFM process and oversee its expansion to become a national programme.”

# Purpose of the Evaluation

The project document foresees that the project will normally be jointly evaluated, prior to its completion, by representatives nominated by the Recipient and Donor Government/agencies, and by FAO. In agreement with the Donor and the Forestry Agency, it has been agreed that the Joint Evaluation will be carried out from November 28th to December 9th, 2011. However the Donor has indicated that it will not send a representative to be part of the Joint Evaluation Team.

The evaluation will follow-up on the MTR and is intended, as the project draws to a close, to provide recommendations to the Government, FAO and the donor on the further steps necessary to consolidate progress and ensure achievement of objectives.

The evaluation will also benefit from an assessment of the effectiveness of forest user groups as a social basis for collective decision making that will slightly overlap with the mission.

# Scope of the Evaluation

The mission will assess the:

- The relevance of the project to development priorities and needs in Mongolia, including more specifically:

- The continued relevance of the project to development priorities and needs, in view of the possible evolution of the situation in the forestry sector since the project started, and capacity of FAO to adapt to changing needs if relevant;

- The extent to which the project took into account and synergized with other interventions carried out in the forestry sector by other stakeholders’;

- Whether the comparative advantage of FAO in implementing this project, which tackles a complex and multi-rooted problem, has been valued upon project design and the extent;

- The Extent to which the Aimag and Soum targeted by the project were appropriate in view of their representativeness, thereby warranting potential for replication in other Aimags (provinces).

- The general realism and appropriateness of the project design, looking back on effective results and conditions of implementation as they occurred, including:

- realism and clarity in the specification of prior obligations and prerequisites (assumptions and risks) and of external institutional relationships, and in the managerial and institutional framework for implementation and the work plan (to the extent that these aspects were not covered by the MTR);

- the extent to which the strategy implied a reasonable level of expenses, compared to other possible approaches;

- the appropriateness of having a two-level (national and local) strategy.

- Efficiency and adequacy of project implementation including:

- availability of funds as compared with budget for both the donor and national component, for the period not covered by the MTR;

- the quality and timeliness of input delivery by both FAO and the Government, taking into account partner and beneficiary assessments;

- managerial and work efficiency at the level of both FAO and the Government; implementation difficulties; performance of monitoring and reporting; the extent of national support and commitment and the quality and quantity of administrative and technical support by FAO, (for the period or aspects not already covered by the MTR);

- the extent to which FAO has collaborated with the other forestry stakeholders in Mongolia on this project, in view of possible opportunities for collaboration and what challenges may have been encountered to developing synergetic actions;

- the utility of the High Level Natural Resources Steering Committee in the pilot.

- Project results, including:

- outputs produced to date (quantity and quality) as compared with the workplan;

- achievement of the project’s immediate objective and how the overall result can be attributed to the project outputs;

- the effectiveness in reaching all of the targeted beneficiaries and differences in benefits received for each;

- specific achievements with respect to:

  - gender equality;

  - institutional strengthening at local and national level, while identifying strengths and weaknesses of the concerned institutions;

  - supporting enabling policies for participatory forest management;

  - supporting the development of a regulatory framework for participatory forest management, at local and national level and the commitment to implementation;

  - capacity building and institutionalization of training on new participatory approaches, for each of the target institutions;

  - piloting innovative approaches for participatory and sustainable forest management, with target groups (benefits, involvement, capacity) and their impact on natural resources;

  - the application of action learning approaches to implementation (plan, act, observe and reflect) to update knowledge and inform future planning and action;

  - building partnerships with international, bilateral, governmental and non-governmental organizations to enhance effectiveness;

  - knowledge development in the field of participatory forest management through empirical research and studies.

- The contribution of the project to the intended development objective and its general long term impacts in the forestry sector in Mongolia, including:

- the extent to which the elements identified at the outset of the project as necessary to reduce forest degradation and deforestation are now coming into place and if so to what extent the situation has changed since the project start;

- the contribution of the project to the human right based approach endorsed by FAO, to which this project is specifically relevant given its focus and target population.

- The prospects for sustaining the project's results by the beneficiaries and the host institutions after the termination of the project. The mission should examine in particular:

- incorporation and acceptance of activities, new concepts, ideas and working practices initiated by the project in the target institutions in daily management and as part of planning and operation;

- pilot activities in forest management with target groups and scope and conditions for scaling-up sustainable forest management;

- the sustainability of the project approach and methods, goals and perceived added value by the target groups;

- the allocation of budgets by local and national governments to embed the project practices and results in the local and national policies;

- policies, legislation and long-term programmatic strategies for PFM;

- integration of PFM in academic and training institutions and in environmental education;

- public awareness.

Based on the above analysis the mission will draw specific conclusions and make proposals for any necessary further action by the Government of Mongolia,  FAO, or donors to ensure sustainable development, including any need for additional assistance and activities of the project prior to its completion. The mission will draw attention to any lessons of general interest. Any proposal for further assistance should include precise specification of objectives and the major suggested outputs and inputs.

# Evaluation methodology

The evaluation will aim to address the questions raised in section 3, by carrying out a rigorous assessment based on clear evidence and sound technical judgment. The team will use a mix of qualitative and quantitative methodologies to collect information of the basis of which questions can be answered. The following data collection methods may be used:

- Review of documents;

- Semi-structured interviews with key informants among all stakeholders of the project including: beneficiaries, partners at all levels, Government counterparts and FAO project management team, supported by checklists or interview guides;

- Observation during visits of projects in the field;

- Focused group Discussions with project beneficiaries;

- SWOT analysis.

The evaluation will adopt a consultative and transparent approach with internal and external stakeholders throughout the evaluation process. Triangulation of evidence and information gathered will underpin the validation of evidence collected and the eventual analysis which will in turn logically support conclusions and recommendations offered.

The assessment will be based on international evaluation norms and standards. The approach should be impartial, independent, and credible. It will seek to provide all project stakeholders with the opportunity to express their views freely and with the required degree of confidentiality.

# Composition of the Evaluation team

The mission will comprise:

- Mr. Don Gimour, International Consultant, Team leader, FAO, with over 30 years worldwide experience in participatory forest management and extensive experience in project evaluation. The team leader will be responsible for organizing the overall evaluation work and for steering main decisions related to methodology, selection of locations or projects to visit in the field or people to be met.

- Mr. L. Dorjtseden, National Consultant, Forestry Specialist with over 30 years of experience in the Mongolian forestry sector, former Senior Forest Officer of the Ministry of Nature, Environment and Tourism. The team member will work under the direct supervision and directions of the team leader

- Ms. Aurélie Larmoyer, Evaluation Officer, FAO, also co-managing a strategic evaluation of FAO’s work and role in forestry over the period 2006-2011 and who will therefore ensure that both exercises can feed into one another and enhance cross-learning. As evaluation manager, the OED officer will ensure the quality control over the evaluation process and assist the team leader in his methodological design prerogatives if needed. As team member, she will participate in collecting the data on areas of work assigned by the team leader.

Mission members should be independent and thus have no previous direct involvement with the project either with regard to its formulation, implementation or backstopping.

# Role of other project stakeholders and consultations

The evaluation team will maintain close liaison throughout the process with representatives of the donor, FAO and concerned national counterparts, as well as with national and international project staff. Key project stakeholders will in particular be requested to comment on these TOR in a view to ensure that the evaluation is set to capture all necessary elements and on the draft report. Once the report is finalized, they will eventually be asked to provide a management response to each of the recommendation formulated, to be follow-up after one year.

Although the evaluation team should feel free to discuss with the authorities concerned anything relevant to its assignment, it is not authorized to make any commitments on behalf of the Government, the donor or FAO.

The project management team in Mongolia will be expected to facilitate and support the evaluation throughout the process and in particular during the in country mission, including with administrative and logistical organization.

# Deliverables

The following documents will be produced as intermediary or final products of the evaluation:

- An end-of-mission debriefing presentation to FAO and non-FAO stakeholders as appropriate, detailing the key preliminary findings and recommendations of the evaluators. The date and venue of the presentation is to be arranged with FAO.

- A draft final report to be submitted first to OED for quality control and then to key project stakeholders for comments. The first draft should be submitted no later than 14 calendar days after return from the mission.

- A final Report not later than 14 calendar days after receiving project stakeholders’ comments on the draft report.

FAO will ensure all relevant stakeholders are given the possibility to comment on the draft report and receive the report’s final version. The independent consultants are fully responsible for their independent report which may not necessarily reflect the views of the project stakeholders. The report will be written in English and in conformity with the headings shown in Annex (Report outline). A canevas for the draft report will be completed in the country to the extent possible and the findings and recommendations will be fully discussed with all concerned parties in a or several team debriefing(s), whereby general consensus should be reached.

The report should follow international evaluation quality standards, as endorsed by the UNEG and OECD DAC. It will illustrate the evidence found that responds to the evaluation issues, questions and criteria listed in the ToR. Findings should rely on clearly sourced evidence and conclusions should logically flow from them, based on transparent judgment criteria and benchmarks. Recommendations should be in line with conclusions and clearly derive from the evidence presented in the findings, and seek to be useful and actionable by the project management. They should be addressed to the different stakeholders and prioritized. Supporting data and analysis should be annexed to the report when considered important to complement the main report.  The mission leader bears responsibility for finalization of the report, with inputs of team members as per initial team agreement.

The final report should be submitted, electronically as well as printed and should include elements suggested in the model report outline (annex 1)

# Timetable and Itinerary of the mission

The evaluation will include the following phases:

- Home based preparatory phase: team members will allocate 5 days to review all relevant documentation provided by the project team and office of evaluation, and prepare the necessary tools for the evaluation. The team leader will communicate with the maximum anticipation to the project management team in Mongolia regarding specific project locations the team should visit and people to be met for interviews.

- Country mission: The team will spend a maximum of 2 weeks in Mongolia to collect information from additional documents and from project stakeholders. The team will carry-out interviews with key informants in Ulaanbaatar as well as in field locations as selected in accordance with the team leader. A tentative schedule for the mission is proposed below and more details regarding meetings and visits to field locations will be discussed amongst evaluators and the project management team at least one week before the mission.

- The country mission will end with a presentation of preliminary findings and recommendations to the project management and key stakeholders in Ulaanbaatar.

- Preparation of the draft report should be achieved with the next 2 weeks following the mission and sent to OED for quality control. Within 5 working days OED should return the report with comments to the team leader, who will adjust as deemed appropriate. The draft report will be sent to project stakeholders for their comments within a maximum of 20 days, and sent back to the team leader for finalization. It is the responsibility of the project management team to ensure country stakeholders are given the opportunity to comment on the report.

- The assignment is not envisaged to exceed 30 days

A tentative agenda for the mission is proposed below.

| # Day | # Date | # Location | # Purpose | # Activity |
| --- | --- | --- | --- | --- |
| # 1 | # 27/11 # Sunday | # Ulaanbaatar | # Arrival of Mission |  |
| # 2 | # 28/11 # Monday | # Ulaanbaatar | # Briefing of the Mission # Finalization of agenda # Project data collection: review of reports, achievements against planned activities, budget issues, etc. # Meeting with Forestry Agency # Meetings with partner organizations | # FAO project team: CTA and NPC # Courtesy call: # Mrs Tungalag, Director FA # Mr. Nyam # Mr. Tugultur # Dutch Embassy: Mr. Halbertsma |
| # 3 | # 29/11 # Tuesday | # Ulaanbaatar | # Meeting with Assistant FAO-Rep # Project data collection: review of reports, achievements against planned activities, budget issues, etc. # Meeting with MNET | # Ms. Oyundelger # Mr. Batbold, MNET # Mr. Batkhuu, NUM # GIZ: Schmidt-Corsitto # GIZ: Hesse |
| # 4 | # 30/11 # Wedn. | # Ulaanbaatar # Darkhan | # Travel to Darkhan # Meeting with Project facilitator # Meeting with Darkhan EPTA |  |
| # 5 | # 01/12 # Thurs. | # Darkhan # Selenge # Bulgan | # Travel to Altansumber FUG (Selenge aimag) # Meeting with Soum authorities # Travel to Bulgan |  |
| # 6 | # 02/12 # Friday | # Bulgan # Darkhan | # Meeting with Bulgan EPTA # Travel to Dundat-Urguu FUG # Travel back to Darkhan |  |
| # 7 | # 03/12 # Satur. | # Darkhan | # Meeting, brainstorming workshop with representatives of all pilot FUGs (2 rep/FUG) and officials |  |
| # 8 | # 04/12 # Sunday | # Darkhan # Ulaanbaatar | # Travel back to Ulaanbaatar # Rest / team meeting |  |
| # 9 | # 05/12 # Monday | # Ulaanbaatar | # analysis of preliminary findings # Meetings with partner organizations | # WWF: Chimed-Ochir # Eco-Asia: Adiyasuren |
| # 10 | # 06/12 # Tuesday | # Ulaanbaatar | # Integration of preliminary findings into draft report # Meetings with partner organizations | # Minister/Vice Minister # Mr. Banzrach, MNET # UNDP |
| # 11 | # 07/12 # Wednes. | # Ulaanbaatar | # Meeting with GEF focal point # Meeting with Forestry Agency | # Mr. Enkhbat, MNET |
| # 12 | # 08/12 # Thurs. | # Ulaanbaatar | # Workshop: Mission presentation at MNET # Dinner with MNET, FA |  |
| # 13 | # 09/12 # Friday | # Ulaanbaatar | # Mission integrate recommendations of previous day |  |
| # 14 | # 10/12 # Satur. | # Ulaanbaatar | # Departure of Mission |  |

The above outline is extracted from OED standard guidance on project evaluation, which can be provided to the team together with the present TORs, for further information.

See also “Template for Terms of Reference: Evaluations of projects/programmes funded by voluntary contributions from resource partners”

The relevance of the project to needs as per its design was already positively assessed by the previous evaluation, and thereby should not be the main focus of this exercise.