## Annex 11. Timeline of key events in the life of the project

| Date | Event |
| --- | --- |
| 13/11/2006 | Project approved and signed by the Kingdom of the Netherlands |
| 01/12/2006 | Signing of agreement between the MNE and FAO |
| 13/02/2007 | Official commencement of project |
| 03/04/2007 | Commencement of CTA - Mr. Patrick Evans |
| 27/05/2007 | Approval of new Forest Law |
| 22/10/2007 | Recruitment of national project coordinator, Mr. Ts Dashzeveg |
| 12/11/2007 | Inception workshop |
| 20/02/2008 | Appointment of project staff |
| 19-31/05/2008 | First training on participatory forestry by RECOFTC |
| 02/06/2008 | Establishment of Forestry Agency |
| 11/06/2008 | Departure of CTA |
| 01/11/2008 | Arrival of new CTA Mr. Dominique Reeb |
| 4-09/12/2008 | Training on PFM concept and planning workshop |
| 14-16/01/2009 | Workshop on reviewing SFMP and constitution |
| 02-09/2009 | Selection of 12 pilot Forest User Groups |
| 16-31/03/2009 | Nepal study tour |
| 20-25/04/2009 | Training on action learning |
| 18-20/05/2009 | PFM guidelines, CBFiM and SFA workshop |
| 29/05-9/06/2009 | Training on MA&D, Phases 1 and 2 |
| 25/06/2009 | Approval by Forestry Agency of FUG constitution, SFA and SFMP |
| 01-03/07/2009 | Mid-year planning workshop |
| 07/2009 | Publication of Nepal study tour report and wide dissemination (1000 copies) |
| 05-09/2009 | Approval by MNET of PFM related sub-decrees |
| 02/10/2009 | Appointment of project steering committee |
| 12/10/2009 | Reprint of Nepal Study Tour Report (1000 copies) |
| 14/10/2009 | First steering committee meeting |
| 19/11/2009 | Appointment of new NPD, Mrs Tungalag, Director, Forestry Agency |
| 08/12/2009 | Approval of Frequently Asked Questions (FAQs) from FUG by Forestry Agency |
| 15-18/12/2009 | CBFiM and 2010 planning workshop |
| 20/01/2010 | CBFiM guidelines |
| 27/01/2010 | Publication and wide dissemination of “Guidelines for foresters” - legal framework for PFM (2000 copies + 2000 copies April 2010) |
| 27/01/2010 | Publication and wide dissemination of “Trees and shrubs of Mongolia” illustrated book (1000 copies + 2000 copies April 2010) |
| 01-02/02/2010 | First National Forestry Forum |
| 02/02/2010 | Launching of forest policy formulation |
| 07/04/2010 | TOR for Forestry Agency PFM Officer officially approved by Ministerial resolution #86 |
| 23/04/2010 | Signature of MoU with Eco-Asia University and Eco-Asia Institute |
| 25/04-09/05/2010 | Training on MA&D, Phase 3 |
| 18/05/2010 | CBFiM training jointly with Forest Agency and NEMA, practice of control burning with FUG, revision of guidelines |
| 18-19/05/2010 | Training on SFMP and preparation of 1st SFMP with Dundat-Urguu FUG, Bulgan |
| 04/06/2010 | Workshop on urban/soum forest concept development |
| 02-12/06/2010 | WUR-CDI support to NUM curricula development for PFM |
| 04/06/2010 | Award to CTA as “best environmental officer” by Minister of MNET |
| 08/06/2010 | Appointment of Steering Committee for forest policy formulation and for NFP |
| 10/06/2010 | First forest policy Steering Committee meeting |
| 15/06/2010 | Publication and wide dissemination of the Forestry Forum proceedings (500 copies) |
| 22/06/2010 | Meeting with Minister of Education Culture and Sciences, agreement on development of school and vocational school curricula |
| 28/06/2010 | Publication of 1st Forestry Forum proceedings and dissemination |
| 01-02/07/2010 | Mid-year planning workshop |
| 09/08/2010 | Award ceremony at Parliament for first 11 FUGs to have developed SFMP themselves |
| 09/08/2010 | Signature of MoU with WWF |
| 11-30/08/2010 | Mid Term Review |
| 18-19/10/2010 | Joint retreat Forestry Agency - FAO - GTZ, “Participatory forest management and development of simple forest management plans”. Agreement on PFM concept |
| 11/11/2010 | PFM as a main topic during the conference on “Climate change and forest eco-systems” organized by the Faculty of Biology, Forestry Department, National University of Mongolia |
| 05/11/2010 | Forestry Agency Board of Directors approved the revised PFM concept |
| 21-28/11/2010 | Study tour Finland |
| 03/12/2010 | Illustrated desk calendar on PFM concept and legal framework widely distributed (1500 copies) |
| 30/12/2010 | Project yearly planner distributed (200 copies) |
| 8-10/12/2010 | 2011 project planning workshop |
| 17/01/2011 | Mongolian translation of FAO guidelines on developing effective forest policy (200 copies) |
| 18/01/2011 | Reprint of 1st National Forestry Forum proceedings (200 copies) |
| 17-21 /01/2011 | Training of project staff and counterparts on conflict management |
| 26/01/2011 | Recruitment of 8 trainees (young forestry professionals, 5 men, 3 women) to be trained on PFM 6 months in the project (training to start on March 1st 2011). Upon successful completion of the training 5 of them will be employed by the Forestry Agency, at Forest Unit level. |
| 15/02/2011 | One day workshop with representatives of 20 FUGs to prepare a joint presentation for the 2nd National Forestry Forum. At this meeting FUGs representatives pledged to form a national FUG association. |
| 16-17/02/2011 | 2nd National Forestry Forum - Forest Policy Reform. More than 200 participants, widely acknowledged on all main TV networks |
| 22/02/2011 | The Dutch Embassy in Beijing informed the project that the no-cost extension is not approved |
| 01/03/2011 | Meeting with Minister MNET, Director Forestry Agency, GIZ Program Manager to present policy recommendations (18 points). Outcome: Minister required to organize a meeting with three tender winners for forest policy formulation where he will stress points proposed by FAO and GIZ |
| 04/03/2011 | Meeting with Minister MNET and teams of three groups in charge of forest policy formulation. Minister stressed the need to change vision about Mongolian forests: it is not wrong to cut trees. It enables keeping younger and healthier forests |
| 04/03/2011 | Official handing over of “Curricular Guidelines for Undergraduate Study in Participatory Forest Management” with Forestry Agency, Eco Asia University and Eco-Asia Institute. |
| 31/03/2011 | The Minister MNET agrees to allocate 3 million USD from GEF allocation for biodiversity and land degradation |
| 9/05/2011 | Curricula for BSc and MSc programs on PFM for the National University of Mongolia have been completed. |
| 30/05/2011 | Translation of the US Forest Service-FAO magazine for kids on the “World’s Forests” and printing of 1000 copies that were distributed to schools and kids summer camps |
| 8/06/2011 | Reprint of “Trees and bushes of Mongolia” (1000 copies) |
| 7-18/06/2011 | Formulation of GEF PIF |
| 20/06/2011 | First draft of GEF PIF sent to FAO HQ |
| 23/06/2011 | Prize award to the 4 best students of the PFM module taught for the first time at Eco Asia University and Eco-Asia Institute. |
| 27-29/06/2011 | Mid-year planning workshop |
| 1/07/2011 | Three research grants awarded to M.Sc. Students from NUM |
| 4/07/2011 | Official endorsement of GEF National Focal Point to commit 2 million USD from Biodiversity, 1 million USD from Land Degradation and 1 million USD from SFM/REDD+, to support countrywide scaling-up of PFM |
| 5/07/2011 | Publication Fire Management Guidelines (1000 copies) |
| 7/07/2011 | Establishment by Ministerial order of a PFM Unit within the Forestry Agency |
| 4/08/2011 | Reprint of the US Forest Service-FAO magazine for kids on the “World’s Forests” (2000 copies) that were distributed to schools and kids summer camps |
| 15/08/2011 | Second draft of GEF PIF sent to FAO HQ |
| 29/08/2011 | Third draft of GEF PIF sent to FAO HQ |
| 29/08/2011 | Submission to the Finnish Ministry of Foreign Affairs of a project proposal (500,000 Euros under the Institutional Cooperation Instrument ICI), prepared by NUM and the Finnish Research Center METLA and facilitated by the project. |
| 7/09/2011 | Publication of PFM guidelines (300 copies) |
| 26/09/2011 | Appointment of project field facilitator in Khentii as Head of the newly established PFM unit within the Forestry Agency |
| 27/09/2011 | Publication of guidelines for soum authorities on how to support PFM (500 copies) |
| 30/09/2011 | Two research and teaching grants awarded to PSATI of Darkhan University |
| Aug/Sept 2011 | Harvesting and sale of firewood by 11 of the 12 original pilot FUGs |
| 6/10/2011 | Fourth draft of GEF PIF sent to FAO HQ |
| 6-10/10/2011 | FAO video and photo mission for preparation of press release about the project’s success to be released at the APFC (Beijing November 7-11, 2011) |
| 12/10/2011 | Approval by the Finnish Ministry of Foreign Affairs of a project proposal to strengthen forest research in Mongolia (see above 29/08/2011) |
| 18/10/2011 | Project workshop to finalize the update and simplification of the MA&D guidelines |
| 26/10/2011 | Silvicultural guidelines published (280 copies) |
| 31/10-4/11/2011 | Study tour to Finland of Mr. P. Altangerel, Member of Parliament and Chair of the Food, Agriculture and Environmental Standing Committee, Mr. Ts. Banzragch, Director of the Strategic Planning Division of the Ministry of Nature, Environment and Tourism and Mr. Ts. Dashzeveg, National Project Coordinator, FAO forestry project, to study the impact of Finnish forest policy on SFM |
| 7/11/2011 | Project success outlined at a FAO press conference at the APFC in Beijing - Release of the video “Herders taking responsibility to protect woodlands” to the international media |
| 21-22/11/2011 | Forestry Agency workshop to train forest unit officers to support the development of SFMPs for FUGs |
| 23/11/2011 | Video on PFM in Mongolia, 20 min - “The spirit of owning the forest” - 200 CD produced |
| 31/1/12 | Project scheduled to finish |