## Annex 5. Staff workshop-agenda and results

Project staff workshop

on

Participatory Forest Management in Mongolia

Monday 5th December 2011, Ulaan Baator

AGENDA

Objectives

Take the opportunity of the final evaluation to have a focused and strategic discussion with key Project staff to obtain their perspectives on the following questions:

1. What are the key issues that need to be addressed to ensure the long term sustainability of the Project's results and lead to national uptake of PFM?

2. What is it that has led to the Project having achieved a reasonable level of success?

Participants

Key Project staff: CTA, Project Coordinator, Project facilitators and GIZ experts.

Process

- Use cards to collect individual ideas

- Sort cards into groups and define key issues

- Group discussion to refine and/or clarify issues key issues

- Prioritise key issues

Output

For Question 1, aim to compile a short list of key issues, perhaps in two categories--(i) those that are already in hand, and (ii) those that are likely to be outstanding when the Project closes.

For Question 2, compile a short list of, say, 6-10 points that might summarise the lessons learned from the Project’s approach and that might have wider relevance.

COLLATION OF WORKING GROUP RESULTS

Task 1. What are the key issues that need to be addressed to ensure the long term sustainability of the Project's results and lead to national uptake of PFM?

1.Forest policy, law, regulations

| Outstanding | In hand |
| --- | --- |
| - Low value/price for forest products | Local wood market |
| -Tax, fee incentives for FUGs | Support FUG on basis of political interest (party member) |
| -Give right to Soum governor for approval of FUG’s MP after being reviewed by head of soum or aimag’s forest unit | Amendments in some law, such as allowing FUG to function in Special Protected Area |
| -To improve coherence between laws and make them more clear | Ensuring different stakeholder’s participation in formulation of new forest policy. |
| -Monitoring the implementation of laws | Creating incentive system to follow |
| -Coordinating forest area and pasture in terms of law and regulation | Giving permit for timber out of cleaning work in FUG |
| -Creating market for NTFPs and be able to sell in closest big market, | Top to down quota system |
| -Owning pasture at the same time | Unenabling certificate of origin for marketplace |
| -Lack/weak demand for thinning products |  |

2. Public-awareness, training

| Outstanding | In hand |
| --- | --- |
| Raise awareness about PFM and MA&D at institutional and NGO levels through workshops | Train identified service providers in MA&D and PFM including soum and Aimag authorities |
| Trainings for authorities to change attitude | Soum officials need to be trained/informed |
| Training for local authorities about laws and regulations | Train officials of Forestry Agency |
|  | Trainings for public |
|  | Train FUGs on silvicultural activities |
|  | Giving permit for timbers out of cleaning work in FUG |
|  | Informing local people |
|  | Providing guidelines, hand-outs |
|  | Establishing Information centers in Aimags |
|  | Train FUGs on report and economy |

3. Capacity building, structure

| Outstanding | In hand |
| --- | --- |
| Professionals to conduct forest management activities | Establishing Forest units and building their capacity |
| To have professional training organization of participatory approach | Link other projects to FUGs to get support |
| Insufficient capacity to scale-up | Capacity building of staff |
| Having one position of specialist on PFM in EPTA of each aimag |  |
| Train one ranger in every soum and head of forest unit |  |
| Make PFM professional team to take part in tenders announced by Forestry Agency |  |

4. Financial issues

| Outstanding | In hand |
| --- | --- |
| No lack of funds for Forestry Agency but wrong priorities on afforestation, pest control, etc | Business for FUGs |
| Increasing fund for PFM |  |
| Financial support for FUGs |  |
| Reward FUGs for protecting forests |  |
| Creating possibilities of finance |  |

5. FUG association, NGOs

| Outstanding | In hand |
| --- | --- |
| FUGs need to organize at national level | Establish FUG association |
| Capacity building of NGO to involve them in PFM |  |
| Using NGOs capacity, having relation with them |  |
| Having NGO which conducts PFM trainings |  |

6. Scaling-up of pilot FUGs’ activities

| Outstanding | In hand |
| --- | --- |
|  | Scale-up of pilot FUGs |
|  | Teach the new FUGs from experiences of pilot FUGs |

Task 2. What is it that has led to the Project having achieved a reasonable level of success?

- Project policy and approach

- Focused on one certain direction – 12 pilot FUGs

- Conducted monitoring on every activity

- Policy and activities implemented by the project were good

- Legal environment

- Legal environment had been created when the project started (Clause 31 of Law on Environmental Protection, 2006, and Clause 18 of Law on Forests, 2007)

- Legal foundation has been set  up

- Lessons learned during the project phases were noted and reflected in laws and sub-decrees immediately

- Amendment of Law on Forests in 2007

- Project team

- Team work

- Strong participatory approach

- Good management team and skilled facilitators

- Good team

- Learned from each other

- Learned from myself and personal capacity has been built up

- Involvement of other stakeholders

- Policy support

- Integrated in national and local institutions

- All levels are involved (soum, aimag and ministry)

- All stakeholders were involved

- Positive attitude of local authorities and high level officials

- Support form soum and aimag authorities

- Support from EPTA

- Good collaboration with the FA

- Close cooperation with other stakeholders

- Tight collaboration with the Ministry, FA, EPTA and soum governors

- Local authorities have supported us

- Local needs and interest

- Fit to the current needs and demand

- Herders’ motivation for protecting the environment

- Needed for FUGs and their members

- People’s perspective of giving importance to the forest

- Good participation of FUG members

- Training and awareness raising activities

- Focused on training rather than providing materials and money

- Frequent trainings and efficient information provided

- High level of capacity building and awareness raising

- Training for EPTA specialists

- Good awareness raising at all levels

- Taught methods of generating income from the secondary resources (first is animal husbandry)

- Financial availability

- Project’s sufficient financing

- Provided with good financial support to the field offices

- Field offices were provided with sufficient materials and financing.

- Piloting

- Field offices worked at the pilot sites

- Worked on pilot FUGs

- Made right decision on selecting pilot FUGs and motivated them

- Selected 12 pilot FUGs

- Other

- Previous FAO-TCP project to develop PFM concept

- Creation of PFM unit in FA

- Approach based on best practices

- Studied experiences in Nepal

- Good knowledge and education of herders