## Slide 1
Capacity Building and Institutional Development for Participatory Natural Resources Management and Conservation in Forest Areas of Mongolia
GCP/MON/002/NET
Project Final Evaluation
Don Gilmour, Aurélie Larmoyer and Tumerkhuu
8th December 2011

## Slide 2: Objectives of evaluation
Build on the MTR in August 2010 to:
“Provide recommendations to the Government, FAO and the donor on the further steps necessary to consolidate progress and ensure achievement of objectives”.
  Relevance and realism of design.
  Project approach to implementation.
  Progress towards achievement of objectives.
  Sustainability of results.
  Recommendations.

## Slide 3: Approach taken to evaluation
Desk review of documents prior to the mission;
Meetings and interviews with key groups and individuals in UB;
Discussions with EPTA officials in Darkhan aimag;
Discussions with soum officials in 1 Soum;
Discussions with FUG members in 2 FUGs;
Stakeholder and staff workshops.

## Slide 4: Basis of Project design
The design of the Project based on the belief that fundamental re-structuring of state-community relationships will lead to sustainable forest management and the enhancement of local livelihoods.
Key aspects of the re-structuring focused on:
Changing the role of the state from centralised control to decentralised and participatory governance and,
Strengthening the rights and abilities of local user groups to regulate access to, and use of, forests in their vicinity.

## Slide 5: Relevance of Project design
Design has stood the test of time, and has served the Project well:
It is relevant to Mongolia’s development agenda;
Strategy, operational modalities, etc. are appropriate to the institutional setting and Mongolia’s reform trajectory;
Several minor additions were made to the activities following Project planning meetings.

## Slide 6: Project approach
The Project was designed as a pilot, with an emphasis on capacity building, learning and knowledge management;
The application of action learning approaches to implementation (plan, act, observe and reflect) is critical to success in any pilot project.
The project does apply action learning in its piloting and testing of different approaches.

## Slide 7
Conceptualise PFM
Create enabling regulatory framework
Pilot PFM implementation
(12-16 FUGs)
Build new institutional arrangements for PFM (FUG, soum; aimag, national)
Global experience
National context
Training courses; Training manuals; PFM in University curricula;
PFM implementation guidelines .
Feedback loops
(Action learning)
Key elements of
project approach
Capacity building

## Slide 8: Progress (Output 1) Functional local organizations/entities (Nukhurlul) for forest management established in pilot sites
FUGs established in each of the 12+4 pilot sites;
The basic sociology underpinning the implementation process is sound and, by and large, the FUG institutional arrangements are functioning effectively (but some problems with governance and emerging conflict);
FUGs are able to exercise effective control over their territory;

## Slide 9: Progress (Output 1-cont.) Functional local organizations/entities (Nukhurlul) for forest management established in pilot sites
11 FUGs commenced active forest management (cleaning their forests) and selling firewood and some NTFPs in 2011 (earned >USD 13,000 from the sales);

## Slide 10: Progress (Output 2) Adapted management planning for local sustainable forest use, reforestation and conservation
Participatory MPs approved for 16 pilot FUGs (75,868 ha of forest under pilot FUG management)
Forest cleaning operations carried out in 11 FUGs with support of soum authorities-firewood sold.

## Slide 11: Progress (Output 3) Adequate legislation and regulations for local level forest resources use, reforestation and conservation
Substantial changes have been made to the regulatory framework to make it more enabling for PFM and a national forest policy process is underway—that will continue the reform process.
Pilot FUGs are well aware of their tenure rights and are able to exercise them--rights are respected by the soum governors.

## Slide 12: Progress (Output 4) Adequate institutional framework at national level for local forest resources use and conservation
Key components of FUG management planning system developed and approved for national use (included in PFM guidelines).
The institutionalisation of PFM into organisational structures and institutional arrangements is still embryonic-but good progress since 2010.

## Slide 13: Progress (Output 4-cont) Adequate institutional framework at national level for local forest resources use and conservation
A PFM Unit was established in the FA (as a national “institutional home” for PFM);
Forest Units established in EPTAs in pilot aimags.
12 soum/inter-soum Forest Units established in pilot aimags (and 26 established in all 7 forested aimags)—most still in their infancy.
PFM database is operational in all plot aimags and is being updated in the FA.

## Slide 14: Progress (Output 5) Improved knowledge on integrated and sustainable natural resources utilization and conservation
A series of studies and research projects has been carried out (reports and documents have been widely circulated).
PFM modules have been included in curricula of three academic institutions (compulsory for UGs at Eco-Asia and for forestry UGs at NUM).
Several films on PFM have been made and shown nation-wide and some shown internationally.

## Slide 15: Progress (Output 5-cont.) Improved knowledge on integrated and sustainable natural resources utilization and conservation
“Green book” (Guide for Foresters) produced and widely circulated.
Guidelines prepared on: PFM; Forest Fire Management; Silviculture; Market Analysis and Development.
Two National Forest Fora held.
Two study tours held (Nepal and Finland).

## Slide 16: Sustainability (1)
Four things need to be sustained:
Community institutions that are responsible for managing forests (FUGs),
Institutions necessary to support FUGs to manage their forests (at national, aimag and soum levels),
Forests, and
Livelihoods.

## Slide 17: Sustainability (2)
Institutions responsible for managing forests (FUGs)
Pilot FUGs are functioning reasonably well as collective decision making bodies, but are still weak and need on-going support;

## Slide 18: Sustainability (3)
Institutions to support FUGs
Strong political will at all levels;
An institutional home to support national implementation of PFM established in the FA;
Forest Units established in the aimag EPTAs and at soum/inter-soum level to support FUGs.
BUT
All institutions are in their infancy and it will take time (and resources) to build their capacity to be fully effective.

## Slide 19: Sustainability (4)
Forests
Key technical guidelines aimed at managing forests sustainably endorsed for national use:
Simple Forest Management Plans;
Silvicultural guidelines;
Volume tables for FUGs;
Fire management guidelines.
BUT
Their application has just begun and it will take time and on-going support for them to be tested and institutionalised within the normal operations of FUGs (with support from Forest Units).

## Slide 20: Sustainability (4)
Livelihoods
Human assets—capacity building.
Social assets—strong FUGs as collective decision making institutions.
Financial assets—FUGs generated $13,000 in 2011.
Natural assets—forest condition is improving (decrease in illegal logging and forest fires)
Material assets—no change.
BUT
It will take time for FUGs to gain confidence and capacity to manage their forests to optimise the livelihood benefits

## Slide 21: Sustainability-summary
Re-structuring state-community relationships from central control to decentralised management involves challenging existing power structures and is inherently political. Change is from forest-centred to people-centred approach. Problems can be expected in the future.
Building new institutions to manage the new relationships involves complex social processes and takes time—simply setting up new organisations is not sufficient.
All institutions are new and are still relatively weak. Substantial on-going support is needed to strengthen them (extension and community development work).

## Slide 22: Progress towards achieving immediate objective (1)
Immediate objective reformulated:
“Participatory Forest Management integrated into rural development in pilot areas and supported by an enabling regulatory framework and empowered institutions at national, regional and local levels”.

## Slide 23: Progress towards achieving immediate objective (2)
FUGs have been established in all pilot aimags with functional institutional arrangements that can operate effectively to plan for and carry out sustainable forest management.
Building blocks are in place for sustainable forest management in pilot areas (procedures for MP preparation, silviculture guidelines, etc. distilled into PFM implementation guidelines)—endorsed by government for national use.

## Slide 24: Progress towards achieving immediate objective (3)
An enabling regulatory framework in place (further refinement necessary)
Supportive government structures in place (national, aimag and soum level)
Conclude that the Project’s immediate objective has been achieved.

## Slide 25: Progress towards achieving development objective (1)
Problem to be addressed:
Stop and reverse the ongoing degradation of the forests of Mongolia and to contribute to poverty alleviation.
Development objective:
The maintenance and improvement of the existing forest cover of Mongolia in order to ensure the sustainable livelihoods of the rural population.

## Slide 26: Progress towards achieving development objective (2)
Maintenance and improvement of Mongolia’s forest cover
Too early to be definitive about the sustainable management of forests across Mongolia-early indications are positive--trends are in the right direction:
  Fires, illegal logging and overharvest of NTFPs in FUG forests have been reduced (help to maintain and improve forests).

## Slide 27: Progress towards achieving development objective (3)
Sustainable livelihoods of rural population.
Too early to be definitive about the sustainable livelihoods of rural populations across Mongolia-early indications are positive--trends are in the right direction:
  Four of five asset classes that constitute livelihoods have improved in pilot FUGs (human, social, financial and natural assets).

## Slide 28: Progress towards achieving development objective (4)
Can conclude that the Project has made a significant contribution towards the achievement of its long term development objective.

## Slide 29: A cautionary note !!
While solid progress has been made overall, PFM implementation in the pilot FUGs is only just into the three-year Foundation Phase of the much longer full PFM process. Many of the supportive organisational structures and institutional arrangements (both government and FUG) are new and fragile and have yet to be fully tested.

## Slide 30: A major risk !!
The enthusiasm to expand the number of FUGs rapidly and develop management plans could overlook the need to carry out sufficient community extension work to build the FUGs as strong institutions sufficiently empowered to exercise their rights effectively.
Management plans without empowered FUGs to implement them are highly likely to fail.

## Slide 31
PFM
process
Project approach
Professional training (NUM, Eco-Asia)
Govt awareness
Public awareness
Strategic partnerships
Factors leading to success
Capacity building of Project team
Capacity building of FUGs and govt staff
Action learning
Policy influence
Multi-level
(local-national)

## Slide 32: Recommendations (1)
For the Government (the PFM Unit in the FA)
Continue to support the strengthening and evolution of the PFM concept at all levels.
For the Government (the wider Government)
Provide adequate resources to:
The PFM unit in the FA.
The Forest Units in the Aimags and Soums.

## Slide 33: Recommendations (2)
For the Government (the wider Government)
Continue process of evolving the regulatory framework to make it more enabling for PFM.
Seek ways of retaining the existing Project field facilitators to support national scaling up of PFM in order to utilise their considerable knowledge and skills in implementing PFM.
Ensure that PFM is embedded into the National Forest Policy as a major form of forest management in Mongolia

## Slide 34: Recommendations (3)
For the Project
Prepare and implement an exit strategy.
Prepare recommendations for the Government aimed at identifying the regulatory and other issues that need to be addressed to maintain the momentum in implementing PFM.
Collect and collate all important publications prepared by the Project and deposit them in appropriate libraries in Mongolia and also in the FAO Bangkok office.

## Slide 35: Recommendations (4)
For the Project
Explore options for retaining the Project facilitators to support national implementation of PFM.
Conduct an “end of Project” workshop.

## Slide 36: Recommendations (5)
For FAO
Speed up the internal FAO process to approve the TCP proposal to maintain essential support for PFM.
Document and publicise the experiences of the Project in implementing PFM in Mongolia to ensure the lessons learned are widely shared.

## Slide 37
Thank you