## Annex 7. Project progress—activities carried out against those planned in original LFA

(Information based on August 2011 Trust Fund Report plus updates). New activities are highlighted

| OUTPUTS AND ACTIVITIES--Planned |  |  | OUTPUTS AND ACTIVITIES—Progress as at October 2011 | COMMENTS |
| --- | --- | --- | --- | --- |
| Output 1: Functional local organisations (Nukhurlul) / entities for forest management established in pilot sites |  |  |  |  |
| 1.1. |  | Assessment of existing Forest User Groups | Completed, see report September 2008-February 2009 |  |
| 1.2. |  | Define criteria for selection of Nukhurluls | Completed, see report September 2008-February 2009 |  |
| 1.3. |  | Establish 2 to 3 model Nukhurluls in selected soums according to the Mongolia Participatory Forestry Concept | Completed, see report March - August 2009. As the 12 pilots FUGs have completed their management plans and obtained their certificates, it was decided to add a few new pilot FUGs to enable project and forest administration staffs to go through a second round of FUG support for further improvement of their skills. At the end of the reporting period 4 new pilot FUGs were added, new total 16 FUGs. |  |
| 1.4. |  | Support Nukhurluls / entities to obtain a legal status | All initial 12 pilot FUGs have obtained the approval of the Bag Khural (local administration), signed their constitution, have prepared their forest maps and have completed their simple forest management plans (SFMP). All 12 FUGs have their SFMP approved by their respective Aimag and Soum authorities. They all have received their certificate that establishes the FUG’s rights to manage and use their forest and they all have developed their by-laws. Activities continue with 4 new FUGs, their management committee have been established, they have adopted their constitutions and they have recently completed their simple forest management plans. |  |
| 1.5. |  | Improve technical and managerial skills of the Nukhurluls/entities members through capacity building | Training of 12 FUGs is mostly completed, covering all required skills as foreseen in the PFM concept, further capacity building is still addressing issues of marketing. Since its inception and up to August 2011, the project field offices carried out trainings involving over 8800 local participants |  |
| 1.6. |  | Discuss and develop a concept for Soum forest with a focus on poverty alleviation | Two soums have been identified, Tsagaan Uur in Khuvsgul and Bugat in Bulgan Aimag and an initial concept was developed in June 2010. However it was decided not to complete this activity to avoid overloading local institutions with new concepts as they are still adjusting to participatory forest management by FUGs. |  |
| 1.7. |  | Define and test other forms of local forest management | Not addressed as no new needs were identified |  |
| 1.8. |  | Ensure and improve coordination between Soums and Nukhurluls | Memorandum of Understanding (MoUs) between the project, Environmental Protection and Tourism Agency (EPTA) and Soum authorities and MoUs between Project, EPTA, Soum authorities and each FUG have been be signed by concerned parties (see report March-August 2009). At least 6 soum governors in the project pilot areas have given the preference to the pilot FUGs for producing the firewood needed for the soum institutions. Short guidelines have been prepared in collaboration with the Forestry Agency to provide key information to soum governors to strengthen and mainstream their support to FUGs. |  |
| 1.9. |  | Set a revolving credit system to support Nukhurluls / entities | Instead of establishing a revolving credit system for FUGs, it was decided to use existing schemes. A set of guidelines on microfinance for facilitators and FUG members has been produced. |  |
| 1.10. |  | Support Nukhurluls / entities in the implementation of their management plans | All initial 12 pilot FUGs have developed their SFMP and had them approved by relevant authorities between July - August 2010. The project is now focussing on supporting their implementation and monitoring. In addition the project has supported the development of SFMPs for 4 new pilot FUGs. All 4 SFMPs were officially approved. It should be noted that the time required to complete SFMPs with new FUGs (about six months) has been considerably shorter than during the first round of SFMPs (about 18 months). |  |
| 1.11 |  | Prepare and update database on workshops, trainings, meetings, public awareness, etc. New activity. | Done and updated twice yearly (February and August). All databases are available at the main project office in Ulaanbaatar. |  |
| 1.12 |  | Monitor attitudinal change amongst stakeholders New activity | Project staffs are recording all attitudinal changes they perceived to be resulting from project work. Databases are available at the main project office in Ulaanbaatar. |  |
| 1.13 |  | Support FUG to FUG capacity building New activity | The approach was tested in two field offices, Khuvsgul (“Taliin Tolgoi” FUG members provided support to a prospective FUG in Tunel soum) and Bulgan (“Dundat-Urguu” FUG members provided support to “Gunchuluut” FUG). Despite the lack of experience of the FUG members in being service providers, the first results are very encouraging. FUG members will still need some limited support to improve their skills but the approach has already demonstrated that experienced FUGs can be very efficient in reaching out new FUGs. |  |
| Output 2: Adapted management planning for local sustainable forest use, reforestation and conservation |  |  |  |  |
| 2.1. |  | Assess current management planning system | Completed, see report September 2008-February 2009. |  |
| 2.2. |  | Develop simple management plans | Completed, see report March - August 2009. SFMPs are under implementation and were found to be adequate and realistic. Attention is now being paid to the monitoring of SFMPs. |  |
| 2.3. |  | Develop suitable multipurpose and qualitative forest assessment methodology | Completed, see report March - August 2010. |  |
| 2.4. |  | Ensure integration of forest management within management of other renewable natural resources, especially livestock | On-going activity, opportunities for better integration are continuously looked after. |  |
| 2.5. |  | Develop adapted mapping and demarcation methodologies | Completed, see report September 2009 - February 2010. |  |
| 2.6. |  | Assess products and markets for management planning purpose | Brochures were prepared for firewood, medicinal plants and herbal tea. The aim of these brochures is to facilitate the gathering of information for FUGs which are developing business plans. |  |
| 2.7. |  | Training of staff on simple management planning | Completed, see report March - August 2010. |  |
| 2.8. |  | Prepare guidelines on simple management planning | Dtailed guidelines on SFMP have been completed and have been published. They are part of the general guidelines for participatory forestry implementation in Mongolia |  |
| 2.9 |  | Clarify and ensure that approved SFMP is legally sufficient to conduct thinning and utilization activities New activity | The newly established PFM Unit within the Forestry Agency has taken responsibility top address this issue. |  |
| 2.10 |  | Develop and publish silvicultural guidelines New activity | Completed. |  |
| Output 3: Adequate legislation and regulations for local level forest resources use, reforestation and conservation |  |  |  |  |
| 3.1. |  | Review and finalize the participatory forestry concept | Completed. First round of reviews completed in December 2008 and January 2009 (see report September 2008-February 2009). The concept has been further refined in July, 2010, based on significant field experience. |  |
| 3.2. |  | Ensure approval of the participatory forestry concept, including the PF Agreements by Government | Earlier version of the PFM concept was approved (see report September 2009 - February 2010). The revised concept has been submitted to the Forestry Agency and has been approved on November 5th, 2010. |  |
| 3.3. |  | Contribute to the amendments / revision of the forest law to create a legal framework for participatory forestry | Completed, see report March - August 2009. |  |
| 3.4. |  | Set-up a national working group on legislation / regulations | Completed by the MNET, see report September 2008-February 2009. |  |
| 3.5. |  | Rank priority issues for the working group | No action required. |  |
| 3.6. |  | Raise stakeholders awareness on the legal framework | The project collected 76 Frequently Asked Questions (FAQs) related to participatory forestry. The FAQs were published as an introduction to the “Guidelines for Forestry Officers”, December 2009, which in addition contains all forestry related legislation. This is the first time that such a comprehensive publication was published. All 4000 copies printed were rapidly distributed. As one of the major project output the “Participatory Forest Management Guidelines” were printed. These guidelines are giving extensive information on the legal framework for establishing and managing FUGs. In addition, numerous radio, TV broadcastings (national and local networks), newspaper articles were produced on PFM in Mongolia. |  |
| 3.7. |  | Organize yearly regional and national meetings to discuss and prepare recommendations for submission to the Government to improve the legal framework for participatory forestry | Under project guidance two National Forestry Forum with a focus on participatory forestry were organized in Ulaanbaatar in 2010 and 2011. Workshops at aimag levels were also conducted. |  |
| 3.8. |  | Prepare recommendations based on feedback from pilot activities | Continuous activity. The two National Forestry Forum produced a set of actions and recommendations including those from the project pilot FUGs. Recommendations were made to refine the PFM concept |  |
| 3.9. |  | Submit recommendations for approval to MNE, Aimag and Soum levels | See 3.8. |  |
| 3.10. |  | Contribute to the development of a specific national law to create a legal status for local groups / entities managing renewable natural resources | With the approval of SFMPs and with FUGs starting to implement forest management activities, a number of legal constraints are emerging. The project is keeping track of these issues and already forwarded them to the Forestry Agency. Little progress has been achieved so far, however with the new PFM unit these issues can be expected to be addressed |  |
| 3.11. |  | Harmonize national and local management systems | Completed, see report March - August 2010. |  |
| 3.12. |  | Review the forest taxation system for Nukhurluls / entities and make recommendations | The principle of reduced taxes or fees for FUGs is getting acceptance amongst the forestry administration. However, and despite project’s advice, no clear regulation has been formulated in the new sub-decrees. The project considers that no tax or fee should be collected from FUGs for own consumption of their own forest products as they are protecting and sustainably using the forest. However, in the future, when FUGs start commercializing their products then, sale tax could be collected. This is a rather sensitive issue and probably more time is needed to reach a satisfactory agreement. |  |
| 3.13. |  | Establish an effective control and permit system | Approved SFMPs are constituting a solid monitoring tool of forest management activities in FUGs area. This monitoring has been tested will be evaluated. |  |
| 3.14. |  | Develop model by-laws for Nukhurluls / entities | Completed. FUG constitution template is developed and approved, see report March - August 2009, and was published in the “Guidelines for Forestry Officers”, December 2009. |  |
| Output 4: Adequate institutional framework at national level for local forest resources use and conservation |  |  |  |  |
| 4.1. |  | Establish a regulatory body (Division, Service) at national level for local forest use and conservation | A PFM Unit within the Forestry Agency was endorsed by the Minister of MNET on July 7th, 2011 and 2 staff were appointed in September 2011 |  |
| 4.2. |  | Establish a service unit at Soum level (funded by Aimag) | The project is working closely with the Forestry Agency and the five pilot aimag EPTAs to establish Forest Units at the aimag level. (19 “inter-soum” forest units and 7 “soum” forest units are now established in the seven forested aimags, 5 “inter-soum” forest units and 7 “soum” forest units in the project pilot aimags). Already 6 Officers were trained on PFM and joined various Forest Units. |  |
| 4.3. |  | Establish an information center at Aimag level | Completed, see report March - August 2010. |  |
| 4.4. |  | Support an institutional review and make recommendations | The project is in regular contact with the Forestry Agency, which was established in August 2008, and is providing advice on institutional strengthening. The project has been instrumental in advising the Ministry of Nature, Environment and Tourism to officially launch the formulation of a new forest policy. |  |
| 4.5. |  | Conduct discussions, seminars at national level to improve the institutional framework | The project supported two National Forestry Forum. Following the first forum the Minister decided to launch a forest policy formulation. |  |
| 4.6. |  | Support the development of a monitoring system for participatory forestry at national level and local level | Completed, see report March - August 2010. |  |
| 4.7. |  | Make proposals to increase government funding to the forestry sector (channelling back forest revenues to the sector) | The government is already providing funding to develop the first forest management plan of FUGs. The recently started forest policy formulation will certainly address this issue. The budget to the forestry sector has been growing sharply since 2008, date of the Forestry Agency establishment and doubled in 2010. Upon recommendation from the project the MNET has agreed to allocate 2 million USD from its GEF RAF-5 allocation for biodiversity and 1 million USD for land degradation to support PFM scaling-up. These allocations will make it possible to beneficiate from the GEF’s Sustainable Forest Management and REDD-Plus Program that provides an incentive mechanism. Thus total GEF funding is expected to reach 4 million USD. |  |
| 4.8. |  | Assist in establishing umbrella organizations for Nukhurluls | A first step towards the establishment of an umbrella organization for FUGs was achieved in February 2011 (see report August 2010 - February 2011). The project is continuing to support this initiative by facilitating meetings and attendance of FUG representatives to regional and national meetings and workshops. |  |
| 4.9. |  | Review university forestry curricula to include participatory forestry Modified to read: Include Participatory Forestry in University forestry curricula, provide text books | A draft “Curricular Guidelines for Undergraduate Study in Participatory Forest Management” for the Eco Asia University and the Eco-Asia Institute has been developed. The PFM module was taught at Eco Asia University. With the support of the Centre for Development Innovation, Wageningen UR, The Netherlands, and in collaboration with the National University of Mongolia, curricula for BSc and MSc programs on PFM have been completed. |  |
| 4.10 |  | Include Participatory Forestry in Vocational Training Schools forestry curricula New activity | Initial agreement has been given by the Minister of MECS in June 2010. This still need to be formalized with the director of the VTS but no progress achieved |  |
| 4.11 |  | Collaborate with other organizations and projects involved in environmental education New activity. | Completed. See report September 2009 - February 2010. |  |
| 4.12 |  | Train facilitators and foresters on participatory forestry | On-going activity,. The project 4 facilitators and their EPTA counterparts are intensively trained on various topics as well as trained on the job and learning from doing together with the FUGs (see list of training). |  |
| 4.13. |  | Train Aimag and Soum authorities on participatory forestry | The Training and Extension Unit of the project has developed six training modules on participatory forestry. All officers, EPTA officers, Forest Units, Forest Rangers, Inspectors and Soum authorities of the four project aimags have already been trained with all modules (see list of training) |  |
| 4.14. |  | Organize study tours for MPs, governors, etc | Study tours in Nepal, in Finland (2) had a major impact on policy makers perception and attitude. The Director of the Forestry Agency participated to various international conferences and workshops. |  |
| 4.15. |  | Organize study tours and exchange visits for staff and Nukhurlul members | Staff visit to Nepal, FUGs to FUGs exchange visits were organized. |  |
| 4.16. |  | Conduct regular public awareness campaigns on participatory forestry | Numerous publications (see list of publications) , numerous radio,and TV reports (see list of public awareness events), numerous meetings, workshops, etc (see list of events0 |  |
| 4.17. |  | Prepare guidelines for Participatory Forestry implementation in Mongolia New activity. | Completed. The guidelines have been published in September 2011. |  |
| 4.18 |  | Train soum authorities on PFM New activity. | The project has commissioned the development of information material as well as specific training for soum authorities and more specifically for soum governors. The information brochure has been published in September 2011. |  |
| 4.19 |  | Develop a scaling-up strategy for PFM New activity. | A brain storming session on the scaling-up strategy was conducted during the project mid-year workshop end of June. The strategy was further elaborated in September 2011. |  |
| 4.20 |  | Support the formulation of a new forest policy New activity. | To support the on-going stakeholders consultations carried out by a contracted team, the project is involving its field facilitators by organizing local workshops to discuss policy issues, prepare recommendations and identify representatives that would attend the regional and national workshops. Short guidelines to facilitate these workshops were prepared. |  |
| 4.21 |  | Develop a project proposal for GEF funding for scaling-up PFM and develop PWM New activity. | A project concept was developed to scale up participatory forest management across the seven forested aimags of central and north Mongolia (Khuvsgul, Selenge, Khentii, Bulgan, Zavkhan, Arkhangai, and Tuv) and to pilot participatory wildlife management at a few pilot sites with forest user groups that are already operational. The GEF PIF was submitted to FAO HQ for further transmittal to the GEF Secretariat |  |
| Output 5: Improved knowledge on integrated and sustainable natural resources utilization and conservation |  |  |  |  |
| 5.1. |  | Yearly review of project research needs and assign priorities | The project has signed MoUs with the National University of Mongolia (NUM) and the State Agricultural University (SAU) in Darkhan. These MoUs foresee the support of research work to be carried out by professors and students in designated project sites. 7 research projects were supported by the project. |  |
| 5.2. |  | Involve universities, research institutions to support knowledge transfer | On-going, see report March - August 2010, September 2010 - February 2011. See also activity 4.9. The project facilitated a project between NUM and the Finnish Research Center METLA (500,000 Euros) to support much needed basic research on silviculture (plantation, thinning regimes, growth and yield). |  |
| 5.3. |  | Conduct a biodiversity assessment in selected pilot areas and identify potential sustainable uses | This activity has been cancelled as no university students were found to conduct the research. |  |
| 5.4. |  | Establish permanent sampling plots to study the effect of participatory forestry | Completed, see report March - August 2009. These plots will be regularly monitored. Agreement was reached with NUM and the University of Darkhan to ensure regular measurements and maintenance on the long-term. These discussions are supported by a GIZ junior expert seconded to the Darkhan University. |  |
| 5.5. |  | Identify new markets for natural resources products | Done by national consultant in May 2010 |  |
| 5.6. |  | Study the impact of grazing and fire on natural regeneration | This activity is carried out together with activity 5.4. |  |
| 5.7. |  | Research on adapted reforestation techniques | This activity is carried out in conjunction with activity 5.4. |  |
| 5.8. |  | Carry out / support studies on wildlife management | The project facilitated the funding, through the TCP-Facility, of the formulation of a participatory wildlife management project. The formulation mission took place in April 2010 and a draft proposal is available. The project proposal relies heavily on the project’s experience and PFM concept |  |
| 5.9. |  | Study on appropriate harvesting techniques | This activity has been cancelled as no university students were found to conduct the research. |  |
| 5.10. |  | Study the impact of illegal logging activities on natural resources | One NUM student is currently conducting research work on this issue in Tunel soum, Khuvsgul aimag. |  |
| 5.11. |  | Study the impact of deforestation on watershed management Modified to read: Study the impact of harvesting of riparian forest and bushes | This activity has been cancelled as no university students were found to conduct the research. |  |
| 5.12 | Study the impact of human settlement on forest use and conditions New activity. |  | One NUM student is currently conducting research work on this issue in Tunel soum, Khuvsgul aimag. |  |
| 5.13 | Conduct a baseline survey New activity. |  | Completed, baseline data were collected in all 12 project pilot FUGs, in 8 other FUGs not involved in project activities for comparison purpose as well as amongst Aimag EPTA officers and soum officials (Soum Governors, Forest rangers, State Inspectors). In total 259 individual surveys were conducted. The report was delivered in November 2009. |  |
| 5.14 | Prepare guidelines on Community-based Forest Fire Management (CBFiM) New activity. |  | Completed. Testing of the guidelines and training on CBFiM was conducted in May 2010. Official approval by the Forestry Agency and NEMA was granted and they were published in July 2011. |  |
| 5.15 | Study on the sociology of collective decision making New activity. |  | Completed in June 2011. The study confirmed that the PFM concept is adapted to the Mongolian context. Recommendations were formulated to improve its implementation. |  |
| 5.16 | Document PFM process in Mongolia and prepare discussion paper to clarify long-term vision New activity. |  | Mission planned in November-December 2011 |  |