1st draft,  May  2004

Strengthening and Expansion of the National Food Information System of ERITREA

(GCPS/ERI/002/ITA)

Terms of Reference for a Joint Evaluation Mission by

The Italian Cooperation, FAO and the Government of Eritrea

Eritrea is a Low-Income Food Deficit country, where livelihoods and food security depend on agriculture, as 80 percent of the estimated 3.6 million of Eritreans live in rural areas.  The small country (122,000 Sq. Km) has large semi-arid zones and three erratic rain seasons which makes sustaining agriculture-based livelihoods very risky and uncertain, as the dominant production systems (crop and livestock) are basically rain fed.  The country is permanently threatened by migratory pests (desert locust) and can be a breeding zone for other crop pests (i.e., armyworm).

Both population and crop production are concentrated in the highland areas above 2000 meters, with its base along the southern border comprising parts of the zobas of Maekel, Debub, and adjoining parts of Anseba and Gash Barka.  In these areas rainfall, with long-term annual averages ranging between 450mm and 700mm, supports crop-based farming systems centred on the cultivation of taff, sorghum, maize, barley and wheat.  To the east, north and west of this cropping region is a more extensive agro-pastoral area extending down to around 700m above sea-level, in which rainfall averages between 100mm and 450mm but is supplemented locally by run-off from the highlands. Here, farming strategies are mainly based on a combination of cultivation and pastoralism.  In the remainder of the country, comprising northern Gash Barka, Northern and Southern Red Sea Coast stretching down to the Red Sea coast, the arid conditions support only pastoralism.

On top of the uncertainty of agriculture and the impact of recurrent droughts, the liberation struggle and the conflict border with Ethiopia (erupted in 1998 and in a deadlock due to the delays on implementing the border demarcation) has taxed the country’s economy and food security.  Direct effects experienced during the war included: loss of labor (through out-migration of refugees, military conscription, or direct casualties from military action), loss of land due to mining, loss of livestock, including oxen and pack animals, combined with disruption of grazing patterns, interruption of marketing channels, restricted access to markets, and destruction of rural infra-structure. Many of these effects acted in concert with those of the severe droughts of the mid-1970s and mid-1980s to strip large numbers of rural households of whatever assets (oxen, farm implements) they had. Any sustainable recovery of agriculture and of sustainable food security will be a lengthy process. The underlying causes of food insecurity have been  weak policies; poor and under-degradation natural resources; lack of foreign exchange to fund investment and social services; shortage of human resources; inadequate food storage, transport and processing facilities; improper sanitation facilities at national and household levels; improper child care practices etc.

As a result of the interaction between the abovementioned factors, the overall poverty in Eritrea was estimated in 2003 to be 66 percent. Poverty is concentrated in rural areas, and is deepest in the arid zones. Poverty is increasing in the urban areas, as food prices continue to rise and the purchase capacity of the population drops inversely.  Malnutrition rates remain above the acceptable levels and the country keeps appealing for international emergency assistance, while trying to move to a recovery phase.  Insufficient funding of emergency appeals and problems on beneficiary targeting combined with insufficient response to non-food appeals keeps holding the country from recovery .

The government prepared in 2003  poverty reduction and recovery papers, as well as a draft policy paper on food security.  Most of the interventions are based on response form the international community or the assumption of a difficult national economic recovery.   Under these circumstances, life saving and relief keeps being the priority.  The impact of not covering the humanitarian appeals is extending the emergency situation while justifying humanitarian assistance becomes more difficult.  One of the problems is the difficulties to project the effect of one of two years of drought in a 4 years or more span.  Once a good year comes, it could be considered that the emergency is over.  This has been the case of the combined effect of drought and war in Eritrea, so a strong work of advocacy is necessary.

Another issue is related to the impact of insufficient support for non-food items.  While the appeal for food aid has been covered around 46% in 2004, the non-food appeal received only 5%.  In the case of agriculture, there are few expectations to raise that figure, meaning that the cumulative effect of uncovered needs during the crisis is still taxing the recovery activities.  On top of that, the economic, monetary and fiscal situation of the country along with the political environment created by the impasse on the demarcation process suggests that more humanitarian issues are to come. This will further delay the process from humanitarian life-saving interventions to livelihood-recovery as well as socio economic development.

1.1	Project Background

Immediately after Independence, FAO started in 1993 assisting Eritrea through IGADD regional projects, namely the Phase I Early Warning & Food Information System for Food Security project (GCPS/RAF/256/ITA) and its Remote Sensing Component (GCPS/RAF/231/JPN), followed by support form its Technical Cooperation Programme (TCP/ERI/4451) from February 1995 to early 1996.  The national institution in charge of coordinating information for early warning and food security (NFIS) was identified as the focal point for support, making it possible to start the project "Assistance for Strengthening the National Food Information System in Eritrea” (GCPS/ERI/002/ITA), which became operational in December 1996, funded by the Government of Italy.

The project activities were interrupted in 1998 due to the border conflict, and the project was scheduled to terminate in July 2000.  From July to December 2000 the technical assistance from FAO continued, funding the NFIS activities and implementing the recommendation of a Tripartite Review Meeting to formulate a Phase II.  Complementary, a 15-month FAO TCP project (TCP/ERI/8821(A)) implemented from November 1998 to December 2000 supported the development of a crop statistics methodology.

A Tripartite Review (TPR) mission in October 1999 recommended fielding a mission to formulate a possible Phase II, in order to continue the strengthening and expansion of the NFIS. Among the needs identified by the TPR mission were:

• strengthening of partnerships with Government and non-governmental agencies concerned with food information and food security;

• comprehensive coverage of urgent information needs related to acute food insecurity caused by emergencies;

• capacity building to address human resources constraints faced by Government agencies;

• extension of data collection and dissemination of information products to sub-Zoba level, and

• improved coverage and balance between NFIS information components, particularly through the inclusion of data components (vulnerability analysis, household food security determinants) relevant for access to food concerns and issues .

By 2000 the project had a fully staffed (4 members) technical unit based on the Ministry of Agriculture, plus additional technical support from FEWS NET.  Some sectoral information systems were in place, and consolidation/improvement of the NFIS seemed around the corner.  The formulation mission (2000) enthusiastically prepared a new phase to strengthen and expand the NFIS.

The Government of Italy approved a second phase of 30 months and US $ 1.6 million in addition to the $ 1 million for the first phase, and the project was ready to start in early 2001, as soon as some normal administrative issues were settled.

Things did not go as planned, and the Technical Unit lost its staff and very important assets (motorcycles for data collection, radio network for data transmission) while the recruitment of new international staff took time.  The regular publications of the NFIS were suspended and its credibility and feasibility became affected.

In July 2002 the International Adviser on Food Security Information and Vulnerability was recruited.  While recruitment of a Chief Technical Adviser (CTA) was in process, a technical backstopping mission from FAO HQ took place in August 2002, to draft a plan for re-launching activities.  The mission concentrated in setting up again and updating the institutional structures of the NFIS, and its recommendations were approved.  By the end of December 2002 the CTA was fielded and the priority was given to implementing the institutional setup and recovering credibility through strategic activities on the technical side.

The Inception Report of the CTA was presented by March 2003, and one of the recommendations was to hold a Tripartite Review Meeting (TPR) on administrative and technical issues.

This took place in March 2004, and one of the most important conclusions was despite the verified revitalizing and technical improvements on the NFIS, some of the outputs as formulated in the enthusiastic framework of 1999/2000 were no longer feasible under the prevailing country situations.  A second important resolution was to call an External Evaluation Mission so the constraints, achievements and avenues for the future could be appropriately considered, as the four working days TPR was not in a position to do so.

1.2	Project Objectives and Outputs

The project Objectives and Outputs as in the PRODOC are:

1.2.1 Development Objective

A substantial reduction in chronic food insecurity, and in vulnerability to temporary food insecurity, of the people of Eritrea at national, community, household and individual levels.

1.2.2 Intermediate Objective

An effective, efficient and sustainable national food information system in place that provides decision-makers from multiple sectors at national and sub-national levels, with accessible, timely and reliable food security and vulnerability information for the identification and characterisation of the food insecure, the assessment of food emergency conditions, the monitoring of relief assistance, including food donations, the formulation of food security policies and strategies, and the development and monitoring of food security programmes and projects.

1.2.3 Immediate Objectives and Outputs

Immediate Objective 1.   Timely and high quality information outputs, based on sound data and information, produced and appropriately disseminated at national and Zoba  levels.

- Output 1.1  Clearly identified and characterized food insecure and vulnerable population groups to be monitored by NFIS on a priority basis.

- Output 1.2 Information needs clearly identified for improved decision-making towards short-term interventions and medium/longer term policy formulation and food security programming.

- Output 1.3.  Sets of tested and validated food security and vulnerability indicators, integrated in the NFIS data base and available for use at national and Zoba levels.

- Output 1.4 Improved and sound databases at NFIS partner institutions relevant for the construction of food security indicators.

- Output 1.5 Early warning information produced and disseminated regularly in order to plan and monitor relief assistance.

- Output 1.6 Food balances produced and disseminated in order to meet information needs to plan food imports in a timely way.

- Output 1.7 Structural vulnerability assessments produced and disseminated for development planning and policy formulation.

- Output 1.8. Information outputs produced and disseminated to contribute to food security policy debates and development planning.

- Output 1.9. Awareness raised in the general public about food security concepts and about major food security issues currently facing Eritrea.

- Output 1.10 Regular crop and food needs assessments conducted under the coordination of the Ministry of Agriculture, the technical support of NFIS and the participation of main stakeholders.

Immediate Objective  2.  Improved human resource capacity at national, Zoba and Kebabi levels to collect, process, analyze, interpret and disseminate food security information.

- Output 2.1. Technical staff of the NFIS Unit adequately trained in integrated food security analysis and dissemination methods.

- Output 2.2. Technical staff at NFIS partner institutions adequately trained in data collection methods, data processing and analysis.

- Output 2.3.  Technical staff at Zoba level trained in data collection methods, data processing and analysis, and reporting methods.

- Output 2.4. Human resources at Kebabi level adequately trained in data collection and reporting methods.

- Output 2.5. Training materials developed and made available on data collection methods, data processing, analysis and dissemination.

Immediate Objective 3.   Strengthened institutional structures at national, Zoba and Kebabi levels for an efficient, effective and sustainable national food information system.

- Output 3.1  Optimal institutional structures and inter-institutional linkages developed at national, Zoba and Kebabi levels in support of the NFIS data collection, processing, analysis and reporting activities.

- Output 3.2. Effective information exchange mechanisms among NFIS partner institutions that facilitate the sharing and integration of food security related data and information.

- Output 3.3.  Effective communications infra-structure in place at national and Zoba levels for the efficient horizontal and vertical transfer of data and information.

- Output 3.4. Effective mechanism in place to continuously assess food security information needs, as well as institutional and technical capacities at national, Zoba and Kebabi levels.

1.3	Overall Project Progress

The project can be evaluated from two different perspectives.  Considering that the project was approved to start at the end of 2000 or early 2001, what was achieved as by April 2004 can be described as low implementation and delivery.    There are almost two idle years since project approval, and by the time activities started (up to date) the national counterparts have not been in place (with the exception of the Agro-meteorologist seconded in November 2003).

The second perspective should appeal more pragmatic, and it is what was done since real execution started, especially since end of December 2003.  The illustrative list below summarizes this period, and is mainly what was presented to the TPR in March 2003. A more detailed understanding of the overall progress can be achieved thorough a careful reading of key documents including:

- Project Progress Reports for phases I and II

- Project Document

- Backstopping Mission Report, August 2003

- Inception and Final Report of Mr. Norman Piccioni, former CTA.

- Final report of Mr. Graham Farmer, former CTA

- Inception Report of Mr. Byron Ponce-Segura, current CTA

- Aide Memoirs of backstopping mission from Mr. Mark McGuire (SAFR),  and Mr. Luca Alinovi (HQ)

- Tripartite Review report, 1999.

- Tripartite Review report, March 2004.

- Technical documents produced by the project

- Reposts on training activities

Some of the abovementioned documents (from phase I) are not currently available in digital format.  All attempts will be made to provide these at the time of the external evaluation.  Meanwhile, the review of achievements from 2003 up to April 2004 is as follows:

Regarding the progress achieved during phase II, this is a summary by project’s objective:

Immediate Objective 1: Timely and high quality information outputs, based on sound data and information, produced and appropriately disseminated at national, Zoba and sub-Zoba levels

To fulfil the mandate of dissemination of food security related information of NFIS, the project has been active in the collection, processing and dissemination of information in the domains of humanitarian food aid, agricultural emergency  assistance, food production, food prices, food balance sheets, nutritional status, vulnerability and agro meteorology.

The project also re-launched in January 2003 the temporarily disrupted NFIS Monthly Food Outlook bulletin and the Dekadal Agro-meteorology bulletin. These bulletins are disseminated in both electronic and hard copy forms to readers. Since the introduction of the electronic dissemination the readership of the bulletin has increased from around 60 local readerships to more than 250 both locally and internationally.  The content of the bulletin has been enhanced by including information on vulnerable groups such as war and drought victims; expellees from Ethiopia; refugee returnees from Sudan; internally displaced populations; hosting communities; HIV/AIDS affected and urban poor. In addition information on nutritional status, food distributions to vulnerable groups, food aid stocks, pledges and appeals are reported. Occasionally technical issues that have direct or indirect bearing on food security are also reported in the bulletins.

The project has recently introduced the NFIS-Forum: an internet discussion platform where interested individuals could raise food security related issues and post it on the plat form for discussion.

In the field of basic Information needs, the project has supported the preparation of National Food Balance Sheet, creation and improvement of database management systems in member institutions, introduction of remote sensing and satellite image interpretation for rainfall and vegetation monitoring, annual crop/livestock assessment and profiling of the different types of livelihoods.

To secure sustainability of the NFIS activities, the project has been supporting Information systems development. This activity is supported through the creation of workgroups from the member institutions. So far three work groups, namely food balance work group, remote sensing and image interpretation work group, market Information workgroup, agriculture monitoring have been formed. In addition the project has provided support to the Nutrition Surveillance System (NSS) and is a member of the team that prepared the Consolidated Appeal Process (CAP), Food Security Sectoral Work Group (FSSWG), and Data for Development Task Force (UNDAF) and the Food Aid Sectoral Work Group (FASWG).

As part of its networking mandates, the project presented two initiatives to the members of the External Support Group (ESG) of NFIS where they could come on board during the implementation of the initiatives. The two initiatives are:

- Agricultural Season monitoring – To minimize the workload of  the MOA staff at subzoba levels when reporting the monthly agricultural condition in their respective areas, the project has initiated a crop calendar for each activity against time of the year. Since reports will be based only on the activities that are executed during specific months, this is hopped will reduce the amount of time spend on reporting.

- Livelihood baseline - having a good understanding of community livelihoods would help to design proper intervention in times of crises. To this end the project has initiated a baseline study of livelihoods for the rural communities of Eritrea. The project has invited all stake holders to participate in this exercise and the indications are quite encouraging.

Immediate Objective 2: Improved human resource capacity at national, Zoba and sub-Zoba levels to collect, process, analyse, interpret and disseminate food security information

The training component is a major thrust of the project. So far the project has conducted a number of on the-job and formal training programs for NFIS and its member institutions.

Four training programmes were conducted for NFIS and its partner institutions. Two training programs one at the basic level and a second one at the advanced level in satellite image interpretation for monitoring rainfall and vegetation for early warning were conducted. Ten participants from five member institutions have attended the training.

This was followed by two different levels basic and advanced level training in database management. The training was attended by seventeen and thirteen participants from nine institutions.

To build the national food balance sheet, the project identified five member institutions that would contribute data for building the Food balance Sheet. From these institutions eight participants were selected and trained in the preparation of balance sheets. The five member institutions have formed the Food balance Workgroup whose mandate is too build the annual food balance sheet.

To strengthen the market information system, the project has selected and trained 13 participants from member institutions in the use of the FAO AgriMarket Database System. Some of these participants will form the Market information workgroup and will be responsible to oversee activities of the market information.

The project has provided on the job training to the newly recruited Agro meteorologist that joined NFIS. The project is also working on identifying suitable training program for the agro-meteorologist.

Two one day workshops that covered food security issues and profiling of rural livelihoods were held in Debub and Gash Barka as a prelude to the crop monitoring and livelihood baseline studies that will be implemented in rural Eritrea.

The project has also provided support to the Africover project which is building GIS capacity within the ministry of Agriculture.

Immediate Objective 3: Strengthened institutional structures at National, Zoba and sub-Zoba levels for an efficient, effective and sustainable National Food Information System (NFIS).

To improve the functioning of the NFIS in delivering the services expected, the project reviewed the strategy document “Strategic Approach to Food Information Needs in Eritrea” taking into account the new demands and changes in the structure of the government. To this end a full set of project’s recommendations were endorsed and implemented. This include a new institutional set up that increased the membership from seven to thirteen government institutions, a shift of chairmanship from the Ministry of Agriculture to the Ministry of National Development which is the main coordinator of Food Security and Poverty Reduction Strategies, reduction of Steering Committee membership from nine to five, more support to the Nutrition Information System and vulnerability issues, creation of a window for external support group (NGOs, UN Agencies and other International organizations) and more presence of NFIS at sub national levels was proposed by the project and endorsed by government.

Based on the strategy document and last TPR recommendations the project has already established the Zoba Food Information System (ZFIS) that will be run under the Zoba Food Information Committee in two zobas namely Zoba Debub and Zoba Gash Barka. In Both Zobas the project is planning to conduct crop monitoring and livelihood profiling exercises.

Preliminary discussions is also underway to establish the ZFIS in Zoba Anseba, Zoba Maekel and Zoba Northern Red Sea

As a mechanism to alleviate lack of counterparts, the project initiated the formation of work groups from member institutions that would take the responsibilities of jointly overseeing the activities of information gathering activities of NFIS.

2.     Purpose of the Evaluation

Considering the prevailing socio economic in the country for the past years; the institutional framework for food security; the spirit of the agreements between the project’s parties and the specific objectives, outputs and activities of the project; the evaluation mission should analyse the achievements and areas for improvement, followed by specific recommendations on priority activities up to the end of the project (June 30, 2005) and beyond.

More specifically, the mission will focus on the following issues:

- the pertinence and role of the project within the Eritrean institutional context for food security;

- the project achievements to date and the perspectives for attaining expected results;

- the necessary adjustments, if any, to the project’s plan of work and approach, in order to ensure and strengthen its sustainability and impact.

Particular attention will be paid to the overall institutional and strategic framework for food security in the country, including and foremost the next-to-be-released national Food Security Strategy.

3. 	Scope of the Evaluation

The mission should assess and consider as scope of work the following:

- Relevance of the project under current development priorities and needs of the Government of the State of Eritrea.

- Clarity and realism of the project's development and immediate objectives, including specification of targets and identification of beneficiaries and prospects for sustainability.

- Quality, clarity and adequacy of project design including:

- clarity and logical consistency between inputs, activities, outputs and progress towards achievement of objectives (quality, quantity and time-frame);

- realism and clarity in the specification of prior obligations and pre-requisites (assumptions and risks);

- realism and clarity of external institutional relationships, management and institutional framework for implementation and the work plan.

- Efficiency and adequacy of project implementation, focusing in particular on the period 2003-2004 and including: availability of funds as compared with budget for both the donor and national component; the quality and timeliness of input delivery by both FAO and the Government; managerial and work efficiency; implementation difficulties; adequacy of monitoring and reporting; the extent of national support and commitment and the quality and quantity of administrative and technical support by FAO.

- Project outputs and activities since 2003 to date, quantitative and qualitative, and perspectives of sustainability, with particular attention to the following:

- enhancement of technical skills and operational capacity of the NFIS Technical Unit towards its functions;

- technical contributions to strengthen and expand the National Food Information System;

- overall improvement of the institutional response to user’s needs in terms of food security information;

- mainstreaming of the gender and poverty dimensions into the National Food Security Information System;

- steps undertaken by the project to support the national institutions towards the adoption of a balanced and phased approach to move from emergency through recovery towards development; to move beyond just food availability to stability, access and biological utilization; and from national aggregated information to regional, community and household empowerment through information;

- Recommendations to adjust project activities and strengthen its potential for sustainability and impact. These will focus mainly on the following aspects:

- Priorities and resources up to the end of the project in June 2005;

- Activities needed to institutionalize the contributions of the project;

- Possible technical assistance needs to strengthen the NFIS;

4. 	Composition of the Mission

The mission will comprise individuals with formal training in agricultural economics, socio-economics or longer term experience in food security policy issues.    At least two members of the mission should have strong background in either one of the following disciplines: household food security, vulnerability assessment, early warning and food information systems development. The proposed composition of the mission is:

- Team leader, trained in socio-economics with experience in food security livelihoods and community development, farming systems and in project evaluation.  The Team Leader will represent FAO.

- Specialist in information systems and data management.  This specialist will represent the Italian Cooperation.

- Specialist in poverty/vulnerability assessment and statistics, possibly with experience on food security issues. He or she will be representing the Government of the State of Eritrea.

The Mission’s members should be independent and thus have no previous involvement with the project formulation, implementation or backstopping. They should preferably have experience in project evaluation and a good understanding of current and historic issues of Eritrea.

- Timetable and Itinerary of the Mission.

The mission should be a total duration of 3 weeks, starting with a technical briefing at FAO Headquarters. This briefing could be one or two days long before travelling to Eritrea. The mission should spend maximum 3 weeks in Eritrea, including the preparation of a final draft report. Considering the enormous difficulties to travel from Asmara to any other African city, especially Harare or Accra, it is recommended to debrief in FAO HQ and if necessary, a video-conference could be arranged in Rome to communicate with Accra of Harare.  A tentative travel schedule is provided below.

Tentative Travel Schedule (September 2004):

The following tentative schedule is proposed, based on the estimate of time necessary to accomplish the different steps of the evaluation. Once the overall proposal will be approved, it will be adjusted according to actual starting dates.

Days 1 and 2	Briefing in Rome

Day 3	Travel to Asmara

Day 4	Briefing with FAOR, Minister of Agriculture, Italian Ambassador

Day 5-6	Meetings with project’s team and NFIS Technical Secretary

Day 7	NFIS Technical Committee and NFIS Steering Committee.

Day 8-9	Meeting with Debub or Gash Barka Food Information Committee

Day 10-11	Meetings with government institutions, project team and NFIS Technical Secretary and other main stakeholders

Day 12-16	Preparation of draft final report and debriefing meetings

Day 17	Travel back to Rome

Day 18	Debriefing at FAO HQ

Day 19-21	Finalisation of the report according to comments from HQ, by Team leader

6. 	Consultations

The mission will be assisted by the ESAF/Food Systems Economist based in the Sub-Regional Office for Southern and Eastern Africa in Harare, Zimbabwe, other officers within ESAF/HQ, and the staff of project GCPS/ERI/002/ITA, the Technical Secretary of NFIS and the Secretary of the NFIS Steering Committee while in Asmara. This will not compromise the necessary independence of the evaluation mission.  The mission can freely liaise with FAO, Government and donor staff, as well as with other stakeholders considered appropriate. Although the mission should feel free to discuss with the authorities concerned anything relevant to its assignment, it is not authorised to make any commitments on behalf of the Government, the donor, or FAO.

7. 	Reporting

The mission is fully responsible for its independent report which may not necessarily reflect the views of the Government, the donor or FAO. The report will be written in conformity with the headings structure provided by FAO. A copy of standard structure for the report will be provided to the mission right upon their arrival in the country.

The draft report will be completed in the country and the findings and recommendations fully discussed with all concerned parties and, wherever possible, consensus should be achieved. The mission will discuss its conclusions and recommendations in a de-briefing meeting to be held in Asmara; the conclusions and recommendations should provide sufficient technical guidance and specify the resource requirements, to enable FAO, the donor, and the Government of the State of Eritrea to make informed decisions for the residual project life. Furthermore, the mission's recommendations should provide guidance on the need for further technical assistance and donor support beyond the current project.  The mission will also complete the FAO Project Evaluation Questionnaire.

The mission leader bears responsibility for preparing the final evaluation mission report, which will be submitted to FAO within two weeks of the completion of the mission. FAO will submit the report to Government and donor together with its comments.

IGAD was previously called the Intergovernmental Authority on Drought and Development