Strengthening and Expansion of the National Food Information System of ERITREA

(GCPS/ERI/002/ITA)

Tripartite Evaluation Mission

Final Report

Asmara and Rome, September-October 2004

Table of Contents

Table of Contents	ii

Abbreviations	iii

Executive Summary	iv

Recommendations	vi

1.	Introduction	1

2.	Background and Context	1

2.A	The national context	1

2.B	The Project	3

3.	Assessment of Project Objectives and Design	4

3.A	Justification	4

3.B	Objectives	5

3.C	Project Design	6

4.	Assessment of Project Implementation, Efficiency and Management	7

4.A	Project Budget and Expenditure	7

4.B	Activities and Outputs	7

4.C	Government Support	14

4.D	Project Management	14

4.E	Technical and Operational Backstopping	15

5.	Assessment of Results and Effectiveness	16

5.A	Effects and Impact	16

5.B	Sustainability of Results	16

5.C	Gender Equity in Project Implementation and Results	17

5.D	Cost-effectiveness	18

5.E	Major Factors Affecting the Project Results	18

6.	Conclusions and Recommendations	19

6.A	Conclusions	19

6.B	Recommendations	20

6.B.1	Recommendations for the Government of Eritrea, the Government of Italy and FAO	21

6.B.2	Recommendations for the Project and NFIS Technical Unit	21

6.B.3	Recommendations for FAO	22

6.B.4	Recommendations for the Government of Eritrea	23

7.	Lessons Learned	23

Annexes	24

1	Terms of Reference

2	List of places visited and key persons met by the mission

3	List of documents and other reference materials consulted by the mission

4	Planned versus actual outputs and activities

5	Members of the Support Group

6	Background information on database development

7	Specific recommendations for NFIS IT development

Abbreviations

BH	Budget Holder

CTA	Chief Technical Advisor

ERREC	Eritrea Relief and Refugees Commission

ESAF	Food Security and Agricultural Projects Analysis Service

ESNA	Nutrition Planning, Assessment and Evaluation Service

ESNP	Nutrition Programme Service

FEWS-NET		Famine Early Warning System Network Project of USAID

FIC	Food Information Committee at Zoba level

FSAU	Food Security Analysis Unit

FSS	Food Security Strategy

GDP	Gross Domestic Product

GIS	Geographic Information System

HQ	Headquarters

IBiMET	National Research Council (CNR), Institute of BioMeteorology

IGAD	Intergovernmental Authority on Development (previously IGADD)

I-PRSP	Interim Poverty Reduction Strategy Paper

JRC	Joint Research Centre of the European Commission, Ispra, Italy

GoE	Government of the State of Eritrea

GoI	Government of Italy

LoA	Letter of Agreement

LSBS	Livelihood Systems Baseline Study

MoA	Ministry of Agriculture

MoH	Ministry of Health

MoLG	Ministry of Local Government

MoND	Ministry of National Development

NDVI	Normalised Difference Vegetation Index

NFIS	National Food Information System

NGO	Non Governmental Organization

NSEO	National Statistics and Evaluation Office

NTE	Not to be Exceeded

ProDoc	Project Document

RAF	FAO Regional Office for Africa

RFE	Rainfall estimate, FEWS satellite imagery based on CCD

SAFR	FAO Sub-Regional Office for Africa

SC	Steering Committee

SDAR	Rural Institutions and Participation Service, FAO

SDWW	Gender and Development Service, FAO

TA	Technical Advisor

TC	Technical Committee

ToRs	Terms of Reference

TPR	Tripartite Review Meeting

TU	Technical Unit

UNDP	United Nations Development Programme

USAID	United States Agency for International Development

WC3	World Wide Web Consortium

WFP	World Food Programme (United Nations)

WG	Working Group

Executive Summary

- The project “Strengthening and Expansion of the National Food Information System, GCPS/ERI/002/ITA” aims at supporting the National Food Information System (NFIS) in Eritrea, including its extension to decentralized administrative levels. In March 2004, fifteen months after the start-up of the second Project phase, a Tripartite Review Meeting took place, and recommended, among others, the organization of an external mid-term evaluation. This was fielded in September 2004 (18 September-1 October 2004) and was composed of Dr Ghiorgis Tecle, representative of the Government of Eritrea (GoE), Mr Michele Ieradi, representative of the Government of Italy (GoI), and Ms Tullia Aiazzi, representative of FAO and team-leader. Intended outputs were the assessment of the Project’s strengths and weaknesses, and the formulation of recommendations for the future. A debriefing meeting took place in Asmara on the basis of a draft Executive Summary, at the presence of the Minister of Agriculture, the Ambassador of Italy, the FAO Representative, the Secretary of NFIS SC, the Italian Cooperation and the Project.

- To meet its mandate, NFIS coordinates and liaises with a number of other governmental institutions to use the information each of these produce, and analyses and elaborates it within an integrated framework to produce timely food security information, for the final use by decision makers in the Government and in the international community. The structure of NFIS Steering Committee and its chairmanship at the Ministry for National Development (MoND), as well as the membership of NFIS Technical Committee, give it adequate leverage and access to key institutions. In consideration of the large rural base of Eritrean economy and society, and the role agriculture plays in food security in the country, the present location of NFIS Technical Unit (TU) within MoA is justified for the time being. NFIS role is also recognized in the national Food Security Strategy.

- The Government of Eritrea supported the Project since its inception. NFIS is housed in the Ministry of Agriculture premises, and is provided with office space for project and NFIS staff. Senior top management in MoND and in MoA expressed appreciation of both NFIS publications and Project’s assistance. Representatives from Technical Committee (TC) member institutions participate in monthly meetings and supply required data and information to NFIS on a regular basis. Moreover, very recently MoA appointed the Head of NFIS TU, as a counterpart to the Project.

- It should be reminded that this is the report of a mid-term evaluation: many activities are planned to be carried out over the next months, and outputs will be achieved only in due time. Indeed, although outputs are still falling short of plans, the Mission is aware that setting-up procedures and mechanisms to ensure NFIS can operate and fulfil its role was and is a time-consuming task which still absorbs most energy of Project staff. Main groups of activities until now were the following:

- capacity building at NFIS and among partner institutions, to improve the collection, processing and elaboration of information on food security in Eritrea; set-up of data transfer process from TC partner institutions to NFIS, organization of Working Groups on different topics, in-service training, training on the use of new software and on other technical issues, regular TC meetings, etc.

- publication of the Monthly Food Security Outlook and of the Agro-met Update, the latter on a decade basis during the rainy season and monthly otherwise;

- proposal, discussion and consensus building on the adoption of the Livelihood Systems Baseline Study (LSBS) as NFIS methodological framework for mapping and assessment of vulnerability and food insecurity in Eritrea;

- testing of the LSBS in Zoba Debub, to the step of sub-Zoba level workshops;

- organization of five out of six Food Information Committees (FIC) at Zoba level (Southern Read Sea Zoba still missing) through an information and awareness-raising workshop in each Zoba.

- The Mission’s main findings and comments are as follows:

- there is evidence of the good and fruitful interaction and collaboration between TC members and NFIS, and between NFIS and the international community in Eritrea;

- a working procedure and a habit of transfer of information from a number of institutions to NFIS has been set up and acquired in each institution’s working routine, which allows NFIS to produce its bulletins;

- NFIS publications are well known and appreciated among stakeholders, although a few issues were raised: the scarce diffusion of both bulletins within national institutions, even among NFIS TC members and Zoba FIC; the desirability of diffusing at least the Highlights section in Tigrinya at a wider level; the quality and reliability of data diffused; a request for more analysis, also forward-looking. The last two are partly related: reliability and quality of data is a wider issue, which cannot be solved by NFIS or the Project alone; more analysis with unreliable data at the moment would be a spurious and misleading exercise, although this should be one of the main tasks of NFIS in the future;

- the focus on Zoba level for data collection, data entry, processing and first analysis is pivotal in the management of the whole information process from the grass-roots level upward, before partial transfer of this information to the central level, for consolidation and further analysis;

- the Project is also giving visibility to the donor: the Italian Cooperation logo appears on all pages of both the Monthly Food Security Outlook and the Agro-met Update. The logo appears as well on NFIS Website, where a link exists to other Italian-funded, FAO implemented projects in Eritrea. Interlocutors are usually aware of the Project being funded by the Italian Cooperation, also among Governmental stakeholders.

- A number of problems have affected Project’s performance, among which the well understood and prevailing difficulty of GoE to meet its commitments in terms of national staff assigned to NFIS. So far, one staff (Agro-meteorologist) was appointed in November 2003 and the Head of NFIS TU was appointed in September 2004. According to information available to the Mission, one position (socio-economist) might be filled by the end of the year, but no perspectives seem to exist for appointing the data-manager/editor. These delays have increased the workload for Project staff, with an effect on rate of implementation, and have hindered transfer of know-how and skill, thus jeopardizing the future institutional sustainability of NFIS.

- The Mission also found a few major weaknesses:

- throughout Project activities and outputs, gender and social development issues at large were overlooked;

- the methodology proposed for the livelihood systems baseline study has to be revised in terms of field-level validation process and definition of key indicators;

- in relation to the methodology currently used by the Project to gather information for its analysis and publications, the Mission considers some adjustments are necessary to improve the overall reliability of the process.

- GCPS/ERI/002/ITA has achieved a number of important results so far, and is heading in the right direction to consolidate them. As to be expected being it at two thirds of its life, substantial work has still to be carried out to meet planned outputs. In particular, efforts will have to be focused on the following:

- building capacities at Zoba level and beyond for data collection, data entry, processing and analysis,

- fine-tuning the livelihood systems approach for vulnerability and food insecurity mapping;

- mainstreaming gender and social issues in data collection and analysis among NFIS partner data-providers and in NFIS outputs;

- improving the information management process.

- The Mission considers that all these outputs, to be meaningful and sustainable in the long term, require more time than presently allowed by the present Project NTE date. Tasks to be accomplished are complex and require careful planning and implementation. The Mission also considers that a new project should be launched at the conclusion of GCP/ERI/002/ITA, to strengthen capacities at Zoba level and below and to further consolidate NFIS role within the national Food Security Strategy. But the new endeavour should build upon solid results stemming from the present initiative, to be really effective in consolidating the whole chain of information collection, processing, analysis and diffusion.

Recommendations

- The Mission recommends that the Project be extended to the end of December 2005, by six months beyond the present NTE date of 30 June 2005. This to allow time to accomplish the foreseen tasks and accommodate for the recommendations below. The extension should be budget neutral: no need should arise for any budget increase, if recommendations formulated below are endorsed.

Recommendations for the Project and NFIS Technical Unit

- The Mission recommends that the LSB methodology, in particular the validation procedure of proposed classification and the identification of key indicators for vulnerability and food insecurity, be thoroughly revised to include work at village level with all stakeholders. This will require more time devoted to the exercise in each Zoba, and mobility allowed to the teams responsible for field-work. It is recommended that a national or international social development expert, with experience in work at field level, be recruited to support the Project to fine-tune the validation methodology, and be responsible for training team workers and lead the field work. This may require two to three weeks on average per Zoba, plus preparation time. Results from the field analysis could then be compiled at NFIS level by the Vulnerability Assessment consultant.

- The Mission recommends that gender and social development issues be streamlined into NFIS activities and outputs. A national or international consultant, depending on availability and competence, should be recruited. It is reckoned that at least two months should be the necessary, including training of NFIS staff at central and Zoba level, and NFIS partners within the TC. This consultancy should be closely coordinated with the consultancy recommended in the previous point.

- The Mission supports the Project proposal to organize and carry out an intensive training for Zoba-level staff on food security issues. The training should be structured in such a way to allow trainees to participate actively in the livelihood systems baseline study in their respective Zobas, providing them the opportunity for field-level work training. It is suggested that international and national consultants be recruited to organize and carry out this training, to allow the proper mix of necessary skills and expertise. Also, flexibility in the consultants’ selection must be allowed, to meet planned time schedule. Last but not least, adequate attention will have to be paid to the selection of trainees, to guarantee the required level of competences, and to ensure within possible limits their return to work to their Zoba administrations.

- The Mission recommends that the Ministry of Labour and Human Welfare be invited as a member of NFIS Technical Committee, in consideration of its role in fighting vulnerability in the country.

- The Mission recommends a number of actions to be taken on information management, to the benefit of NFIS, Zoba administrations and MoA Remote Sensing/GIS unit. Main areas of activity recommended are as follows:

- set-up an optimal process at NFIS level for management of data provided by partner institutions, which should allow in the future searches for historical data and any other more complex analysis;

- create a Zoba databases, to gather at this level information collected at village and desk-level;

- support each NFIS partner institutions to organize its own information into a database with some help from NFIS staff. The TC members will share part of this information with NFIS to allow the production of the bulletins, as they already do now in hard copy format. In the long term, information stored in this way could be integrated into a single national database, to be possibly set up at NFIS;

- support the MoA Remote Sensing/GIS Unit, to allow an incremental improvement in the quality of its outputs, which will be beneficial to NFIS in the immediate future, when data layers coming from the livelihood systems zoning will have to be recorded and analysed.

- All other Project activities will be continued as per the present plan of work. The Mission recommends Project staff to make a particular effort to involve the recently appointed Head of NFIS in their implementation, so as to ensure the maximum possible transfer of skills and knowledge by the end of the Project.

- Recommendations above have implications for Project activities and on requirements for expertise. The Mission recommends that a Budget Revision be done to allow funds for a bulk of consultant person/months to be made available to recruit the expertise required on gender and social analysis, field level work, training of Zoba staff, database development and any other requirement which could rise. Expertise will also still be required on vulnerability assessment, though in the Mission’s opinion not on a full time basis. The P4 International Advisor on Food Security and Vulnerability Assessment post is due to phase out by the end of 2004, but arrangements can be made to have him still on board for the required periods throughout the year 2005. A more precise estimate of actual workload will have to be done in consideration of the availability of the other consultancies recommended.

Recommendations for FAO

- In consideration of the wide range of technical issues relevant for the Project and for NFIS, namely gender, participatory methodology, nutritional issues, the Mission suggests that SDWW, SDAR and ESNP be included in the Task Force of GCPS/ERI/002/ITA. This to allow proper backstopping from these services, as well as feedback from the Project into FAO normative activities on a wider scale.

Recommendations for the Government of Eritrea

- The Mission agrees strongly with the recommendations formulated by the TPR in March 2004, to complete appointment of NFIS staff as soon as possible, to allow adequate capacity building during the remaining life of the Project.

- The Mission is aware that work at Zoba level and beyond depend on a number of factors, including availability and time of Zoba staff, security conditions, fuel availability, etc. Within this complex picture, the Mission recommends GoE to facilitate Project activities at decentralized level insofar as possible, to allow proper and meaningful implementation of the livelihood systems baseline study and vulnerability assessment zoning exercise.

- The Mission recommends that GoE seeks support from its development partners, to improve capacities and performance of NFIS partner institutions, aiming at the production of better quality data and information on food security related matters at country level. In particular, agricultural statistics, market monitoring, ground validation of remote sensing information, and agro-meteorology deserve priority attention. The Mission is aware of advanced discussions on the first two themes with FAO, which it fully supports, as well as of a general interest at UNDP level in this regard. This could be instrumental for the preparation of full fledged proposals in favour of other institutions members of NFIS, not benefiting yet of specific support.

- Further, for consideration in the medium to long-term, the Mission suggests that the role of NFIS be expanded to become the think-tank of GoE for all issues regarding food security, including the follow-up and monitoring of the national Food Security Strategy, macro analysis and scenario building within this framework.

Recommendation for the Government of Eritrea, the Government of Italy and FAO

- The Mission recommends that a new project proposal be formulated by June 2005, with external technical support from, to be discussed and approved by concerned parties by the end of that year. This should focus on capacity building at Zoba level and beyond, and on strengthening NFIS role at central level within the Food Security Strategy framework.

# Introduction

- The project GCPS/ERI/002/ITA, referred from here on as the Project, became operational in December 1996, to last 24 months with funds from the Italian Government. The border conflict between Eritrea and Ethiopia from mid-1998 to end of 2000, delayed implementation and asked for progressive adjustments to planned activities. A new phase was funded again by the Italian Government in 2000, but due to a number of reasons, it took off only in January 2003 with the arrival of the new Chief Technical Advisor (CTA) to Eritrea.

- In March 2004, the second Tripartite Review Meeting (TPR) took place and formulated a number of recommendations, including a revised version of Project objectives and outputs and the organization of a mid-term evaluation mission, which “..should take place as soon as possible, preferably in June 2004, to review in depth the project achievements and progress made towards stated project objectives and outputs. The Evaluation Mission should make clear recommendations on priority activities for the remaining period of the project, while also assessing sustainability of project results beyond June 2005, and the need for possible future interventions.”

- The Tripartite Evaluation Mission (referred to as the Mission) took place in September 2004 (18 September-1 October 2004) and was composed by Dr Ghiorgis Tecle, representative of the Government of Eritrea (GoE), Mr Michele Ieradi, representative of the Government of Italy (GoI), and Ms Tullia Aiazzi, representative of FAO and team-leader. The team undertook extensive meetings and discussions with all stakeholders in Eritrea, including high-level GoE representatives, at central and decentralized level, the donor, the FAO Representative, the National Food Information System (NFIS) and Project staff, partner institutions and organizations. Meetings had been held also in FAO Headquarters to assess links and collaboration between the Project and FAO technical units. A debriefing meeting took place in Asmara on the basis of a draft Executive Summary, at the presence of the Minister of Agriculture, the Ambassador of Italy, the FAO Representative, the Secretary of NFIS SC, the Italian Cooperation and the Project. This is the final report, which takes into account comments formulated and submitted by concerned parties to the Evaluation Mission.

- The Mission wishes to thank all those who contributed to its successful implementation, namely the Minister of Agriculture, the Ambassador of Italy in Eritrea and the FAO Representative in Eritrea. Also, it wishes to thank the project staff and NFIS partners who made available their time to meet the Mission and provide it with useful information. In particular, warmest thanks go to the Italian Cooperation Office in Eritrea, who seconded as a resource person to the Mission Mr Alessandro Dinucci. His contribution was greatly appreciated by the team members.

# Background and Context

## The national context

- Eritrea is a young nation that became independent from Ethiopian rule after thirty years of armed struggle, through a UN supervised referendum in 1993. The country has a total population of about 3.63 million, 70-80% of which considered rural. One of the Low Income Food Deficit countries in the world, its annual GNP per capita in recent years was in the range of US$ 170-220. During the period 1992-1997, GDP growth reached 7%, but since 1998, it declined to about 4%, to fall faster in more recent years, due to drought and to the border conflict with Ethiopia. Since the Peace agreements were signed at the end of 2000, efforts are taken to restore the development momentum, but the pursuit of poverty alleviation and food security faces considerable challenges.

- According to the recent National Living Standards Measurement Survey (LSMS) the overall poverty estimate for Eritrea is 66% with about 37% below the poverty line. Poverty is concentrated in rural areas, and it is usually believed to be most acute in the most arid areas, although some different hypothesis were formulated recently. Urban poverty is also believed to be on the increase due to limited job opportunities and weak economic activities in urban centres. Approximately 400,000 people are internally displaced, returning refugees, deportees. Together with demobilized fighters, all of them have to be reintegrated into some economic activity, and most of them back to the agricultural sector.

- The contribution of agriculture to the country GDP has been modest and accounts for less than 20%. This is mainly due to the dominance of a rain-fed subsistence farming model of production, whose outputs are low value agricultural products, and to the prevailing semi-nomadic pattern for the livestock sector. Rural poverty, and the structural food insecurity of the country, was further exacerbated since 1998 by war, and more recently, by drought. Domestic agricultural production being well below requirements also in “good years”, it was always supplemented through imports: typically 25% to 50% of the demand is met from this source. Food aid delivery being the other source of food for the country, dependence on it has increased and remains high.

- Eritrea strongly needs to effectively consolidate and expand national food production as well as food imports. Practitioners and policy makers in the country have well recognized that the current state of affairs of agricultural production arrangements is not sustainable. Thus there seems to be a likely shift of strategy in the medium term to promote integrated farming by encouraging irrigation development in the high potential areas.

- Since 1996, the Government is highly committed to a decentralisation strategy, whereby greater autonomy of decision and responsibility over implementation is given to the Zoba and sub-Zobas level (region and province), for all initiatives concerning their development. All line ministries are represented at Zoba level, and respond to the Zoba Administrator, who is appointed by the President. In principle, only regulatory and normative functions are retained at the ministries’ central level.

- Between 2003 and 2004, the GoE produced in parallel the national Food Security Strategy (FSS, April 2004) and the Interim-Poverty Reduction Strategy Paper (I-PRSP, April 2004), both prepared under the leadership of the Ministry of National Development (MoND) and through an in-depth consultation process among national institutions. The FSS at national level rests upon three pillars: Enhancing the domestic production capacity in agriculture and fisheries; Enhancing national capacity to import adequate quantity of food by increasing export earnings; Using Food Assistance efficiently. The third pillar, which includes “..the establishment of mechanisms to anticipate national food production estimates, projected supply gaps and needs for food assistance, as well as use of food assistance in ways that promote the nation’s development..” mentions explicitly NFIS strengthening as one of the priority measures to achieve these objectives. Also, the Strategy foresees setting up a monitoring and an evaluation mechanisms, for both national and household food security.

- Within this complex context, the importance of making available to decision and policy makers, data and information as sound as possible on agricultural activities and outputs, vulnerability levels for the different groups of population, climate forecasts, prices behaviour, etc., cannot be overemphasized. NFIS has therefore a vital role to play within the national effort of Eritrea to alleviate poverty and attain food security.

## The Project

- At independence in 1993, the Government of the State of Eritrea established an Early Warning and Food Information System: the development of a reliable food information system in these areas was seen as a condicio sine qua non to effective planning of food imports and relief operations. Initial assistance to the system was provided with the support of Italian funds and FAO as implementing agency, through the regional project GCP/RAF/256/ITA, “Early Warning and Food Information System for Food Security”, based at IGADD. This initiative was complemented in Eritrea by the FAO funded bridging Technical Cooperation Project TCP/ERI/4451 “Preparatory Assistance for the Establishment of a Food Information System”. These projects reviewed the availability of data and the requirements for technical assistance of the Ministry of Agriculture (MoA) and participating agencies. The early warning system evolved quite early on into the National Food Information System.

- In 1996, the parties concerned (GoE, GoI, FAO and IGAD) agreed on a new proposal stemming from the previous experience, and the Project, titled “Assistance for Strengthening the National Food Information System in Eritrea”, started officially in December 1996 with the CTA arrival to Asmara. The project was housed at MoA and worked alongside the NFIS Technical Unit. Partner institutions of NFIS were also involved, through individual contacts and regular meetings of the NFIS Technical Committee (TC). Anticipated support from IGAD activity at regional level was not sustained and the project developed and progressed as a national endeavour.

- Activities were on-going, when the border conflict between Eritrea and Ethiopia escalated, and international staff was evacuated in June 1998. The Project therefore came to a mandatory halt until technical assistance was resumed between June 1999 and July 2000, with small additional funding from the donor. The first Project TPR took place in October 1999, and “..indicated that the project had performed well, especially considering the difficult prevailing circumstances. Resources had been used appropriately in response to declared needs and constraints upon the project activities were relevant. At the same time, the work envisaged in the Project Document had not been completed in all aspects, for a variety of reasons.” The TPR also recommended that a second project phase be formulated (April 2000). The new Project Document (ProDoc), with new title “Strengthening and Expansion of the National Food Information System in Eritrea” but unchanged project code, was signed in the second half of 2000 and made provisions for a new additional budget, planned to last 30 months. Activities were due to start soon, but recruitment of the CTA proved much longer than foreseen. Eventually, the second phase started in January 2003.

- A related FAO-supported intervention was carried out from November 1998 to December 2000, the 15-months project TCP/ERI/8821 “Development of Crops Statistics Methodology”, dealing with the development of a crop statistics methodology. This project had as its main objective to ensure a timely and reliable flow of data/information on food, agriculture and livestock, providing information outputs that should eventually feed into NFIS. In 2003, two staff from National Statistic and Evaluation Office (NSEO) also took part into an FAO workshop in Accra on agricultural statistics.

- Since start-up, the Project has used maps and outputs produced by the Africover project, funded by Italy and implemented by FAO. The Project also is the key responsible for the organization and follow-up on behalf of FAO of the Joint FAO/WFP Crop and Food Supply Assessment in Eritrea. Further, it collaborates closely with other FAO programmes, such as: i) GIEWS (FAO Global Information Early Warning System), responsible for the analysis and diffusion at global level of early warning and food security information coming from all countries; ii) EMPRES/Locust and Armyworm Control; iii) with FIVIMS; and with a number of FAO services including AGSP on agriculture market information issues, SDRN on remote sensing and ESNA on food composition tables, etc.. Also, the formulation mission for GCP/ERI/008/EC, Technical Support to the Ministry of Agriculture (Food Security programme) closely interacted with the Project to avoid overlapping and duplications in outputs and activities.

# Assessment of Project Objectives and Design

## Justification

- As stated above, the present Project is the second phase of an intervention launched in 1996, to contribute to build the capacities of the young Government of Eritrea towards setting up a food security information system. A very summarized version of the overall context for decision making at that time should include the following factors: i) the structural food insecurity of the country, due to its particular geographic position and topography; ii) the highly diversified patterns of agricultural and livestock production systems co-existing within the national boundaries, and their high dependence on climatic vagaries because of the lack of infrastructures and services; iii) the GoE policy to plan development from the grass-roots level and to build its own capacities and human resources.

- The TPR mission of October 1999, during the first phase of the Project, identified the following needs to be met by further assistance:

- strengthening of partnerships with Government and non-governmental agencies concerned with food information and food security;

- comprehensive coverage of urgent information needs related to acute food insecurity caused by emergencies;

- capacity building to address human resources constraints faced by Government agencies;

- extension of data collection and dissemination of information products to sub-Zoba level, and

- improved coverage and balance between NFIS information components, particularly through the inclusion of data components (vulnerability analysis, household food security determinants) relevant for access to food concerns and issues.

- The strategy developed during the first project phase for NFIS role and mandate set the basis for meeting the complex needs of a food security information system within the national institutional environment, so as to allow the different elements to be brought together under a single framework.

- The Project formulated in 2000 took into account all the above factors and elements, and focused appropriately on providing technical assistance for capacity building at central and decentralized level. The Mission considers that the vision for NFIS formulated at that time was appropriate. Its further refinement along the years have contributed to adjust it to rapid changing circumstances, and have proved the soundness of the first core design, as well as its in-built flexibility, necessary for any long-term sustainability.

## Objectives

- The ProDoc for the first phase (1996-2000) stated as Development Objective “Enhanced food security at the national level and for food insecure groups of the population”. Two Immediate Objectives were agreed as follows: “Institutional capacities and linkages developed in support of an integrated national food information system” and “Methods and procedures adapted/developed, documented and implemented for the acquisition and management of agronomic information for forecasts and estimates of crop and livestock information”.

- The ProDoc for the second phase (foreseen for 2001-2003, actual implementation 2003-2005) states as Development Objective: “A substantial reduction in chronic food insecurity, and in vulnerability to temporary food insecurity, of the people of Eritrea at national, community, household and individual levels.” The Intermediate Objective is “An effective, efficient and sustainable national food information system in place that provides decision-makers from multiple sectors at national and sub-national levels, with accessible, timely and reliable food security and vulnerability information for the identification and characterisation of the food insecure, the assessment of food emergency conditions, the monitoring of relief assistance, including food donations, the formulation of food security policies and strategies, and the development and monitoring of food security programmes and projects.” Three Immediate Objectives were also set:

- Timely and high quality information outputs, based on sound data and information, produced and appropriately disseminated at national, Zoba and sub-Zoba levels.

- Improved human resource capacity at national, Zoba and sub-Zoba levels to collect, process, analyse, interpret and disseminate food security information.

- Strengthened institutional structures at national, Zoba and sub-Zoba levels for an efficient, effective and sustainable national food information system.

- In March 2004, the TPR revised the wording of the Immediate Objectives, to make them more pertinent and realistic under the circumstances of implementation. The version presently valid for the Project, and analysed by the Mission, is therefore the following:

- Timely and high quality information outputs, based on available data and information, produced and appropriately disseminated to end users;

- Improved human resource capacity from central down to Kebabi levels to report, collect, process, analyse, interpret and disseminate food security information;

- Strengthened NFIS institutional structures from central down to Kebabi levels for an efficient, effective and sustainable food security information system.

- Overall, the objectives are quite clear, and there is a direct and straightforward link between the Immediate Objectives and the Intermediate Objective. The initial wording of the first Objective possibly set too ambitious targets in terms of the quality of information available to NFIS, since the latter could not possibly influence, but in limited terms, the capacity of partner institutions to produce reliable data in their respective fields of actions.

- The third Objective in the revised version calls for a more specific responsibility within NFIS, to set-up its own decentralized structures, and limits at the same time the Project’s responsibility in supporting generic institutions (who, which ones?) at Zoba level and beyond.

- The TPR also endorsed modifications at the level of outputs, re-wording some, deleting and adding others. Here again, the aim was to better tune Project results to real circumstances. The Mission does not consider this to pre-empt Project responsibilities, rather a necessary reality check of possible targets and achievements, in consideration of the more difficult circumstances of implementation than foreseen in 2000.

## Project Design

- The ProDoc identifies primary beneficiaries in the food insecure population in rural and urban areas, and “immediate target beneficiaries” in the policy and decision makers within GoE and among the development partners. This terminology is somewhat confusing, since difference between immediate and primary beneficiaries is not very clear. The two groups mentioned, being respectively beneficiaries in the long term and immediate clients of the Project, are correctly identified, although they should be called secondary beneficiaries. The primary beneficiaries, on the other hand, are staff from NFIS and other partner institutions, including Zoba administrations, who directly benefit of the Project technical assistance and training support.

- Overall, the Mission considers that the ProDoc forwarded a slightly too ambitious project proposal, in comparison mainly to the time frame established for implementation. The links between outputs and immediate objectives 1 and 3 are somewhat inconsistent, a few outputs tend to be repetitive, but factors such as investment needed to improve quality of data produced by NFIS partner institutions and the complexity of strengthening institutional structures at decentralized level, were partly overlooked when defining outputs and objectives. On the other hand, human resources planned were not really appropriate to meet requirements, and although a full-time CTA was obviously necessary, a more articulated mix of international and national expertise for shorter and repeated periods could have been more effective and pertinent, while contributing equally to national capacity building. It should be noted however that only partial use was made so far of funds allocated for consultants (see below).

- On the other hand, the ProDoc identified correctly risk factors which have indeed affected project implementation: i) the unresolved border conflict with Ethiopia, affecting also access to some areas due to security considerations; ii) scarcity of qualified Government staff to be appointed as Project counterparts, and high turnover thus affecting institutional capacity building and sustainability; iii) occurrence of drought, forcing focus on emergency rather than “normal” type of food security information. No provision or mitigating measure was however proposed to tackle any of these risks should they prove true.

- In relation to internal management arrangements and institutional set-up, the Mission considers that indications within the ProDoc were adequate and took in full account the national institutional environment. Adjustments proposed later in 2002 by FAO/ESAF (Food Security and Agricultural Projects Analysis Service) backstopping mission (see below) could not probably be envisaged in 2000 and did not challenge the initial core proposal of NFIS resting on the pillars of partner institutions responsible for providing data and information within their respective mandates.

# Assessment of Project Implementation, Efficiency and Management

## Project Budget and Expenditure

- The use of an unchanged budget code between the first and second Project phases (1996-2000 and 2003-2005) has as most evident consequence FAO Oracle System bringing forward the total Project budget since 1996. The first contribution from the GoI was US$ 800,040, and additional funding in 1999 raised the budget for the first phase to US$ 942,431. The ProDoc of September 2000 shows an indicative budget for donor support of US$ 1,664,354. The total budget in Oracle Data Warehouse (FAO accounting/financial system) issued in mid-September 2004 for the period 1996 - 30 June 2005 (NTE date), amounts to US$ 2,561,238.

- In March 2003, Budget Revision K was proposed and approved in July 2003, with adjustments to allow full Project implementation over the planned 30 months. Due to low expenses/delivery of the project during 2001 and 2002, January 2003 was considered the first month of the Project second phase. The Technical Advisor position was accounted for since first entry on duty (July 2002) and the CTA presence was extended by two weeks, to make provision for his entry on duty in mid-December 2002. Other major adjustments reflected actual cost of General Service (GS) staff in Eritrea and foreseen need for contractual agreements with external data providers (e.g. University of Asmara).

- In April 2004, Budget Revision L was submitted to the Finance Department in FAO. It foresees savings under Consultants, Training and Technical Support Services, and increased expenses under Locally Contracted Labour and Travel.

- The Oracle spreadsheet at 15/9/2004 indicates total expenses as being US$ 1,765,527, or 69% of the total budget. Expenses for Prior Years (from 1996 to 2002 included) amount to US$ 977,027, and in 2003 total expenses amount to US$ 386,824, 75% of which for salaries of both professional and GS staff. Second highest expenditure item was Non Expendable Equipment. This reflects to a reasonable extent the technical assistance nature of the Project, though funds spent on Training and Consultants are quite low in relation to initial budget allocation (34% and 44% respectively spent so far out of each total budget line). The rate of expenditure for this year at mid-September is 51%, and further 30% is planned to be spent by the end of the year. Again, major expenses items are salaries (70% spent out of budgeted so far), and Non Expendable Equipment, the latter already above budgeted amount for this year. This budget item includes computer equipment and the like, handed over to NFIS governmental partners.

- Further commitments for 2004 are in the range of US$ 230,000 (personal communication by the CTA), which summed to the planned budget, makes available for 2005 the total amount of US$ 565,711, corresponding to 22% of the total budget.

## Activities and Outputs

- It should be reminded that this is the report of a mid-term evaluation: many activities are planned to be carried out over the next months, and most outputs should be achieved in due time. Indeed, although outputs are still falling short of plans, the Mission is aware that setting-up procedures and mechanisms to ensure NFIS can operate and fulfil its role was and is a time-consuming task which still absorbs most energy by the Project staff. Here below, groups of activities and outputs are summarized, whereas Annex 4 presents Project outputs and activities, according to the revised Logframe produced by the TRM, in synoptic format.

- In August 2002, a backstopping mission by FAO/ESAF supported GoE in the revision of NFIS institutional structure. The new model endorsed became operational with the start-up of the Project second phase. This included the transfer of NFIS chairmanship from MoA to MoND, the reduction in size of NFIS Steering Committee (SC) to the five key Government institutions involved in food security, the opening of NFIS TC to new members, the set-up of Zoba Food Information Committees (FIC), the restructuring of NFIS Technical Unit (TU), the organization of a Support Group composed of donors, international organisations and NGOs. All this required elaboration and diffusion of information on the new set-up, networking and coordination with all partners, within the government and the international community. This was also aimed at the identification of users’ information needs.

- The Steering Committee is the decision-making body of NFIS, its members are MoND, MoA, Ministry of Health (MoH), Eritrean Relief and Refugees Commission (ERREC) and NSEO, the latter integrated recently into MoND. The SC meets according to requests and at least twice a year. The SC Secretary is the Minister of Agriculture.

- The Technical Committee, whose members are MoH, MoA, Eritrean Grain Board, Water Department, ERREC, Civil Aviation Department, Custom Office, Ministry of Local Government, Ministry of Fisheries and the University of Asmara, meets regularly on a monthly basis to discuss relevant issues to NFIS, and holds extraordinary meetings on request. Its Secretary is the head of the Policy and Planning Unit of MoA, who is also National Project Coordinator of the Project. Unavoidably, representatives of the different institutions to the TC have a certain degree of turn-over, which hampers somewhat the efficacy of these meetings. The role of these institutions is to provide quality and reliable data to NFIS. On the other hand, the Project’s mandate is to assist them to improve “food security data collection, processing, analysis and dissemination systems in the NFIS member institutions” (Output 1.4, TPR revised wording), without however being involved in direct collection of raw data. This activity is carried out mainly through in-service training, training on the use of new software, regular TC meetings, etc. The Mission had evidence of the good interaction and collaboration between TC members and NFIS, which is undoubtedly one of the important Project results so far. The Project provided also one full computer station to each TC members, and relevant technical assistance whenever required.

- In order to facilitate coordination and focus on relevant and pertinent issues, the Project has contributed to set-up a number of Working Groups (WG) among TC members, each entrusted with responsibility for specific topics and benefiting of specific training. These are:

- Marketing Information Group: this WG has to deal with the major obstacle of a restricted number of sources of first hand data on markets and prices. Only six urban markets are in fact monitored regularly by the Grain Board and the Ministry of Trade and Industry data collectors. Twelve representatives from the different institutions were trained in the use of the FAO Agrimarket software, first time to be tested in the country. The Project has received interesting feedback on the software gaps and weaknesses. Information flow is regular.

- Remote Sensing Group: a number of training sessions were organized for approximately twenty-four participants from the institutions members of this WG, also with support from FEWS-NET. It should be noted that initially, NFIS TU had a GIS sub-unit, which was transformed into the Remote Sensing and Agro-Meteorology sub-unit. Information flow is regular. The JRC (Joint Research Centre, European Commission) will support the Remote Sensing WG with a specific training course on GIS/RS in November 2004. This initiative stemmed from an agreement between FAO and JRC to join efforts and develop an advanced methodology for crop monitoring in the region, based on JRC experience in Somalia (MARS project), which consists of improving NDVI data quality with information from Africover maps (AfricNDVI). This new methodology will be adapted to the complexity of Eritrea regions, in collaboration with NFIS. The Mission was also informed that the Italian institution IBiMet was invited to present its methodology “Eritrea EWS for Food Security and Environmental Monitoring based on Africover database Project”, similar to JRC product and tested in Tigray, which is more similar to Eritrea in terms of topography and pluviometric patterns. Eventually NFIS preferred JRC, which offered a free training course and uses the Project’s agro-ecological zoning system. The Mission found these initiatives very interesting, and suggests that some consideration be given to the possibility of developing a partnership between JRC, IBiMet and NFIS to produce one single methodology appropriate to Eritrea

- Within the same field, the Project proposed at the end of 2003 to support the GIS/Remote Sensing Unit of MoA with a consultancy, whose detailed ToRs had been prepared by the back-stopping mission from ESAF/SAFR. However, this was eventually refused by NFIS Technical Secretary, although the Project provided some equipment all the same. This Unit is staffed at the moment with a senior and a junior GIS/Remote Sensing expert. Most of the Unit work consists of producing thematic maps requested from MoA and other Ministry users. GIS database is mostly based on the layers of the Africover Project, which also supplied the GIS software (ESRI ArcView). GIS data are organized in many different folders and are mostly in ESRI ShapeFile format. Satellite images are separated from other GIS data and are managed in a different way. The Mission found GIS Unit personnel well trained on GIS basic issues and map production, but it considers they would need some technical assistance on GIS data management and analysis.

- Recently, the Project also introduced to the TC the Dynamic Atlas software produced by a Canadian company for FAO/SDRN (Environment and Natural Resources Service). Dynamic Atlas is a powerful GIS tool, which allows building thematic maps and very useful territorial data warehouse. It is mainly utilized in Eritrea by the FAO Emergency Unit. The Mission, after analysing the software, was also informed that the Project is using its maps for the preparation of the Bulletins, and appreciates this collaboration. The same software could also be useful for MoA GIS/RS Unit.

- Food Balance Sheet Group: since much of the information this WG deals with is classified or difficult to access, it is not really operational at the moment. However, training on FAO methodology for Food Balance Sheets was carried out for seven participants, including elaboration of a specific FBS format for Eritrea, and the Group members have the tools to apply the approach, should they wish to do so.

- Agriculture Monitoring System Group: this WG of very recent creation aims at supporting MoA to set up an information system which will then feed into NFIS. It should be noted that no information on cropped area, type of crops, etc., is geo-referenced. Also, major problems exist on measuring standards. A workshop was carried out on this System, with 88 participants from the six Zobas. So far, the Project has proposed a Crop Calendar model, to be used by MoA at Zoba level, to concentrate information and technical messages only on the specific cultural practices on-going at any given time, and to feedback to the central level relevant information on crops development. This seems to be a useful tool, although it should be completed with information on the gendered division of labour for each practice (see below). A similar calendar for livestock-related activities in also planned.

- Training was also carried out on database development at different levels, for both users of MS Access database and programmers. Overall, approximately 75 people were trained at central GoE level.

- Partly related to the Agriculture Monitoring System Group, is the support provided by the Project on behalf of FAO, and by NFIS because of its mandate, to the Joint FAO/WFP Crop and Food Supply Assessment, already mentioned above.

- NFIS Support Group is composed by 20 members (see Annex 5) plus FEWS NET, and has the role of NFIS advisory body, providing resource persons whenever required. The Group meets once per year, for the presentation and discussion of NFIS activity report and new work-plan, otherwise they meet for specific topics in smaller groups. A number of its members contribute to the Nutrition Surveillance System Expert Group, and twelve of them take part into the Livelihoods and Vulnerability Assessment Support Group, set-up by the Project to discuss and share results of the work on LS (see below). FEWS NET is mentioned separately, as it is at the same time a member of the Support Group and one of NFIS partners as data-provider (see below). The Support Group seems to be highly appreciated by all stakeholders.

- To complete setting up NFIS structure, the Project contributed to the organization of five out of six Food Information Committees at Zoba level (Southern Red Sea Zoba still missing) through an information and awareness-raising workshop in each Zoba. Also, computer equipment was already or will be provided to each Committee. Overall, approximately 150 people took part into the Project’s workshops in the six Zobas. Project’s activities in this field are lagging behind schedule, this apparently due mainly to scarce time availability of Zoba Administrators.

- The Mission met two Food Information Committees (Zoba Debub and Zoba Maekel). Although their members acknowledge and stress the importance and relevance of this structure at Zoba level, they also claim that it adds extra-burden to their already heavy work-loads, and that staff should be assigned to the Committee full-time to make it a meaningful and efficient structure. The Mission shares and supports the Project’s planned focus on this level of the administration, since it is pivotal in the management of the whole information process from the grass-roots level upward. In fact, it is only from Zoba level that raw data collection can be better organized and quality control performed. Also, although ideally first data entry into any information system should be carried out at the lowest possible level, i.e. Kebabi level, it is likely that the Zoba level will perform this task, together with a first analysis, before partial transfer of this information to the central level, for consolidation and further analysis.

- The most visible output of the Project and NFIS so far is the publication of the Monthly Food Security Outlook and the Agro-met Update Bulletin. Both are cleared by the Secretary of NFIS SC, and are distributed as print-outs to the SC members, the Zoba Governors and a few donors, and through e-mail to more than 270 addressees, including national and international stakeholders, media, regional organizations, FAO Task Force, etc. Special issues are produced of both publications, whenever considered useful.

- The first issue of the Monthly Food Security Outlook produced under the present Project phase was published in January 2003. It is a six to nine-page publication, with a Highlights window on the front page and sections on rainfall assessment, agricultural situation, nutrition situation, price report, food aid and humanitarian situation, food security technical information, NFIS news. It must be noted that the Outlook, besides providing updated information and analysis on Eritrea food security situation, plays also an important role in the extension/advocacy of technical information and recommendations on a number of related topics (agro-meteorology, agricultural practices, seed production system, etc.). It also provides, still to a very limited extent, some forward-looking analysis and macro-forecast.

- The Agro-met Update Bulletin, a two to four-page publication, had its first issue under the present Project phase in August 2003, and is published three times (dekadal) per month during the rainy season, and monthly during the dry season. It provides information, as per its name, on rainfall records and estimates for the decade or month. Starting in March 2004, the Agro-Met Update has become a joint publication with FEWS-NET, the latter providing NDVI maps.

- The Mission asked all its interlocutors about access and usefulness of these publications. A few recurring comments were raised:

- The diffusion through electronic format is a strong obstacle to wider access within national institutions, even among NFIS TC members and Zoba FIC, as apparently very few civil servants, apart from senior managers, have a professional e-mail address. Due to weak provider capacity, problems exist also in the distribution of the publications through Zip-files, etc.

- A further obstacle to wider diffusion is considered to be the use of English. However, it should be noted that neither product is aimed at a wide public; rather they are intended for decision makers, professionals in the field of food security, the international community, all clients who can usually read a technical text in English. Still, the Mission finds interesting and worth pursuing the recent Project’s proposal to translate the Highlights section of the Outlook into Tigrinya and distribute only this as a print-out leaflet to a wider audience. Also, as again suggested by the Project, more than one copy of the Bulletins could be sent to Zoba Administration to be made available through the Notice Boards in the Administration buildings. The Mission suggests that some attention be given to the possibility of using radio broadcast as a means to diffuse information related to food security and early warning to a wider audience throughout the country.

- Diffusion among the international community is good, and partners from the Support Group appreciate and value them as the single precious source of information available in the Country on food security related issues. At the same time, it is acknowledged that being it a government publication, it might at times provide one perspective only. Some doubts were raised also on the quality and reliability of data diffused. This is a well know problem, in particular for data such as rainfall estimates for which no ground control system exists to validate remote sensing information, in spite of Project’s efforts to cross-check information. However, for this and other types of data, neither the Project nor NFIS have the capacity or mandate to solve, rather it should be tackled at other institutional levels.

- Also, the request is formulated by some partners for more analysis and forecast to be published in the Bulletins. This is partly understandable, as everyone likes to read well structured analysis and sound judgment formulated, to compare with one’s own. However, it is not really clear what this analysis should be, and perhaps the Project and NFIS could discuss this more in depth with its clientele. Nevertheless and more important, the quality and reliability of data reaching the Project and NFIS at the moment allows only some degree of analytical work and informed forward-looking judgment, which are already done. More in-depth analysis and forecast at the present moment would probably be only a spurious and misleading exercise, and the Mission does not think it would contribute to raise NFIS profile and would pay the country and the international community a good service. At the same time, the Mission sees this type of analytical and scenario building exercise as a long-term objective for NFIS.

- As mentioned above, NFIS and the Project receive information on food security related issues from TC members. The process consists of the transfer of both electronic and paper documents, which are filed at NFIS level per each bulletin issue in folders. The Project considers this to be working properly. The Mission considers most important that a working procedure and a habit of transfer of information from a number of institutions to NFIS has been set up and acquired in each institution’s working routine. Nevertheless, the Mission considers some adjustments are necessary to improve the overall reliability of the process, as a few process weaknesses should be covered. In particular:

- Data collection procedures beyond Zoba level are not yet well documented, whereas precise rules should be established and applied by all concerned for data collection, to ensure data quality. A technical document should be prepared describing all steps, and made available to all stakeholders.

- No document was produced so far describing all different data structure feeding into NFIS data repository. The absence of such document increases substantially the possibility of mistakes made with the data supplied by the partner institutions.

- Further, the Mission found a gap in the Project metadata management, since neither spatial nor alphanumeric metadata are collected during the data production flow from the different data providers (NFIS partner institutions). Metadata are information about data, which allow users to know who for instance is the data provider or the data validation time. Although this gap has no impact in the short term period, it may become a real problem in the mid- and long-term period, when users may want and have to analyse data of previous years.

- In early September 2004, the final approval was given to the Project by NFIS SC to launch NFIS Website. This enables users to access all information related to food security, as well as all Project documents. The Mission considers the Website to be rich in information, users’ friendly and easily accessible and readable, therefore appropriate taking into account the slow Internet connections in the country.

- At the beginning of 2003, in order to improve the output quality, the Project realized a users’ forum based on e-mail system. Through this, they collected questions and suggestions from users via e-mail and replied on special Bulletin sections/issues. Users’ comments arrived for some time, but then interest died out and no activity is on-going at the moment. Considering the recent NFIS Website issue, the Mission suggests to set up a new electronic forum based on this. This kind of software allows users to insert their comments directly on the Website prepared form. NFIS staff will be able to reply to each questions or suggestions. All comments will be accessible directly on the forum Website section by all users, who will be able to add or reply to each other. Forum rules will be put in evidence on the first forum page. In relation to those rules the forum administrator will have to check each message in order to verify its compliance with the forum mandate.

- An important activity and output of the Project was the elaboration and adoption of the Livelihood Systems Baseline Study (LSB) as NFIS methodological framework for assessment of vulnerability and food insecurity in Eritrea. The core idea is to identify the different livelihood systems which exist in the country, starting from an agro-ecological zone perspective, “map” these within each Administrative zone and identify within each, key indicators for food insecurity and vulnerability. These would then be monitored constantly at village level and be the basic data for food security monitoring and analysis at Zoba and central level. The system would allow at the same time the build-up of a sample frame for any further surveying exercise. The steps foreseen by the proposed methodology are the preparation of a desk-study (Baseline study on Livelihood Systems) for each Zoba, through which the different systems would be identified and described, validation of the desk study through a sequence of workshops at Zoba and Desk level with administration and village-level representatives, restitution of results, identification of key indicators and set-up of a data collection system from grass-roots back to Zoba and central levels.

- The adoption of the methodology proposed to NFIS required a huge effort by the Project in terms of awareness raising and training on these concepts. The draft version of the methodology was issued in July 2004. Work at Zoba level was also delayed by a number of factors, and so far, the exercise has been carried out up to the workshops step only in Zoba Debub, selected for piloting the methodology, where approximately 160 participants took part into the validation workshops. Partners from the Support Group contributed actively to the exercise, including three staff seconded by NGOs (Care, Oxfam, CRS) to support the workshops. Results from these have to be analysed yet, but the Project foresees the possible need to cross-check these with further field work, before restitution to the decentralized levels takes place. The Mission, after looking at the desk-study and at the very preliminary workshop results, strongly suggests the re-thinking of the validation process, to allow much more focused discussion with all stakeholders, women included (see below 5.C), at grass-roots level. In fact, a far more detailed analysis of the proposed livelihood systems is necessary, since information available for the desk-study allowed only a generic document to be produced. Also, proposals were formulated by different partners that the livelihood systems proposed so far have to be further split into sub-system: the Mission has no means to verify the validity of these suggestions, to be answered only through accurate field-level work. Interestingly, FEWS Net proposed to contribute to the whole effort by funding a consultancy from outside the country to carry out the desk-review for two or three Zobas.

- The Project collaborates with the Nutrition Surveillance System Expert Group, under the leadership of the Nutrition Unit of MoH. Besides regular attendance and active participation to the Group’s meetings, and some support through ESNA, the Project provided technical backstopping to the Group through the Manager of the Nutrition Surveillance Project for Somalia/Food Security Analysis Unit (FSAU), funded by USAID. As part of a wider effort at sub-regional level to promote the utilisation of information on nutrition in the context of food security information systems, two one-week technical support missions were carried out. The first visit aimed at identifying needs and possible actions in this field. Follow up activities, prompted by the Project with the technical support of FSAU, included the signature of a Letter of Agreement between NFIS and Ministry of Health (MoH) and the organization of the Nutrition Surveillance System Group, to discuss issues related to the establishment of a Nutrition Surveillance System. The second mission (September 2004) aimed at further developing the integration of food security and nutrition information: technical recommendations were formulated and will have to be discussed by concerned parties. Two nutritional surveys are carried out per year in all Zobas.

- The Project has also prepared a number of information and training PowerPoint presentations on different topics, including Sustainable Livelihoods concepts, Food Security Concepts, Food Balance Sheets, presentation of NFIS, etc. These have been used in workshops and information sessions with partner institutions. The Mission had access to all of them, and considers they are quite useful tools, although some improvement on layout could be necessary for a few of them.

- The Project networks and takes part into a number of working groups at national level, including the UNDAF process, the CAP working groups, Food-Aid Targeting Ad-hoc Group, etc.

- Last but not least, the Mission finds that the Project is also giving visibility to the donor: the Italian Cooperation logo appears on all pages of both the Monthly Food Security Outlook and the Agro-met Update. The logo appears as well on NFIS Website, where a link exists to other Italian-funded, FAO implemented projects in Eritrea. Interlocutors are usually aware of the Project being funded by the Italian Cooperation, also among Governmental stakeholders.

## Government Support

- The Government of Eritrea has supported the Project from its inception. NFIS is housed in the Ministry of Agriculture premises, where office space was made available. The Minister of National Development and the Minister of Agriculture view NFIS as a key system and stated to appreciate the support provided by the Project. The Mission had strong evidence of the Minister of Agriculture’s feeling of ownership for the Project and NFIS. Also, the members of NFIS Technical Committee and of Zoba FIC, appointed to contribute to these bodies, are mostly government employees with full-time regular duties.

- The ProDoc foresaw a total governmental contribution of US$ 325,666, split among staff time, facilities and supplies. The commitment in the form of staff inputs (76%) summed up to 103.5 person years during 30 months of Project life. Until September 2004, staff made available to NFIS Technical Unit fulfilled only 21% of planned contribution: one agro-meteorologist was appointed in November 2003 and the Head of the TU was appointed during the first half of September 2004. According to information available to the Mission, one position (socio-economist) might be filled by the end of the year, but no perspectives seem to exist for appointing the data-manager/editor.

- On the other hand, contribution to the TC exceeds by large planned commitments, with 163% of staff time contributed by September 2004. Analysis of contributions from Zoba and sub-Zoba staff are positive so far for the former, but it is a premature assessment, since the Project is delayed in its decentralized activities and so far, Zobas and Sub-Zobas were asked to contribute manpower only to a very limited extent.

## Project Management

- The ProDoc made provision for two international consultants, the CTA and the Technical Adviser, plus two support staff, all of them with 30-month contracts. The Technical Adviser was recruited in July 2002, and all other staff was in post by 1st January 2003, considered as the starting date for the Project second phase.

- The Mission is aware of the huge efforts made by the Project staff to carry out its mandate, including development of fruitful partnerships and synergies. The analysis of results and outputs provides enough evidence. Also, quite some effort was devoted to build capacities and skills of Project and NFIS staff: the Project Secretary is responsible for a number of technical and administrative tasks including data gathering and processing, spreadsheet elaboration, procurement, etc; the Agro-meteorologist, Government staff, has seen his tasks widened, including for example work on socio-economic information. Although this adds to his workload, it also contributes to improve his competences.

- The Mission has also evidence of the good communication and collaboration between the CTA and the FAO Representative, who is the Budget Holder (BH) for the Project. This contributes to the smooth management of administrative and financial matters.

- The Mission acknowledges and respects the GoE requirements in terms of bureaucratic procedures for approval of any activity, as well as its will to avoid different financial treatments among staff (civil servants versus consultants) working within the Government institutions. The procedures within GoE to work at decentralized level have delayed activities at Zoba level, which were then further postponed by the electoral process in Spring 2004.

- Indeed, the Mission finds that the pace of Project activities was hindered partly by the lack of Government counterparts available full time to the international staff. This along with the low use of consultants, in spite of these being budgeted, and the Technical Advisor’s fragile health conditions, contributed to the heavy and diversified work overload falling under the direct responsibility of the Project CTA.

- Therefore, all factors analysed, the Mission considers that overall management of the Project so far was efficient and effective, and that besides the reasons mentioned above, other delays in the present phase of the Project are due to unrealistic assessment of data availability and training requirements at the level of NFIS partners.

## Technical and Operational Backstopping

- The Leading Technical Unit (LTU) for the Project within FAO is ESAF, responsible also for coordinating the Project Task Force. As already mentioned, the BH for the Project according to FAO present decentralized system, is the FAO Representative in Eritrea. Members of the Task Force are also SAFM (Multidisciplinary Team at the Sub-regional Office for Southern and East Africa) and TCAP (Technical Cooperation Department/Field Programme Development Service). Since approval of the present ProDoc, a number of technical and backstopping missions were carried out in support of the Project, well appreciated by  the BH and the Project. Some complaints were formulated in relation to the non-facilitating and indeed hindering role played by the Personnel Unit in RAF, in terms of support to Project staff, and by the procurement service in HQ.

- ESAF fielded the first backstopping mission in August-September 2002. This mission was critical to the start-up of Project activities a few months later. In 2003, ESAF sent two backstopping missions (October and December) respectively from HQ and SAFR. Although ToRs differed and both were appreciated by Project staff, issues tackled were very similar. The Mission would suggest therefore a more rational use of resources, although it recognizes that at certain moments in project implementation, some redundancy in support from outside may still play a role.

- In 2004, ESAF took part into the TPR, with the Leading Technical Officer from HQ, and sent in May 2004 a two-week technical mission to review and advise on the Project’s communication strategy and to implement the designed NFIS website.

- In 2003 and 2004, as already mentioned, two one-week technical support missions were carried out by the Manager of the Nutrition Surveillance Project for Somalia/Food Security Analysis Unit (FSAU), funded by USAID.

- Last, the second Tripartite Review Meeting was organized and held in Asmara in March 2004, with representatives from the Government of Eritrea, the donor and FAO. The TPR analysed achievements to date, discussed problems raised by the Project, including FAO rules and regulation for project management and the urgent need to provide full national counterparts to Project staff, to allow proper capacity building and ensure Project sustainability. Also, the TPR formulated a number of recommendations, among which: i) increase delivery for training and work at Zoba and lower administrative levels; ii) the organization of monthly meetings between the Director of MoA Planning and Statistics, the Project and the donor; ii) the set-up of a joint monitoring committee at national level; and iv) the organization of a mid-term external evaluation. Also, the TPR agreed to a number of changes in wording and focus in the ProDoc objectives and outputs.

- All parties agree that the TPR was a milestone in the Project’s life, and helped to clear doubts and misunderstandings which had arisen with time. Correspondence from the Project’s file indicates that the TPR had been requested for quite some time. Although this delay may also have contributed somehow to a reduced pace of implementation, the Mission considers that it took place at a proper point in time, when problems were more easily identified and circumscribed and solutions identified. Some of the recommendations were put in practice immediately and have already proved their value (e.g. the monthly meetings) and others are under implementation. One, the recruitment of national consultants to make up for the lack of counterparts, has been lagging behind for quite some time yet and only in September the Head of NFIS Technical Unit was appointed by GoE.

# Assessment of Results and Effectiveness

## Effects and Impact

- The Mission has evidence of the positive profile and image of the Project and NFIS among stakeholders. Its work and products are appreciated at the Government level, both MoND and MoA, by partner institutions and by the international community. Also, the Project approach has ensured a high degree of ownership among governmental stakeholders for NFIS as an institution and for its role.

- The Project has triggered a high level of awareness and information on food security and vulnerable livelihood systems. In relation to the latter, the Mission is aware that in 2003, ERREC, CARE and WFP carried out a survey on Rural Livelihoods and Coping Strategies. Although some may consider this to be a duplication, the Mission considers on the contrary that the methodology proposed by the Project differs from the above exercise as it can provide useful information on long-term livelihoods and coping strategies. Once its outputs will be available, a sounder comparative analysis of both approaches will be possible, and synergies developed.

- Finally, there might be the feeling that the Project’s methodology and WFP VAM system overlap and duplicate to some extent. However, as discussed with WFP staff, in the medium term strengthening NFIS also on vulnerability assessment through a more comprehensive approach will enable WFP to phase out its VAM unit in the country. Moreover, within the framework of FAO-WFP LoA for a strengthened collaboration in the field, recent events have triggered better cooperation between the Project and WFP, in particular on information production.

## Sustainability of Results

- Under the context of NFIS, sustainability of Project results concerns basically the long term viability of the institutional mechanisms set-up for information gathering, processing and analysis. More specifically, the capacities built during the Project among NFIS and its partners’ staff, in order to manage, control and adapt to changing requirements and circumstances the processes proposed, and the pertinence, soundness and users’ friendliness of the latter.

- Insofar capacity buildings is concerned, in spite of efforts by Project staff, the only very recent appointment of a full time Government staff as Head of NFIS Technical Unit, and the lack of a socio-economist and of a GIS/Data Manager, are serious obstacles to attaining full transfer of know-how and skills within the Project present time horizon.

- Further, the slow pace and intensity of Project activities at decentralized level so far, and the lack of NFIS structure at decentralized level (Zoba and below) hinders for the time being the sustainability of Project’s results beyond the central level of GoE.

- Insofar sustainability of processes is concerned, perspectives differ for different data providers. The processes set-up for transfer of marketing, remote sensing and nutrition related data to NFIS, look sound and relatively well tested so far. Further follow-up by the Project for the remaining implementation period should ensure long-term sustainability for these sectors, though some adjustments are required in relation to data management at NFIS level. On the other hand, the process related to collection and transfer of data from Zoba level including the key indicators for each livelihood system, is not yet designed. Recommendations formulated below should contribute to its set up.

## Gender Equity in Project Implementation and Results

- The ProDoc acknowledges the importance GoE attributes to “gender equity and empowerment of women as integral components of human development”. Indeed, the Government position on gender is stressed repeatedly in its official documents, including the FSS and the I-PRSP.

- The ProDoc refers to malnutrition rates among women and children, and to pregnant and lactating women and women-headed households being more affected by food insecurity. No specific recommendation or mention is made however to look at gender issues or disaggregated data when identifying vulnerability indicators, domestic food production, intra-household food deficits, access to resources, etc. Although this must have been considered an unnecessary level of detail in the mind of the formulation team, the Mission tends to think that whenever the issues at stake are information, data collection, food security and the like, at least mentioning the need for gender-disaggregated data collection and analysis would be necessary.

- Overlooking gender issues in the ProDoc may have contributed to overlooking gender issues during Project implementation. The Mission has found very little evidence of gender issues being mentioned in training and information material produced by the Project and in its activities. Findings in this respect are as follows:

- the Monthly Food Outlook Bulletins refer in a number of issues to the nutritional status of pregnant and lactating women, and to women and elders being vulnerable groups. Still, “gender approach” is mentioned once in one Monthly Food Outlook Bulletin (Issue n. 10, November 2003), in relation to the difficult access to ploughing services “female, elderly and male-away headed households” have, and suggesting tractor services to be provided to disadvantaged households;

- gender awareness is mentioned once as an element for necessary diversification of sources in the methodology for baseline study on livelihoods system. Indeed, the baseline desk study on Zoba Debub mentions women’s new income-generating activities, but no further analysis is made of gendered livelihood systems. The Project acknowledges that women should have been invited to the LS validation workshops in Zoba Debub and its sub-centres (virtually none – three out of 120 participants – was present), but since the workshop’s organization was under the direct Zoba Governor’s control, they had not control over invitation aspects. In any case, the Project had not taken into account when designing the validation methodology through workshops at desk-level, that rural women traditionally do not leave their home and villages for this type of event. Moreover, it is usually acknowledged that in order to obtain reliable information on livelihood systems, or any other information on people’s lives for that matter, people have to be met in their own social and cultural environment to understand and discuss issues easily missed when in an unfamiliar, artificial place. This means that a validation methodology of a generic desk-study through workshops would always be flawed and partial, from the perspective of a sound livelihood systems analysis;

- in a 52 slides Power Point Presentation on NFIS and SLA for a Zoba Governor, one reference only is made to population numbers by sex, and none is made in the proposed example questionnaires for data collection to the need for gender-disaggregated data and analysis; no reference to the need for gender-disaggregated data collection is made within the training material for nutritional status surveys; no mention is made of impact of gender issues on food security (intra-household access to food, female-headed households, access to assets, mobility, etc.) in training material prepared by the Project on livelihoods and vulnerability concepts;

- no reference to gender division of labour is made in the proposed model of agricultural calendar: if the calendar is intended for “understanding what agricultural activities are undertaken each month” as the Project states, it might be useful to identify who does what in the field and when, so as to help the very few extension agents to pose the right questions to the right group of persons. Equally, a proper agricultural calendar indicating activities by gender could also be useful for other purposes, such as focusing information and advice and support to the actual implementers of each practice.

- The Mission considers that this recurring overlook throughout Project activities and outputs for gender issues is detrimental to the achievement of sound final results, in particular in relation to the LSBS. Further, the methodological flaw in the LSBS would also affect the integration of wider social and cultural issues into the analysis of food insecurity and vulnerability in Eritrea. At the same time, the Mission notes that no provision was made in the ProDoc for specialized consultancy/ies on these aspects, and that no backstopping missions, to the knowledge of the Mission, ever touched on these subjects.

- In consideration of the relatively early stages of advancement of the LSBS, the Mission considers that it is possible to make up for the lack of attention to gender and social development issues in this methodology and throughout other Project activities, as long as an appropriate action is taken immediately.

## Cost-effectiveness

- The Project has to be commended for developing interesting partnerships to meet some gaps and widen its scope of action, notably with FEWS NET for map development and with FSAU/Somalia on nutrition. Also, the secondment by some international NGOs of their staff to take part into the LSBS workshops is good evidence of the Project capacity to use effectively resources available outside its immediate control.

- However, taking in consideration the overall scarcity of human resources in Government, the Mission thinks that the CTA time could have been more profitably employed, and therefore a higher cost-effectiveness be achieved, if more room had been allowed for recruitment of skilled consultants, either international or national, to provide technical support on some specific areas and carry out more specialized tasks (e.g. social and gender issues analysis, data base manager, etc.).

## Major Factors Affecting the Project Results

- As mentioned above, the ProDoc analysed a number of risks which could affect adversely Project implementation and attainment of planned results. The Mission unfortunately has to acknowledge that all these risks became true, and are still affecting Project implementation and results.

- The Mission also notes that some of the weaknesses and delays found in Project implementation are due to the lack of appropriate expertise made available. Even though short-term consultancies might apparently not contribute to national capacity building, adequate ToRs can be prepared to avert this risk and include proper in-service training arrangements. A more flexible use of external resources, either national or international consultants or FAO technical services staff, would have helped in meeting Project objectives within planned time frame.

- Indeed, in consideration of the wide range of technical issues tackled by the Project, more technical units in FAO should have been included in the Task Force to provide their support. Particularly, services which could have contributed to a better performance so far are SDWW (Gender and Development Service) and SDAR (Rural Institutions and Participation Service).

# Conclusions and Recommendations

## Conclusions

- NFIS is responsible for providing the Government of Eritrea with reliable information on the status of food security in the Country. This role is also recognized in the National Food Security Strategy. To meet its mandate, NFIS coordinates and liaises with a number of other governmental institutions to use the information each of these produce, and analyse and elaborate it in an integrated framework, for the final use by decision makers in the Government and in the international community. The structure of NFIS Steering Committee and its chairmanship at MoND, as well as the membership of NFIS Technical Committee, give it adequate leverage and access to key institutions. In consideration of the large rural base of Eritrean economy and society, and the role agriculture may play in food security in the country, the present location of NFIS TU within MoA is justified for the time being.

- GCPS/ERI/002/ITA is supporting NFIS to build its own and its partners’ capacity to collect, analyse, transfer and process data and information. The Project has achieved a number of important results so far:

- set-up of a coordination and information transfer process within GoE and with external partners, which allows NFIS to perform its task of diffusion of elaborated information on food security in the country, including the production of two useful and regularly issued publications;

- proposal, discussion and consensus building on NFIS using an adapted livelihood systems approach to map vulnerability and food insecurity in the country, including initial testing of the methodology;

- capacity building at NFIS and among partner institutions, to improve the collection, processing and elaboration of information on food security in Eritrea.

- A number of problems have affected Project’s performance, among which the well understood and prevailing difficulty of GoE to meet its commitments, by late assignment of national staff to NFIS. This has increased the workload for Project staff, with an effect on rate of implementation, and has hindered transfer of know-how and skill, thus jeopardizing the future institutional sustainability of NFIS. The Mission acknowledges and appreciates the recent effort of GoE to appoint the Head of NFIS TU Head, but reminds that other two positions are still vacant.

- A key level within the national system for ensuring food security is properly identified by all stakeholders in the Zoba administrative level. Initiatives in this direction correspond also to the GoE policy on decentralization of administration. The Project is tackling this appropriately: it is foreseen that a number of staff from Zoba Administrations will be trained on food security issues, data collection and analysis, etc. This training will be all the more useful and sustainable if participants will be experienced staff who will then be appointed full time to the Zoba Food Information Committees, lest these institutions will not perform as necessary and desirable. This would affect negatively the whole chain of transmission of quality and reliable information from grass roots to central level.

- The Project is heading in the right direction to consolidate these results. As to be expected being it at two thirds of its life, substantial work has still to be carried out to meet planned outputs. In particular, efforts will have to be focused on the following:

- building capacities at Zoba level and beyond for data collection, processing and analysis,

- fine-tuning the methodology of the livelihood systems baseline study for vulnerability and food insecurity mapping;

- mainstreaming gender and social development issues in data collection and analysis among NFIS partner data-providers and in NFIS outputs;

- improving accessibility and security of the data management process.

- The Mission considers that all these outputs, to be meaningful and sustainable in the long term, require more time than presently allowed by the present Project NTE date. Tasks to be accomplished are complex and require careful planning and implementation. For example, it looks unrealistic to foresee that appropriate work will be carried out in the remaining five Zobas over the next six months, when testing the approach in pilot Zoba Debub still requires much fine-tuning and field-level work. Also, preparing, organizing and carrying out the training course will be a time consuming exercise, which will absorb much energy of Project and NFIS staff. Present scarcity of fuel at national level might also affect mobility for Project and NFIS staff.

- Further, the Mission also considers that a new project should be launched at the conclusion of GCP/ERI/002/ITA, to strengthen capacities at Zoba level and below and to consolidate NFIS role within the national Food Security Strategy. Activities and procedures involved in a project formulation and approval process require at least one year, which means that in the best of hypothesis, a new project could be operational only towards the end of 2005. Moreover, the Mission considers that this new endeavour should build upon solid results as possible stemming from the present initiative, to be really effective in consolidating the whole chain of information collection, processing, analysis and diffusion. Therefore, adequate time should be allowed to the present Project to pursue its objective and accomplish its tasks.

## Recommendations

- Evaluation missions usually formulate their recommendations specifically for each party concerned. In this case, the same formula was followed, plus two recommendations addressed to the three parties. In the hope this will simplify reading and identifying areas of responsibility, more substantive recommendations are listed alongside minor issues, when aimed at the same addressee.

### Recommendations for the Government of Eritrea, the Government of Italy and FAO

- The Mission recommends that the Project be extended to the end of 2005, therefore by six months beyond the present NTE date of 30 June 2005. This to allow time to accomplish the foreseen tasks and accommodate for the recommendations below. The extension should be budget neutral, since no need exists for any budget increase, if recommendations formulated for Project staff are endorsed.

- The Mission recommends that a new project proposal be formulated by June 2005 to be discussed and approved by concerned and other parties by the end of that year. This should focus on consolidating the information collection and analysis process at Zoba level and below, and on strengthening NFIS role at central level, within the Food Security Strategy framework.

### Recommendations for the Project and NFIS Technical Unit

- These recommendations are addressed to both Project and NFIS, as most of them will have to be carried out by the two entities together.

- The Mission recommends that the LSBS methodology, in particular the validation procedure of proposed classification and the identification of key indicators for vulnerability and food insecurity, be thoroughly revised to include work at village level with all stakeholders. This will require more time devoted to the exercise in each Zoba, and mobility allowed to the teams responsible for field-work. It is recommended that a national or international social development expert, with experience in work at field level, be recruited to support the Project to fine-tune the validation methodology, and be responsible for training team workers and lead the field work. This may require two to three weeks on average per Zoba, plus preparation time. Results from the field analysis could then be compiled at NFIS level by the Vulnerability Assessment consultant.

- The Mission recommends that gender and social development issues be streamlined into NFIS activities and outputs. A national or international consultant, according to availability and competences, should be recruited. It is reckoned that at least two months should be necessary, including training of NFIS staff at central and Zoba level, and NFIS partners within the TC. This consultancy should be closely coordinated with the consultancy recommended in the previous point.

- The Mission supports the Project proposal to organize and carry out an intensive training for Zoba-level staff on food security issues. The training should be structured in such a way to allow trainees to participate actively in the livelihood systems baseline study in their respective Zobas, providing them the opportunity for field-level work training. It is suggested that international and national consultants be recruited to organize and carry out this training, to allow the proper mix of necessary skills and expertise. Also, flexibility in the consultants’ selection must be allowed, to meet planned time schedule. Last but not least, adequate attention will have to be paid to the selection of trainees, to guarantee the required level of competences, and to ensure within possible limits their return to work to their Zoba administrations.

- The Mission recommends that the Ministry of Labour and Human Welfare be invited as a member of NFIS Technical Committee, in consideration of its role in fighting vulnerability in the country.

- The Mission recommends a number of actions to be taken on information management, to the benefit of NFIS, Zoba administrations and MoA Remote Sensing/GIS unit. Main activities are mentioned here below, whereas specific details, outputs and required inputs, as well as indications on timing, are provided in Annex 7:

- set-up an optimal process at NFIS level for management of data provided by partner institutions, which should allow in the future searches for historical data and any other more complex analysis;

- create a Zoba databases, to gather at this level information collected at village and desk-level;

- support each NFIS partner institutions to organize its own information into a database, to be developed on MS Access with some help from NFIS staff. The TC members will share part of this information with NFIS to allow the production of the bulletins, as they already do now in hard copy format. In the long term, information stored in this way could be integrated into a single national database, to be possibly set up at NFIS;

- support the MoA Remote Sensing/GIS Unit, to allow an incremental improvement in the quality of its outputs, which will be beneficial to NFIS in the immediate future, when data layers coming from the livelihood systems zoning will have to be recorded and analysed.

- All other Project activities will be continued as per the present plan of work. The Mission recommends Project staff to make a particular effort to involve the recently appointed Head of NFIS in their implementation, so as to ensure the maximum possible transfer of skills and knowledge by the end of the Project.

- Recommendations above have implications for Project activities and on requirements for expertise. The Mission recommends that a Budget Revision be done to allow funds for a bulk of consultant person/months to be made available to recruit the expertise required on gender and social analysis, field level work, training of Zoba staff, database development and any other requirement which could rise. Expertise will also still be required on vulnerability assessment, though in the Mission’s opinion not on a full time basis. The P4 International Advisor on Food Security and Vulnerability Assessment post is due to phase out by the end of 2004, but arrangements can be made to have him still on board for the required periods throughout the year 2005. A more precise estimate of actual workload will have to be done in consideration of the availability of the other consultancies recommended.

- The Mission recommends that the sequence and wording of project’s objectives and outputs as agreed upon during the TPR in March 2004, be adopted officially in all Project reports.

### Recommendations for FAO

- In consideration of the wide range of technical issues relevant for the Project and for NFIS, namely gender, participatory methodology, nutritional issues, the Mission suggests that SDWW, SDAR and ESNP be included in the Task Force of GCPS/ERI/002/ITA. This to allow proper backstopping from these services, as well as feedback from the Project into FAO normative activities on a wider scale.

- The Mission, although aware that keeping the same project code facilitates approval of new project phases, recommends that new codes be given when projects extend over many years and new funds are allocated to new phases of the same initiative, for the sake of budgeting and accounting procedures.

### Recommendations for the Government of Eritrea

- The Mission agrees strongly with the recommendations formulated by the TPR in March 2004, to complete appointment of NFIS staff as soon as possible, to allow adequate capacity building during the remaining life of the Project.

- The Mission is aware that work at Zoba level and beyond depend on a number of factors, including availability and time of Zoba staff, security conditions, fuel availability, etc. Within this complex picture, the Mission recommends GoE to facilitate Project activities at decentralized level insofar as possible, to allow proper and meaningful implementation of the livelihood systems baseline study and vulnerability assessment zoning exercise.

- The Mission recommends that GoE seeks support from its development partners, to improve capacities and performance of NFIS partner institutions, aiming at the production of better quality data and information on food security related matters at country level. In particular, agricultural statistics, market monitoring, ground validation of remote sensing information, and meteorology deserve priority attention. The Mission is aware of advanced discussions on the first two themes with FAO, which it fully supports, as well as of a general interest at UNDP level in this regard. This could be instrumental for the preparation of full fledged proposals in favour of other institutions members of NFIS, not benefiting yet of specific support.

- Further, for consideration in the medium to long-term, the Mission suggests that the role of NFIS be expanded to become the think-tank of GoE for all issues regarding food security, including the follow-up and monitoring of the national Food Security Strategy, macro analysis and scenario building within this framework.

# Lessons Learned

- Unless attention to gender issues is explicit and detailed in the ProDoc, there is always the risk that this aspect will be overlooked during project implementation.

- Assessment of risks, and their probability of occurrence, should not be limited to an intellectual exercise when formulating a project, but adequate measures should be foreseen to minimize their negative impact on project implementation. A possible averting measure is to plan explicitly closer monitoring of project activities through more frequent local steering committees or tripartite review meetings.

Annexes

Minutes, Tripartite Review Meeting 23-24 March 2004, MoA, Asmara

Ref. to Annex 1 for the ToRs of the Evaluation Mission, to Annex 2 for the list of people met and itinerary and to Annex 3 for the list of documents consulted.

Eritrea rural livelihood security assessment: report of the findings, CARE, WFP & ERREC, July 2003, Asmara, Gates Foundation

The CAP for 2004 identified a food deficit of 417,000 MT. The CAP for 2005 reckons with food aid requirement of 431,000 MT, 76% of total food use.

The two processes were supported by UNDP and consultations took place with development partners.

Terminal Report, GCPS/ERI/002/ITA, Draft, July 2000, Asmara

? Emergency Prevention System for Transboundary Animal and Plant Pests and Diseases

GCPS/ERI/002/ITA, Project Document, September 2000

Terminal Report, GCPS/ERI/002/ITA, Draft, July 2000, Asmara

? It should be noted that institutions dealing officially in the country with vulnerability are ERREC and Ministry of Labour and Human Welfare. The latter is not a member so far of NFIS.

The AMSG members are the Planning and Statistics Unit (chair), the National Agriculture Research Institute (NARI), the Agriculture Promotion and Development Department (APDD) and one MoA Representative for each Zoba.

The present administrative decentralized structure foresees the Zoba level (region), the Desk level (province) and the Kebabi level (a number of villages)

The Technical Advisor was on sick leave for one and a half month in 2002, for one month in 2003 and for two months in 2004.

Usually, this heading includes also environmental impact of results, which however is not pertinent for the present Project.

The case of ESNP (Nutrition Programmes Service) is slightly different, since although the service is not a Task Force member, one of its experts is involved in the Project, by supporting the National Nutrition Surveillance System.

A number of similar recommendations had been formulated by the backstopping mission by ESAF in August 2002.

Please refer also to Annex 6 for background information on IT development