Appendix 1

FAO Inter-Country Programme for Community IPM in Asia

Phase IV Mid-Term Review 2000

Report on Australia’s Contribution

GCP/RAS/167/AUL

Addendum Contributing to the Inter-Country Programme for IPM in Asia

(Note: For Overall Findings – see Main Report)

Contents

page

A.	Funding and Use of Funds	2

B.	Summary of Outputs to Which Australian Finance Contributed	2

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Funding and Use of Funds

- Summary Tables 1 and 2 estimate the use of Australian funds by programme objective and country. Summary Table 2 is a sub-set of Summary Table 1, providing the breakdown of the regional component by country where individual countries benefited from staff visits, work by consultants, attendance at meetings, etc. Some 33% of regional-level expenditures benefited all countries (publications, website, information exchange, etc.).

- Some US$ 6.2 million of the Australian budget of US$ 9.6 million have been expended to date. Slightly over half of that expenditure has contributed to regionally-based activity. Australia’s contribution at the country level was devoted largely to work in China and in Southeast Asia (Cambodia, Indonesia, Philippines and Thailand). Regional funds also indirectly supported the Programme as a whole, including inter-country exchanges, technical support and information. To date, Australian funding has not been applied in Vietnam due to needs elsewhere. This was possible as adequate funding was available from the Norwegian budget and substantial funding was being provided bilaterally by other donors, in particular DANIDA.

| Summary Table 1: Estimated Distribution of Expenditures to Date by Objective and Country (includes Regional Activities Directly Benefiting Individual Countries and Those Benefiting All Countries - REG) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Countries* (and Regional) | CMB | CPR | INS | PHI** | THA | REG | Total |
| Estimated expenditure to date US$ million | $0.69 | $0.76 | $0.81 | $0.10 | $0.49 | $3.35 | $6.19 |
| 1. Developing and Implementing Training Capability | 35% | 50% | 0% | 35% | 25% | 5% | 15% |
| 2. Developing and Implementing Community IPM | 35% | 10% | 75% | 65% | 40% | 8% | 23% |
| 3. Developing Field Management Capacity | 10% | 20% | 15% | 0% | 20% | 18% | 17% |
| 4. Improved Policy, Planning and Prog. Development | 15% | 15% | 5% | 0% | 10% | 54% | 34% |
| 5. Enhancing Broader Awareness of IPM | 5% | 5% | 5% | 0% | 5% | 15% | 10% |
| Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| * CMB = Cambodia; CPR = China; INS = Indonesia; MAL = Malaysia; NEP = Nepal; PHI = Philippines; THA = Thailand; REG = Regional ** Activities in Philippines were for developing IPM in schools and integrated soils management (as envisaged in regional component) |  |  |  |  |  |  |  |

| Summary Table 2: Estimated % Distribution of the Use of the Regional Contribution (US$ 3.35 million) in Countries and that Portion which is attributable to Work in all Countries |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | BGD | CMB | CPR | IND | INS | LAO | MAL | NEP | PHI | SRL | THA | VIE | All |
| 1. Developing and Implementing Training Capability | 0% | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 1% | 1% | 0% |
| 2. Developing and Implementing Community IPM | 0% | 1% | 0% | 0% | 3% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 2% |
| 3. Developing Field Management Capacity | 2% | 1% | 2% | 1% | 3% | 1% | 0% | 2% | 0% | 1% | 1% | 1% | 3% |
| 4. Improved Policy, Planning and Prog. Development | 1% | 5% | 3% | 1% | 7% | 1% | 0% | 5% | 1% | 2% | 4% | 4% | 20% |
| 5. Enhancing Broader Awareness of IPM | 0% | 0% | 1% | 1% | 1% | 0% | 1% | 0% | 1% | 1% | 1% | 0% | 8% |
| Total: 100% | 3% | 8% | 7% | 3% | 14% | 2% | 1% | 8% | 2% | 4% | 7% | 8% | 33% |
| *BGD = Bangladesh; CMB = Cambodia; CPR = China; IND = India; INS = Indonesia; LAO = Laos; MAL = Malaysia; NEP = Nepal; PHI = Philippines; SRL = Sri Lanka; THA = Thailand; VIE = Vietnam; All = Regional expenditures benefiting all countries |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Summary of Outputs to Which Australian Finance Contributed

- Note that as more than one source of funds was used in the countries to which Australia contributed, except Thailand it has not been possible to split out specific outputs as being attributable to Australia. It may also be noted that as the Australian budget covers the post of Regional IPM Coordinator and the posts of Senior IPM Programme Development Officer and Senior IPM Scientific Officer and Training Officer, much of the work contributes to the Regional Programme as a whole (for the performance of that Programme –see main report).

| Outputs as per Project Document |  | Progress at Mid-Point of Phase IV 1998-2000 |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Self-reliant training capability where it does not yet exist within government agencies and/or non-government organizations which are planning or managing Community IPM programmes in member countries. |  |  |  |  |  |
| Summary of Training During Phase IV in Countries Visited by The Mission |  |  |  |  |  |
|  |  | Cambodia | China | Indonesia | Thailand |
| Farmer Field Schools (FFS) |  |  |  |  |  |
| No. of FFS |  | 681 | ~988 | 300 + | 72 |
| No. of Trainees |  | ~18,400 | ~29,192 | 10,000 + | 1,330 |
| No. of Women |  | N/A | ~ 8,000 | N/A | N/A |
| Non Rice FFS |  | 92 | `15 | N/A | N/A |
| ## Training of Trainer (TOT) Courses for Government and NGO staff |  |  |  |  |  |
| No. of TOT |  | 4 | 9 | 0 | 4 + 2 |
| No. of Trainees |  | 151 | 271 | 0 | 104 + 98 |
| No. of Women |  | 55 | N/A | 0 | N/A |
| Non Rice TOT |  | 3 | 0 | 0 | 1 |
| Farmer TOT Courses |  |  |  |  |  |
| No. of FTOT |  | N/A | ~58 | 84 | 0 |
| No. of Trainees |  | 250 | ~1,699 | ~ 2,000 | 0 |
| No. of Women |  | N/A | ~500 | N/A | 0 |
| Non Rice FTOT |  | 200 | ~3 | N/A | 0 |
| Summary |  |  |  |  |  |
| No. of Farmers |  | ~ 20,000 | ~29,192 | 4,240 | 1,565 |
| No. of Govt. Trainers |  | 150 | ~271 | 32 | 202 |
| No. of Farmer Trainers. |  | 450 | ~1,699 | 230 | 0 |
| Overall approximate totals: Trained Farmers: 55,000; Government trainers: 660; Farmer Trainers: 2380 |  |  |  |  |  |
| Notes: Cambodia, all paid for by IC Programme; China, Indonesia, Thailand partially paid for by local authorities |  |  |  |  |  |
| Outputs: Trainers capable of managing season long TOT courses without outside help. | See table above: In all of the countries, government trainers carry out CIPM training as part of their official duties, but in Indonesia this is very ad-hoc and depends on the goodwill of supervisors. In China, each province in the Programme has a structure of IPM Committees from the provincial level down through the counties and townships. However, only in Sichuan would there appear to be a well-institutionalised core group of trainers at the provincial level. |  |  |  |  |
| Objective 2: Developed content and methods of community IPM activities appropriate to different farming systems and social conditions. |  |  |  |  |  |
| Curricula available for specific farming systems and community needs | Work to date has concentrated on paddy rice production with relatively small amounts of work on other crops, particularly vegetables and commercial crops such as tea and chillies. The close links to the regional vegetable and cotton IPM programmes has facilitated this. Rice IPM is fully covered and curricula are flexibly adjusted in most of the countries each season. Curricula are also designed for the different, provinces in each country. The mission did note with concern that sometimes materials seemed to concentrate on insect ecology and material was limited, dealing with other pests (such as weeds and fungal and micro-biological pests). Similarly, such subjects as water management and fertiliser, although apparently covered in courses, were not always included in the guides. Business analysis was often not a prominent part of the training. This may contribute to the Mission’s impression that there could be a fall-back to traditional pedagogic methods in some situations. The exceptions are Cambodia and Indonesia which are generally more developed in all respects than the other countries: - Cambodia: Curricula cover - plant nutrient management; gender equity; crop-specific technology; on-farm production of pathogens by farmers; rodent management; health and pesticides; and three cropping systems - single crop rice, vegetables, and mung bean. - Indonesia: A wide range of curricula have been developed on various topics: soil fertility, plants, pests, diseases, natural enemies / bio-agents, farmers' organisation forums and advocacy on farmers' rights and many different cropping systems, rice-rice; rice – secondary crops; rice – vegetables; vegetables- vegetables. In Thailand, curricula have been adapted for use in schools. Other activities of particular interest included, 4 FFS for the handicapped in Cambodia |  |  |  |  |

| Action research completed by IPM farmers, in collaboration with specialist organizations, which increases the scope and depth of agro-ecological understanding. | Action research has been formally initiated in Cambodia and Indonesia: In Cambodia, there have been 47 Action Research (AR) activities (29 on rice and 18 on vegetables). Thirty of these took place in the last wet season. Supported by UNDP, “Farmer Life Schools” have been piloted in 6 locations which use approaches and methods adapted from FFS to observe and analyse the social situation within the community. In Indonesia, there are 8 Farmer Field Laboratories supported by the Programme; 9 Farmer Learning Facilities; and hundreds of farmer field studies. Four main AR projects deal with: studies on soil / fertility management, certain problematic pests, natural enemies / bioagents, botanical pesticides, trap crops, varieties, new crops, etc.; facilitating farmer studies and FFS in surrounding villages; farmer advocacy on local issues/problems; and producing and marketing compost, healthy seed/seedlings, and free/low pesticide products. In several cases, such as brown plant hopper and white stemborer, research findings have been consolidated and disseminated, leading to changes in farming practice. |
| --- | --- |
| A range of community IPM activities designed tested and documented in collaboration with government agencies and/or NGOs. | NGO involvement has varied. In China, traditional bodies such as the Women’s and the Youth Unions could be important. There was little work with other departments or projects to make use of CIPM methods, but in China, trainers were used to assist in the Dutch-assisted poverty alleviation programme. In Cambodia, training in CIPM has been provided to NGOs such as NPA, World Education, CRS, Concern, Oxfam Quebec, ADRA, EU/Prasac and CAAEP. Indonesia had a much greater range of activities: - IPM for teachers and students of Soedirman University; - Training on IPM for schoolteachers in a Junior High School for introducing IPM in the curriculum; - Gita Pertiwi Foundation, World Education, and Duta Awam Foundation in training on Farmer Action Research; Rio Tinto Foundation in TOT for Rio Tinto Staff; Cinta Desa Foundation and Tanah Karo Farmer Network (under World Education support) in Planning Meeting for Follow-up activities; - Collaboration between IPPHTI (IPM Farmers’ Association) and 32 Farmers' Organizations supported by an NGO network to struggle for Farmers’ rights. An interesting development in Thailand has been the introduction of FFS as a discovery learning methodology in schools. |

| Fora for communicative action established by/for farmers and community groups engaged in IPM activities. | Training material was developed on participatory planning and master trainers courses held in Cambodia and Indonesia. FFS members gained in confidence, analytical and communication skills. Farmers were trained in facilitation skills as part of FTOT (see above). Many Farmer-Trainers were previously in some form of leadership role within the community but many were not, and in all cases their capacity to make a contribution to local debate has been increased. This is particularly important in the case of women, who are forming an increasingly large proportion of trainees. It is clear that the leadership of FFS closely overlaps that of other village organizations and institutions. It seems likely that in many cases leaders joined the FFS rather than becoming leaders after the FFS experience, but some of the latter has probably occurred. This cross-over of leadership has facilitated the rejuvenation of the other organizations and their use to pursue the resolution of problems defined by the FFS members. Community IPM activities outside Indonesia are only beginning to develop. Groups often continue to exist after the FFS and concentrate on helping their neighbours with IPM and extending IPM to other crops. Farmers identify needs for common action on soil preparation, planting and varieties in order to conserve water and to reduce the risk of heavy build-up of pests in isolated fields at the beginning or end of the season. In some cases, farmers also reported that they had rediscovered old practices of communal work. To date, community-level activities identified by farmers outside Indonesia concentrate on improvement of agronomic practices, irrigation, and in some cases marketing, including the development of IPM products. IPM clubs/associations have been widely formed, but outside Indonesia most of these have not been active outside their own villages and there seems in some cases to have been a significant top-down element with government trainers forming the leadership. In Indonesia, community activities are much more developed and have moved towards political action and the representation of farmers, in a situation where there was a vacuum during rapid political change not filled by the former government-promoted organizations. In Indonesia, IPPHTI (Indonesian IPM Farmers’ Association) was established in 10 provinces with national, provincial and district level congresses. During 1998-2000, some 110 fora were convened, addressing four main topics education / facilitation; organising; science and technology; and farmer’s rights / advocacy. Skills for conducting fora have been developed in 15 training courses. Farmer-to-farmer workshops have been convened on Tungro Disease Control, Ecology and Soil. In China Anhui: 7 IPM farmers' associations with 45 affiliated interest groups (5-10 farmers); Anhui – 7 IPM farmers' associations with 45 affiliated interest groups (5-10 farmers); Hubei – 28 associations in 26 villages; Sichuan - 100 Alumni unions with information station function and 30 activity groups. |  |
| --- | --- | --- |
| Objective 3: Strengthened management capability for Community IPM programmes within member countries, and improved cooperation among member countries to sustain this capability |  |  |
| Field leaders and trainers with the knowledge, skills and experience required to plan, organise, coordinate and support a wide range of Community IPM activities |  | In all Australia-supported countries, except Cambodia, the Programme is nationally managed and has begun to leave the project mode. The development of curricula and the work programme is undertaken primarily by nationals. In Thailand, IPM is institutionalised within the formal structure in different ways: as regular work of the Department of Non-Formal Education with farmers and non-formal education students; as regular work through the Office of the National Primary Education Commission with students in primary schools; and as part of the mission of the Institute for Biological Agriculture and Farmer Field Schools, and within the Department of Agriculture Extension system at province, district and sub-district levels. Elsewhere, institutionalisation has often occurred primarily at provincial and local levels. This is the case in China. In Indonesia, the new IPM Farmers’ Associations, as well as the local authorities, are also important. This now reflects itself in quite substantial financial support being mobilised at the local level in these countries. In all countries, some senior staff have benefited from attendance at inter-country programme meetings. A Team members, have undertaken training assignments in other countries which have enhanced their skills. These are especially from Indonesia (12 persons), but also from China. Overseas consultancies have included: season-long TOTs in several Asian countries and Ivory Coast; assessment of IPM field training implementation in India and Nepal; and managing an IPM project in CARE, Bangladesh. The total number of trainers is referred to above, i.e. in excess of 4,500 government trainers for the countries visited. Probably more than 60 trainers are capable of carrying out international assignments to assist in the initiation of training. In China, a study tour by 13 IPM leaders, primarily from the provincial level, took place in California in 2000. This tour appears to have been very useful in exposing personnel to IPM and organic farming in a commercial, developed country context, which is of relevance for China. |

| Objective 4: Improved ability of policy-makers and planners to initiate, support and evaluate community IPM programmes |  |
| --- | --- |
| Case studies of community IPM activities, prepared and made available to planners, programme managers and trainers. Studies of special issues completed and results made available as inputs for policy making. | National workshops and studies on pesticides and the health of the farmers have been initiated in an action research framework in Cambodia and Thailand. Thailand has been the test-bed for participative study methodology. Other case studies include: - Cambodia: Impact of IPM training, Landlessness and Impact of IPM training, Rat and Crab farmer management practice, FTOTs and their contribution to civil society; - China/Regional: A workshop in Sichuan on gender and IPM in August 2000. China was able to disseminate the benefits of its progress in mainstreaming an emphasis in women which included both the other provinces of China, and Laos and Vietnam; - Indonesia: Case studies have been conducted on: advocacy on a water dispute; advocacy on irrigation maintenance; national, provincial and district-level farmer congresses; community IPM in 6 villages; gender; soil studies; various other technical studies (e.g. of white stemborer). |
| Advice to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects. Assistance to member governments and donors when mutually agreed in programme execution. | All the concerned line agency staff know about the Programme. Parliamentarians and ministers probably, are generally not aware of details, but senior figures often attend field days. In the majority of cases, senior staff responsible for extension, and sometimes for IPM, do not fully understand the total implications of FFS, as distinct from discussions at a demonstration. Advice and support have been provided to member governments by the Programme staff stationed in Cambodia, China, Indonesia and Thailand. A few of these staff also have technical responsibilities (science and health) and their effectiveness has also, in several cases, been enhanced by them having cross-responsibilities for the Regional IPM cotton and vegetable programmes. |

| Objective 5: Enhanced awareness in member and donor countries about Community IPM activities in Asia |  |
| --- | --- |
| Information on Community IPM available to the scientific community | There is contact with scientists in China and to a more limited extent other countries for curriculum development and involvement in farmer field studies. Elsewhere, scientists have had greater difficulty adapting to discovery learning as distinct from making recommendations. The Programme website has provided a valuable resource to all engaged in Community IPM and beyond. Two websites are maintained by provinces in China. In Thailand, a website has been developed for schools. A regional science and farmers workshop was held in 2000 in Jakarta. Programme staff have published in scientific journals. The target of 5,000 scientists reached, has been greatly exceeded through a combination of published papers and presentations at international conferences. |
| Information on IPM activities available to appropriate media organisations and advocacy groups | Progress in reaching the general public has been much greater. Community IPM is publicised in the local press and television. The Programme will also be covered on BBC World television. In Indonesia, a monthly tabloid newspaper (10,000 copies per issue) is being produced by the newly- established National IPM Farmers’ Association, which has received support from the Programme. Support has been provided to television with footage. There has been widespread press coverage of FFS training. |