- Appendix 5

- FAO Inter-Country Programme for Community IPM in Asia

- Phase IV Mid-Term Review 2000

- Indonesia – Summary Country Report

(Note: For Overall Findings – see Main Report)

- Contents

page

A: Introduction	2

A.1	The Mission	2

A.2	Status of the Programme at the Start of Phase IV	2

A.3	Support Received from the Regional Programme	2

B: Discussion of Outcomes and Impacts	2

B.1	Coverage	3

B.2	Beneficiaries	4

B.3	Cost-effectiveness of Training	4

B.4	Community Activities	4

B.5	Sustainability	5

B.6	Effectiveness at Policy Level	5

C: Major  Conclusions and Recommendations	5

C.1	Conclusions	5

C.2	Recommendations	6

- Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Introduction

## The Mission

- The Mission to Indonesia formed part of the Mid-term Review of Inter-Country Programme for Community IPM in Asia. This review took place some three years into the Fourth Phase of the Five-year Community IPM Programme. The main purposes of the Review, as per the Terms of Reference, were on the basis of the results and experience to date to assist management in deciding:

- staffing activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

- the desirability of, and options for, further technical and financial assistance which could consolidate current work and expand into emerging areas of opportunity.

- The full team consisted of four independent consultants, one representative of the FAO Evaluation Service and one country representative. Three groups were formed for country visits. The two-person team was in Indonesia for five days from 4-9 November and consisted of:

- Piao Yongfan – Country Representative from China – Deputy DG Agricultural Extension, China;

- Sean Foley – Consultant – Environmental Management and Agricultural Systems Specialist.

- During its visit, the team held discussions with the Directorate General of Food Crop Production, universities and a range of NGOs. Visits were made to two farmer research sites in West Sumatra and West Java, and an IPPHTI national coordination and planning workshop.

- The Mission wishes to express its appreciation to all those in Indonesia who provided such warm hospitality and who were always ready to answer questions and provide information. The Mission also wishes to emphasise that in such a short visit it had, of necessity, to make judgements on very limited information and its conclusions must be treated in that light.

## Status of the Programme at the Start of Phase IV

- The Community IPM (CIPM) Programme in Indonesia is the oldest in the region, and as a consequence it is more advanced in terms of the range of activities, and has the greatest coverage and depth. At the start of Phase IV, the World Bank-assisted National IPM Project was nearing completion, as a result of which a large pool of experienced trainers (both government staff and farmers) were available; IPM was well- established in the 12 major rice growing provinces and significant levels of local funding were already available. As a result of previous phases, one million farmers had participated in FFS, and many tens of thousands in FFS follow-up activities. The concept and trialing of Community IPM originated in Indonesia, and it has consistently expanded in coverage, range and depth of issues addressed, now including advocacy for farmer’s rights and broader organisational and economic issues affecting farmers.

## Support Received from the Regional Programme

- While the national programme is strong, co-location with the ICP office has resulted in a strong two-way flow of information and skills between the national programme and ICP. The ICP has also been instrumental in providing backstopping for the expanding range of CIPM activities, especially the formation of IPPHTI. Indonesia has also been the main source of expertise for the A Team, a clear indication of the two-way nature of the relationship.

# Discussion of Outcomes and Impacts

- This report, prepared after two brief field visits, cannot do justice to the achievements of the IPM Programme in Indonesia, or to the staff whose dedication has made it possible. It is fair to say that the IPM Programme stands out as one of the few development projects or programmes in Indonesia which has truly achieved, indeed greatly exceeded, its formal objectives. The Indonesian programme has made it possible for farmers, their families and communities to achieve significant and lasting improvements in their welfare, their health and the health of their environment. More generally, IPM training has provided farmers, both men and women, with the necessary intellectual tools to address a broadening range of social, economic and environmental issues that affect their lives and livelihoods.

## Coverage

- The extent of the programme has narrowed somewhat, due to the inability of IPM farmers from the province of Ache to participate due to continuing conflict in the province. In all of the other 10 provinces the number of farmers participating in FFS, now all conducted by farmer trainers, has continued to increase, as have the number of farmer-run TOT. Coverage has extended to upland areas growing vegetables (e.g. West Sumatra and West Java), and in these and other areas, farmers are actively carrying out field studies and farmer research on an expanding range of crops; in some areas farmers are now turning their attention to the certifying and marketing of pesticide- (and fertiliser-) free produce. The programme has become so extensive, and local initiatives, funding and organisation so much the norm, that it is nearly impossible to identify and count all the IPM-related activities that are taking place. IPPHTI carried out a partial survey of activities at the time of the mission, the results of this survey are summarised in the table below.

| Summary of Available Data on IPM Activities in Indonesia – January 1998 to August 2000 Survey by IPPHTI (9 of a total 11 provinces; 66 of a total 122 districts |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Unit | Approximate Number of Farmers Involved | Remarks |
| FFS (Farmer Field School) |  | 300 | 25 | FFS on various commodities, facilitated by Farmer Trainer or PHP (Pest Observer) |
| Training for Farmers |  | 84 | varies from 20-50 | Training on various topics, mainly on bio-agents and facilitating FFS, and also a few on advocacy and gender |
| Farmer Studies |  | 68 | varies from 20 – 50 | Studies on various topics: such as soil and fertilizer (incl. Compost, bokashi etc.), bio-agents, variety, agriculture techniques (spacing, sticking, etc), botanical pesticide, etc. |
| Farmers’ Forum |  | 110 | Village level 15–30, Sub-district 25–100, District 30–300, Province 200–400, National 500; Field Meetings involving non-IPM Farmer 400–1000 | Various farmers' forum: provincial/district IPM Farmer congresses; IPPHTI’s Management Board coordination meeting; socialization of IPPHTI Organization; Farmer Trainer workshop; socialization of IPM. |
| Farmer Action Research |  | 3 | 15–25 | Only 3 of 17 Farmer Action Research (supported by FAO and Field Leader Association) were recorded by the census |
| Farmers' Cooperatives |  | 4 | 20–40 |  |
| IPM implementation in the field |  | 11 | 15–75 | Various activities like planting rice without pesticide, breeding rice seed. |
| Mass Action for Pest or Field Management |  | 14 | Village level 35–200, Sub-District 25–400, District 7000 | Various activities like: “rat hunting”, mending the irrigation canal, tungro disease control in a wide area, doing agro-ecosystem observation and analysis together in a wide area. |
| Farmer Advocacy |  | 28 | Lobbying 2–4, Dialogue 10– 200, Demonstration 1000 | Advocacy on various activities: Dialogues between IPPHTI with legislatives district and sub-district government; advocacy on: land tax, irrigation tax, credit package, irrigation pollution, and Farmer’s Rights. |
| Other Activities |  | 7 | 40 | Various activities done by others supporting farmers like: mass propagation of bio-agents by Field Laboratory, pesticide residue testing by Laboratory, etc.; or activities by farmers like making ID for the member of the organization, making calendar, etc. |
| Notes on Funding | 40 % of activities were funded by local government budget (provincial and district). 30 % were self-funded by farmers. 20 % were funded by the National IPM Programme (only up to November 1999 when the Programme was closed). 10 % were funded by FAO. |  |  |  |

## Beneficiaries

- As with the range of activities being undertaken by self-organised farmers' groups, it is next to impossible to identify the full range of beneficiaries, let alone specify or quantify the benefits they are receiving; doing this would require a wide ranging field study. Identified benefits in rice and vegetable production include reduced input costs, in all cases for pesticides and in some areas substitution of organic fertilisers (composts) for inorganic fertilisers. There are also subsidiary benefits for farmer family health and the health of the local environment. In general, the farmers that have benefited most are those with small to medium parcels of land (0.2 to 0.5 ha) in densely populated areas; benefits to farm labourers, many of whom are landless, have probably been marginal, although they may have benefited from increased or more stable yields (if they receive a share of the harvest) or from lowered health impacts from pesticide poisoning.

## Cost-effectiveness of Training

- Based on the limited amount of information available of training costs – all but 10% of which is locally funded and all of which is provided by farmers – it appears that costs per participant for a whole season FFS cluster around US$ 8-10; costs per farmer TOT appear to be somewhat higher. The range and depth of IPM-related activities that are occurring, the growing ability of IPM farmer groups to attract local funding and the cross-fertilisation between groups that is taking place through local IPM associations, strongly suggest that FFS (and associated follow-up activities) are a highly cost-effective way of both conducting extension and multiplying and maintaining the benefits to farmers and their families.

- Cost-effectiveness of IPM for farmers: The primary economic benefit to farmers has come from removing or radically reducing the cost of pesticides; this has been especially important given the high rates of inflation and severe devaluation Indonesia has experienced since 1997. In this sense IPM is directly and clearly cost-effective in increasing the net income from rice and other crops. No recent systematic data are available on this issue, but there is consistent and widespread anecdotal evidence, i.e. what farmers say about input costs and income, to confirm that IPM is cost-effective. Reduced costs for family health have also been widely reported.

## Community Activities

- With the formation of district and provincial level IPM associations, and now the national association (IPPHTI), activities initiated by IPM farmers and their partners have moved beyond the community level and they are now becoming advocates in issues that affect all farmers, e.g. agricultural policy, land titling, irrigation management, market organisation and produce prices. In Indonesia, there has been no initiative to develop an IPM in Schools programme; this is partially due to the monolithic nature of the education system and curriculum; decentralisation can be expected to lead to changes in this.

## Sustainability

- The Indonesian IPM programme is now largely self-managed and self-financing. However, based on what was reported by national and provincial team members, international support is still important, both in terms of the political support and legitimacy it provides as well as linkages and access to the growing international store of knowledge and experience on IPM. Decentralisation of government functions, nominally occurring from the beginning of 2001, will provide a clearer indication of whether or not the IPM Programme continues to be able to attract funding and in kind support from district and provincial governments; it will also provide an indication of the degree to which advocacy on IPM and farmer related issues is effective at these levels of government.

## Effectiveness at Policy Level

- Beyond the major achievement of the Presidential Decree of 1996 formalising IPM for rice and banning many pesticides for use on rice, progress on the policy front has been slow; even the World Bank IPM project did not achieve its policy goals. It is clear that there is great opposition to operationalising IPM as the national standard for pest control and/or FFS as the national method for delivering agricultural extension/education to farmers – partly this arises from bureaucratic competition within government (at many levels) and partly from the degree to which pesticide companies have managed to penetrate the whole apparatus of government from national to local levels. With decentralisation, it may be possible for advances in policy, particularly operational policies, to be made at the provincial and district levels more easily, and in this respect advocacy at these levels will be particularly important.

# Major  Conclusions and Recommendations

- The Indonesian CIPM programme is successful, mature and staffed by people with many years of experience. The following conclusions are based on a brief visit informed by longer-term familiarity with the Programme, and are addressed to ‘fine tuning’ various aspects of the Programme. The conclusions and recommendations have been discussed with the country and ICP teams.

## Conclusions

- The overall conclusion is that both the ICP and Indonesian National IPM Programmes have been successful in meeting their objectives and in many instances have exceeded expectations, in terms of the range, geographical spread and quality of activities at the local levels that they have supported or initiated. In addition, the National Programme has undertaken a range of supporting activities not initially planned for. Specific achievements include the following:

1	Numerous government officials from crop protection at different levels, farmers and others have been trained as qualified facilitators for ICP and the National IPM Programme. These facilitators have been actively involved in farmer training, farmer-to-farmer training, farmer science studies, farmer groups, networking, advocacy, etc. These activities, and the enthusiasm with which they have been undertaken, helped to ensure self-sustaining development of IPM and expansion of the Programme by farmers and local organizations/NGOs based on their interests and concerns.

2	A range of community IPM activities have been designed and organized at village, sub-district, district, provinces and national levels by farmers, farmer leaders, officials, and ICP members. Soil management, through processing and applying composts, water management, biological control with self-made botanical and microbial agents, ecological knowledge enhancement through action research, promotion of capability for dealing with technical and social issues through workshops and forums on results, analysis, planning, sharing, etc. have all been achieved. These activities have been developed gradually, season by season, by the accepting and supporting suggestions from farmers, NGOs and other supporters, including consideration of changes in farming systems, the results of farmer science bases and a wide range of other issues addressed during the period.

3	Based on a better understanding of farming systems and field ecological issues, many action research facilities in different regions, and POSTs (farmers’ laboratories for bio-agents and compost production in connection with official district labs and universities) have been established. These activities of “farmer science” are driven by farmers’ interests and confidence in handling their farming systems, field ecosystems, economics and health. In addition, these have led to rapid development of farmers’ environmental knowledge, practical methodologies and cooperative relationships within/between farmers, groups, organizations, and the results have had direct relevance to farmers’ activities and welfare. In addition, the programme has played an important role in training and supporting farmer leaders/group leaders in many locations.

4.	The impact of ICP achievements, technical support, backstopping and its interactions with the national IPM Programme, as well as with related agencies including NGOs and farmer associations, has mobilized official involvement and support for IPM including policy, funds, staff, materials, etc. Especially the function of official plant protection (crop protection) agency has been reoriented towards IPM training, resulting in closer relationships between pest observers and farmers at various levels.

5.	Follow-up activities, training methodology, curriculum development for TOT and FFS have been expanded to vegetables from rice, which was the entry crop for ICP, and this has led to addressing a widening range of social, economic and technical issues of concern to farmers.

6.	The National IPM Farmers’ Association (IPPHTI) established at the IPM farmers' congress in 1999 is a visible symbol that Community IPM development and broader expansion of IPM is now linked with farmer empowerment. Various farmer groups can now more easily interact, stay informed and be assisted through growing networks and associations, i.e. in some locations irrigation issues seem to be moving towards resolution through dialogue with officials; the IPM newspaper written by farmers (70%) is a new development, the second edition of which was recently published. Establishment of clubs such as “Paguyuban” has assisted farmers to discuss, exchange and express their ideas, experiences, views and suggestions. It is reasonable to anticipate that these activities will have a growing effect on policy decisions and publicity with the coming government decentralization.

## Recommendations

- Maintaining Focus on Core Issues/Capabilities: With the progress of the IPM, achieved by the ICP and the Indonesian National IPM Programme, the context of the Programme has continued to become broader, including technical and social, economic and environmental aspects. A great number of demands, including funding, activities, planning, policies, etc. from trained farmers, farmer groups, networks and organizations, will continue to be developed. However, the IPM training project finished at the end of 1999. This means there will be limited funding input from the central government and other related direct input, which had been allocated to the local level. It means that the identifying priority context for the next two years should be important to ICP. Based on our observations, the following aspects could be considered as focal points:

- improvement of “farmer science”/action research context and related techniques need to be strengthened. Farmers are interested in making and applying composts and bio-agents with simple techniques and equipment. However, there seems to be a lack of mature techniques even in universities and research institutes. ICP could provide cross-country exchanging/ studying/collaboration opportunities to several qualified facilitators from the A-Team, since some countries like China have a long history and rich experience in these aspects. In addition, market development of pesticide-free products is also a potential sharable/ cooperative field among member countries in the region; experiments on seed variety comparisons and cultivation could be increased in “farmer study” groups;

- assistance for curriculum development should be expanded so as to ensure the quality and relevance of farmer-to-farmer training;

- organizational assistance is needed to enhance interactions among IPM alumni groups with local and national universities and NGOs.

- Developing Relationships between IPPHTI and Other Farmer Associations: There are a wide range of farmer and agriculturally-orientated organisations in Indonesia; however, based on the information available, it is fairly clear that the majority of them are not run by and/or for farmers. IPPHTI is already active in building links with selected organisations but the range could be expanded, with particular focus on groups that are promoting ‘pesticide-free’ agriculture and who are interested in advocacy work at the district level.

- Inclusion of Gender Issues in TOT and FFS: Since agriculture and rural areas are becoming increasingly ‘feminised’, women’s involvement in the training, field studies and roles in networks should be increased. Gender issues should be included in ordinary FFS, workshops and other group discussions.

- Deepening Documentation and Dissemination Capability: CIPM and the National IPM Programme have accumulated a lot of experiences and references which can not only provide ideas for further development of IPM, but also help IPM members/farmer associations to build a strong atmosphere of favourable public concern and policy directions. Support for IPM newspapers and other media channels should be considered.

- Broadening Donor Base: With the completion of the National IPM Programme last year, there are funding obstacles to local/IPM farmer groups in accordance with their enlargement and increase of activities. However, since national decentralization reform has switched on, there are possibilities to look for financial support from local governments and other donor agencies. ICP could assist broadening of donor bases for local groups as well as providing co-financial support (seed funds).

- Developing an Explicit Exit Strategy: At the national level, it would be worthwhile for the Programme to conduct a strategic planning exercise, or several as needed, with the explicit goal of planning for the cessation of the national programme. These could encompass defining goals, objectives and strategies for the coming two years and, most importantly, setting priorities for the consolidation of the wide range of activities currently being supported. This planning could encompass establishing ‘spin-off’ organisations and other similar issues. In the event that funding is available beyond 2002, the strategic plan would provide a strong starting point for the detailed design of a follow-on programme.

- Summary of Results Against Immediate Objectives and Outputs – Indonesia

- Progress at Mid-Point of Phase IV 1998-2000

| Objective 1. To create self-reliant IPM training capability where it does not yet exist within government agencies and/or non-government organisations which are planning or managing Community IPM Programmes in member countries. |  |  |
| --- | --- | --- |
| Output 1. Trainers capable of managing season-long TOT courses without outside help. | - Indonesia, the most advanced of the regional countries involved in the Programme, has many trainers capable of managing season-long TOT courses and all other forms of support activity, including providing support to other countries in the region. - IPM is institutionalised within the formal structure, although active support is available; macro forecasting system and economic threshold are still being used. - IPM training is formally still an additional duty, and the core job of Pest Observers is still surveillance. - Indonesia has a very large number of experienced trainers, many from under the National IPM Programme: more than 2,300 IPM Trainers (Pest Observers or PHP) in 22 provinces; more than 2,000 Farmer Trainers in 12 rice bowl provinces. - Under FAO IPM Indonesia, there are no centrally-planned FFS. In fact, there are numerous numbers of field schools run by Pest Observers and Farmer Trainers in many localities supported by local governments and NGOs. - From the survey, conducted with IPPHTI in November 2000, approximately 300 FFS + TOT (various TOT: on bio-agents, on facilitating FFS, etc.) over 1998-2000. - In collaboration with IPPHTI, at least 10,000 farmers in 10 provinces were trained. - From the IPPHTI survey in 10 provinces, 540 of 629 activities were locally funded or at least contain a contribution from local funds (both by farmers' funds or district/province government budget). The rest are partly funded by national/FAO. |  |
| Objective 2. To develop the content and methods of Community IPM activities appropriate to different farming systems and social conditions. |  |  |
| ### Output 2.1 Action research (AR) completed by IPM farmers, in collaboration with appropriate specialist organisations, which increases the scope and depth of agro-ecological understanding needed for the design and implementation of other activities. | - Up to now, 8 ARFs / Farmer Field Laboratory by FAO (West Java Province: Karawang, Pangalengan, Indramayu; Central Java Province: Grobogan, Boyolali, Brebes; Lampung Province: Tulang Bawang; North Sumatera province: Deli Serdang) - 9 Farmer Learning Facility led by PHP (West Java: Ciamis, Purwakarta; Central Java: Sragen, Grobogan; Yogyakarta: Sleman; East Java: Madiun, Kediri, Tulungagung, Tuban) - Beside these, hundreds of farmer field studies are conducted across the country. Samples of their study results are shown in local exhibitions, farmer congresses, etc. Due to the economic crisis, a lot of farmers conducted studies on bio-agents, composting, manures, etc. - Four main AR projects: studies on soil / fertility management, certain problematic pests, natural enemies / bio-agents, botanical pesticides, trap crop, variety, new crops, etc.; facilitating farmer studies and FFS in surrounding villages; doing farmer advocacy on local issues/problems; and producing and marketing compost, healthy seed/seedlings, and free/low-pesticide products. - Topics, based on common farmer problems in the area through participatory planning methods, addressed include: soil /fertility management, and compost processing, natural enemies / bio-agents, botanical pesticides, trap crop, variety, healthy seed selection and production, etc. - An overall assessment indicated that farmers can do effective research and convince the local policy makers on various farming practice recommendations. - Collaborative links have been established with: IPPHTI (Indonesian IPM Farmer Association), and IPM farmer groups. Some visits made by government officials/agencies, researchers, University, IPM Field Leader /Trainer Associations, NGOs. - In several cases, such as brown plant hopper in North Sumatera and white stemborer in Indramayu, West Java research findings have been consolidated and disseminated and led to changes in farming practices. |  |
| Output 2.2. Curricula available for specific farming systems and community needs. | - A wide range of curricula have been developed on various topics: soil fertility, plant, pests, diseases, natural enemies / bio-agents, farmers organisation forums and advocacy on farmer’s rights. - There are many different cropping systems for which curricula have been prepared: varying from rice-rice; rice – secondary crops; rice – vegetables; vegetables- vegetables Three training curricula were developed by IPPHTI together with FAO ICP Indonesia: Field Guide on Strengthening Farmer Trainer; Field Guide on Organising Farmer Science.; Field Guide on Organising Farmer Advocacy. Two training materials were developed by FAO ICP Indonesia: Field Guide on How to Conduct Impact Studies; Field Guide on How to Conduct Studies on Tungro Disease. One curricula developed by IPM Farmers and Field Leaders: Field Guide on Participatory Ecology Training and Soil Management. - Many farming systems covering all types of rice, vegetables and other crops have had curricula prepared for them. Curricula preparation is based on farmer demands and is developed by IPM farmer trainers with support from the Programme. They are then tested and used directly in training, and are designed to be flexibly adapted to local needs. There are direct links via the farmers that are involved and through other channels, between AR and curricula development. - All key topics are covered by curricula, and new ones are prepared when demand exists. |  |
| ### Output 2.3. A range of Community IPM activities designed, tested, and documented in collaboration with government agencies and/or NGOs in member countries. | - Major meetings conducted or supported by FAO ICP Indonesia: field management training for field leaders (340 field leaders were involved); TOT on IPM for teachers and students of Soedirman University who will conduct field lecture; training on IPM for schoolteachers in State’s Junior High School in Ciamis, West Java for introducing IPM in local curriculum and extra curriculum; supporting the short course on IPM for senior extension workers in Brawijaya University, East Java; Involving Gita Pertiwi Foundation, World Education, and Duta Awam Foundation in the training on farmer action research in Grobogan, Central Java; supporting Rio Tinto Foundation in TOT for Rio Tinto Staffs, and strengthening their programme: FFS by farmers and follow-up activities; supporting Cinta Desa Foundation and Tanah Karo farmer network (under World Education support) in planning meeting for follow-up activities programme planning. - Linkages between IPPHTI and government in all levels (provincial and district legislatives) through dialogue and lobbying (in 5 provinces and 22 districts). Linkages between IPPHTI and IPM Field Leader Association (WAKOM PL). Collaboration between IPPHTI and 32 farmers' organizations supported by NGO network to struggle for farmers' rights. - There are several topics suggested by farmers' groups: strengthening farmer-to-farmer training, strengthening farmer studies, strengthening local advocacy, local marketing, water management, soil management, legal aid, strengthening farmers’ organisations. |  |
| ### Output 2.4. Forums for communicative action established by/for farmers and community groups engaged in IPM activities. | - During 1998-2000, some 110 fora (according to the sample / data taken from the census done by IPPHTI) in various locations. IPPHTI was established in 10 provinces with national, provincial and district level congresses. - Four main topics have been addressed: education / facilitation; organising; science and technology; and farmer’s rights / advocacy. - Skills for conducting fora have been developed in: 10 training course in 10 provinces by IPPHTI and FAO ICP Indonesia: 5 training courses in West Java Province: Ciamis and Karawang District; in Lampung Province: Lampung Utara District; and in North Sumatera: Simalungun District), with different sources of funds: Farmers' Fund, National Programme, and District Government Budget. - Workshop on Community IPM in Songgoriti; Farmer-to-Farmer Workshop on Tungro Disease Control; Farmers' Workshop on Ecology and Soil in Ciamis. - Backstopping has been mostly provided during workshops, with IPPHTI representatives at provincial and national levels. Only few visits provided to district level congresses/fora. |  |
| Objective 3. To strengthen the management capability for Community IPM Programmes within member countries, and improve cooperation among member countries in a manner which will sustain this capability. |  |  |
| Output 3. Field Leaders and trainers with the knowledge, skills and experience required to plan, organise, coordinate and support a wide range of Community IPM activities. | - More than 30 people for in-country workshops and 12 persons have overseas experiences. - Main methods are through workshops, English training and as resource persons for season long TOT in other countries. - Consultancies are mostly season-long TOTs in several Asian countries and Ivory Coast; assessment of IPM field training implementation in India and Nepal; managing an IPM project in CARE, Bangladesh. - The number of people trained in CIPM is at least 340 field leaders who came back to their original duties and more than 2000 IPM training specialists (pest observers). - The A Team does not have an institutional base, although there is a recent initiative by 130 field leaders from 8 provinces to establish IPM trainers' associations through their recently conducted national workshop. The crop protection director has not given clear support for this activity. |  |
| Objective 4. To improve the ability of policy-makers and planners in member countries to initiate, support and evaluate Community IPM programmes. |  |  |
| Output 4.1 Case studies of Community IPM activities prepared and made available to planners, programme managers, and trainers. | - Case studies prepared are: water as a source of living: a study on farmer advocacy in Boyolali, Central Java; advocacy on water / irrigation in Tulang Bawang Udik, Lampung; White stemborer studies in Indramayu, West Java; shallow planting by Mr. Aep Saepudin, an IPM farmer in Tasikmalaya; 6 village cases of CIPM in Indonesia; national IPM farmer congress; provincial IPM farmer congresses in Lampung, West Sumatera, Central Java, and East Java. - More general case studies on CIPM, new curricula, e.g. soil management, activities of A-Team and IPM farmer’s media. - Minister and his staff, parliament members at national and local levels, local government policy makers in many provinces join the IPM farmer congresses at national, provincial and district levels. In each congress, usually there is a dialogue session among them with IPM farmers' representatives on the result of the discussion during farmer congresses. - There have been two international meetings /workshops conducted here attended by totally around 15 director-level or above. - Several local government policy makers (governors and district heads) give direct support to IPPHTI, IPM farmer training, bio-agent training and production, farmer-to-farmer activities, etc. - Case study materials are disseminated through the IPPHTI network. |  |
| Output 4.2. Studies of special issues completed, the results of which are made available as inputs for policy making and programme planning in member countries in support of Community IPM Programmes. | - Studies on: leafminer (the pest and its natural enemies); compost; soil ecology; bio-agents; white stemborer; brown plant hopper; shallow planting; fertilizer with colour chart indicator; soybean pests and natural enemies, etc. - All studies are conducted in collaboration with IPM farmers and disseminated through the IPPHT network. |  |
| Output 4.3. Advice provided to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects, with special attention paid to the design of community-based approaches. | - Usually via IPM farmer congresses: Minister of Agriculture, Director-General of Food Crops, Director of Crop Protection, International Cooperation Bureau, Governors, Head of Regents (Bupati), Head of Agriculture Services in province and district levels. |  |
| Output 4.4. Assistance provided to member governments and interested donors in the execution of projects (or project components) which promote and support Community IPM. | - Continuing assistance through ICP to the rest of the region. - Up to November 1999, with the National IPM Programme. |  |
| Objective 5. To enhance broader awareness in member and donor countries about Community IPM activities in Asia. |  |  |
| ### Output 5.1. Information on Community IPM available to the scientific community. | - Some 20 Indonesian scientists directly involved in research activities; many more exposed to CIPM approach through outreach methods, conferences and seminars. - Two international workshops: Farmers and Science, and Community IPM |  |
| ### Output 5.2. Information on IPM activities available to appropriate media organisations and advocacy groups. | - Web site, IPPHTI brochures, Spider newsletter and “Media Petani Indonesia”. - During FAO IPM international workshops (twice), national and provincial IPM farmer congresses. |  |