Appendix 7

FAO Inter-Country Programme for Community IPM in Asia

Phase IV Mid-Term Review 2000

Sri Lanka – Summary Country Report

(Note: For Overall Findings – see Main Report)

Contents

page

A: Introduction	2

A.1	The Mission	2

A.2	Institutional Structure	2

A.3	Support Received from the Regional Programme	2

B: Discussion of Outcomes and Impacts	3

B.1	Coverage	3

B.2	Beneficiaries	3

B.3	Cost-effectiveness	3

B.4	Community Activities	4

B.5	Sustainability	4

B.6	Effectiveness at Policy Level	4

B.7	Benefits from the Regional Programme	5

C: Major  Conclusions and Recommendations	5

D: Summary of Results Against Immediate Objectives and Outputs	7

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Introduction

## The Mission

- The Mission to Sri Lanka formed part of the Mid-term Review of the Inter-Country Programme for Community IPM in Asia. This review took place some three years into the Fourth Phase of the Five-year Community IPM Programme. The main purposes of the review, as per the Terms of Reference, were on the basis of results and experience to date, to assist management in deciding:

  - staffing activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

  - the desirability of, and options for, further technical and financial assistance which could consolidate current work and expand into emerging areas of opportunity.

- The full team consisted of four independent consultants, one representative of the FAO Evaluation Service and one country representative. Three groups were formed for country visits. The two-person team visited Sri Lanka for one week from 4-11 November and consisted of:

- Michele P Pimberg – Consultant – Agro-Ecology Specialist;

- John Markie – FAO - Evaluation Service.

- During its visit the team held discussions with the Department of Agriculture, the Mahaweli Development Authority, two provinces, the Ministry of Finance – Department of International Cooperation, the Netherlands Embassy and the FAO Representation. Visits were made to Farmers' Field Schools and follow-up activities in several parts of the country.

- The Mission wishes to express its appreciation to all those in Sri Lanka who provided such warm hospitality and who were always ready to answer questions and provide information. The Mission also wishes to emphasise that in such a short visit it had, of necessity, to make judgements on very limited information and its conclusions must be treated in that light.

## Institutional Structure

- For purposes of rice production Sri Lanka is served by three separate sets of government structures. Agriculture is a devolved responsibility to the eight provincial governments, which are supported with central funding from the Department of Agriculture (DOA) for block demonstrations (Yaya) and technical guidance and the core staff of agricultural officers are also a central DOA responsibility. In addition, separate arrangements exist for the significant irrigated areas. Large-scale irrigation falls under the Mahaweli Authority which has its own minister. It covers 119,000 farmers producing rice and accounts for 25% of rice production. Medium-scale irrigation is largely in so-called inter-provincial areas and in these districts, irrigation and extension is a direct DOA responsibility. Work in FFS has been in all eight of the country’s provinces with the support of the provincial administrations, with an NGO Sarvodaya Economic Enterprise Development Services (SEEDS), and the Mahaweli Authority. There has been very little work in inter-provincial areas.

## Support Received from the Regional Programme

- There has been a low level of funding and limited international staff time devoted to the IPM Programme in Sri Lanka as it was not covered by core funding, after the Netherlands decision to not provide further support at the regional level. It is against this perspective that the effectiveness and impact of the Programme must be judged.

# Discussion of Outcomes and Impacts

## Coverage

- Overall coverage of the Community IPM Programme remains very small and this is a major disadvantage in demonstrating the efficacy of the Programme to policy makers. The number of farmers fully trained in FFS to date is 8,520 and by the end of Phase IV can be expected to be of the order of 16,000 at the present rate of progress. There are 1.8 million farm families in Sri Lanka of which more than half grow rice. Total percentage of farmers covered for whom rice is a significant crop will be less that 2%. In Mahaweli, 1,500 farmers or 1.3% of the total have been trained to date but there are 119,000 farmers so the potential exists to more rapidly demonstrate impact. The low level of coverage after over 10 years of apparent activity is the argument used by the sceptics as to why the Programme cannot make a meaningful contribution. The Mission does not share this view as funding levels and thus rates of expansion have been low.

## Beneficiaries

- The Programme is present in all provinces. The Mahaweli area can best be referred to as middle-income for agriculture, but possibly poorer overall than most irrigated areas. In the provinces, the Programme deals with small-scale irrigated areas and not the larger schemes. The wealthy have little interest in the FFS and most are not full-time farmers.  On the other hand, FFS are not representative of the poorest of the poor. The poorest rural dwellers have little land. The poorest farmers have no access to irrigation and thus do not grow paddy rice (they tend to farm steep hillsides destructively). Poor farmers or part-time farmers who grow some subsistence rice are less likely to be heavy users of pesticides. There is thus some question whether they should be a primary target audience. It is also clear that unless they possess unusual qualities the poorest are unlikely to occupy leadership positions. There was some evidence that when farmers intensified their production practices in line with their learning from the FFS, this produced a greater demand for labour which could benefit the poorest

- Women frequently have the primary responsibility for agriculture, with husbands living at home but seeking other work. This is especially the case if the farm is small. Women appear to be genuinely welcomed in the FFS. There was no data but missions had the impression that women made up about a third of the membership and were well-represented among farmer trainers and the FFS leadership.

## Cost-effectiveness

- Training: In terms of people trained, incremental expenditure in addition to staff time for an FFS is only US$128 if conducted by agricultural staff and US$108 if conducted by farmers, i.e. about US$ 8 per participant in direct incremental costs for a season’s training. Costs of TOT training must also be added which are about US$ 580 in incremental costs per trainee for agricultural staff. Assumptions have to be made about how much training they will actually do but assuming an average of 10 FFS conducted per trainer the costs per trainee rise to US$12. The possibilities for further increasing the cost-effectiveness of training and boosting the number of farmers which can be reached exist in Farmer-to-Farmer training. Farmer-Trainers have to date been provided with one or two weeks’ additional training in facilitation methods. Thus, the incremental training cost is low. The costs of the FFS is also slightly lower using Farmer-Trainers but the average size of the FFS seems smaller and there have been some concerns expressed about quality. The Mission met several Farmer-Trainers who were relatively satisfied with results but did not see a FFS which had been run by farmers.

- Cost-effectiveness of IPM for farmers: It seems to be generally accepted that IPM in rice reduces production costs and the two surveys carried out on impact also concluded that there was a very substantial increment in yield following FFS training, probably due to an improvement in other practices such as reincorporating straw, weeding and increased fertiliser applications. In provincial areas (i.e. not Mahaweli), there was found frequently to be a doubling in yields. The NGO study found a decrease in average production costs per hectare of US$ 78 for insecticides and a much larger-scale study by an independent consultant reported an average of US$ 110 per hectare. He also reported that farmers were able to reduce seed rates. In the Mahaweli area, farmers do have one hectare each, elsewhere the area is lower but nevertheless figures are substantial.

## Community Activities

- It is only in the last 18 months that there has been a move to go beyond FFS towards the other elements of the Community IPM approach, including farmer trials, participatory planning and the encouragement of IPM clubs. The Mission concluded that the FFS did provide a strong basis to move forward with participatory planning, group activities and improved decision making on other elements of the farming system. The Mission queried the emphasis to be placed on this aspect at the cost of increasing FFS coverage over the remaining two years of the Programme.

## Sustainability

- The Mission was not able to form a clear view of the sustainability of the benefits from FFS at the farmer level, although the general impression was positive. Some observers reported that follow-up was essential for at least  a further three seasons following a FFS. This often tended to happen anyway as the trainer had forged a relationship with the farmers.

- Prospects for the spread of FFS without continued support from the Programme: Projects have from time to time funded additional IPM activity and in the North Central Province out of 45 FFS, 37 were funded by a project with the funding being obtained directly by the province. It seems likely that  the NGO Sarvodaya Economic Enterprise Development Services (SEEDS) would continue a certain amount of FFS activity without Programme support (perhaps 5-10 FFS per year). However, no government body has institutionalised funding for FFS except in kind through release of staff. There is strong support for the Programme in 4-5 provinces and by the Mahaweli Authority but funds have been deployed for block demonstrations which is the policy of the Department of Agriculture. In the Department of Agriculture (DOA), the attitude to the Programme tends towards hostility, especially among the extension specialists. The argument against the Programme is basically that there is a political necessity to provide universal extension services and it is not possible to divert funds to FFS which can only reach a few farmers. This mistrust in the Department of Agriculture has negative implications for the future of the whole Programme in Sri Lanka.

- No study has been made comparing results from the official extension approach (which relies on block demonstrations) with that from FFS but the Mission feels that it would be very worthwhile to carry out such a study using a fully independent and reputable institution and to widely publicise the result for the benefit of policy makers.

## Effectiveness at Policy Level

- Although the Programme contributes to the general level of awareness on pesticides, as will be evident from the discussion above, the impact of the Programme to date on policy for extension and pesticides has been limited. No policy level outputs have been developed with the exception of an input to the national task force on pesticide suicides. Efforts have been made by national partners in the provinces to publicise their work in the national press and with local authorities through attendance at field days, etc. The Programme has also provided film footage for national television.

- This having been said, Sri Lanka is a literate society with a section of the population which is highly educated and very much in touch with developments in Europe and North America. There is an active group of campaigning NGOs. There is thus a high degree of awareness of the dangers of pesticides for human health and a concern for environmental issues. This is reflected in a much more effective pesticide register and control on pesticide sales, storage, packaging, etc. than would be found in many countries at a similar stage of development (although considerable scope for improvement remains). It has also produced a demand for pesticide-free foods, perhaps a very limited national demand for organic products and political support for work on the environment.

## Benefits from the Regional Programme

- In the absence of an international staff member, there is little inter-action on a continuing basis between nationals trained in IPM and the regional programme.  Very few people have internet access and thus make use of the webpage, etc.

# Major  Conclusions and Recommendations

- The Mission is of the view that the prospects for national development of FFS and Community IPM without support from the Programme are slight. It is also convinced that the approach has much to offer Sri Lanka. If the Programme is to acquire greater national support it will have to achieve a clear demonstration effect. The Mission emphasises that while it considers achieving a demonstration effect essential and some greater focus and concentration of effort is essential for this, it does not consider that in such a short visit it could derive definitive answers. In this spirit, the following thoughts are offered for consideration:

  - There is as of today, a trainer capability to run 55 farmer-led FFS and some 50 trainer-led FFS per season, which is 420 FFS during the remaining two years of the Programme, or some 8,300 farmers. As there is an excess of trainers to resources available to carry out training, the Mission recommends that in view of the high cost-effectiveness of FFS in Sri Lanka, the Regional Programme allocate additional funds to Sri Lanka for FFS to maximise on available trainers. This will assist in moving towards the demonstration effect referred to above.

  - Farmer-Trainers should increasingly become the main actors in bringing FFS to immediately contiguous areas with their own FFS. This has several advantages. The Farmer-Trainers feel more confident in an adjacent area and simple problems like travelling and time lost in travelling are reduced. Lessons are reinforced for all the FFS from which the trainers come as they feel they are a demonstration to others. The area develops a corporate identity as an IPM area. Impact can be more clearly seen.

  - Some consideration should be given to concentrating a greater proportion of effort in Mahaweli, for the following reasons:

    - there is considerable support from the Mahaweli Authority, even if this is not reflected in actual funding;

    - this accounts for the greatest area of rice in the country where farmers are dependent solely on a rice-based cropping system;

    - as this is a rice area, it already has comparatively high yields but it also accounts for much of the pesticides applied in rice;

    - in the provinces much of the rice is grown primarily for subsistence but in Mahaweli this is a cash crop and there is the possibility to improve marketing of insecticide-free rice and perhaps even limited quantities of organic rice.

This could lead in time to a de-facto change in counterpart agency.

  - Consideration could be given to concentrating FFS in Yaya block demonstration areas. This requires further study but could have the advantage of reinforcing the participatory learning approach of FFS/CIPM in the demonstrations. It may also decrease the potential for conflict with the DOA and increase the possibilities for institutionalisation of CIPM within government programmes.

  - The Programme systematically identify and hold discussions with ongoing area, agricultural and rural development programmes/projects, to see if there is scope to incorporate FFS/CIPM within these projects and programmes. An encouraging start has been made with the FAO-Japan SPFS expansion proposal.

  - A scheme to be developed together with Sri Lankan retail/wholesale businesses for insecticide-free rice clearly bearing a Community IPM logo. Help may be obtained in this from such partners as SEED and Mahaweli Venture Capital. Technical support could also be sought from the Agricultural Marketing Service in FAO.

  - Building on the comparative strength of the FFS and responding to criticisms that the IPM approach is not tackling other aspects of the farming system, follow-up to FFS in participatory planning concentrate on extension of the FFS analytical and learning approach to other aspects of the system such as water and soil management and market analysis for alternative and supplementary crops.

  - In the absence of a very clear indication of funding beyond Phase IV the Programme continues to concentrate on rice IPM and does not enter into other topics, attractive as they may be for farmers and for reduced pesticide use.

  - In addition to and in view of the level of concern in Sri Lanka with the health risks evident in the high usage of pesticide on vegetables, and that Sri Lanka is not included in the regional vegetable IPM programme, FAO to give consideration to a separate TCP project with the Department of Agriculture to examine policies and technical possibilities for reduction of pesticide use in vegetables and the introduction of vegetable IPM.

- In conclusion, the staff of the Programme are encouraged to more systematically publicise the Programme and its achievements to the public and policy makers at all levels. It is only if such visibility is obtained that the basis for expansion and influence on the wider approaches to extension and pest management will be achieved.

# Summary of Results Against Immediate Objectives and Outputs

| Progress at Mid-Point of Phase IV 1998-2000 |  |
| --- | --- |
| Objective 1: Self-reliant training capability where it does not yet exist within government agencies and/or non-government organizations which are planning or managing Community IPM programmes in member countries. | In the Department of Agriculture support is weak. In the Mahaweli Authority which is responsible for 25% of rice production and about 10% of rice farmers, support is good but no funding is provided. In provinces in 4-5 cases there is some support and in a few cases limited funding is provided. Overall, coverage of the Community IPM programme remains very small and this is a major disadvantage in demonstrating the efficacy of the Programme to policy makers. The number of farmers fully trained in FFS to date is 8,520 and by the end of Phase IV can be expected to be of the order of 16,000 at the present rate of progress. There are 1.8 million farm families in Sri Lanka of which more than half grow rice. Total percentage of farmers covered, for whom rice is a significant crop, will be less that 2%. In Mahaweli, 1,500 farmers or 1.3% of the total have been trained to date but there are 119,000 farmers so the potential exists to more rapidly demonstrate impact. The low level of coverage after over 10 years of apparent activity is the argument used by the sceptics as to why the Programme cannot make a meaningful contribution. The Mission does not share this view, as funding levels and thus rates of expansion have been low. There is as of today a capability to run 55 farmer-led FFS and some 50 trainer-led FFS per season, which is 420 FFS during the remaining two years of the Programme, or some 8,300 farmers. Funding is, however, only available for 94 FFS per season, equivalent to 376 FFS in the remaining two years of the Programme. The amount of training can be boosted further by full utilisation of the existing trainers as per the above calculation and through additional TOTs for government staff and farmer trainers. In addition, Agricultural Instructors trained in IPM and trained farmers will continue to have some multiplier effects at a less formal level and through the demonstrations. |
| Outputs: Trainers capable of managing season-long TOT courses without outside help. | All provinces of Sri Lanka, the Mahaweli Authority and two NGOs have trained trainers deployed each season to carry out FFS. Since the start of the IPM Programme, some 90 Master Trainers have been trained on full TOT. Of these, some 75 are now said to be available to carry out training. Since 1994, there have been 3 TOT for some 90 master trainers and 381 FFS conducted by master trainers. For Phase IV figures are: - Season TOT for agricultural staff (mainly instructors) 1 for 32 trainers - 11 week-long TOTs for farmers covering some 230 farmers - FFS by master trainers have been 155 covering some 3,201 farmers. - FFS by farmers working in groups of 2-3 have been 59 covering some 1,039 farmers (average FFS size is 19.8) The conduct of full FFS has been largely dependent on Programme funding with a rather few cases of provincial funds being allocated and in one district 35 of the 47 of the FFS conducted were with funding from a project. Training is carried out during official working hours and in some provinces and in the Mahaweli Authority trainers have been expected to carry out IPM abbreviated FFS/demonstrations as part of their duties; but without project support little full FFS training takes place. The NGO Sarvodaya could also be expected to continue a few FFS per season without project support. |
| Objective 2: Developed content and methods of Community IPM activities appropriate to different farming systems and social conditions: Outputs: Curricula available for specific farming systems and community needs | Work to date has concentrated on paddy rice production with a small amount of work on chillies which are sometimes grown in the second season rotation with rice. In addition to rice`, a preliminary survey was made of pesticide use in vegetables. Ten pilot FFS were conducted on chillies and some 20 on vegetables. A concept paper on vegetable IPM was discussed during a project formulation meeting. Rice IPM is fully covered and curricula are flexibly adjusted. The following are available in Sinhalese: - Conducting FFS training - Handbook for conducting FFS - Handbook for Farmer TOT training. |
| Action research completed by IPM farmers, in collaboration with specialist organizations, which increases the scope and depth of agro-ecological understanding. | Action research has not been formally initiated but a manual was prepared on farmer studies, which was incorporated in the last TOT for government trainers. A 3-day workshop held for Mahaweli Master Trainers and small funding provided for farmers’ trials. A programme for farmer studies is expected to be initiated from next season. Eighty-three farmers trials were provided limited support from 1999-2000. The Mission was able to verify that some serious trial work had taken place but some lacked discovery learning and resembled on-farm trials. Trials also seem to have reinforced some useful practices such as incorporation of rice straw and other organic matter. |
| A range of Community IPM activities designed tested and documented in collaboration with government agencies and/or NGOs . | Training material was developed on participatory planning and 11 days devoted to this for 32 Master Trainers. Fourteen groups have now initiated participatory planning activities. The NGO Sarvodaya conducted 2-3 of these. Particularly innovative suggestions from participatory planning groups included marketing of pesticide-free rice, variety trials and salinity alleviation. |
| Fora for communicative action established by/for farmers and community groups engaged in IPM activities | FFS members gain in confidence, analytical and communication skills. Farmers are trained in facilitation skills as part of FTOT (see above). Many Farmer-Trainers were previously in some form of leadership role within the community but many were not and in all cases their capacity to make a contribution to local debate has been increased. This is particularly important in the case of women who are forming an increasingly large proportion of trainees. It is clear that the leadership of FFS closely overlaps that of other village organizations and institutions. It seems likely that in many cases leaders joined the FFS rather than becoming leaders after the FFS experience, but some of the latter has probably occurred. This cross-over of leaderships has facilitated the rejuvenation of the other organizations and their use to pursue the resolution of problems defined by the FFS members. Community IPM activities in Sri Lanka are not well-developed beyond the FFS. Groups often continue to exist after the FFS and concentrate on helping their neighbours with IPM and extending IPM to other crops. Farmers identify needs for action on common soil preparation, planting and varieties in order to conserve water and to reduce the risk of heavy build-up of pests in isolated fields at the beginning or end of the season. Farmers also reported that they had rediscovered old practices of communal work. To date, community- level activities identified by farmers concentrate on improvement of agronomic practices, irrigation and in some cases marketing issues are being discussed. The participatory planning provides a forum for 14 groups to date. One hundred and seven IPM clubs have been formed, but most of these have not moved to concrete action and there seems in many cases to have been a significant top-down element with government trainers forming the leadership. There have been 39 national tours for IPM clubs with 20 participants per tour. There are district-level IPM farmer associations in three districts. |
| Objective 3: Strengthened management capability for Community IPM programmes within member countries, and improved cooperation among member countries to sustain this capability Output: Field Leaders and trainers with the knowledge skills and experience required to plan, organise, coordinate and support a wide range of community IPM activities | The Programme is partly managed by a national employed by the Programme but depends entirely on a project mode. There is one international A Team member who attended the Workshop on Science and the Farmer in Indonesia. A further five trainers who went on a recent study tour to Indonesia could qualify for A team membership. However, no basis exists for sustainable national management and this is a key concern. The Sri Lanka programme has participated in the various meetings organised regionally by the Programme. One DOA staff visited Bangladesh to learn about farmer-to-farmer training and curriculum development but is not currently actively engaged in this. |
| Objective 4: Improved ability of policy-makers and planners to initiate, support and evaluate Community IPM programmes Outputs: | Outputs under Objective 4 were mainly addressed to the Inter-country programme level and limited specific actions were taken in Sri Lanka. All the concerned line agency staff know about the project. Parliamentarians and Ministers probably do not. In 4-5 of the provinces where the project has been active, provincial Council members have attended field days. Decision makers are not really aware of the differences between FFS and Community IPM and in the majority of cases senior staff responsible for extension and for IPM do not fully understand the full implications of a FFS as distinct from discussions on a demonstration. |
| Case studies of Community IPM activities, prepared and made available to planners, programme managers and trainers. Studies of special issues completed and results made available as inputs for policy making. | There have been two studies: - Impact Study on Integrated Pest Management Programme in Sri Lanka (private consultant); - Measuring Cost-Effectiveness by the NGO Sarvodaya. A workshop was held on pesticide-health effects as a component of IPM, which was attended by 10 DOA trainers, 2 NGO staff and 2 staff of the pesticide registration office. |
| Advice to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects. Assistance to member governments and donors when mutually agreed in programme execution | An adviser has recently been stationed in Sri Lanka and is providing active assistance in all aspects of programme development and execution. Costs for Sri Lanka have been reduced as he works as South Asia coordinator and science advisor for the Programme. A one-hour presentation made to the presidential taskforce on suicide prevention was given to discuss the importance of IPM training as an approach to reduce suicides using agro-chemicals. Materials were distributed |
| Objective 5: Enhanced awareness in member and donor countries about Community IPM activities in Asia Outputs: | Outputs under Objective 5 were mainly addressed to the Inter-country programme level and limited specific actions were taken in Sri Lanka. |
| Information on Community IPM available to the scientific community | No specific action, although scientists are involved to some extent in TOT and to some extent in provincial committees |
| Information on IPM activities available to appropriate media organisations and advocacy groups | Support has been provided to TV with footage. There has been press coverage of FFS training. Regular contacts are maintained with the campaigning NGO MONLAR. |