FAO Inter-Country Programme for Community IPM in Asia.

Phase IV Mid Term Review 2000

Main Report

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December, 2000

Abbreviations Used in the Text

| TOT | Training of Trainers |
| --- | --- |
| AR | Action Research |
| AUSAID | Australian Agency for International Development |
| BPH | Brown Plant Hopper |
| CIDSE | Coopération Internationale pour le Développement et le Solidarite |
| CIPM | Community IPM |
| CRS | Catholic Relief Services |
| DANIDA | Danish International Development Agency |
| DIFID | UK Department for International Development |
| FAO | Food & Agriculture Organization of the UN |
| FTOT | Training of Trainers of Farmers |
| GTZ | German Technical Cooperation Foundation |
| ICP | Inter-country Programme |
| IFAD | International Fund For Agricultural Development |
| IIED | International Institute for Environment & Development |
| IPM | Integrated Pest Management |
| IPPHTI | Indonesian IPM Farmer’s Association |
| IRRI | International Rice Research Institute |
| M&E | Monitoring and Evaluation |
| NGO | Non-Governmental Organization |
| NORAD | Norwegian Aid |
| NPA | Norwegian People’s Aid |
| PPD | Plant Protection Department |
| TEF | Thai Education Foundation |
| TOT | Training of Trainers |
| TRIPS | Trade Related Intellectual Property |
| UNDP | United Nations Development Programme |
| USAID | United States Agency for International Development |
| WTO | World Trade Organization |

Preface

There is little doubt that FAO’s Inter-Country Community IPM Programme in Asia is exceptional and deserves special attention from those who decide about its future. It is a flagship among FAO’s programmes in terms of its size and impact, and the enthusiasm it has generated world-wide. It grew from outrage about pesticides. Insecticides are frequently perceived to:

- Disregard farmers’ lives and health;

- Symbolise the greed, exploitation and hypocrisy of ‘life science’ companies;

- Be anti-ecology in that many are general biocides that kill everything with a nervous system;

- Allow corporations to capture benefits, while hazards, environmental damage, and costs are ‘socialised’ among farmers and the public;

- Present a major threat to food security by causing widespread insect damage.

The Programme has translated this outrage into a unique approach to non-formal education, the Farmer Field School. The FFS has ignited millions of small rice farmers’ self-confidence, reduced their pesticide use and costs of production, improved their yields and health, and set them on a path of continued learning and collective action to improve their livelihoods. This Mission’s members, during their field visits in the different countries, could not help but be swept along by the enthusiasm of the farmers involved. The FFS has become a model for farmer learning in other crops, such as vegetables, fruits, tea and cotton. It offers a non-formal education model that, as no other, brings together agro-ecology, participation, gender equity and civil society.

The Mission’s task was to look at Phase IV, the Community IPM phase of the Programme that emphasises ‘follow-up’ of FFS, i.e., activities that seek to establish farmer management of IPM at the community level and capture enduring benefits from farmer empowerment. The Mission could not, however, limit its examination to Phase IV. In the first place, it was difficult to divorce Phase IV from the rest of the Programme, especially since some countries have only recently started IPM activities, while in others Phase IV represents a continuing evolution. Secondly, the end of Phase IV marks a discontinuity of sorts. Hence the Mission had to consider the future of the entire Programme beyond the two years that mark the end of Phase IV.

The Mission considers the CIPM Programme a unique international effort that seeks to move beyond the current technology and market-driven designs for global society to one that is increasingly informed by social learning, deliberative democracy and ecological rationality. Much can be learned from this large-scale experiment.

Given the complexity of the Programme, and the importance of the task, the Review Team had to be made up of people who knew the Programme well. There was no way in which outsiders could learn its intricacies and do justice to its achievements in the short time available for the Mid-term Review. The fact that the team members knew the Programme well means that they are not neutral towards it. In fact, they are all deeply impressed by the achievements of the Programme. It has basically affected their outlook on development. For most, it has generated optimism that it is possible, after all, to steer events in a positive direction. But this partiality does not mean that the conclusions of the Review were foregone. The very fact that the Review Team has such high regard for the Programme has meant that it has been critical in its examination whether it lives up to its expectations, and very critical especially in assessing what future roles it can play.

By splitting into three groups, the team visited seven countries for a maximum of five days each. Together with the team’s previous knowledge of the Programme, consultations with the national and regional staff, and the documentation available, these field visits provided the basis for the findings and recommendations presented in this report. Despite severe time constraints, the team believes it has been able to capture the big picture, but it also realises that, with a programme so large and complex, errors may have been made while some judgements might have been more strongly substantiated.

Acknowledgements

The Mission wishes to express its appreciation to all those, national and international in the countries visited, in the Inter-Country Programme Office and in FAO-RAP who provided such warm hospitality, an extensive range of briefing materials and who were always ready to answer questions and provide information.

Contents

page

Abbreviations															   2

Preface																   3

Acknowledgements														   4

Executive Summary														   5

A: Introduction	10

B: FINDINGS	10

B.1	Introduction	10

B.1.1 Development and Coverage of the IPM Programme	10

B.1.2 Focus on the Rice Crop and in Intensive Systems	11

B.1.3 Expansion to Other Crops	11

B.2	Has the Regional Community IPM Programme Reached its Targets?	11

B.2.1 Summary of Progress Against Project Objectives	12

B.3	The Conceptual Evolution from Pest Control to Community IPM	16

B.4	Impact of Community IPM for Food Security	17

B.4.1 Immediate Results for Food Security	17

B.4.2 Medium-term Impacts on Food Security	17

B.5	Impact and Validity of the Community IPM Approach for Farmers	17

B.5.1 Cost-effectiveness of IPM for Farmers	17

B.5.2 Capabilities of Farmers to Better Manage their Farms and Livelihood Systems	18

B.5.3 Farm Family Health	18

B.5.4 Emphasis on Women	18

B.5.5 Questions of Equity	19

B.6	Impact and Validity of Community IPM for Development of the Community, Civil Society and 	Governance	19

B.7	Impact of Community IPM for Development of Government Institutional Structures	20

B.7.1 Departments of Agriculture	20

B.7.2 Provincial and Local Governments and Authorities	21

B.8	Impact of Community IPM through National NGOs	21

B.9	Impact on the Policies and Approaches of the International Financing Institutions, and Donors	22

B.10	Impact on Policy	22

B.11	Overall Impact on Pesticide Use, Health and Environment (see also Farmer Health above)	23

B.12	Impacts on Curriculum Development and the Role of Science	23

B.13	Farmers' Field Schools and Community IPM as a Model for Learning and Innovation	24

B.14	Appropriateness and Impact of Regional Programme	26

B.15	Overall Sustainability of the Programme	27

C: RECOMMENDATIONS	28

C.1	Exit Strategy for the Project	28

C.2	Recommendations for the Medium-term Future at International Level	28

C.2.1 Establishing a Foundation	28

C.2.2 Policy Project	29

C.2.3 International Funding Agencies, FAO and National Governments	29

C.2.4 FAO Regional Programmes for Vegetables and Cotton	30

C.3	Recommendations for the Immediate Future for the Inter-Country Programme	30

C.3.1 Foundation and Funding	30

C.3.2 Staffing and Location	30

C.3.3 Gender	30

C.3.4 Improve Curriculum Development Process and Role of Science	30

C.3.5 Documentation	30

C.4	Recommendations for Ongoing Work at National Level	31

C.4.1 Consolidation at the National Level by the Inter-Country Programme	31

C.4.2 National Programme Development	31

C.4.3 Support for Design of National CIPM Strategies by the Inter-Country Programme	31

C.5	Recommendations for Studies by Research, Academic and Development Organizations	32

D: Background to the Programme	33

D.1	The Farmers’ Field Schools and Community IPM	33

D.1.1 The Farmers’ Field School (FFS)	33

D.1.2 What is Community IPM?	34

D.2	The Situation for the Regional Programme at the end of Phase III	34

E: Project Objectives and their Relevance	35

F: Programme Design	37

G: Budgetary Expenditure and Implementation	38

G.1	Budgetary Expenditures	38

G.2	Efficiency and Effectiveness of Implementation	41

H: Outcomes, Effects and Impact	41

H.1	Summary of Results Against Immediate Objectives and Outputs	41

H.1.1 Summary Table 7 Training During Phase IV in Countries Visited by The Mission	41

H.1.2 Summary Table 8: Progress at Mid-Point of Phase IV 1998-2000	42

H.2	Effects and Impact (See Findings)	50

H.3	Cost-effectiveness	50

H.3.1 Cost Effectiveness of the CIPM methodology and FFS: see Findings –	50

H.3.2 Cost-Effectiveness of the Programme Modalities	51

Annex 1: The Conceptual Basis of the CIPM Programme by Niels Röling Mission Leader	53

Annex 2 Terms of Reference Mid-Term Review Phase IV	60

Appendices

Donors:

1. Australia Expenditure and Outcome Summary

2. Norway Expenditure and Outcome Summary

Countries

3. Summary Country Report – Cambodia

4. Summary Country Report – China

5. Summary Country Report – Indonesia

6. Summary Country Report – Nepal

7. Summary Country Report – Sri Lanka

8. Summary Country Report – Thailand

9. Summary Country Report – Vietnam

Executive Summary

- The review mission found this an extremely impressive Programme. By the mid-point of Phase IV most output and immediate objective targets, for the whole five-year duration, had been exceeded. More importantly, development impacts were considerable. The mission found that particularly in Cambodia, China, Indonesia, Nepal and Vietnam, the Programme had:

  - demonstrated an approach to farmer learning and innovation which clearly recognises the farmer as decision maker and lays the basis for continued learning and for wider participation in society;

  - enabled farmers to increase their incomes from rice, while adopting more environmentally friendly and healthy farming practices (i.e. drastically reducing or eliminating the use of pesticides, in particular insecticides);

  - laid a basis for strong national Community IPM programmes, supported by Government and more importantly, mobilising the joint initiative of farmers.

- The Findings Section of this report includes analyses of impacts, which are all positive, in terms of:

  - food security;

  - benefits to farmers (economic, health, gender, equity and capacity to manage livelihood systems and participation in society);

  - pesticide use, health and the environment;

  - a model for farmer learning and innovation.

- Only one area is noted where impacts have been disappointing and this is the uptake and institutionalisation of the CIPM approach and its application to other aspects of rural learning by national governments and international institutions. The validity of the reasons given for this poor uptake by these institutions are reviewed and they are urged to re-examine their concerns. The institutionalisation by rural communities themselves is however, found to be impressive, especially in Indonesia.

- The summary of results against immediate objectives and outputs (page 41) illustrated the strong performance of the Programme. In particular it may be noted that:

  - over 120,000 farmers have been trained in season long Farmer Field Schools (FFS); and some 730 government staff and 5,500 farmers have been trained as trainers. Only in Vietnam and Indonesia, however, is overall coverage of farmers adequate for real demonstration of impact and this is a limitation in persuading policy makers of the Programme’s efficacy;

  - there are valuable examples of trained farmers going on to undertake their own research and innovation and of community initiatives for income, environment and social concerns;

  - women are well represented in CIPM activities and there are valuable examples of women-only activities;

  - valuable new pilot work has been undertaken in pesticides and health and in CIPM in schools.

- The mission concluded that the CIPM model should be replicated as an integrated approach for:

  - farmer learning and innovation which could be initiated in many aspects of systems, not just IPM, and could also be extended to other aspects of rural learning such as nutrition and health;

  - improving the balanced management of agro-ecosystems;

  - an entry-point for community initiative and empowering individuals as members of society.

- Recommendations are made for the future emphasising:

  - an exit strategy for the Inter-country Programme which will consolidate the progress made to-date, in particular laying the basis for:

    - strong independent national programmes supported, where necessary, by donors;

    - a foundation to maintain the benefits of the inter-action and mutual support between countries.

  - longer-term development of a foundation with mixed membership of countries, donors and non-governmental partners (including CIPM farmers) to facilitate and provide for mutual support and to continue to provide leadership and innovation for the development of CIPM, referred to above;

  - funding of a regional FAO project to support national governments in the development and application of improved pesticide policies;

  - areas for study by academic and research institutions on the functioning of the Community IPM model.

# Introduction

- The Mid-term Review of Inter-Country Programme for Community IPM in Asia took place some three years into Phase IV of the Five year Community IPM Programme. As per the Terms of Reference, on the basis of results and experience to-date, the main purposes of the Review were to assist management in deciding:

- staffing, activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

- the desirability of, and options for, further technical and financial assistance which could consolidate current work and expand into emerging areas of opportunity.

- The team consisted of four independent consultants, one representative of the FAO Evaluation Service and one country representative. The mission agreed the scope of its work and then split into three groups for two weeks of country visits. The mission then came back together to finalise its report and to hold in-depth discussions on its findings with the regional team and with the FAO offices in Bangkok and later Rome. The mission was  composed as follows:

Nepal and Vietnam:

- Niels Röling –Team leader and Extra-ordinary Prof. of Agricultural Knowledge Systems, Wageningen University

- René Salazar –NGO specialist in sustainable agricultural development, particularly genetic resources

Cambodia, Indonesia and Thailand

###### Sean Foley – Environmental management and agricultural systems specialist

###### Piao Yongfan – Country Representative from China with extensive experience of addressing the development of the Country IPM Programme – Deputy Director-General, National Agro-Technical Extension and Service Center, Ministry of Agriculture

China and Sri Lanka

- Michel P Pimbert– Consultant – Agro-ecology specialist – International Institute for Environment and Development (IIED);

- John Markie – FAO - Evaluation Service.

- During country visits, talks were held and visits made to the responsible Departments of Government, national programme teams, donors and, most importantly, FFS and CIPM activities.

# FINDINGS

## Introduction

### Development and Coverage of the IPM Programme

- Beginning in 1980, what is now called FAO's Inter-country Programme for Community IPM in Asia has, during the course of its development, covered all the main rice producing developing countries of East, Southern and South East Asia (with the exception of PDR Korea and Myanmar). Throughout its development, the Programme has evolved both in coverage and conceptually.

- The point of entry both historically and in each country in the development process has been the establishment of Farmer Field Schools (FFS) focused on IPM in rice. FFS are now a significant part of the development process in all Programme countries. Summary Table 7 (page 41) provides an estimate of the current coverage achieved through FFS. In Indonesia, Vietnam and parts of Bangladesh the majority of rice producers in the major rice growing areas have now been directly or indirectly reached through IPM FFS. In other Asian countries associated with the Programme, work is at a much earlier stage of development and in terms of coverage the proportion of farmers and of the rice growing areas is low.

### Focus on the Rice Crop and in Intensive Systems

- The most important crop in Asia is rice, and most of the farming systems are rice-based systems. In rice-based systems, CIPM needs to succeed in the agro-ecological pest management of the rice crop before local farmers and policy makers will consider expansion of the approach to other crops. Overall, the largest proportion of pesticides are used in rice and cotton.  In wet rice, pesticides enter directly into the water system and cause especial risks. The Mission therefore agrees that the current major focus of the CIPM Programme on rice is the most appropriate and strategic.

- The Mission also feels that the greater relevance of and demand for CIPM is on intensive systems where pesticides are heavily used, and where production technology is disrupting agro-ecological systems. Furthermore, CIPM is not only a technology but also an educational process of empowerment and human development. It is in intensive systems that farmers’ traditional knowledge systems have been displaced by institutional and even corporate knowledge systems resulting in greater dependency. CIPM potentially re-strengthens the role of farmers as decision-makers, innovators and source of knowledge in agricultural research in general, and in pest management in particular. It helps them become more active and effective partners in development.

### Expansion to Other Crops

- Local farmers and government partners are increasingly demanding the expansion or strengthening of the CIPM Programme to other crops. These demands have increased due to the clear success of CIPM in rice.

- The need for CIPM on other crops is very evident where rice farms are planted to vegetables, grains and legumes after the rice is harvested. The large quantities of pesticides, often applied in vegetables, and the manner of application create severe risks for the health of producers and consumers. CIPM in rice will fail if the same lands are flooded with pesticides during the season following the rice crop.

- Adapting CIPM from one crop, rice, to a number of crops obviously raises wider and more complex challenges emanating from farming systems which are less stable than wet rice systems, and have different biotic and abiotic stresses. Expansion to new crops requires developing and improving the CIPM-FFS and TOT curricula. It also demands additional contributions by researchers and research institutions. While the FAO IPM programmes on vegetables and cotton have developed some of these curricula, the Mission felt this area needed special attention.

## Has the Regional Community IPM Programme Reached its Targets?

- The first task of the mid-term review Mission was to examine the extent to which the objectives of Phase IV, covering 1998 to 2002, have been met during the first three years of the Programme. Especially since, in a number of countries, budgets for the last two years have been limited and funding has sometimes been uncertain, achievements in the first three years of the Programme are important. Careful examination of the objectives formulated in the Project Document, and assessment of their achievement in each of the countries visited, allowed the Mission to draw clear conclusions.

- The mission findings below analyse in some depth the overall impacts of the Programme in terms of the Development Objective: “To assist government agencies, non-governmental organisations and community groups in member countries to establish and strengthen community IPM programmes in rice-based farming systems”.

- Prior to this analysis the mission presents a brief summary of progress on Project Immediate Objectives and Success Criteria and the progress in particular countries. This summary is reflected in greater depth in the body of the report and the country appendices.

### Summary of Progress Against Project Objectives

| Summary Table 1: At the Mid-Point of the Five Year Phase IV Programme |  |
| --- | --- |
| Objective 1: Create self-reliant training capability where it does not yet exist within government agencies and/or non-government organizations. Success criteria: By the end of Phase IV at least 10 member countries will have a self reliant capability to train IPM trainers, embodied in a total of at least 600 additional trainers capable of managing season-long rice IPM TOT courses and Farmer Field Schools | More than 600 additional trainers are already in place. In parts of Bangladesh, China, Indonesia, Philippines and Thailand, IPM training would continue in these countries if all funding were to cease today. Ongoing donor funds would also assure this in Cambodia and Nepal and strengthen it in Vietnam |
| Objective 2: Develop the content and methods of community IPM activities appropriate to different farming systems and social conditions. Success Criteria: By the end of Phase IV, community IPM activities are taking place in at least 600 locations across 7 or more member countries. These activities will be organized and implemented by farmers with a substantial amount of the human and material cost of these activities being met by the local community. | Community IPM activities (i.e. beyond FFS) are already taking place in Cambodia, China, Indonesia, Sri Lanka, Thailand and Vietnam. Far more than 600 additional locations have been covered. Some local funds have been mobilised in all locations and in Vietnam follow-up farmer studies are generally entirely farmer financed. These activities have the greatest depth and variety in Indonesia where local funding is now the norm. |
| Objective 3: Strengthened management capability for Community IPM Programmes within member countries and improved cooperation among member countries in a manner which will sustain this capability. Success Criteria: By the end of Phase IV, a total of at least 60 Field Leaders from 6 or more countries capable of planning and coordinating Community IPM Programmes at the Provincial and National level, and capable of carrying out international training/advisory assignments. In addition, 250 IPM Trainers have the ability required to initiate and support Community IPM activities in their own countries. | Sustainable Community IPM development management capability is now firmly established in Bangladesh, China (Provinces), Indonesia (at local level), Thailand and Vietnam. With some capacity in NGOs in the Philippines and Sri Lanka. The body of Field Leaders capable of planning and coordinating Community IPM activities at the Provincial and National levels now far exceeds 60 in Indonesia alone, with leadership capability having being particularly developed by Phase IV in China and Vietnam. The number of IPM trainers available is in the thousands (see table in the main text). The A Team has been created as a network and for the execution of international assignments. This is based largely on Indonesian trainers and is discussed in detail in the Findings, below. |
| Objective 4: Improved ability of policy-makers and planners in member countries to initiate, support and evaluate community IPM programmes. Success criteria: By the end of Phase IV, at least 100 have been provided with an opportunity to discuss IPM policy and/or programme design issues. | There has been less activity in this area than on other objectives and a consultant has recently been commissioned to carry this work further (3 years of senior policy advisor is budgeted under the Norwegian contribution). Project staff are continuously making contacts at the policy levels of Government and are influential (see findings below). Staff at the level of Chiefs of Plant Protection attend the Programme Advisory Committee at which development issues are discussed. A policy meeting on women in Community IPM was held in China with participation from Laos and Vietnam. Policy work has also dealt with health in Nepal, Sri Lanka and Vietnam and with the introduction of Community IPM into education in Thailand. |
| Objective 5: Broader awareness in member and donor countries about community IPM activities in Asia. Success criteria: By the end of Phase IV, at least 5,000 scientists who are involved in agricultural development and at least 1 million members of the general public, in member and donor countries, have been exposed to information which describes what community IPM is and what the ICP is doing. | Contact with scientists in China and Vietnam for curriculum development and involvement in farmer field studies has been substantial. Elsewhere scientists have had greater difficulty adapting to discovery learning as distinct from making recommendations. The target of 5,000 has been greatly exceeded through a combination of published papers and presentations at international conferences. The Programme website has provided a valuable resource to all engaged in Community IPM and beyond. Progress in reaching the general public has been much greater. Community IPM is publicised in the local press and television. The Programme will also be covered on BBC World TV. In Indonesia a monthly tabloid newspaper (10,000 copies per issue) is being produced by the newly established National IPM Farmer’s Association, which has received support from the Programme. |

| Summary Table 2: Status of the FAO Inter-Country Programme |  |  |  |
| --- | --- | --- | --- |
| Country | End of Phase III December 1997 | Current Situation December 2000 | Comments |
| Bangladesh | 2 | 2 | Technical and raining support via CARE, DANIDA and UNDP projects. |
| Cambodia | 3 | 3 | Large, diverse and dynamic programme now in place. |
| China | 2 | 3 | Ongoing programmes in five provinces. |
| India | 2 | 1 | Lack of government interest in CIPM. |
| Indonesia | 2 | 3 | FAO support for IPM farmer trainers, action research and advocacy. |
| Laos | 2 | 3 | A growing programme with good government support (in collaboration with IPM vegetable programme). |
| Malaysia | 1 | 1 | Government is focused on agri-business. |
| Nepal | 1 | 3 | Rapidly expanding training, already moving towards farmer managed activities. |
| Philippines | 2 | 2 | What was a large programme has now stagnated. |
| Sri Lanka | 2 | 3 | High level of interest in the provinces, but funding is needed to match the potential |
| Thailand | 1 | 3 | Widespread training organised by both Ministries of Agriculture and Education. |
| Vietnam | 3 | 3 | Large scale national IPM programme completed, evolution initiated towards CIPM. |
| Notes: 1 = No active FAO support; 2 = Low level of activities; and 3 = High level of activities supported by FAO. |  |  |  |

- Below, for each country visited, a short description is given of the extent to which Phase IV objectives have been achieved.

  - China: With Netherlands Government funding, intensive development has taken place in two provinces during this phase, with four other provinces also involved. These include most of the major rice growing provinces and among them Sichuan is one of China’s poorest provinces. Although, as yet, a relatively small proportion of farmers has been reached, CIPM is well established with clear benefits to farmers and significant mobilisation of public funds from the provinces and local governments for continuing development. Work in women’s CIPM provides a particularly useful example for other countries. A significant problem is the relatively high cost of training with project funding, but costs are lower with national funds.

  - Cambodia: The Cambodian IPM programme has trained some 20,000 farmers and created a cadre of more than 150 government trainers who have the ability to organise further FFS in 13 provinces. New approaches have been developed and tested for IPM in schools and for handicapped farmers. The FAO team has played an important role in mobilising funds for further expansion (DANIDA, World Bank and IFAD) and continued innovation (Asia Foundation, UNDP and numerous NGOs). Recent work has focused on farmer-to-farmer training, which will continue to be a priority for the coming two years.

  - Indonesia: Since 1989, the Indonesian National IPM programme was a ‘stand alone’ independent programme. With the termination of the World Bank/USAID assisted project, CIPM developed as an essentially new programme, building almost entirely upon the very large farmer-to-farmer IPM movement (25,000 IPM farmer trainers). The IPPHTI (The National IPM Farmers’ Association) was officially established in 1999. Unfortunately, the programme has not become institutionalised in Government at central level but strong support is received in many provinces. FAO CIPM programme staff and Indonesia A Team members have organised and implemented large-scale training in areas of organising farmer-to-farmer training and farmer science. The Indonesia programme continues to be the ‘kitchen’ for the development of CIPM approaches, programmes and methods, serving as a source of ideas, experience and expertise for other programmes in the region. Key regional components of the programme (health, farmer science, farmer-to-farmer education, farmer advocacy and media, A Team development) still find their source in the Indonesian programme. Most importantly, however, the Indonesia CIPM has now become the largest scale farmer-to-farmer education and action programme in existence.

  - Nepal. The country became a member of FAO’s ICP only in 1998 at the start of Phase IV with funding from Norway. There is now a National IPM Programme with five regions and 35 rice-growing districts. The country has some 65 TOT-trained IPM trainers. At the time of the Mission’s visit, with FAO funding 188 FFS run by Department of Plant Protection (DPP) staff and 35 FFS run by farmers had been held. An additional 18 FFS were funded through World Education and the Government of Nepal funded another 63. In total, 6,000 farmers have already been trained with FAO funding (the target for Phase IV was 5,000), of whom 2,000 were women. The Programme is expanding rapidly in Nepal and seems to receive a great deal of attention from Government and donors. The Mission is impressed with the rapid expansion from scratch at the start of Phase IV and has no doubt that the objectives of Phase IV have been more than adequately met in Nepal

  - Sri Lanka. IPM development restarted with this phase. The National IPM Programme does not have major funds from the Regional Programme. Nevertheless, there has been good progress, and it can be expected that some 2% of rice farmers will have been reached through an FFS by the end of Phase IV. The programme enjoys good support from the Mahaweli Authority (a separate ministry) which operates irrigation areas producing 25% of national rice production.  Support is also good in some provinces, but not at present in the Department of Agriculture, which prefers a traditional extension approach. It is important for the programme to demonstrate capacity for expansion during the next two years.

  - Thailand. The programme in Thailand has developed rapidly in the last two years. Currently, (late 2000) five full-season TOTs are running under the Department of Agricultural Extension’s new IPM-dedicated Institution for Biological Control and Farmer Field Schools. This programme has gained Royal patronage and both the Prime Minister and Crown Prince have visited IPM farmer activities. The Thai programme is also notable for the fact that the Ministry of Education is active and highly supportive of IPM. Several TOTs have been organised for Department of Non Formal Education field staff and university graduate students in conjunction with the Thai Education Foundation (TEF). TEF is also the pioneer of the IPM in Schools programme which was presented a National Environmental Education Award in 1999. Thailand has also been a site for regional work in participatory health monitoring. The FAO Regional Programme provides technical and training support plus a half-time resident expert. Importantly, nearly all field activities are being funded by national and local governments.

  - Vietnam. The IPM Country programme in Vietnam is currently the largest one in Asia in terms of budget for Phase IV (provided by Norway). Since its inception in 1992, a cadre of some 1,350 Plant Protection Department (PPD) trainers and some 3,000 farmer-trainers have been trained in TOT. Eighty-three percent of all rice growing villages in Vietnam have had at least one rice FFS. In all, this amounts to more than half a million alumni from nearly 11,000 FAO-funded, 6,000 locally funded and over 3,000 other donor-funded FFS. Under Phase IV, a total of almost exactly 2,000 FFS in rice were carried out by PPD trainers with Norwegian funds, an achievement well above the target set for Phase IV. DANIDA has earmarked US$ 8.5 million for the National IPM programme and other donors are also buying into IPM. The development towards community activity ‘C’IPM has focused on 4 villages in each of 19 Provinces which have worked together in TOT, joined in regular monitoring and quality control, and collaborated on field studies. The Mission believes that the work in Vietnam can be considered a success. It worries that CIPM has not yet become part of the regular Government funding structure.

## The Conceptual Evolution from Pest Control to Community IPM

- The historical evolution from the outrage about pesticides, to the FFS as entry point for mass non-formal education, to consolidation of, and building on, the gains made through follow-up in CIPM, does not sufficiently explain the conceptual progress that CIPM embodies. That evolution is best explained by referring to the Miller/Bawden Quadrants

| Figure 1: CIPM and the Miller/Bawden Quadrants |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Holism |  |  |  |  |  |
| Po s i t i v s m |  | II Management of Ecosystems: Still based on positivism, but has moved to a systems perspective. Ecosystem approaches fall into this quadrant. Ecologists usually look at ‘natural’ systems, in which people are only considered as elements of nature and not as intentional beings whose designs determine the future of ecosystems (i.e. humans as a major force of nature). The focus in Quadrant II is on use of natural controls and agro-ecosystem management. | III Ecological Sustainability Emerges from Human Interaction: Represents a holistic approach coupled to a constructivist epistemology. Thus it provides room for human learning, to futures that emerge from interaction among multiple stakeholders, and to communicative rationality. In this quadrant one can look at cognitive and institutional aspects of land use, the ‘soft side of land’. Community IPM with its focus on farmers as experts, on FFS, and on farmer empowerment typically fits in Quadrant III. |  | Constructivism |
|  |  | I Technology Transfer: Thinking based on reductionism and positivism. In rice IPM, the focus in this quadrant is purely on pesticide reduction, scientific thresholds for decision making, and on transfer of science-based knowledge. | IV Pray: Perhaps this is the quadrant for those who consider spirituality as a key ingredient in ecological rationality. Abraham Maslow, who has analysed spiritual peak experiences, describes them as follows: ‘The complete human person at certain moments is able to perceive the unity of the cosmos, to fuse with it and rest in it, for the moment totally satisfied in his desire for being at one’. Such spirituality is a wellspring of ecological rationality. Paying attention to spirituality is not alien to an Asian IPM Programme. |  |  |
| Reductionism |  |  |  |  |  |

- Experience suggests that those who operate in Quadrants I or II find it impossible to understand Quadrant III, while Quadrant III encompasses the previous two. People whose thinking has not moved beyond II find it hard to understand the CIPM Programme. A fair judgement requires that we look at it in the context of Quadrant III. The IPM Programme has of necessity evolved to Quadrant III, while also operating in II and I. The initial (entomological) concern with the integrated management of ‘bugs’ had to expand to (non-formal education) concern for human behaviour and empowerment. Understanding sustainable development as an emergent property of farmer interaction and empowerment has swept the Programme along to other issues, enlarged the problem definition and allowed it to embrace other crops and dimensions of sustainable livelihoods as defined by farmers themselves.

## Impact of Community IPM for Food Security

### Immediate Results for Food Security

- From the very start of the Regional Programme for IPM in Asia, some 20 years ago, strategic considerations of national food security have been a key factor in the acceptance of the Programme by national governments. Severe food shortages can be a source of political instability. It was demonstrated and gradually accepted that pesticides by destroying the natural balance can lead to epidemic outbreaks. Nowhere was this more clearly demonstrated than for the Brown Plant Hopper (BPH) in rice. In Indonesia, the destruction of thousands of hectares of paddy rice as a result of pesticide-induced outbreaks of the Brown Plant Hopper contributed to food shortages.

- CIPM is not just about insects, rats and other pests. It is about growing a healthy crop. As discussed below, all the indications are that improvement in the totality of crop husbandry, including better pest management results in higher production. Thus more food is available both at the local and national levels.

- At the household level, IPM is directly linked to food security. Farm families are the primary consumers of their own production and epidemic outbreaks reduce their food supply. Instability in production negatively affects incomes, even if they are not marginal farmers. All the indications are that pregnant women and young children are the first to suffer damaging under-nutrition. With reduced costs for pesticides and increased output, an initial income benefit to farmers has been demonstrated. This increases farm households' capacity for investment in the farm business and education to further develop their livelihoods and also their capacity to purchase other essential elements of the food basket. Rural income growth in general contributes to employment and increase in purchasing power.

### Medium-term Impacts on Food Security

- A major ingredient of food security at the household and regional level is yield stability. Optimising a target variable, such as yield, and suppressing all other variables (e.g. through using biocides) leads to less resilient ecosystems subject to disruption and instability. Ecologists have coined the term ‘adaptive management’ for another way of dealing with ecosystems for human purposes. IPM is a form of adaptive management, which relies on observation of the crop, anticipation on the basis of what has been observed, and on using natural controls. The Mission is convinced that CIPM will contribute in the medium-term to improvements in the management of the total agro-ecosystem. The Mission was pleased to see the attention paid in IPM to experimentation and awareness raising with respect to expanding the genetic resource base thus reducing instability.

- A final issue in food security is information to decision makers when problems are emerging. Senior political figures in all countries are protected from bad news. Nowhere is this truer than when the democratic base is weak and isolated. Farmers involved in CIPM become more articulate and active at the community level. This can contribute to responsive and effective governance in food security.

## Impact and Validity of the Community IPM Approach for Farmers

### Cost-effectiveness of IPM for Farmers

- IPM in rice decreases production costs, due to reduced pesticide inputs, and also brings about increases in yields and yield stability due to better management of the rice agro-ecosystem.

- Extensive field evidence in Indonesia, Philippines, Vietnam and to a lesser extent China, Sri Lanka and Thailand, using both longitudinal (before and after) and comparative (with and without) studies, shows that following FFS, farmers reduce their use of insecticides substantially. In many areas, yields have also increased due to improved overall levels of pest management, fertiliser management, changes in plant density and other measures. Initial incremental income margins were found as high as 40% in low productivity areas of Sri Lanka to 10-25% in China and 30% in Thailand. Very extensive studies in Vietnam confirmed savings on pesticides of US$8-20 per hectare. Evidence is weak on the extent to which the improvements in farm practices resulting from FFS are maintained, but what systematic evidence there is from Indonesia and Vietnam is generally positive, although it would appear that there can be major benefits from both reinforcing existing gains and stimulating further progress through follow-up as implemented in CIPM.

- There is also a growing market in many of the countries for pesticide-free food, including rice, which commands a price premium. In most countries, work in exploiting this income advantage is at an early stage but a potential is there. Unleashing this potential requires the involvement of cooperatives and businesses and not sole reliance on government marketing channels.

### Capabilities of Farmers to Better Manage their Farms and Livelihood Systems

- A major strength of the FFS approach is that it enhances farmers’ capabilities to analyse their agro-ecosystem and make decisions based on their observation and analysis. An important question is the extent to which the Programme enhances farmers’ overall capability to analyse their farming systems and crops, to acquire information for decision making and in general to improve management.

- There is strong anecdotal evidence that farmers trained in FFS will apply the same skills for IPM in other crops. They also gain confidence and contacts within the agricultural services. Farmers become more assertive demanders of advice and information. It is doubtful whether, without additional follow-up, they are able to make the crossover into analysis of other aspects of their livelihood system.

- The Mission is convinced that CIPM does provide a strong basis to move forward through follow-up activities with participatory planning, group activities and improved decision making in other elements of the farming system, including farmer field studies. The Mission is aware that there is a trade-off between expanding FFS coverage over the remaining two years of the Programme, and consolidating gains made by follow-up activities in areas already covered.

### Farm Family Health

- The reduced use of toxic pesticides has its first positive effect on the health of the farm family.

- There was strong anecdotal evidence in all countries visited, supported by participatory impact studies in Indonesia, Thailand, Cambodia and Vietnam, of frequent instances of short-term ill effects, and some instances of more serious poisoning among farmers as a result of pesticide use. IPM has the effect of reducing this. The elimination of pesticides stored in the home can also reduce risks to children and adult deaths.

### Emphasis on Women

- Women frequently have the primary responsibility for agriculture, with husbands living at home but seeking off-farm work, or migrating - the so-called ‘feminisation of agriculture’. This is especially the case if the farm is small. The pace of the feminisation of agriculture is increasing.

- Women appear to be genuinely welcomed in the FFS in most countries. There were inadequate data in some countries, but excellent records of women’s participation in others, such as Cambodia, China, Vietnam and Nepal.  The mission had the impression that women made up about a third of the membership across the countries visited and were well represented among farmer trainers and FFS leadership. In China, FFS and training of farmers as trainers (FTOT) have been specifically designed for women, with evident benefits in fitting the group’s activities to women’s timetables and education level, and avoiding male dominance. In the view of the mission, a greater emphasis on women-only FFS could have advantages in other Asian countries and in the other provinces of China.

### Questions of Equity

- The wealthy usually have little interest in IPM - they are commercial producers or absentee landlords. On the other hand, FFS are not representative of the poorest of the poor; the poorest rural dwellers have little land. The poorest farmers often have no access to irrigation and thus do not grow paddy rice. In the region, the poorest are found in arid areas and also often in remote uplands, farming hillsides destructively. Poor farmers or part-time farmers who grow some subsistence rice are less likely to be heavy users of pesticides. There is, thus, some question whether they should be a primary target audience. However, the mission does conclude that the FFS and the holistic community IPM approach can have application in sustainable management of the natural resource base and the livelihood system in marginal areas. International agencies, national governments and NGOs are urged to pay closer attention to the potential of the CIPM for dryland and upland farming systems.

- When farmers intensify their production practices, in line with their learning in the FFS, this can lead to a greater demand for labour, which could benefit the poorest members of communities. Where IPM farmers go on to develop economic activities on their farms and in the village, this may also contribute to wealth and employment generation at the local level.

- The poorest rice farmers are often also the least educated and articulate. It is clear that unless they possess unusual qualities the poorest are unlikely to occupy leadership positions in the FFS, but they are not excluded and do benefit in raising their own capabilities as farmers and contributors to the community. In short, IPM is likely to decrease rather than increase their marginalisation.

## Impact and Validity of Community IPM for Development of the
Community, Civil Society and Governance

- There has been both under- and over-statement of the transforming characteristics of FFS for communities.

- The Mission found that FFS-trained farmers possessed greater confidence to speak in public and were more articulate. The farmers who had gone on to be trained as trainers themselves had enhanced organisational skills. Many of these farmers had already been village leaders or have come to occupy leadership positions. Thus, there were definite, if intangible benefits at the community level. There was evidence that groups of FFS alumni, especially those which included farmer-trainers, continued various joint activities, particularly in helping each other on IPM and helping other farmers. In Sri Lanka there was reportedly some reinforcing of community consciousness, mutual assistance and group action.

- As noted above, follow-up support to FFS to engage in participatory planning and development of joint activities has only been a strong feature of the Programme in Phase IV.  In this Phase significant action has been restricted to Indonesia. Elsewhere impact is for the moment more limited and outcomes of this follow-up process are less predictable.

  - Indonesia has developed a structure of IPM associations confederated at sub-district, district, provincial and national levels. The national level organization, which is very recent, produces a news tabloid and plans conferences, exchanges, etc. The associations have been an important focus for the continued expansion of FFS using local resources (see below). IPM associations and their federations have been active in defending farmers’ rights. Particular areas for group action have been land titling, irrigation management, marketing and product prices. The organisation at the apex and middle levels, is representative of farmers, rather than being composed of farmers with leaders tending to be the former trainers. This organisation has emerged at a time of democratic change when the former state-promoted organisations were failing to satisfy the need for a farmers’ political voice.

  - In Vietnam, farmer maintained and supported groups have become important without substantial support from the Programme. They are particularly active in field studies on such things as rat control, fertilizer and agronomic practices. The Coordinator of the National IPM Programme is deeply convinced of the need for CIPM follow-up activities to consolidate the gains from FFS. IPM came at a time of change from top-down command interventions to a more open market-driven process - the FFS filled a vacuum. Erstwhile ‘mass organisations’ such as the Farmers’ Union state that they also wish to function as conduits for farmer influence and ability to demand services.

  - In Sri Lanka and China, there has been a tendency to form associations from the top down and it is not clear the extent to which they exist, except on paper. On the other hand, FFS alumni in Sri Lanka are revitalising the activities of existing community organizations, such as those responsible for water management. In China, in a government driven framework, and in Sri Lanka, spontaneously, groups are beginning to undertake economic activities.

  - In Cambodia in a separate pilot development the FFS approach (Farmer Life Schools) was applied to analyse the livelihood and social systems in villages in much the same way as an agro-ecosystem.

- The mission concluded that further development based on FFS can very usefully contribute to wider community development goals in the context of income generation, livelihood systems, environmental regeneration, primary health care and governance. However, there are dangers in applying fixed formulae, especially during the early stages of this open-ended process. The strength of IPM has to-date been on the farm and the greatest returns may often be gained by continuing to build on this advantage for the sustainable management of natural resources and development of farm businesses.

## Impact of Community IPM for Development of Government Institutional Structures

(for relationship to research institutions see below)

### Departments of Agriculture

- Given the differences between FFS and regular extension, the way in which this will evolve need to be carefully monitored. The models by which regular extension work can build on CIPM needs to be carefully developed and analysed. The Mission hopes that DANIDA, the AREP in Nepal, and others which are planning to invest in the use of FFS models in regular extension are willing to pay systematic attention to this issue.

- In a number of countries, e.g. Vietnam, Thailand and Nepal, the FFS is considered as a potential model for redesigning the work of the regular extension services and a great deal of donor money is potentially available for the purpose.

- Few other examples were found of Departments outside Plant Protection making use of the FFS or emulating the approach in their own work in agriculture or such areas as health. The significant exception was Thailand where the approach is now starting to be applied for project learning in schools and in adult education. In the majority of cases, the development of community IPM has been through Plant Protection Departments. This was essential for technical content and formed a natural point of entry. However, it has significantly reduced the potential for FFS to be taken up as the national approach for learning and innovation in agriculture and institutionalised within Government.

- Plant protection unit (PPD) staff are normally made available for work on IPM programmes, although there are limits on availability due to the continuance of other duties and special allowances are often paid. In this respect the implementation of IPM programmes suffers similar difficulties to most other externally assisted development. In Indonesia the bureaucratic rivalries engendered by a project framework within the Plant Protection Department itself have meant that staff terms of reference have never been adjusted to reflect a responsibility for FFS and that, with the cessation of World Bank project funding in 1998, central government application of the FFS has come to an end. In Vietnam, where an approach to extension following the change from a command economy was lacking, in Nepal and in some provinces of China, there appears to have been more fundamental mainstreaming of the IPM task within the Plant Protection Departments, although as with many other development programmes there is a reliance on external funds to actually do the job.

  - In Nepal, Vietnam, Indonesia, Sri Lanka and Thailand the extent to which CIPM has become institutionalised within the government framework and budgetary process has been very limited.

  - The issue of institutionalisation should not be divorced from understanding of the nature of nation states and governments in the region. CIPM will gain support from and reinforce progressive and democratic forces within government. However, we must not forget that given top-down, unjust and undemocratic forces within governments, and given the continued efforts of pesticide corporations to exploit opportunities provided by corruption, a parallel focus on a local, farmer-driven IPM ‘movement’ seems to be an essential ingredient of effective CIPM. For example, the institutionalisation of CIPM in current Myanmar is undesirable.

  - The lesson from the CIPM Programme seems to be that sustainability of CIPM is not only a question of institutionalisation within formal government structures, but especially (also) of building a vibrant farmer-driven IPM movement.

### Provincial and Local Governments and Authorities

- Both in Indonesia and elsewhere, responsibilities for agriculture are being increasingly decentralised and it is at this level that Community IPM and FFS have found champions able to ensure continuity. It is also at this level that boundaries between departments within agriculture start to break down. In many other countries of the region it is unfortunately the case that virtually no budgets exist within government departments to cover anything except salaries and so development action relies on external funds. Numerous examples were recorded by the Mission of local authorities contributing to the budgets of FFS development (in Indonesia more than 500 FFS a year are supported through local funding). A degree of sustainability at this level seemed to have been achieved in at least 9 of the 12 major rice-growing provinces in Indonesia and also in some provinces of China and Vietnam.

## Impact of Community IPM through National NGOs

- Examples of national NGO involvement in CIPM were found in all countries and in Bangladesh, Indonesia, Nepal, Philippines, Sri Lanka and Vietnam they have executed FFS, including expansion to other crops. National NGOs provide important opportunities for mainstreaming the approach and for sustainability, but there have also been concerns about quality and the scale of independent activity is naturally limited for these organizations. One specific issue is that NGO trainers do not always have an agricultural background - this can be particularly problematic when it comes to new and complex crops.

## Impact on the Policies and Approaches of the International
Financing Institutions, and Donors

- The World Bank has been a major funder of IPM development in Indonesia for some years. It continues to be particularly important in influencing extension policy in the Asia Region.

- Major World Bank supported projects to improve agricultural research and extension are underway in Cambodia and Nepal. In the former, FFS have been applied in the extension project. In Nepal, such an event is highly likely. The Bank is also a sponsor of the Global IPM Facility.

However, at the moment the Bank does not seem to be convinced of the cost-effectiveness of FFS for more general application. Similarly, FAO itself has been as prominent in promoting block demonstrations for agricultural extension. Many bilaterals, including AUSAID, DANIDA, GTZ, NORAD, the Netherlands and USAID which have supported significant efforts in FFS,  have not changed their commitment to standard extension approaches.

## Impact on Policy

- A Policy Advisor has just been appointed. The Programme's impact on policy has been largely indirect and there are some difficulties of attribution. However, it is clear that the Programme has contributed to a climate in which the place of pesticides, especially insecticides is increasingly questioned.

- In particular, throughout its life the Programme has contributed to the growing realisation that insecticides have led to, rather than prevented, epidemic outbreaks of BPH in rice. There has been continued counselling by the Programme when pest build-ups have occurred and government area wide spraying is almost a thing of the past. The Programme's voice has also contributed both at the central level and in field education to the limitations on sales of the more toxic pesticides in many of the countries of the region. Increased farmer awareness and demands by the IPM Farmers Association in Indonesia may have contributed to the re-imposition of the ban on the more toxic pesticides.

- Plant Protection Departments (PPD) are particularly vulnerable to the influence of the pesticide industry both through corruption and the reliance of some PPD staff on pesticide sales for income. Nevertheless, the Programme has very definitely moved many Plant Protection Departments from the role of pesticide proponents to IPM proponents.

- Whilst well aware of the need to do so, the Programme has had relatively little influence on:

  - the policy and funding priorities of public research in agricultural science and technology development (e.g. encouraging reallocation of resources to support agro-ecological research and  development of the knowledge base for CIPM in crops other than rice);

  - the policies and interventions of multilateral and bilateral donor policies (e.g. harmonisation of donor interventions in different sectors to support pesticide reductions at policy, project and technical levels).

- The Mission notes that when Community IPM has led to the formation of stronger farmer organisations and federations (as in Indonesia) more bottom up, participatory policy processes have emerged. Farmers are directly voicing their own policy priorities in national and local parliaments and government agencies on local problems and local rights, from land to credit to water and corporate farming. In the view of the Mission more now needs to be done at the policy level - see recommendations.

## Overall Impact on Pesticide Use, Health and Environment
(see also Farmer Health above)

- Rice covers the largest area in the region and receives most pesticides in total. Rice plants grow in water and pesticides enter the water system, affecting aquatic life and the quality of water for other uses. Other major threats to the environment and human health stem from the intensive use of pesticides on high-value crops and especially vegetables and cotton. Community IPM significantly contributes to reducing pesticide use with its environmental and health implications:

  - FFS-trained farmers rely more on cultural practices and the management of natural enemies to control rice pests;

  - in Vietnam, the use of imported insecticides has decreased from 2.7 kg/ha in 1991 to 2.6 kg/ha in 1998, a year that showed relatively high imports in an otherwise declining trend. In the same period, yields have increased from 3.1 tonnes/ha to 3.9 tonnes/ha, i.e. by 26%;

  - there is evidence that the biological diversity of birds, fish, amphibians and arthropods is greater in the rice fields of farmers who have adopted Community IPM;

  - whilst no nation-wide epidemiological studies have been carried out, trained farmers report fewer instances of acute or chronic pesticide poisoning;

  - on the whole, consumers are increasingly concerned about the health risks posed by pesticide residues in food, demanding safer food in the market place or through campaigns that highlight the values of Community IPM;

  - the Mission was unable to get comprehensive data on pesticide imports and sales before and after the initiation of Community IPM programmes. However, there is anecdotal evidence from China, Indonesia and Sri Lanka that shops selling pesticides closed down in areas where Community IPM had spread.

- However, the Mission notes that Community IPM alone cannot adequately address the need to reduce pesticide use and its associated environmental and health hazards. These issues need to be tackled at many levels, including international and national policy, regulatory capability and increasing consumer consciousness.

## Impacts on Curriculum Development and the Role of Science

- Scientists could contribute more to IPM curriculum development. Most scientists have proved unable to move to Quadrant III in Figure 1, i.e. researchers tend to continue to focus on components of the system, such as host plant resistance, biological controls, and pesticide management. In IPM countries, they have tried, and still try, to get FAO support to carry out on-station ‘IPM research’ (i.e. scientific research into biological controls), the results of which they expect to be transferred to farmers by FFS. It is one thing to carry out purely scientific research to identify pests, establish their life cycles, the pheromones that attract them, their population dynamics, natural enemies, etc. for which on-station research is very important. However, it is quite another thing, to develop an IPM curriculum that works at the farm and rural community level. Such field research involves farmer practices, lifestyles, knowledge of local conditions, negotiation of collective action, and the development of appropriate technologies, i.e. participatory technology development.

- IPM curriculum development is also a moment where scientific knowledge becomes relevant and validated in different contexts. Curriculum development is one of the important science interfaces of IPM. In fact, the curriculum is the new and exciting vehicle developed by the IPM Programme for the utilisation and development of scientific knowledge that is totally different from technology transfer. As CIPM broadens to new crops and other aspects of rice production, the demand for farmer-led curriculum development becomes more important. The Mission believes that an effective CIPM curriculum development process will prevent the tendency to revert to a ‘technology transfer’ mode of farmer training.

- The mission is aware, based on discussions in the field and with the ICP team, that curriculum development is already a highly participative process usually requiring many iterations before it is complete. It is also an on-going process and a process specific to each locality and agro-ecosystem. However, it appears that knowledge of this process remains tacit among CIPM practitioners. Hence, there is a clear need to systematise the accumulated learning and rich experience on participatory curriculum development, and disseminate this information widely both within and beyond the family of CIPM practitioners.

- The Mission observes that in countries such as Vietnam there is a dynamic process of curriculum development involving farmers, researchers and trainers. However, the Mission notes there is a need for clearer guidelines on curriculum development that will ensure that it is farmer-led. Further, curricula must reinforce the discovery learning and educational process of CIPM, but also translate contributions from mainstream researchers into curricula.

- Where IPM FFS have expanded due to strong farmer-led demand to more complex agro-ecosystems, such as vegetables and fruit trees, the scientific basis and the effective adaptation of the educational process may not yet be adequately developed. A pragmatic approach is advised, taking into consideration the fact that curricula are at an early stage of development. Problems and research agendas should continually be identified by farmers taking into consideration broader scale problem identification, scientific information and studies from researchers.

## Farmers' Field Schools and Community IPM
as a Model for Learning and Innovation

- As already noted, the Mission found that one of the most important reasons why FFS had not been mainstreamed in extension was the bureaucratic rivalries and mistrust deriving from its basis in the Plant Protection rather than Extension Departments. This probably applies as much in international as national development agencies. The facilitation of learning as promoted by CIPM implies a sea change in the way extension staff relate to farmers, becoming their friends and expert colleagues, rather than instructors, and some extension agents perceive this as a lack of status.

- In discussing the issues involved, the Mission also notes that the mindless transfer of models rather than principles between development situations has been one of the more negative features of development. It is the application of the principles of FFS that is the key, not the details of practice. Community IPM represents a comprehensive learning approach at the farmer and community levels that is not restricted to IPM. In extending the approach beyond IPM it is essential to keep to the fore the principles which have made it strong:

  - starting from a base in an agro-ecological system and building analytical and interactive decision making skills in that system before moving on to other aspects of the farm agro-ecological or agro-economic system;

  - mutual support within the group;

  - not cutting corners through:

- reducing the duration of training for trainers or farmers;

- non-application of pedagogic and field-based methods;

- presenting ready-made solutions, rather than reinforcing analytical and decision making capability.

- The main substantive argument used for the non-applicability of the FFS model on a wide scale is its incremental costs for government recurrent budgets. It is argued that governments must provide extension as a public good to all farmers and more cost-effective and quicker methods of reaching farmers are essential. This is first and foremost a misstatement of the question addressing just one facet of community IPM. It can contribute to life-long learning, livelihoods, community empowerment and innovation. The expenditures for CIPM should not just be seen in terms of extension, health, community development or rural reconstruction but in terms of all of them. CIPM includes education which lays the foundation for farmers to actively use extension.

- A further problem for this discussion is that there is very inadequate evidence of the effectiveness of varying extension approaches in a post-green revolution era when the farmer needs to understand the agro-ecological and business environment, not just apply the technology. The recent discussion on the issue has been polemical with both sides of the argument twisting data.

- In the view of the Mission, there are no examples of alternative systems that have been as widely tried and proved as efficacious in Asia, as the IPM Farmer Field School. The question is whether governments, which have decided that extension is a public good they intend to provide, and which have employed large numbers of staff with this intent, can afford to ignore the potential provided by the FFS approach, bearing in mind that, once educated in an FFS, farmers become more effective and discerning users of information provided in lower cost ways than the initial FFS training. With some continuing support they will go on to analyse new information and test it against their own experience on their own farms and in FFS groups.

- The indications are that FFS can be employed as a support to strengthen farmers' capacity to utilise information and other inputs provided through regular extension activities (e.g. block demonstrations).

- This having been said the experience is that, with the significant exceptions of Vietnam and Indonesia, rapid scaling-up of CIPM has not occurred and in many countries there appears to be a genuine problem of cost, particularly incremental staff cost. The Mission believes that economies can, and are being made. In fact, the Mission is impressed with the attention paid to this issue in the different countries. Economies might include:

  - use of Farmer-trainers; attention to geographical positioning and systematic pyramid training (Government Trainer to Farmer Trainer to Farmer to Farmer);

  - engaging NGOs in scaling up FFS coverage;

  - cooperation with local policy makers and businesses for such things as production and marketing of IPM and organic products;

  - rapid adjustment downwards of FFS allowances as soon as the programme gains credibility;

  - forcing down padded costs of FFS and transparency in expenditures; and

  - spreading the load between Government Departments, for example initiating FFS on another natural resource management topic (e.g. plant nutrition) and then later introducing IPM in a mature Field School.

- The Mission also believes that there could be potential to utilise the mass media to support FFS, especially farmer-to-farmer FFS provided that there is no loss of the practical Field School either in the mass media presentation or on the ground for each farmer group.

## Appropriateness and Impact of Regional Programme

- The Regional Programme structure has provided not only the dynamic leadership and vision for the Programme as a whole but also the funding mechanism for national programmes.

- There appears, however, to be a perception by some donors and some countries that the regional mechanism imposes excessive overheads on the Programme and is inefficient due to its dependence upon FAO. The Mission believes that this is partially a misconception, but that the time has now come to place the regional functions in a different framework (see below).

- During the remainder of Phase IV, now that FAO has its new computerised financial system (Oracle) in place, there is opportunity to improve reporting. There can also be greater transparency and clearer forward planning in the allocation of resources to countries and in contracting staff, while retaining the essential flexibility required for the Programme to put in place its exit strategy (see recommendations).

- The Regional Programme is active in resource mobilisation, concept and curriculum development, science-linkage, quality maintenance, informal networking, awareness-raising on pesticide issues and the provision of policy and programme development advice to governments and national programmes.

- The Mission believes that it is essential for IPM activities in Asia to maintain these and other central support and initiating functions.

- At the regional level, the Programme has established a number of regional components: health, education, gender, ecology, the A Team and information activities. These thematic components are not present to the same extent in all countries:

  - Health. The Mission was impressed by work on participatory health monitoring in Cambodia, Indonesia, Thailand and most recently Sri Lanka. This is a new activity that features a methodology for discovery learning by pesticide users of the immediate consequences of spraying on their own health. The activity energises local people, and provides an avenue for awareness raising and empowerment.

  - Education. Work in schools has been very impressive and seems potentially to provide a strong additional foundation for the institutionalisation of IPM. It has progressed furthest in Indonesia and Thailand, but plans are underway to establish similar activities in other countries.

  - Gender. The Mission has been impressed with the extent to which gender has become an indelible part of the Programme in all countries visited (see section 3.4). At the country level, considerable efforts have been made to promote participation of women in IPM activities, both qualitatively and quantitatively. The Women’s Union was involved in China and Vietnam, and women’s literacy groups in Nepal. A conference on gender was also held in China, including participants from Cambodia and Laos. At the regional level, however, the gender component has been neglected by comparison to components such as health and ecology. It is hoped that serious attention will be given to the work that was planned under this component as part of the addendum funded by Norway.

  - Ecology. The Mission has not had an opportunity to examine this component. It has read and found exciting the curriculum ‘Living Soils’ developed by Programme staff. Soils provide a special challenge for discovery learning, and the curriculum developed has paid much attention to overcoming this problem. In some countries, plans were afoot to develop ecology components, involving the monitoring of the environment. Given the impact of such approaches elsewhere (e.g. ‘frog watch’ in Australia), the Mission believes that this component could play an important strengthening role in the total approach.

  - The A Team (Asia Team). This is a group of national trainers who are a regional resource. All of these senior trainers played important roles during the development of the IPM programmes in their respective countries, as trainers, networkers, developers of curricula, participants in strategizing, and in leadership roles.  At the regional level, however, the Asian Trainers Team (A Team) has not lived up to all expectations. Despite dozens of international assignments being carried out there is limited communication between members of the team and they have yet to establish effective mechanism(s) for planning their own activities, rather than just responding to requests. Further, the advice and support of the A Team may not always be fully appreciated by programme managers who sometimes have difficulty in accepting strategic advice from ‘outsiders’. If these problems can be solved, the A Team can play a key role in the further development of CIPM in the context of the proposed Foundation and independently.

  - Information Service. The Regional Programme issues a newsletter and maintains an informative website. The Mission found that in countries visited, those consulted were not making great use of the Website and most did not have easy Internet access. Language remains a problem in many of the countries. However, the website is serving a purpose beyond the Programme itself.

- Above all, the Regional Programme has provided the leadership, vision and activism in the continuing development and application of the Community IPM concept. This is something humanity cannot afford to lose. As the Mission was confronted with the need to consider an ‘exit strategy’ for the Regional Inter-Country Programme, it has carefully examined the need for a continuing presence of some central unit in the region with the kinds of functions described above. It is of the strong opinion that the continuation of the provision of such functions is highly desirable and that ways should be found to maintain them on a different basis. One of the most important recommendations of this report will deal with this issue.

## Overall Sustainability of the Programme

- As will be evident from the above, sustainability at the local level and through the farmer and community developments discussed above is thus the strongest feature of the Programme in the absence of further donor inputs. In Indonesia sustainability is assured at the local level - farmers everywhere will continue to a greater or lesser extent to apply the skills they have acquired in the Programme, and many local governments will allocate funds for CIPM work. Some NGOs have taken up the approach and will continue to apply it in their work.

- Institutionalisation within national government services remains very weak. In Vietnam DANIDA is committed to rapid expansion and deepening of the national programme and in Cambodia, and probably Nepal, World Bank resources will be directed towards this. However, even here continuing technical support and follow-up from the Regional Programme are necessary for success.

- In short, continuing benefits are assured but the potential benefits to be realised from capitalising on the investment to date are very considerable.

# RECOMMENDATIONS

## Exit Strategy for the Project

- Community-IPM has come of age in Asia and it is now time to replace the Inter-country Programme, gradually moving the leadership and vision to Asia and to Asians.

- Self-sustaining national programmes have so far only been established in Indonesia and the majority of rice growing communities have been touched only in Indonesia and Vietnam. Development in most countries of the region has reached the point where strong national programmes are now needed which can benefit from a networked regional resource but which must be funded and developed independently. The development of such strong national programmes will continue to require regional support for networking, quality maintenance, science linkage, etc. At the regional level the Inter-country Programme and the A-Team provide a basis for further development but sustainability has yet to be achieved.

- The exist strategy for the Programme thus emphasises (see recommendations below):

  - consolidation at the national level with a strategy developed in each country for the remainder of  Phase IV. This strategy will generally avoid major new initiatives for the coming two years and include vigorous efforts to ensure institutionalisation of the Programme and the mobilisation of additional resources both nationally and from the international community for continued Programme expansion;

  - new modalities for provision of the essential inter-country leadership, services and advocacy.

## Recommendations for the Medium-term Future at International Level

### Establishing a Foundation

- The time has come for stakeholders in the Regional ICP to assume responsibility for the future direction of development and a status independent of FAO which will allow advocacy, resource mobilisation, further development of the A team and other tasks to be pursued more effectively than is possible in the context of an inter-governmental organisation. The Regional Programme should thus, immediately move to establish an Asian foundation for Community IPM. The Foundation would be established, and could gradually assume, the regional responsibilities of the Asia CIPM Programme during the remainder of Phase IV and beyond.

- The first urgent step is a strategic assessment and development of a design. The legal framework for the foundation would be important and it is probable that only certain countries of the region offer suitable options. It could be advantageous to involve potential funders early on in developing the structure and mandate of the Foundation. In the view of the Mission a flexible membership structure should be established, excluding only stakeholders, such as pesticide companies, whose involvement would be disruptive rather than constructive to the work of the Foundation.

- The Foundation could have as its mission the spread and strengthening of community IPM throughout the Asia Region and could have a flexible mandate, including:

  - providing a dynamic vision for CIPM in Asia;

  - technical support to the development of national and sub-national CIPM by governments and NGOs, including curriculum development (process, methods and science), methods for quality control and impact evaluation, regional training, and networking;

  - drawing on and strengthening the A-team as a regional resource and integral component of the development strategy for the Foundation (country members of the A-team, could take turns in organising a regular national IPM workshop. At each national workshop, representatives from other A-teams could participate and give prominence to regional developments, maintain the regional network, etc.);

  - providing a link to the international community;

  - assistance to national programmes in resource mobilisation;

  - raising public awareness and acting as an information resource for the region on community IPM, including application of the principles in other programmes such as health and education;

  - catalysation and participation in comparative research and case studies on community IPM, farmer and system orientated agro-ecological research and on the workings of the pesticide business and the impacts of pesticides;

  - policy development and advice for CIPM, pesticides and agro-ecology;

  - intelligence gathering particularly on pesticides and their abuse;

  - advocacy on pesticides, raising awareness, and possibly including, support to farmers in developing legal actions.

### Policy Project

- The risks of pesticides to food security have been amply demonstrated. There is now growing consumer demand to reduce the pesticide contamination of food in Asia and mounting concern both among the public and national governments to safeguard the environment, protect human health and comply with international food standards in trade. Much of the normative work for the international normative and legislative framework with respect to both pesticides and bio-safety takes place through, or in association with FAO. A separate regional project for policy in pesticides and the related enabling framework for IPM should be developed by FAO Headquarters. This could work closely with the proposed Foundation and be closely integrated with FAO Regular Programme work and the work of the Global IPM Facility. It would work strategically, including on key issues, such as green taxes and incentive structures, for human health and eco-friendly development to:

  - assist countries in assessing:

    - the extent of pesticide hazard (including economic costs, benefits and risks) in:

      - food (food security, consumer safety, intra- and inter-regional trade);

      - health and safety (pesticide production, marketing, storage and use);

      - damage to the production eco-system (agriculture, fisheries);

      - damage to the wider environment;

    - tax, subsidy and trade policies with respect to pesticide import, manufacture and sale, including the potential for green taxes on pesticides;

    - policies for agricultural intensification;

    - the legislative and institutional capacity for consumer, user and public protection and legal recourse in the event of damage to health, assets and the environment;

    - existing regulatory frameworks and capacity for updating and enforcement (institutional capacity);

  - publicise issues and bring them to the attention of higher level policy makers;

  - facilitate information and dialogue on international agreements and norms;

  - develop policy data bases and information which at the conclusion of the Programme would be absorbed into FAO’s Regular Programme activities, including information on pesticide manufacture and trade; and

  - catalyse policy research.

### International Funding Agencies, FAO and National Governments

- National governments, international financing institutions, bilateral cooperation agencies, international NGOs and FAO are recommended to vigorously pursue the development of national CIPM programmes (see below).

- National governments, international financing institutions, bilateral cooperation agencies, international NGOs and UN Agencies are encouraged to replace their standard models in agricultural extension, outreach and adult education, with the CIPM approach for adult learning, innovation in agriculture, natural resource management, health, nutrition, rural business and livelihood development.

- FAO needs to clarify on the basis of its experience, its policy position on the farmer learning research continuum and approach to extension. In this context the Farmers’ Field School should be embraced as the entry-point for farmer learning in FAO programmes.

### FAO Regional Programmes for Vegetables and Cotton

- Continued support is required from FAO regional programmes in vegetables and cotton and for the further development of the CIPM approach into new crops and new aspects of the agro-ecosystem, and livelihoods where the CIPM approach has an important role to play.

## Recommendations for the Immediate Future for the Inter-Country Programme

### Foundation and Funding

- In addition to ensuring achievement of Programme outputs and immediate objectives for Phase IV, an important priority for the Programme’s exit strategy to which staff and resources must be committed during the next two years, is to:

  - make preparations for and establish the Foundation;

  - consolidate and mobilise resources for continuing national programmes.

### Staffing and Location

- In view of the additional pressures that this will place on the Programme it is essential to preserve stability in key staff and location of the Regional Programme office for the remainder of Phase IV. Disruption at this point could jeopardise previous investments and achievements.

### Gender

- Pay serious attention, during the remaining two years, to carrying out the regional work that was planned as part of the Addendum funded by the Government of Norway.

### Improve Curriculum Development Process and Role of Science

- The Mission recognises the important role that scientists can play, in addition to trainers and farmers, in CIPM curriculum development and farmer field studies. It therefore recommends that the curriculum development process be made more explicit, so that donors, scientists, policy makers, trainers and others have more understanding of the roles of the different actors, the process over time, and the transformation of technical knowledge in discovery learning.

### Documentation

- In the countries visited much work remains to be done to document what has been achieved during the Programme. The Mission recommends that efforts be made to document and disseminate existing data on case studies, strategies, interventions and their impacts. This work will need to be dovetailed with studies by others, discussed below.

## Recommendations for Ongoing Work at National Level

### Consolidation at the National Level by the Inter-Country Programme

- Quality control of FFSs and TOTs in the last two years is an important concern. One of the greatest danger of CIPM is the mechanical and below standard implementation of FFSs with respect to the technical and educational aspects. The lowering of quality standards often follows the success and rapid expansion of programmes. This concern is applicable to all the member countries but especially in Vietnam, Nepal, China, Cambodia and Sri Lanka. The uncertain impact of farmer-to-farmer training, and the lack of attention to impact evaluation are causes of worry and leave the whole IPM effort vulnerable to criticism from its detractors and people who do not understand what the Programme is trying to achieve. The concern with maintaining quality is especially high for CIPM, as the IPM capacities are transferred to local farmers as FFS trainers and even TOT trainers. There is a need to closely monitor and to support the quality of activities under this new phase of IPM. In view of this consideration, the Mission recommends the following:

  - FAO teams in the individual countries should refrain from launching major new initiatives, except on health studies (see below), expanding IPM in schools (where programmes now exist), and improvement of the science in programmes;

  - given the likelihood that the current FAO supported activities will come to an end in the coming two years, major emphasis should be given in the remaining time to consolidate the gains made, i.e. emphasis on quality enhancement through in-service training, TOTs, institutionalisation in government of IPM activities and their funding, expansion of participatory M&E methods;

  - consolidation of existing impact evaluations of key activities under CIPM, such as Farmer TOTs and FFSs, is an important step that needs to be conducted in the coming two years;

  - participatory health monitoring of spraying impact needs to have increased focus. This is one area that will have longer-term implications to the pesticides use and one closest to people’s hearts. The initial work in Indonesia and Vietnam should be increased and expanded to other countries.

### National Programme Development

- Whereas the Foundation would work at the regional (Inter-Country) level, the Mission also envisages a longer-term CIPM capacity at the individual country level. In most countries visited, a strong base for CIPM has been established, or will be in the next two years. The Mission recommends that in all the countries visited a major effort be made to mobilise expanded funding for national CIPM programmes. The ICP group can assist country programmes and FAO country teams in the design and marketing of stand-alone national CIPM projects. Flexible ways forward for expansion need to explored, involving: application of the concept to new areas; and consolidation in established areas - as well as the strengthening of government capacity at the centre and decentralised levels and the promotion of local farmer-managed CIPM. Technical support from the proposed Foundation will be important for the success of these national programmes.

### Support for Design of National CIPM Strategies
by the Inter-Country Programme

- Both consolidation and development will require elaboration of strategies for National CIPM Programmes that will, hopefully, remain in place after the end of Phase IV, and are more likely to remain if national CIPM strategies have been developed. The Mission recommends that local FAO teams stimulate formulation and acceptance of national CIPM strategies. These strategies should build on the impact evaluations and review prospects for financing and institutional support and sustainability. National CIPM strategies must be able to protect and expand the special nature of CIPM, where sustainable land use is the emergent property of informed and empowered interaction among farmers, and between farmers and institutional support structures. Important tasks for CIPM are:

  - ensure the maintenance of quality when scaling up FFS across different areas, population groups, intensive crops and other natural resources. This includes refresher training, maintaining the cadre of qualified government trainers and farmers, etc.;

  - ensure that IPM becomes institutionalised as part of normal government procedures and help strengthen networks that oppose pesticide use;

  - strengthen incipient clean food movements and linkages with concerned consumer groups;

  - facilitate and strengthen farmer organisations as partners in the gender-sensitive development of sustainable rural livelihoods;

  - increase the emphasis on women and their roles in FFS and FTOT; and

  - liase with the Foundation for the further conceptual and methodological development of CIPM.

- Donors are strongly urged to support the development of strategies and expansion of national CIPM programmes, either directly or through FAO.

## Recommendations for Studies by
Research, Academic and Development Organizations

- Further work and critical analysis is needed for the conceptual and methodological development of Community IPM. The areas suggested below are of relevance for the entire development community. It is therefore not expected that the Regional Programme carry out this research - at best its role should be that of a catalyst.

  - No study has been made comparing results from the official extension approach (e.g. block demonstrations) with that from FFS and Community IPM. The Mission feels that it would be very worthwhile to carry out such a study using a fully independent and reputable institution and to widely publicise the result for the benefit of policy makers.

  - At present, the confusion about the FFS as a regular extension method gives rise to the possibility of disastrous use of the FFS model as the regular extension approach. What is required is careful field-experimental research or careful evaluation of efforts to integrate FFS and regular extension, so as to develop optimal ways in which regular extension can build on FFS and play a role in follow-up activities.

  - Development of approaches and methodologies for participatory assessments of the impacts of pesticide use on biological diversity, local environmental processes, and drinking water supplies, involving farmers and other members of the local community.

  - The technical options which government research and extension staff can offer farmers usually reflect and reinforce mainstream definitions of IPM that seek more efficient use of pesticides and product substitution (e.g. pest-resistant varieties for pesticides) within a farming landscape that remains essentially unchanged in structure and function.  More agro-ecological research is needed to develop the scientific and technical knowledge for approaches based on management of whole farm landscapes and the re-introduction of appropriate levels of functional biological diversity to suppress pests and solve other agronomic problems (nutrient management, plant breeding, soil and water conservation). CIPM-trained farmers need this knowledge base when they choose to reduce (or eliminate) their reliance on the purchase of off-farm inputs to produce rice and other crops.

  - The working relationship between scientists, farmers, extension staff and FFS trainers in the dynamic and adaptive process of curriculum development and post FFS support is unclear. There is a need to better document how curriculum development and follow-up activities for FFS work might be improved through changes in the institutional norms, operational procedures, incentive and reward structures, culture, professional training and capacity building of government agricultural research and extension organisations.

  - More knowledge is needed on how, and under what conditions, the learning process supported by FFS/Community IPM actually spreads to more people and places.

  - International and national level policy research on pesticide trade and its impacts is urgently needed. Particular attention should be given to analysing the industrial, technological and marketing strategies of transnational agrochemical corporations, and to their possible influence in setting international and national norms and regulations on the production, use and disposal of pesticides and transgenic products.

  - The potential impacts of trade liberalisation and new WTO agreements on agriculture are unclear for the future of Community IPM and its institutionalisation at the local level. Research is required to allow national decision makers to develop appropriate policy responses to globalisation. The impacts of Trade Related Intellectual Property Rights (TRIPs) on public research and control over rice germplasm also need further analysis through policy research.

# Background to the Programme

- Beginning in 1980, what is now called FAO's Inter-Country Programme for Community IPM in Asia has, during the course of its development, covered all the main rice producing developing countries of East, Southern and South East Asia (with the exception of PDR Korea and Myanmar). The Programme has evolved both in coverage and conceptually.

- A torchbearer for the Inter-Country Programme has been the separate national Programme in Indonesia. Here over a period of more than 20 years, work progressed from demonstrating the effects of pesticides on pest build-up and instability of yields, to the Farmer Field Schools (FFS). With assistance from USAID and the World Bank, FFS and later CIPM were expanded to most of the country’s main rice growing areas. The point of entry both historically and in each country in the development process has thus, been the establishment of FFS focused on IPM in rice. FFS are now a significant part of the development process in all Programme countries.

## The Farmers’ Field Schools and Community IPM

### The Farmers’ Field School (FFS)

- A Farmer Field School is a participatory learning experience in which a group of farmers discover ecological concepts and analytical skills by observing field conditions during the course of a whole cropping season, with guidance from a specially trained facilitator.  The knowledge which farmers develop during the Field School helps them to make crop production decisions that are healthy, efficient and sustainable. The FFS is not a channel for sending messages to farmers or transferring technology.

- IPM Farmer Field School basics:

- The IPM Field School is field based and lasts for a full cropping season.

- The number of FFS meetings might vary from at least 10 up to 16 weekly meetings.

- The primary learning material at a Farmers' Field School is the rice field.

- The Field School meeting place is close to the learning plots, often in a farmer’s home and sometimes beneath a convenient tree.

- FFS educational methods are experiential, participatory, and learner centred.

- Each FFS meeting includes at least three activities: the agro-ecosystem analysis, a “special topic”, and a group dynamics activity.

- In every FFS participants conduct a study comparing IPM with non-IPM treated plots.

- An FFS often includes several additional field studies, depending on local field problems.

- Between 25 and 30 farmers participate in a FFS.  Participants learn together in small groups of five.

- All FFSs include a Field Day in which farmers make presentations about IPM and the results of their studies.

- A pre- and post-test is conducted as part of every Field School for diagnostic purposes and for determining follow-up activities.

- The facilitators of FFSs undergo intensive season long residential training to prepare them for organising and conducting Field Schools.

- Preparation meetings precede an FFS to determine local needs and recruit participants.

- Final meetings of the FFS often include planning for follow-up activities.

### What is Community IPM?

- Community IPM involves farmers organising and implementing their own IPM activities. These farmers become the instigators of local agricultural development rather than the recipients. Community IPM is based on group action, which uses agro-ecological concepts to analyse problems, carry out experiments, conduct training for other farmers, protect the health of the community and mobilise support from government agencies and the public.

- Community IPM emerged from training programmes that used the Farmer Field School approach. Across Asia, the graduates of FFS have decided to plan and manage ‘follow-up’ activities involving three interrelated elements: i) training and learning processes; ii) experimentation and knowledge-generation; and iii) organising and group development. Most Community IPM activities involve at least two of these elements, although different elements are prominent in different activities. Together, the three elements of Community IPM lead towards farmer empowerment.

Examples of Community IPM activities where training is prominent are: FFS conducted by IPM farmers for other farmers; and incorporation of IPM into the curriculum of local schools.

- Examples of activities where experimentation is prominent are: insect zoos and compensation studies (managed by farmers as part of FFS); field studies which are organised and implemented by groups of FFS graduates; action research facilities, involving a number of studies carried out by IPM farmers over a number of cropping seasons.

- Examples of activities where organising is prominent are: IPM farmer clubs, associations and congresses; planning and technical meetings organised by farmers; farmers' advocacy and efforts to mobilise funding from local government in support of community action.

## The Situation for the Regional Programme at the end of Phase III

- All countries of the region had worked with IPM but most lacked experience of Farmers’ Field Schools and the Community IPM approach to development. In Indonesia, Vietnam and parts of Bangladesh the majority of rice producers in the major rice growing areas had been directly or indirectly reached through IPM FFS. In other Asian countries, associated with the Programme, work is at a much earlier stage of development and in terms of coverage the proportion of farmers and of the rice growing areas reached is low

- Regional:  The only on-going regional component at the end of Phase III was an international course for Asian IPM Trainers (A-Team) funded by the Netherlands under a separate Addendum.  The regional office was transferred from Manila to Jakarta, absorbing several of the staff who had been engaged in the long running Indonesia programme.

- Bangladesh:  Limited technical assistance was being provided by FAO-ICP to a UNDP-funded IPM project with the Department of Agricultural Extension. The FAO IPM team in Indonesia was also organising exchanges with CARE International that was implementing IPM in a number of NGO projects.

- Cambodia: ICP had a international expert in the country managing TOT courses funded under the FAO Technical Cooperation Programme.

- China:  ICP assistance, including an international expert, had been withdrawn from China by the end of Phase III due to lack of funds.  The Chinese Government was continuing some IPM training activities in two provinces.

- India:  Limited technical assistance was being provided by FAO-ICP to a UNDP-funded IPM project with the Plant Protection Department of the Federal Government.

- Indonesia:  ICP was not active in Indonesia, but a separate FAO team was providing technical assistance to the National IPM programme funded by Government, US-AID and World Bank.

- Laos:  ICP was not active in Laos throughout Phase III. However, the FAO vegetable IPM programme placed an expert in Laos who was organising rice IPM training.

- Malaysia:  There were no ICP activities in this country during Phase III.

- Nepal:  This country was not a member of ICP during Phase III. Nevertheless, ICP staff were instrumental in starting a small IPM project funded by the FAO Technical Cooperation Programme.

- Philippines:  Support for the National IPM programme had come to an end, but some local activities (including IPM in schools and pilot Integrated Soil Management activities) were being implemented by two National Experts funded by the ICP.

- Sri Lanka:  ICP had a single national expert providing advice to a number of government and NGO organisations, but ICP did not have funds to organise any training.

- Thailand:  There were no significant ICP activities in Thailand throughout Phase III.

- Vietnam:  ICP had two experts in the country, supporting a large-scale IPM programme managed by the Plant Protection Department and funded by the Government of Australia under a separate Addendum to Phase III.

# Project Objectives and their Relevance

- Much of the Project Document as a whole can be taken as a definitive objective statement. By Phase IV it had already been demonstrated that the benefits intrinsic in the Programme objectives were being achieved through the CIPM methodology and were relevant in contributing to solutions for:

- the pesticide crisis;

- instilling agro-ecosystems centred management in agriculture;

- farmers' empowerment, economic and livelihoods development;

- an alternative and more soundly based approach for farmer (adult) learning; and

- increasing food security, at both household and national levels.

- The development objective is nothing short of a transformation in the way farmers observe, analyse and make decisions for their farm agro-ecosystem and in the way governments and NGOs can assist development of this. The Programme is essentially about education on the one hand, and reducing pesticide pollution and danger to health on the other:

  - crops, in particular paddy rice, managed so that –

    - the environmental damage and hazard from pesticide use is reduced;

    - human health risks due to pesticide application and handling and pesticide residues in food are reduced;

    - yields are stabilised and food security increased;

    - costs are reduced and yields improved.

  - human capacities strengthened so that –

    - farmers can better make informed decisions for livelihoods and agro-ecosystems;

    - participation in community endeavour of all kinds is increased.

- The great majority of the resources under Phase IV were thus directed, first and foremost, for people dependent upon rice and rice-based cropping systems to:

  - scale-up and significantly widen the coverage of farmers’ field schools;

  - deepen, and build on the Farmers’ Field Schools (FFS) and the skills acquired within them, for continuing farm and community level analysis and action on IPM and other issues;

  - institutionalise sustainable programmes for expansion and support of farmer based CIPM within countries through government at national and local levels and, as appropriate, through civil society.

- The Programme was also intended to:

  - achieve changes in policies, regulations and implementation, to limit the harmful effects of pesticides on the environment and human health, both through the Farmer Field School community base and through more direct involvement at policy levels; and

  - establish a continuing networked capacity at regional level for support to Community IPM.

- Immediate objectives as stated in the Project Document were:

  - to create self-reliant training capability where it does not yet exist within government agencies and/or non-government organizations which are planning or managing Community IPM programmes in member countries;

  - to develop the content and methods of Community IPM activities appropriate to different farming systems and social conditions;

  - to strengthen the management capability for Community IPM programmes within member countries and improve cooperation among member countries in a manner which will sustain this capability;

  - to improve the ability of policy-makers and planners in member countries to initiate, support and evaluate Community IPM programmes.

  - to enhance broader awareness in member and donor countries about Community IPM activities in Asia.

- The Mission found the Phase IV priorities and objectives of the FAO Programme for Community IPM in Asia to be very relevant to national and regional needs.

  - The Programme had established a comparative advantage (centre of excellence) in working with rice. The most important crop in Asia is rice, and most of the farming systems are rice-based systems. CIPM usually needs to succeed in the agro-ecological pest management of the rice crop before local farmers and policy makers will consider expansion of the approach to other crops and farming systems. Overall, the largest proportion of pesticides are used in rice and cotton.  In wet rice, pesticides enter directly into the water system and cause special risks. There is a particular need for CIPM in intensive systems where pesticides are heavily used, and where production technology is disrupting agro-ecological systems. Furthermore, CIPM is not only a technology but also an educational process. It is in intensive systems that farmers’ traditional knowledge systems have been displaced by institutional and even corporate knowledge systems, applying green revolution technology. It is often in these systems that farmers most need to re-establish their understanding of the agro-ecology of their farm. The Mission therefore agrees that the major focus of the Phase IV Programme on rice was the most appropriate and strategic.

  - The country coverage was also appropriate, in that all the major developing rice producing and consuming countries of Asia were included, except for Myanmar. In terms of countries of concentration, the choice was less clear cut, in that this depended to some extent on donor preferences. In Bangladesh bilateral donors were providing significant support for national CIPM development and this justified a limitation in the resources. Elsewhere the resource allocation picture became distorted by the fact that policy changes in the Netherlands resulted in a decision to not provide Inter-Country Programme funding at quite a late stage in the design process. This left the Programme without earmarked resources for India, Philippines and Sri Lanka. The section on budgetary expenditures (page 38) gives an understanding of the split of resources between the various purposes.

# Programme Design

- By the time of Phase IV the programme design was tried and tested. It was rightly called an Inter-Country rather than a regional Programme, in that the regional component was intended, and had successfully contributed, to the development of national programmes. These were designed separately.

- While leaving scope for the flexibility essential in this type of programme, objectives and means of verification were relatively clearly stated and there was coherence between outputs and objectives (i.e. log-frame concepts were adhered to). Targets were rather crudely expressed in numbers, without reflecting a concern with quality which has in fact been a hallmark of the Programme.

- Funding was from three donors, each picking up separate components of the Programme and this did introduce a weakness, as referred to above. It may be noted that such shortfalls from one donor are not uncommon in joint programmes.

- The Programme was well-coordinated with other FAO regional activities in IPM (vegetables and cotton) by strong working level links in sharing technical staff. Links with IRRI for rice technology were addressed through a memorandum of understanding.

- The separate policy component in the Programme was relatively small (36 person months) and there is some question as to how adequately the Programme could have been expected to focus on this area.

- Questions have arisen as to whether the regional support team was too large in comparison with the national programmes. It was difficult for the mission to come to a clear conclusion on this, but on balance the criticism was found invalid. There was and remains much leadership, coordination and exchange, conceptual and methods development to be carried out at central level, as well as management of the Programme inputs for national programmes. Consultancies and partial funding for staff had been made efficient use of by sharing with other FAO IPM programmes, and by stationing staff with shared regional and national responsibilities outside of the Jakarta office.

- At a more fundamental level, questions arise as to whether an inter-country project continued to be the most appropriate institutional framework for support to the sustainable development of Community IPM at national level and to establish a regional framework. Examination of this had been muted during Phase III, and while it had not occurred during that Phase, the mission makes precise proposals for a new framework at the end of Phase IV – see Recommendations.

# Budgetary Expenditure and Implementation

## Budgetary Expenditures

- The Phase IV Inter-Country Programme was originally budgeted for US$ 34.6 million. In the event mainly due to the Netherlands redistributing authority to country offices for the great bulk of project approvals, it became difficult for the Netherlands to contribute the originally estimated US$ 10 million to a large regional programme. Actual budgets approved totalled US$ 21.9 million, with US$ 9.6 million from Australia, US$ 10.0 million from Norway and three individual projects from the Netherlands covering training activities in China - US$ 2 million and Cambodia - US$ 0.2 million; and a contribution for regional and other country activities of US$ 0.1 million.

- Summary Tables 3-6 below summarise expenditures to date (US$ 12.43 million –slightly over half of the total funds available for Phase IV). Further details can be found by donor in the respective donor appendices, including the estimated expenditure for each donor by country. Summary Table 6 is a sub-set of the previous Summary Tables. Some 37% of expenditures were contracted at the regional level but 78% of this benefited individual countries (staff visits, work by consultants, attendance at meetings, etc.) The remaining 32% of regional level expenditures benefited all countries (publications, website, information exchange, etc.).

- With the availability of bilateral DANIDA funding in Vietnam, it became possible to concentrate Australian expenditures in others of the approved countries and work at the regional level and to utilise funds from the Norwegian unallocated reserve for work in Sri Lanka. Permission will now be sought from Norway to undertake further expenditures in Sri Lanka, and this is recommended by the mission (see Sri Lanka Appendix). It is also recommended that in view of the reduced call on the Norway allocation for Vietnam (as a result of the DANIDA funding), work originally budgeted in Laos and particularly in Nepal, receive support at a higher level than originally envisaged. It may also be noted that very little funds have been expended in countries other than Sri Lanka which were unbudgeted by the contributing donors and that the great bulk of funds has been expended in poorer countries of the region where CIPM remained to be established.

| Summary Table 3: Estimated % Distribution of Donor Funds By Objective and Total Distribution of Funds by Objective |  |  |  |  |
| --- | --- | --- | --- | --- |
| Countries* (and Regional) | Australia GCP/RAS/167/AUL | Netherlands GCP/CMB/006/NET, GCP/CPR/030/NET, GCP/INT/483/NET | Norway GCP/RAS/172/NOR | Total |
| Total Expenditure To Date US$ million 12.43 | 6.19 | 1.17 | 5.07 | 12.43 |
| Percentage Breakdown |  |  |  |  |
| 1. Developing and Implementing Training Capability | 15% | 51% | 44% | 31% |
| 2. Developing and Implementing Community IPM | 23% | 14% | 23% | 22% |
| 3. Developing Field Management Capacity | 17% | 19% | 10% | 14% |
| 4. Improved Policy, Planning and Prog. Development | 34% | 13% | 20% | 27% |
| 5. Enhancing Broader Awareness of IPM | 10% | 3% | 2% | 6% |
|  | 100% | 100% | 100% | 100% |

| Summary Table 4: Estimated Distribution of Expenditures to Date by Objective and Country (includes Regional Activities Directly Benefiting Individual Countries and Those Benefiting All Countries) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Countries* (and Regional) | BGD | CMB | CPR | IND | INS | LAO | MAL | NEP | PHI | SRL | THA | VIE | ALL | Total |
| 1. Developing and Implementing Training Capability | 0% | 2% | 10% | 0% | 0% | 2% | 0% | 3% | 0% | 1% | 1% | 12% | 0% | 31% |
| 2. Developing and Implementing Community IPM | 0% | 3% | 2% | 0% | 6% | 0% | 0% | 0% | 1% | 0% | 2% | 6% | 2% | 22% |
| 3. Developing Field Management Capacity | 1% | 2% | 3% | 0% | 2% | 0% | 0% | 1% | 0% | 0% | 1% | 3% | 1% | 14% |
| 4. Improved Policy, Planning and Prog. Development | 0% | 3% | 2% | 1% | 2% | 1% | 0% | 3% | 0% | 2% | 2% | 4% | 7% | 27% |
| 5. Enhancing Broader Awareness of IPM | 0% | 0% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 3% | 6% |
| Total | 1% | 10% | 18% | 1% | 11% | 3% | 0% | 7% | 1% | 3% | 6% | 26% | 13% | 100% |
| *BGD = Bangladesh; CMB = Cambodia; CPR = China; IND = India; INS = Indonesia; LAO = Laos; MAL = Malaysia; NEP = Nepal; PHI = Philippines; SRL = Sri Lanka; THA = Thailand; VIE = Vietnam; REG = Regional |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Summary Table 5: Estimated Distribution of Expenditures to Date by Whether Expenditure Directly at Country or Directly at Regional Level |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Countries* (and Regional) | BGD | CMB | CPR | IND | INS | LAO | MAL | NEP | PHI | SRL | THA | VIE | REG |
| Expenditure to date (US$ million) – Total 12.43 | 0.00 | 0.98 | 1.77 | 0.00 | 0.81 | 0.21 | 0.00 | 0.49 | 0.15 | 0.12 | 0.49 | 2.75 | 4.65 |

| Summary Table 6: Estimated % Distribution of Expenditures Defined as Regional by Benefiting Country and Expenditures Benefiting All Countries (US$ 4.65 million) (37% of Expenditures are classified as Regional but as much of this is spent directly to benefit individual countries, only 13% of Total Expenditure is for All Countries) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Countries* (and Regional) | BGD | CMB | CPR | IND | INS | LAO | MAL | NEP | PHI | SRL | THA | VIE | All | Total |
| 1. Developing and Implementing Training Capability | 0% | 1% | 1% | 0% | 0% | 0% | 0% | 2% | 0% | 0% | 1% | 1% | 0% | 6% |
| 2. Developing and Implementing Community IPM | 0% | 2% | 1% | 0% | 3% | 0% | 0% | 0% | 0% | 0% | 1% | 3% | 5% | 15% |
| 3. Developing Field Management Capacity | 1% | 1% | 2% | 1% | 2% | 1% | 0% | 1% | 0% | 1% | 1% | 1% | 2% | 14% |
| 4. Improved Policy, Planning and Prog. Development | 1% | 4% | 2% | 1% | 6% | 1% | 0% | 6% | 1% | 3% | 4% | 4% | 18% | 51% |
| 5. Enhancing Broader Awareness of IPM | 0% | 0% | 1% | 1% | 1% | 0% | 1% | 0% | 1% | 1% | 1% | 0% | 7% | 14% |
|  | 2% | 8% | 7% | 3% | 12% | 2% | 1% | 9% | 2% | 5% | 8% | 9% | 32% | 100% |
| *BGD = Bangladesh; CMB = Cambodia; CPR = China; IND = India; INS = Indonesia; LAO = Laos; MAL = Malaysia; NEP = Nepal; PHI = Philippines; SRL = Sri Lanka; THA = Thailand; VIE = Vietnam; All = Regional expenditures benefiting all countries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Efficiency and Effectiveness of Implementation

- The results of the project in terms of progress against immediate and development objectives speak for themselves in terms of the effectiveness of implementation. Actual implementation efficiency has been high drawing on an established team set up during the previous phases of the Programme. There has also been continuity of operational and technical support responsibilities in FAO. Areas which would benefit from some additional attention include:

  - financial reporting by FAO;

  - critical implementation reporting by the Programme.

# Outcomes, Effects and Impact

## Summary of Results Against
Immediate Objectives and Outputs

- Summary Tables 7 and 8 below, review the progress of the Programme against immediate objective and output targets. As already, noted targets have in general been significantly exceeded. Details are provided for countries visited by missions and for the funding from Australia and Norway in the respective appendices.

### Summary Table 7 Training During Phase IV
in Countries Visited by The Mission

| Summary Table 7 Training During Phase IV in Countries Visited by The Mission |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cambodia | China | Indonesia | Nepal | Sri Lanka | Thailand | Vietnam |
| Farmer Field Schools (FFS) |  |  |  |  |  |  |  |
| No. of FFS | 681 | ~988 | 300 + | 271 | 214 | 72 | 1,999 |
| No. of Trainees | ~18400 | ~29,192 | 10,000 + | ~ 6,000 | 4240 | 1,330 | ~50,000 |
| No. of Women | N/A | ~ 8,000 | N/A | ~ 200 | N/A | N/A | ~19,500 |
| Non Rice FFS | 92 | ~15 | N/A | 0 | 0 | N/A | 174 |
| Training of Trainer (TOT) Courses for Goverrnent and NGO Staff |  |  |  |  |  |  |  |
| No. of TOT | 4 | 9 | 0 | 2 | 1 | 4 + 2 | 0 |
| No. of Trainees | 151 | 271 | 0 | 71 | 32 | 202 | 0 |
| No. of Women | 55 | N/A | 0 | N/A | N/A | N/A | 0 |
| Non Rice TOT | 3 | 0 | 0 | 0 | 0 | 1 | 0 |
| Farmer TOT Courses |  |  |  |  |  |  |  |
| No. of FTOT | N/A | ~58 | 84 | 0 | 11 | 0 | 34 |
| No. of Trainees | 250 | ~1,699 | ~ 2,000 | 0 | 230 | 0 | 1,276 |
| No. of Women | N/A | ~500 | N/A | 0 | N/A | 0 | 459 |
| Non Rice FTOT | 200 | ~3 | N/A | 0 | 0 | 0 | N/A |
| Summary |  |  |  |  |  |  |  |
| No. of Farmers | ~ 20,000 | ~29,192 | 10,000 + | ~ 6,000 | 4,240 | 1,565 | ~50,000 |
| No. of Govt. Trainers | 150 | ~271 | 2,300 | 71 | 32 | 202 | 0 |
| No. of Farmer Trainers. | 450 | ~1,699 | 2,000 | 0 | 230 | 0 | 1,276 |
| Overall approximate totals: Trained Farmers: 120,000; Government trainers: 730; Farmer Trainers: 5,500 |  |  |  |  |  |  |  |
| Notes: Cambodia, Nepal and Sri Lanka all paid for by IC Programme; China, Indonesia, Thailand and Vietnam partially paid for by local authorities |  |  |  |  |  |  |  |

### Summary Table 8: Progress at Mid-Point of Phase IV 1998-2000

| Outputs as per Project Document | Progress at Mid-Point of Phase IV 1998-2000 |  |
| --- | --- | --- |
| Objective 1: Self-reliant training capability, where it does not yet exist, within government agencies and/or non-government organizations which are planning or managing Community IPM programmes in member countries. Success criteria: By the end of Phase IV at least 10 member countries will have a self-reliant capability to train IPM trainers, embodied in a total of at least 600 additional trainers capable of managing season-long rice IPM TOT courses and Farmer Field Schools |  |  |
| Outputs: Trainers capable of managing season long TOT courses without outside help. | The numbers trained are impressive, and far exceed targets. In the countries visited by the mission, overall approximate totals were: Trained Farmers: 120,000; Government Trainers: 730; Farmer Trainers: 5,500. It must be borne in mind that while not all of these trainers are available to the CIPM Programme, there are also substantial numbers of trainers from previous phases, especially in Indonesia and Vietnam, so the number of trainers available for continuing expansion of the Programme is substantially higher (e.g. Indonesia - more than 2,300 IPM Trainers (Pest Observers) in 22 provinces; Vietnam more than 2,000 Farmer trainers in 12 rice bowl provinces). In Vietnam there is seen to be little need for further training of Government Trainers at present as an adequate number are available. In all of the countries Government Trainers carry out CIPM training as part of their official duties, but in Indonesia this is very ad-hoc and depends on the goodwill of supervisors. - In China each province in the Programme has a structure of IPM Committees from the provincial level down through the counties and townships. However, only in Sichuan would there appear to be a well institutionalised core group of trainers at the provincial level. With the exception of Indonesia and Vietnam, overall coverage of the Community IPM programme remains relatively small and this is a disadvantage in demonstrating the efficacy of the programme to policy makers. |  |
| Objective 2: Developed content and methods of community IPM activities appropriate to different farming systems and social conditions. Success Criteria: By the end of Phase IV, Community IPM activities are taking place in at least 600 locations across 7 or more member countries. These activities will be organized and implemented by farmers with a substantial amount of the human and material cost of these activities being met by the local community. |  |  |
| By the mid-point of Phase IV quantitative success criteria had already been exceeded. |  |  |
| Curricula available for specific farming systems and community needs | Work to date has concentrated on paddy rice production with relatively small amounts of work on other crops, particularly vegetables and commercial crops (such as tea and chillies). The close links to the regional vegetable and cotton IPM programmes has facilitated this. Rice IPM is fully covered and curricula are flexibly adjusted in most of the countries each season. Curricula are also designed for the different provinces in each country. An exception seems to be Nepal, where the materials used were from the Inter-Country Programme. The mission did note with concern that sometimes materials seemed to concentrate on insect ecology and material dealing with other pests was limited (such as weeds and fungal and micro-biological pests). Similarly such subjects as water management and fertiliser, although apparently covered in courses, were not always included in the guides. Business analysis was often not a prominent part of the training. This may contribute to the Mission’s impression that there could be a fallback to traditional pedagogic methods in some situations. The exceptions are Cambodia, Indonesia and Vietnam which are generally more developed in all respects than the other countries: - Cambodia: Curricula cover - plant nutrient management; gender equity; cop specific technology; on-farm production of pathogens by farmers; rodent management; health and pesticides; and three cropping systems - single crop rice, vegetables, and mung bean. - Indonesia: A wide range of curricula have been developed on various topics: soil fertility, plant, pests, diseases, natural enemies / bio-agents, farmers organisation forums and advocacy on farmers' rights and many different cropping systems, rice-rice; rice – secondary crops; rice – vegetables; vegetables- vegetables. - Vietnam: Curricula have been developed for: biological studies (including parasites, NPV, Bt); composting; management of soil-borne disease in vegetables; rat management; vegetables; gender; cotton; rice-fish. The following farming systems are covered by curricula: rice-rice; rice-rice-secondary crop (potato; sweet potato; maize; vegetable); rice-secondary crop-rice; industrial crops (soybean-cotton; maize-cotton); and rice-fish. Farmers have developed curricula for: plant genetic resources, including, seed rehabilitation, line selection, variety evaluation and plant breeding. In Thailand, curricula have been adapted for use in schools. Other activities of particular interest included 4 FFS for the handicapped in Cambodia. |  |
| Action research completed by IPM farmers, in collaboration with specialist organizations, which increases the scope and depth of agro-ecological understanding. | Action research has been formally initiated in Cambodia, Indonesia and Vietnam: - In Cambodia, there have been 47 Action Research (AR) activities (29 on rice and 18 on vegetables). Thirty of these took place in the last wet season. Supported by UNDP, “Farmer Life Schools” have been piloted in 6 locations, using approaches and methods adapted from FFS to observe and analyse the social situation within the community. - In Indonesia, there are 8 Farmer Field Laboratories supported by the Programme; 9 Farmer Learning Facilities; hundreds of farmer field studies. Four main AR projects deal with: studies on soil / fertility management, certain problematic pests, natural enemies / bio-agents, botanical pesticides, trap crops, varieties, new crops, etc.; facilitating farmer studies and FFS in surrounding villages; farmer advocacy on local issues/problems; and producing and marketing compost, healthy seed/seedlings, and free/low pesticide products. In several cases, such as brown plant hopper and white stemborer, research findings have been consolidated and disseminated, leading to changes in farming practice. - In Vietnam, there have been 1,171 farmer field studies, focusing on crop management problems, e.g. density, variety evaluation, fertilizer choice and management and, seed rehabilitation. Approximately 800 farmers in 19 provinces participated in Farmer-participatory evaluation of IPM programme impact in CIPM villages focused primarily on economic and qualitative indicators of changed agronomic practices. Elsewhere, the mission was able to verify that some serious trial work had taken place, but some lacked discovery learning and resembled on-farm trials. Trials also seem to have reinforced some useful practices, such as incorporation of rice straw and composting. |  |
| A range of community IPM activities designed tested and documented in collaboration with government agencies and/or NGOs. | NGO involvement has varied. In China and Vietnam, the traditional bodies such as the Women’s and the Youth Unions could be important. In Sri Lanka, the NGO Sarvodaya was involved in training. In Nepal, NGOs were heavily involved in training with World Education being contracted to carry out 18 FFS and develop an NGO network as a model for expansion FFS. As well as World Education, the National IPM programme also works with other NGOs: CARE International (4 FFS), two local NGOs, CEAPRED (1 FFS) and SEWA Nepal (1 FFS). With the perspective of longer-term collaboration, the Programme also worked with CEAPRED to develop a vegetable IPM curriculum. World Education has developed curricula for credit and health based on IPM principles. There was little work with other departments or projects to make use of CIPM methods, but in Anhui, China Trainers were used to assist in the Dutch-assisted poverty alleviation programme. In Cambodia, training in CIPM has been provided to NGOs such as NPA, World Education, CRS, Concern, Oxfam Quebec, ADRA, EU/Prasac and CAAEP. Indonesia had a much greater range of activities: - IPM for teachers and students of Soedirman University; - Training on IPM for schoolteachers in a Junior High School for introducing IPM in the curriculum; - Gita Pertiwi Foundation, World Education, and Duta Awam Foundation in training on Farmer Action Research; Rio Tinto Foundation in TOT for Rio Tinto Staff; Cinta Desa Foundation and Tanah Karo Farmer Network (under World Education support) in Planning Meetings for Follow-up activities; - Collaboration between IPPHTI (IPM Farmers’ Association) and 32 Farmers' Organizations supported by an NGO network to struggle for Farmers’ rights. An interesting development in Thailand has been the introduction of FFS as a discovery learning methodology in schools. |  |
| Fora for communicative action established by/for farmers and community groups engaged in IPM activities | Training material was developed on participatory planning and master trainers courses held in Cambodia, Indonesia, Sri Lanka and Vietnam. FFS members gained in confidence, analytical and communication skills. Farmers were trained in facilitation skills as part of FTOT (see above). Many Farmer-Trainers were previously in some form of leadership role within the community, but many were not, and in all cases their capacity to make a contribution to local debate has been increased. This is particularly important in the case of women, who are forming an increasingly large proportion of trainees. It is clear that the leadership of FFS closely overlaps that of other village organizations and institutions. It seems likely that in many cases leaders joined the FFS, rather than becoming leaders after the FFS experience, but some of the latter has probably occurred. This crossover of leadership has facilitated the rejuvenation of the other organizations and their use to pursue the resolution of problems defined by the FFS members. Community IPM activities outside Indonesia are only beginning to develop. Groups often continue to exist after the FFS and concentrate on helping their neighbours with IPM and extending IPM to other crops. Farmers identify needs for action in common on soil preparation, planting and varieties in order to conserve water and to reduce the risk of heavy build-up of pests in isolated fields at the beginning or end of the season. In some cases farmers also reported that they had rediscovered old practices of communal work. To date, community level activities identified by farmers outside Indonesia concentrate on improvement of agronomic practices, irrigation, and in some cases marketing, including the development of IPM products. For example, in Vietnam 79 groups worked with disease management, 166 with rat management, 100 with soyabeans and 10 with rice seed. IPM clubs/associations have been widely formed, but outside Indonesia most of these have not undertaken activities outside their own villages and there seems in some cases to have been a significant top down element with Government trainers forming the leadership. In Indonesia, community activities are much more developed and have moved towards political action and the representation of farmers, in a situation where there was a vacuum not filled by the former government-promoted organizations, during rapid political change. In Indonesia IPPHTI (Indonesian IPM Farmers’ Association) was established in 10 provinces with national, provincial and district level congresses. During 1998-2000, some 110 fora were convened, addressing four main topics education/facilitation; organising; science and technology; and farmers’ rights/advocacy. Skills for conducting fora have been developed in 15 training courses. Farmer-to-farmer workshops have been convened on Tungro Disease Control, Ecology and Soil. Examples from other countries include: - China: Anhui – 7 IPM farmer associations with 45 affiliated interest groups (5-10 farmers); Anhui – 7 IPM farmer associations with 45 affiliated interest groups (5-10 farmers); Hubei – 28 associations in 26 villages; Sichuan 100 Alumni unions with information station function and 30 activity groups. - Vietnam: CIPM has focused on 4 villages in each of 19 provinces which have worked together in TOT, joined in regular monitoring and quality control, and collaborated on field studies. However in Vietnam, IPM Clubs have not been financed by the Programme. |  |
| Objective 3: Strengthened management capability for Community IPM programmes within member countries, and improved cooperation among member countries to sustain this capability. Success Criteria: By the end of Phase IV, a total of at least 60 field leaders from 6 or more countries capable of planning and coordinating Community IPM programmes at the provincial and national levels, and capable of carrying out international training/advisory assignments. In addition, 250 IPM Trainers have the ability required to initiate and support Community IPM activities in their own countries. |  |  |
| Field Leaders and trainers with the knowledge, skills and experience required to plan, organise, coordinate and support a wide range of Community IPM activities |  | In all countries, except Cambodia, Nepal and Sri Lanka, the programme is nationally managed and has begun to leave the project mode. The development of curricula and the work programme is undertaken primarily by nationals. In Thailand, IPM is institutionalised within the formal structure in different ways: as regular work of the Department of Non-Formal Education with farmers and non-formal education students; as regular work through the Office of the National Primary Education Commission with students in primary schools; and as part of the mission of the Institute for Biological Agriculture and Farmer Field Schools, and within the Department of Agriculture Extension system at province, district and sub-district levels. Elsewhere, institutionalisation has often occurred primarily at provincial and local levels. This is the case in Sri Lanka where the Mahaweli Irrigation Authority is also important and in China and in Vietnam. In Indonesia, the new IPM Farmers’ Associations as well as local authorities, are also important. This now reflects itself in quite substantial financial support being mobilised at the local level in these countries. In Vietnam, an estimated 54% of all rice FFS and 60% of all follow-up activities nation-wide were funded from government or other local resources. The six-country target has been exceeded, with capacity in at least eight countries significantly enhanced during Phase IV. In all countries, some senior staff have benefited from attendance at Inter-Country Programme meetings. A Team members, have undertaken training assignments in other countries which have enhanced their skills. These are especially from Indonesia (12 persons) but also from China and Vietnam. Overseas consultancies have included: season-long TOTs in several Asian countries and Ivory Coast; assessment of IPM field training implementation in India and Nepal; managing an IPM project in CARE Bangladesh. The total number of trainers is referred to above, i.e. in excess of 4,500 government trainers for the countries visited. Probably more than 60 trainers are capable of carrying out international assignments to assist in the initiation of training. Trainers have also been trained in English and management for six months in the USA, under separate Netherlands financing. As far as the team could determine in the case of the three from China, only one of these acquired adequate English to contribute independently to work outside China (Vietnam had 10 participants). In China, a study tour by 13 IPM leaders, primarily from the provincial level, took place in California in 2000. This tour appears to have been very useful in exposing personnel to IPM and organic farming in a commercial, developed country context, which has relevance for China. |
| Objective 4: Improved ability of policy-makers and planners to initiate, support and evaluate community IPM programmes Success criteria: By the end of Phase IV, at least 100 have been provided with an opportunity to discuss IPM policy and/or programme design issues |  |  |
| The target has clearly been exceeded – see below, but a new policy advisor has only just begun work. |  |  |
| Case studies of Community IPM activities, prepared and made available to planners, programme managers and trainers. Studies of special issues completed and results made available as inputs for policy making. |  | National workshops and studies on pesticides and the health of the farmers have been initiated in an action research framework in Cambodia, Nepal, Sri Lanka, Thailand and Vietnam. National workshops were also organized (in Vietnam there was a TOT for health work and Thailand has been the test-bed for participative study methodology). Other case studies include: - Cambodia: Impact of IPM training, Landlessness and Impact of IPM training, Rat and Crab farmer management practice, FTOTs and their contribution to civil society; - China, Laos, and Vietnam: A workshop in Sichuan on gender and IPM in August 2000. China was able to disseminate the benefits of progress in mainstreaming an emphasis in women both to the other provinces of China, and Laos and Vietnam; - Indonesia: Case studies have been conducted on: advocacy on a water dispute; advocacy on irrigation maintenance; national, provincial and district level farmer congresses; community IPM in 6 villages; gender; soil studies; various other technical studies (of e.g. white stemborer); - Sri Lanka Impact Study on Integrated Pest Management Programme in Sri Lanka by a private consultant and Measuring Cost-effectiveness by the NGO Sarvodaya; - Vietnam: An in-depth study guided by an external consultant of the profitability for farmers of IPM in rice in five provinces; Development of IPM system for Brown Plant Hopper (BPH) management in a problem area of unexplained periodic outbreaks - 3-year study, 50-50 co-financed by FAO-IPM and Ho Chi Minh City; and also studies of training of farmer trainers and IPM activities; Community IPM in Yen Phuong Village; IPM Clubs and Community IPM Programme in Dong Thap Province; Women in IPM Programme-Quang Binh Province. |
| Advice to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects. Assistance to member governments and donors when mutually agreed in programme execution. |  | All the concerned line agency staff know about the Programme. Parliamentarians and ministers probably, are generally not aware of details, but senior figures often attend field days. In the majority of cases, senior staff responsible for extension, and sometimes for IPM, do not fully understand the total implications of FFS, as distinct from discussions at a demonstration. Advice and support has been provided to member governments by the Programme staff stationed in Cambodia, China, Indonesia, Nepal, Philippines, Sri Lanka, Thailand and Vietnam. A few of these staff have also technical responsibilities (science and health) and their effectiveness has also in several cases been enhanced by them having cross-responsibilities for the regional IPM cotton and vegetable programmes. Examples of technical support include: - Sri Lanka: presentation to the presidential taskforce on suicide prevention to discuss the importance of IPM training as an approach to reduce suicides using agro-chemicals; - Vietnam: Crop loss assessment field studies on leaffolder in 3 provinces, BPH in 2 provinces, to demonstrate to local agriculture officials that they should raise their thresholds for instructing farmers to apply pesticides during outbreak periods. Gender: Work in gender and related issues in addition to the high level of women’s participation in FFS has included a: - Case study on gender and IPM in Nepal; - A workshop in Sichuan China on gender and IPM in 2,000. China was able to disseminate the benefits of its progress in mainstreaming an emphasis on women in a workshop which included both the other provinces of China, and Laos and Vietnam. |
| Objective 5: Enhanced awareness in member and donor countries about Community IPM activities in Asia Success criteria: By the end of Phase IV, at least 5,000 scientists who are involved in agricultural development and at least 1 million members of the general public, in member and donor countries, have been exposed to information which describes what Community IPM is and what the ICP is doing. |  |  |
| Information on Community IPM available to the scientific community |  | There is contact with scientists in China and Vietnam and to a more limited extent other countries for curriculum development and involvement in farmer field studies. In Vietnam, a five-day scientists and farmers workshop was held with five IPM researchers. Elsewhere, scientists have had greater difficulty adapting to discovery learning, as distinct from making recommendations. The Programme website has provided a valuable resource to all engaged in Community IPM and beyond. Two websites are maintained by provinces in China. In Thailand, a website has been developed for schools. A regional science and farmers workshop was held in 2000, in Jakarta. Programme staff have published in scientific journals. The target of 5,000 scientists reached has been greatly exceeded through a combination of published papers and presentations at international conferences. |
| Information on IPM activities available to appropriate media organisations and advocacy groups |  | Progress in reaching the general public has been much greater. Community IPM is publicised in the local press and television. The Programme will also be covered on BBC World television. In Indonesia, a monthly tabloid newspaper (10,000 copies per issue) is being produced by the newly established National IPM Farmers’ Association, which has received support from the Programme. A newsletter is also produced in Nepal. Support has been provided to television with footage. There has been widespread press coverage of FFS training. Examples of contacts with NGOs include the campaigning NGO -MONLAR in Sri Lanka. |

## Effects and Impact
(See Findings)

page

B.4	Impact of Community IPM for Food Security	17

B.4.1 Immediate Results for Food Security	17

B.4.2 Medium-term impacts on Food Security	17

B.5	Impact and Validity of the Community IPM Approach for Farmers	17

B.5.1 Cost-effectiveness of IPM for farmers	17

B.5.2 Capabilities of farmers to better manage their farms and livelihood systems	18

B.5.3 Farm family health	18

B.5.4 Emphasis on women	18

B.5.5 Questions of Equity	19

B.6	Impact and Validity of Community IPM for Development of the Community, Civil Society and 	Governance	19

B.7	Impact of Community IPM for Development of Government Institutional Structures (for relationship 	to research institutions see below)	20

B.7.1 Departments of Agriculture	20

B.7.2 Provincial and Local Governments and Authorities	21

B.8	Impact of Community IPM through National NGOs:	21

B.9	Impact on the Policies and Approaches of the International Financing Institutions, NGOs

and Donors	22

B.10	Impact on Policy	22

B.11	Overall impact on pesticide use, health and environment (see also Farmer Health above)	23

B.12	Impacts on Curriculum Development and the Role of Science	23

B.13	Farmers' Field Schools and Community IPM as a Model for Learning and Innovation	24

B.14	Appropriateness and Impact of Regional Programme.	26

B.15	Overall Sustainability of the Programme	27

## Cost-effectiveness

### Cost Effectiveness of the CIPM methodology and FFS: see Findings –

- Cost-effectiveness of IPM for Farmers (B.5.1)

- Farmers' Field Schools and Community IPM as a Model for Learning and Innovation (B.13)

### Cost-Effectiveness of the Programme Modalities

- As already commented in the discussion of the programme design, among the criticisms voiced of the Programme are:

  - The regional structure is too costly: National programmes sometimes looked at the regional structure and felt that in its absence more resources would be available for work at the country level. There continues to be a need for more leadership, coordination and exchange, conceptual and methods development to be carried out at central level, as well as management of the Programme inputs into national programmes. Consultancies and partial funding for staff had been made efficient use of by sharing with other FAO IPM programmes and by stationing staff with shared regional and national responsibilities outside of the Jakarta office. It may also be noted that only 13% of total expenditures cannot be attributed directly to benefits by individual countries (see page 39).

  - The international inputs could be substituted by national technical inputs: With the success of the Programme in strengthening national capacity it becomes more and more the case that staff from the country and from the region can assume greater responsibilities. This has been happening through use of the A Team and the reduction in numbers of staff employed full-time in the CIPM Programme. The Mission found that international staff had contributed to the dynamic growth of national programmes and served as a means of increasing international exchange. For example, it was commented in Sri Lanka (where there was a very capable national expert) that in the absence of an international, contact with the Inter-Country Programme was much reduced. However, the Mission endorses the intent to reduce the number of international staff as part of the exit strategy.

- The execution of the Programme through FAO was found to have been a cost-effective way of linking the Programme to other FAO regional programmes in IPM and the global expansion of the CIPM approach with the Global Facility. The links to FAO’s other normative work had also proved beneficial, although there was room for further strengthening. Inter-country staff had also provided cost-effective technical and methodological support to programmes financed bilaterally at the national level. This might not have proved as easy if they had not been from FAO – a UN Agency.

##### Annex 1: The Conceptual Basis of the CIPM Programme
by Niels Röling Mission Leader

and Prof. of Agricultural Knowledge Systems, Wageningen University

The conceptual basis of the Programme is at the cutting edge. It represents beta/gamma science, is an example of adaptive management, is sophisticated in its epistemological basis, and has made considerable advance in operationalising social learning and interactive design as approaches for dealing with ecological challenges. The Programme has further practically demonstrated totally new ways of thinking about the utilisation of scientific knowledge and ‘extension’ for enhancing innovative performance in agriculture, two areas that have been stuck in the positivist grove for decades.

Where the Programme perhaps has been less effective, is in explicitly linking its exciting work in agro-ecology and human learning to marketing and other economic aspects. For example, INDAP in Chile has decided that small farmers cannot effectively be assisted by transfer of technologies for higher productivity in price-squeezed commodities such as wheat, rice and potatoes. Small farmers only have a chance if they grow high-value crops for the new sophisticated urban middle class consumer, and if they can add value by cutting out the middle man and form their own ‘micro-empresas’, by developing effective marketing chains, by processing, attractive packaging, and by ensuring food safety. Asian small farmers, for example, in Vietnam, are very much of the same opinion. This is an area of opportunity for the CIPM Programme. Its focus on farmer empowerment and organisation means that it has much to contribute to small farmers’ livelihoods.

Below we shall briefly provide some highlights of the conceptual basis of the CIPM Programme.

The Utilisation of Scientific Knowledge. There are few ideas that are so difficult to change as the positivist notion that science is the growing point of human knowledge, and that scientific method is the only road to objectively true knowledge about an objective reality that exists independently of the human observer. Science builds a growing body of objectively true knowledge. The utilisation of scientific knowledge leads to progress. Hence scientific knowledge needs to be delivered to so-called ultimate users whose adoption of the knowledge represents innovation.

The IPM FFS operates on a totally different principle. It is designed to foster discovery learning. It is this that makes the FFS more than just technical training. In addition to learning about biological controls and other aspects of agro-ecosystem management, farmers undergo an apparently liberating and empowering learning experience that changes their outlook and self-confidence.

The IPM TOT emphasises facilitation of learning processes so as to help farmers become experts. Lecturing and transfer are discouraged. Superficially, this all sounds like participation, ‘bottom-up’ development, and so on. But this is deceptive. The FFS is based on a curriculum that incorporates sophisticated scientific knowledge about rice ecology. This aspect of the FFS is poorly understood. The fact that the IPM Programme has been blamed for being unfriendly to science is based on scientists’ lack of understanding of the nature of the curriculum. The curriculum development process is, in fact, a new and very exciting approach to the design of the interface between science and practice in agriculture.

The doctoral dissertation of Frank Van Schouwbroeck makes clear what the difference is between science-driven transfer of technology and curriculum development. When Van Schouwbroeck came to Bhutan, he was asked to use his entomological knowledge on stem borers in maize, the staple crop in the area. But Van S. was not convinced. He spoke to farmers about the issue and eventually discovered that farmers had a much more important problem than stem borers in maize. They grew mandarins (a small citrus fruit) for nearby markets in India as their major cash crop, and this crop was seriously affected by fruit drop. Farmers had little idea what caused this sometimes-massive phenomenon. Van S. went to work on this problem which was caused by the Chine fruit fly. He first carried out a great deal of on-station research. This work covered the biology of the fruit fly, including the life cycle, population dynamics, pheromones that attract it, and so forth. As an entomologist, Van S. could have obtained his doctoral degree in entomology on this work alone.

But Van S. had discovered that the scientific knowledge about the fruit fly did not allow him to design an effective method to control it. In fact, he spent a good year working with farmers to develop effective practices. These needed to take into account the fact that the fly cannot be controlled at the farm level, but only at the community level. This work can be called curriculum development. His dissertation reports on both, the on-station scientific research, and the curriculum development, as two different types of equivalent and equally important types of research. Curriculum development uses scientific research. But at the same time, it cannot be done any other way than in a process of interactive design together with farmers.

Another example is the doctoral work of Gus Hamilton. Years of transfer-based extension work in dry areas of Queensland, Australia, had not had much impact on farmers’ practices with respect to zero tillage, considered highly desirable for water retention and erosion control. The science was all there, but it was not utilised. Together with farmers, Hamilton developed and tested a curriculum for farmer discovery learning based on a ‘rain simulator’, basically a tank wagon with a shower. This equipment allowed farmers to experiment with rainfall on different surfaces. The equipment, originally designed for on-station research, allowed farmers to measure run-off, examine the colour of the water that came out at the end of the process, and assess water retention. Since farmers seldom stay around in a good rain shower to look at what happens to the soil, the rainfall simulator proved a huge success. Without teaching or transfer, farmers observed what happened to their land under different conditions, and drew their own conclusions. The take-up of zero tillage increased dramatically in the area, even though farmers did not all draw the same conclusions.

Curriculum development has not sufficiently been made explicit and transparent. This does not mean that it is done badly by the CIPM Programme. In fact, the curriculum for the rice FFS is a masterpiece that represents a sophisticated mix of ecological knowledge and non-formal education. The curriculum ‘Living Soils’, developed and tested by W. Settle together with farmers, is an exciting effort to introduce discovery learning to ‘integrated soil fertility management’. The curricula for IPM in vegetables developed by the Regional Programme for vegetable IPM are also excellent.

The process and nature of curriculum development have insufficiently been made explicit. There is insufficient shared understanding about this process among the farmers, trainers, officials, NGO staff, and scientists involved in the Programme. This is a dangerous situation, especially at a time when there is pressure in most of the countries, by farmers and governments who want to apply the success achieved in rice to higher value crops, to expand IPM to crops other than rice. There are instances where the inclusion of other crops has meant that ‘telling them how it is’ has crept back into the process. There are instances where trainers have fallen back on the rice curriculum when they could not handle a new crop. There are also instances where the curriculum for wet rice has been copied lock, stock and barrel to bananas or other crops. Furthermore, some curricula for new complex crops are being developed at the district level without evidence of sufficient access to scientific knowledge. Such loss of quality is not a feature in the FAO funded activities, but occurs during the scaling up of the programme by other agencies. It is of particular concern that the new curricula do not pay sufficient attention to the element of discovery learning that is the active ingredient in the FFS. The process of curriculum development should be made explicit, widely publicised and used in TOT. Attention should also be paid to process for upgrading curricula.

FFS and Extension

The FFS and follow-up though CIPM represents a form of farmer training. It provides a transformational experience, much like conscientising alphabetisation. It is therefore not a form of regular extension but a form of farmer education. In most industrial countries it is considered normal that farmers receive agricultural education that qualifies them to be good farmers. In most developing countries, such farmer education is totally absent. The FFS and the follow-up in CIPM is a form of non-formal education that works like a wake-up call. Small rice farmers have been conditioned by the Green Revolution process to become receivers of science-based uniform recommendations that have destroyed their indigenous knowledge, replaced their plant genetic resources, and discouraged their own experimentation. The FFS wakes them up from this temporary lethargy. It therefore creates a basis for effective extension work.

This achievement is totally not recognised for what it is. Departments of Agriculture in some of the Programme countries are considering adoption of the FFS as the basis for their regular extension work, without much specification of what they have in mind. An example is the World Bank-supported AREP in Nepal. Another example is a recent publication by World Bank economists. Demonstrating a total lack of understanding of the empowerment function of the FFS, this article evaluates the unit cost per farmer of ‘agricultural extension programmes based on the FFS approach’ and concludes that there is a risk of ‘fiscal unsustainability’. Such lack of understanding detracts from the important achievement by the Programme, and undermines a very positive development that promises to break through the stalemate in extension thinking. It is important, therefore, that the difference between the FFS approach and regular extension is made much more explicit. What needs to be developed through practical field experimentation is how regular extension can build on what has been achieved through FFS.

There is lack of understanding at the moment of how the learning effect created by the FFS diffuses. In the classical extension model, autonomous diffusion of technologies multiplies the impact of extension (which usually does not reach more than the top 10 – 20% farmers directly). It is not unlikely that the use of biological controls, reduced pesticide use, better fertiliser use, plant spacing and other cost-cutting technical practices promoted by FFS will diffuse autonomously. In fact, their diffusion might become propelled by market forces as these technological changes begin to exert downward pressure on prices. However, it is questionable whether the transformational learning experience diffuses. It is likely that this is not the case. This means that special attention must be paid to scaling up that learning experience. It is to the cost-effectiveness of that aspect that economists must turn their attention. By introducing a totally new practice, the CIPM Programme has opened up new and exciting conceptual developments in the field of extension that, with active support by organisations such as the World Bank, remains mired in conventional positivist thinking.

Epistemology

The historical evolution from the outrage about pesticides, to the FFS as entry point for mass non-formal education, to consolidation of, and building on, the gains made through follow-up in CIPM, does not sufficiently explain the conceptual progress that CIPM embodies. That evolution is best explained by referring to the Miller/Bawden Quadrants (Figure 1).

| Figure 1: CIPM and the Miller/Bawden Quadrants |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Holism |  |  |  |  |  |
| Po s i t i v s m |  | II Management of Ecosystems: Still based on positivism, but has moved to a systems perspective. Ecosystem approaches fall into this quadrant. Ecologists usually look at ‘natural’ systems, in which people are only considered as elements of nature and not as intentional beings whose designs determine the future of ecosystems (i.e. humans as a major force of nature). The focus in Quadrant II is on use of natural controls and agro-ecosystem management. | III Ecological Sustainability Emerges from Human Interaction: Represents a holistic approach coupled to a constructivist epistemology. Thus it provides room for human learning, to futures that emerge from interaction among multiple stakeholders, and to communicative rationality. In this quadrant one can look at cognitive and institutional aspects of land use, the ‘soft side of land’. Community IPM with its focus on farmers as experts, on FFS, and on farmer empowerment typically fits in Quadrant III. |  | Constructivism |
|  |  | I Technology Transfer: Thinking based on reductionism and positivism. In rice IPM, the focus in this quadrant is purely on pesticide reduction, scientific thresholds for decision making, and on transfer of science-based knowledge. | IV Pray: Perhaps this is the quadrant for those who consider spirituality as a key ingredient in ecological rationality. Abraham Maslow, who has analysed spiritual peak experiences, describes them as follows: ‘The complete human person at certain moments is able to perceive the unity of the cosmos, to fuse with it and rest in it, for the moment totally satisfied in his desire for being at one’. Such spirituality is a wellspring of ecological rationality. Paying attention to spirituality is not alien to an Asian IPM Programme. |  |  |
| Reductionism |  |  |  |  |  |

These quadrants represent different ways of thinking (‘blinding insights’) about natural resource use. The quadrants are based on two dimensions: an epistemological dimension, dealing with assumptions about the nature of knowledge, and an ontological dimension dealing with assumptions about reality.

Thus Quadrant I is characterised by people whose thinking is determined by positivism and reductionism. Miller calls this quadrant the techno-centric quadrant. It focuses on the technical fix, be it spraying or reducing pesticide use. The experience in the CIPM Programme is that people operating in Quadrant I emphasise scientific research on component biological controls, scientific thresholds for spraying, and find it very difficult to understand alternatives to technology transfer.

Quadrant II is ‘inhabited’ by people who combine a positivist epistemology with (hard) systems thinking. People do not feature in this quadrant. Outcomes are determined by natural causal forces. People might be regarded as such a natural force, but there is no interest in how people’s cognition, institutions, or collective action could bring about change in natural resource management. The blinding insight in this quadrant emphasises eco-systems and the use of biological controls. The admirable achievements of the IPM Programme, in terms of understanding and managing the ecology of the rice-based agro-ecosystems originate from thinking in this quadrant.

Holling and his colleagues have recently made very important contributions to the understanding of the dynamics of large ecosystems in which humans play dominant roles. They conclude from these studies that ecosystems basically go through cyclic patterns of change while humans tend to focus on linear development. Thus human control tends to focus on the optimisation of one or more target variables while suppressing all the others. Such management leads to ‘weakened ecosystems and vulnerable human societies’. Hence their ecological research leads to important conclusions for human behaviour. A resilient human society must be based on adaptive management’, based on monitoring, experimental probing and above all social learning about ecosystems to capture human opportunities. But as ecologists, Holling and his colleagues are not optimally positioned to deal in depth with that social learning and adaptive management itself. Their achievement is to have translated their ecological knowledge into requirements for the way people deal with ecosystems.

Quadrant III combines a holistic systems perspective with a constructivist epistemology. This quadrant explicitly provides room for soft thinking, for social learning, and for the very crucial notion that the future of ecosystems is a human artefact. That is, this quadrant focuses on sustainability as the emergent property of human interaction (conflict, negotiated agreement, learning, and collective action). Moving to Quadrant III is a crucial step that few scientists have been able to take. It is one thing, as Holling and his colleagues have done, to draw conclusions for human behaviour from scientific analysis of natural systems. This is comparable to epidemiologists and oncologists drawing conclusions about smoking (a human behaviour) from their studies of mortality and morbidity of organisms. It is quite another thing to deal with human behaviour itself, as the dissertation of Van Schouwbroeck has also demonstrated.

In Quadrant III, human behaviour itself is given central attention because it is human behaviour that determines the outcome. Scientists are usually not equipped to deal with human behaviour. Their solution for behaviour change is ‘to tell people what’s out there’, or ‘to give them the facts’. In practice, this is an ineffective strategy for change, as has been shown time and again with respect to smoking, climate change, pesticide use and so forth. Quadrant III allows the kind of thinking that can effectively combine ecological insight and knowledge about human behaviour as it affects ecological processes. In such field as entomology, irrigation, soil and water conservation, forestry, and so forth, it is increasingly realised that professionalism is impossible without moving to Quadrant III, without combining science with soft systems thinking, or with explicit insight into the ways in which ecosystem states emerge from human interaction. Such combinations of scientific and soft systems thinking are called ‘beta/gamma science’. Experience suggests that those who operate in Quadrants I or II find it impossible to understand Quadrant III, while Quadrant III encompasses the previous two.

The CIPM programme has of necessity evolved to Quadrant III, while also operating in II and I. The initial (entomological) concern with the integrated management of ‘bugs’ has expanded to (non-formal education) concern for human behaviour and empowerment. The CIPM Programme has operationalised adaptive management by developing practical ways for farmers to observe, monitor and probe their agro-ecosystems for capturing human opportunity. In this, the Programme has gone further than Holling and his colleagues themselves, who seem to have got stuck in designing large scientific computer-based simulations of ecosystems as a basis for social learning. The CIPM Programme is a practical example of beta/gamma science, a truly exciting cutting edge achievement. But its very sophistication in this respect also means that it is not easy for others to understand what has been achieved, as we already noticed with the World Bank economists referred to earlier. People whose thinking has not moved beyond II find it hard to understand the CIPM Programme. Understanding sustainable development as an emergent property of farmer interaction and empowerment has swept the Programme along to other issues, enlarged the problem definition and allowed it to embrace other crops and dimensions of sustainable livelihoods as defined by farmers themselves.

A brief note, finally, about Quadrant IV. This a bit of a difficult case. Miller was not too clear about it and called it the ‘ego-centric’ quadrant where the solution to pest problems was to ‘pray’. Perhaps this is the quadrant that provides a home for those who consider spirituality as a key ingredient in ecological rationality and as the step beyond soft systems. In that view, linking explicit discursive consciousness to deeper layers of implicit knowledge and transcendental consciousness is a necessary condition for moving beyond the blinding insight of beta/gamma science.

Abraham Maslow, who has analysed religious peak experiences of a large number of people whom he met during his career as a (humanist) psychologist, names the following key aspects reported by most of his respondents:

- the clear perception that the universe is one whole of which one is an integral part;

- non-judgemental, or comparative, total acceptance of everything;

- we are lifted to greater than normal human heights and able to see things beyond normal human concerns;

- the experience justifies life as such, the world is experienced as good, beautiful, and never as bad or undesirable. Existence becomes sufficient in itself.

‘The complete human person at certain moments is able to perceive the unity of the cosmos, to fuse with it and rest in it, for the moment totally satisfied in his desire for being at one’. It seems that such spirituality is the wellspring of ecological rationality. In this view, ecological rationality is not only a self-serving interest in survival, but also the practical implication of the experience of our essence. Paying attention to such spirituality is not altogether alien to an Asian IPM Programme. So far, CIPM seems not to have seriously moved into Quadrant IV.

Conclusion

This brief effort to describe the conceptual basis of the CIPM Programme should be sufficient to underpin the Mission’s conviction that this programme does indeed represent renewal. It has forged ahead to develop concrete practice for issues that others, as indeed some of the members of the Mission, have only been able to address theoretically. The current state of widely shared human knowledge does not allow humanity to think about the design of global society in other terms than technical fixes and economics. But there is no technical fix for the self-inflicted eco-challenge that we have brought upon ourselves. Nor is the global market likely to help us deal with it. We shall need ‘a third way’, a widely shared understanding of global ecosystems as human artefacts. CIPM is one of the rare human undertakings that is experimenting in practice with this ‘third way’ and that has demonstrated how ecological rationality can be operationalised in practice. In that sense, it is a truly exciting undertaking that deserves to be given room and chance to evolve.

##### Annex 2 Terms of Reference
Mid-Term Review Phase IV

I. Background

The Inter-Country Programme for IPM in rice (ICP) was launched in 1980 and subsequently received core funding from the Governments of Australia and the Netherlands over a period of more than 15 years (Phases I, II and III). Additional funding was provided from the Arab Gulf Fund (Phase II) and the Swiss Government (Phase III). During this period the Programme helped member governments and NGOs to develop IPM Programmes which trained over a million farmers.

In earlier phases of the Programme, FAO played a pioneering role in developing and advocating IPM methodologies, and was the primary source of expertise and funding for pilot field activities in member countries. Subsequently, FAO helped to create the training capacity which allowed Governments to launch National IPM Programmes.  As the Programme achieved one set of objectives, new goals were formulated which took advantage of the capability and interest generated.

The current situation is very different from the one that existed 20 years ago, or even 5 years ago. The effectiveness of IPM as a technology for use in rice is now well established.  It is also widely accepted that Farmer Field Schools are an effective approach for training farmers in how to implement IPM in the context of growing a healthy crop. In some ways, the IPM Field School has become part of the mainstream of agricultural development in Asia. National IPM Programmes have not only started in a number of countries, they are now facing up to the challenges of institutionalisation. NGOs are helping to develop previously unforeseen applications for IPM, such as IPM in schools or for handicapped farmers, and are now seeking support for the expansion of these activities.  Some donors are increasing their funding for IPM training, while others may be losing interest.  Meanwhile, IPM farmers are starting to form their own groups and develop their own agenda for action in ways that create new challenges for government agencies, NGOs and donors.

The Programme Document for Phase IV was approved by FAO following a meeting with representatives of the member countries and donors held in Bangkok in February 1997.  Phase IV officially started in January 1998 at which time the Regional IPM Office moved from Manila to Jakarta.

The Programme Document for Phase IV has a budget of US$ 34,609,904. Three bilateral donors were approached to support the Programme.  Agreements for regional funding were reached with the Governments of Australia and Norway. In addition, the Government of Netherlands has been funding activities in Cambodia, China, and Sri Lanka through country-specific agreements. The attached table provides a summary of the projects which make up the Programme during Phase IV.  To date the total amount which has been provided by the donors is US$22,844,908.

During the last two and a half years, the Programme has given emphasis to ‘Community IPM’ which involves farmers managing their own IPM activities. These activities include: participatory needs assessment and planning; the conduct of field studies and exchanges of technical information; farmer-to-farmer training based on the Field School approach; the formation of clubs and associations to represent the interests of IPM farmers; local and national advocacy on IPM and other issues affecting rural livelihoods. As part of these community-based activities, IPM often encompasses a number of agro-ecological concerns (bio-control, soils, and seeds) and different social groups (men and women farmers, school children, the disabled).

II. Purpose of the Review

This review of the Programme is being carried out in accordance with section H2 of the Programme Document, which states “A more comprehensive review of the project will be carried out in the third year of Phase IV, with the involvement of outside experts. The Mid-Term Review will assess the progress which has been made and, if necessary, propose modifications in the design of the project. The Review Mission will include field visits to selected  member countries. Team members and their Terms of Reference will be approved by FAO headquarters and the donors, based on short-lists and drafts prepared by the Regional Coordinator. ICP experts will provide support to the review team in the form of background papers and consultations.”

The Inter-Country Programme, in addition to National IPM Programmes, such as the one in Indonesia, have been the subject of a number of reviews and evaluations. The Mid-Term Review of Phase III (August 1996) gave special attention to three issues: the geographical and technical scope of the Programme; IPM and community development; and policy directions. The results of that review greatly influenced the formulation of Phase IV.  It is not intended that the current Review should repeat this earlier work. Nevertheless, a review is needed which will take account of both the lessons that have been learned in the last three years and the availability of resources during the second half of the project.

The second half of the current phase could, if justified by results, be revamped to include revised modalities, focus and priorities in order to build on progress to date and face new challenges working with reduced resources and new forms of partnership. This Review will thus assist management in deciding on:

- staffing, activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

- the desirability of, and options for, further technical and financial assistance which could consolidate current work and expand into areas of emerging opportunity and priority.

III. Scope of the Review

- The mission will assess:

  - the degree to which the Programme is appropriately designed, to ensure:

    - clarity of objectives and goals, focus and realism in the overall Programme and in the individual areas of work and country programmes;

    - clarity and logical consistency between, inputs, activities, outputs and progress towards achievement of objectives (quality, quantity and time-frame and the extent to which indicators are in place to verify progress).

  - in the light of the overall role played by the Programme to date (Phases I to IV) and its broad effect on the development and application of IPM in the Asia Region, the relevance of the Programme results to evolving needs, including systematic assessment of:

    - the actual work carried out during the present phase in relation to planned outputs and objectives (but also including unplanned work);

    - the likelihood that remaining planned outputs will be produced in accordance with the project documents and effects achieved, in the light of the financial and human resources available to the Programme);

  - the sustainability of achievements to date, including:

    - expansion of the Programme’s approach, coverage and expansion into sub-sectors beyond IPM (adoption and replication by government, NGOs, farmers organizations and donors);

    - continuance, once established, of programme approaches and techniques by individual communities and groups of farmers and spontaneous spread of programme approaches to other farmers;

    - institutional and policy changes by government conducive to IPM including those with respect to pesticides;

    - potential for graduating countries from the programme to self-reliance where the IPM programme in rice is now self-sustaining;

    - programme impacts, if any, on research and on the wider development agenda;

    - in the light of the above sustainable programme impacts on the environment;

  - the relevance and effectiveness of the Programme’s approaches, particularly in terms of:

    - improving food security, poverty alleviation and promoting sustainable rural livelihoods;

    - the economic sustainability of IPM approaches at farmer level;

    - the potential applicability of the farmers’ field school approach in different categories of poverty situation to work with the eco-system/production system;

    - strengthening civil society and rural empowerment;

    - enhancing gender balance in development;

    - agricultural systems, rural development and environmental education;

    - education, awareness and practice for health and safety;

    - conservation of biodiversity;

    - influencing policies;

    - viability at national level of IPM approaches for food security and in economic terms;

    - participatory development of technologies, systems and approaches;

  - the cost-effectiveness of the Programme including the appropriateness of arrangements to facilitate partnerships, networking and efficiency.

- Recommendations will be made for:

  - changes that are needed in either the design of the programme, the strategies which it employs, and/or the areas on which it focuses during the remaining two years of Phase IV in order to ensure the consolidation and sustainability of achievements to date;

  - particular tasks or results which need to be given high priority for completion and/or establishment on a self-sustaining basis over the next two years with phasing out of assistance;

  - possible arrangements and approaches for longer-term cooperation between FAO and other partners at national and international level (including established national institutions) which will enhance the impact and sustainability of the Community IPM Programme after the completion of Phase IV;

  - any further assistance which may be justified on the basis of the review from FAO and donors (any specific action which should be taken to initiate new projects and/or extend the existing Programme), including:

    - clear articulation of objectives and priorities for differing levels of resource availability;

    - suggestion of any new modalities to be explored.

An annex summarising inputs and the activities supported in each country by each donor will be included.

IV. Composition of the Review Team

The review team will consist of six members as follows:

Team Leader

Mission member approved by Australia

Mission member approved by Netherlands

Mission member approved by Norway

Representative of the countries participating in the Programme

Staff Member from FAO Evaluation Service (PBEE).

The Team Leader should be internationally recognised in his or her field.  The person should have at least 15 years experience in agricultural development and be familiar with programmes and policies of governments and donors in Asia.  Between the Team Leader and the other mission members there should be least expertise in each of the following fields: i) IPM, ecology and natural resource management; ii) education and extension; iii) rural development policy formulation and planning; iv) agricultural production systems.

V. Programme and Itinerary for the Mission

The Review will take place for 4-5 weeks in November 2000. The indicative programme of the mission will be as follows:

3 days	Briefings Jakarta and the ICP, plus team discussions

2 weeks 	Break in groups for visits to member countries

4 days 	Finalisation of mission report, including findings and recommendations - Jakarta.

1 day 	De-briefing of entire mission – RAP

1 day		De-briefing mission leader - Rome

At the convening of the mission in Jakarta, under the direction of the mission leader, areas of responsibility for assessment and report writing, in addition to the country visits will be assigned to mission members, it being recognised that the review mission report is a single document, representing the views of the mission as a whole.

It would not be practicable for the members of the Review Team to visit all twelve member countries that are involved in the Programme. Consequently, an itinerary will be drawn up which focuses on the six countries where the Programme has assigned international experts. Progress reports for other countries will be available to the Review Team.

During the mission, the members will be divided into pairs, each of which will visit two countries. This will ensure that sufficient time is available for field visits and meaningful discussion in the countries which are visited

VI. Consultations

It is the intention that the mission findings and recommendations will be agreed by the whole team and the report finalised before the mission disperses and that these will be discussed in detail with Programme management and the operations and technical staff from RAP. The mission will complete its report in Jakarta and then proceed to RAP for one day of de-briefing. Ideally the mission should provide an opportunity for a process of open thinking on the future of the Programme.

During country visits the mission will maintain close liaison with the Representatives of the donors and FAO and the concerned national agencies, as well as with national and international project staff. Although the mission should feel free to discuss with the authorities concerned anything relevant to its assignment, it is not authorised to make any commitments on behalf of the governments and donors participating in the Programme or FAO.

VII. Reporting

The mission is fully responsible for its independent report which may not necessarily reflect the views of the governments and donors participating in the programme or FAO. With some room for flexibility, the report will be written in conformity with the following headings:

Executive summary (maximum 2 pages)

Introduction

Major Findings and Recommendations

Background to the Programme

Programme Objectives and Their Relevance

Programme Design

Summary of Programme Implementation (including Budget and Expenditure)

Programme Results including:

Outputs

Development Process

Programme Effects and their Sustainability and Impact

Cost effectiveness

Lessons Learned

Annexes as required, including:

- Country Reports (x 6 – which should concentrate on conclusions and not description)

- Summary by donor of inputs and activities supported in each country

- Terms of Reference

The findings and recommendations will be completed and agreed prior to termination of the mission. The report also will be completed to the maximum extent possible. The mission will also complete the FAO Project Evaluation Questionnaire.

Bangladesh, Cambodia, China, India, Indonesia, Laos, Malaysia, Nepal, Philippines, Sri Lanka, Thailand, Vietnam.

Pesticides are chemicals that are used as biocides to suppress unwanted organisms. They include herbicides, fungicides, bactericides, insecticides, rodenticides, and so forth. Usually the ‘active ingredient’ in a pesticide is also toxic for other organisms than the one for which it is intended. The herbicide Paraquat, is a favourite means of suicide in some Asian countries. In rice, the main pesticides used are insecticides. Pesticide use can usefully be examined in the context of different approaches to pest management: (1) industrial and green revolution; (2) IPM; (3) organic agriculture (M. Pimbert (1991). Designing Integrated Pest Management for Sustainable and Productive Futures. London: IIED, Gatekeeper Series 29).

The excellent records kept by Sri Lanka show that pesticides are an important means of committing unpremeditated suicide.

In Sri Lanka this included milling, seed production and insecticide-free rice production. In China considerable emphasis was placed on the development of labelled IPM food crops for sale.

World Education in Nepal has followed up functional literacy classes with FFS.

Exceptions were Bangladesh, Cambodia, Laos, Thailand and the Mahaweli Authority in Sri Lanka.

In Vietnam, funds at the district level have been freed for IPM by shifting funds from other budget items.

Including national chapters of international NGOs, such as World Education, Care and CIDSE.

For example in a paper prepared for the Development Economics Group of the World Bank, Quizon, Feder and Murgai, (September 2000) indicate a cost per farmer of at least US$62 for IPM training derived from Indonesia data which includes international technical assistance and takes no account that trained trainers become a continuing resource for training long after the project is finished or that not all the training was directly for FFS. In fact, incremental cost of training funded at the local level in Indonesia is currently US$ 8 per head. Defenders of FFS quote only this incremental cost of training an individual farmer in low-cost situations such as Vietnam, where the figure would be around US$15 or Sri Lanka where it is US$8 in projects. Discussion also revolves around over and understatement of the effectiveness of farmer-to-farmer training and diffusion effects on which evidence remains poor.

National programme funding by the Netherlands did support work in China and to a smaller extent some work in Cambodia and Sri Lanka.

Van Schouwbroeck, F. (1999). Learning to Fight a Fly: Developing Citrus IPM in Bhutan. Wageningen: Wageningen University. Published Doctoral Dissertation. Van Schouwbroeck is now working in Nepal with SNV.

Hamilton, N.A. (1995). Learning to Learn with Farmers. An Adult Learning Extension Project. Wageningen: Wageningen University, Published Doctoral Dissertation. Also appeared as a report of the Department of Primary Industries, Brisbane, Queensland, Australia

J. Quizon, G. Feder, and R. Murgai (2000). A Note on the Sustainability of the Farmer Field School Approach to Agricultural Extension. Washington: World Bank, Development Economics Group.

The figure is based on original work by Miller. (A. Miller (1983). The Influence of Personal Biases on Environmental Problem-Solving. Journal of Environmental Management, 17: 133-142; and Miller, A. (1985). Technological Thinking: Its Impact on Environmental Management. Environmental Management 9 (3): 179-190. Miller developed his ideas based on his experience in working in a major Canadian programme to combat the Spruce Bud Worm in the forests of New Brunswick. His ideas were elaborated by Bawden, R. (1997). The Community Challenge: The Learning Response. Keynote Plenary Address to the Annual International Meeting of the Community Development Society, Athens (Georgia), July 1997; and Röling, N. (2000). Gateway to the Global Garden. Guelph: University of Guelph, Eighth Annual Hopper Lecture.

Holling, C.S. (1995). What Barriers? What Bridges? Chapter 1 in: Gunderson, L.H., C.S. Holling and S.S. Light (Eds.). Barriers and Bridges to the Renewal of Ecosystems and Institutions. New York: Colombia Press: 3-37.

Jiggins, J. and N. Röling (2000 in press). Adaptive Management: Potential and Limitations for Ecological Governance. International Journal of Agricultural Resources, Governance and Ecology (IJARGE) 1 (1): .

Constructivism is based on new biological understanding of how organisms perceive (Maturana, H.R. and F.J. Varela (1987, and revised edition 1992). The Tree of Knowledge: The Biological Roots of Human Understanding. Boston (Mass.): Shambala Publications). There is no way for an outside reality to project itself on the nervous system or mind in such a way that an objective ‘truth’ can be claimed. Our understanding of the world around us must necessarily be based on a language active construction process that is based on learning, reasoning, experimentation and so on. Research is one approach to reality construction. Thomas Kuhn has established the constructivist nature of science by describing how paradigm shifts take place when a ‘normal’ science within the blinding insight of a quadrant slowly becomes untenable as a result of inconsistencies with the context. We then enter a ‘post-normal science’ phase. CIPM typically belongs to post-normal science in that it has moved beyond the confines of a positivist epistemology. (Kuhn, T.S. (1970). The Structure of Scientific Revolutions. 2nd Ed. Chicago: University of Chicago Press).

Checkland, P. (1981). Systems Thinking, Systems Practice. Chicester: John Wiley. Checkland, P. and J. Scholes (1990). Soft Systems Methodology in Action. Chicester: John Wiley.

In classical practice, the humanities were generally denoted as ‘alpha’, while the natural sciences where referred to a ‘beta’. Social sciences, such as sociology, economics, and psychology, and their applications to planning, management, etc., have been called ‘gamma’ sciences.

Maslow, A. (1964). Religion and Peak Experience. West Lafayette: Kappa, Delta, Phi.