Appendix 2

FAO Inter-Country Programme for Community IPM in Asia

Phase IV Mid-Term Review 2000

Report on Norway’s Contribution

GCP/RAS/172/NOR

Addendum Contributing to the Inter-Country Programme for IPM in Asia

(Note: For Overall Findings – see Main Report)

Contents

page

A.	Funding and Use of Funds	2

B.	Summary of Outputs to Which Norwegian Finance Contributed	3

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Funding and Use of Funds

- Summary Tables 1 and 2 estimate the use of Norwegian funds by programme objective and country. Summary Table 2 is a sub-set of Summary Table 1 providing the breakdown of the regional component by country where individual countries benefited from staff visits, work by consultants, attendance at meetings, etc. Some 34% of regional-level expenditures benefited all countries (publications, website, information exchange, etc.).

- Some US$ 5.1 million of the Norwegian budget of US$ 10 million has been expended to date. Norway’s contributions at country level were devoted primarily to work in Nepal and Vietnam. Slightly over half the total expenditure was in Vietnam and 24% benefited the regional component. There was very limited expenditure under Immediate Objective 5 - Enhancing Broader Awareness of IPM. In China, and for the most part in Laos and Sri Lanka, funds were devoted only to Immediate Objective 1 - Developing and Implementing Training Capability. Regional funds also indirectly supported the Programme as a whole, including inter-country exchanges, technical support and information. The work on policy has only recently begun to receive more attention with the appointment of a senior expert.

- With the availability of bilateral DANIDA funding in Vietnam, it became possible to utilise funds from the Norwegian unallocated reserve for work in Sri Lanka (2.2% of Norwegian total financing). In the view of the Mission, this has contributed to valuable progress there. Permission will now be sought from Norway to undertake further expenditures in Sri Lanka, and this is recommended by the mission (see Sri Lanka Appendix). It is also recommended that in view of the reduced call on the Norway allocation for Vietnam (as a result of the DANIDA funding), work in Laos and particularly in Nepal, receive support at a higher level than originally envisaged.

| Summary Table 1: Estimated Distribution of Expenditures to Date by Objective and Country (includes Regional Activities Directly Benefiting Individual Countries and Those Benefiting All Countries - REG) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Countries* (and Regional) | CMB | CPR | LAO | NEP | PHI | SRL | VIE | REG | Total |
| Estimated expenditure to date US$ million | $0.08 | $0.16 | $0.21 | $0.49 | $0.05 | $0.12 | $2.75 | $1.21 | $5.07 |
| 1. Developing and Implementing Training Capability | 20% | 100% | 90% | 70% | 50% | 80% | 50% | 4% | 44% |
| 2. Developing and Implementing Community IPM | 50% | 0% | 0% | 10% | 50% | 10% | 24% | 32% | 23% |
| 3. Developing Field Management Capacity | 20% | 0% | 5% | 10% | 0% | 0% | 12% | 8% | 10% |
| 4. Improved Policy, Planning and Programme Development | 5% | 0% | 5% | 10% | 0% | 10% | 12% | 52% | 20% |
| 5. Enhancing Broader Awareness of IPM | 5% | 0% | 0% | 0% | 0% | 0% | 2% | 4% | 2% |
| Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| * CMB = Cambodia; CPR = China; LAO = Laos; NEP = Nepal; PHI = Philippines; SRL = Sri Lanka; VIE = Vietnam; REG = Regional ** Activities in Philippines were for developing IPM in schools and integrated soils management (as envisaged in regional component) |  |  |  |  |  |  |  |  |  |

| Summary Table 2: Estimated % Distribution of the Use of the Regional Contribution (US$ 1.21 million) in Countries and that Portion which is attributable to Work in all Countries |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | BGD | CMB | CPR | IND | INS | LAO | MAL | NEP | PHI | SRL | THA | VIE | All |
| 1. Developing and Implementing Training Capability | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4% | 0% | 0% | 0% | 0% | 0% |
| 2. Developing and Implementing Community IPM | 0% | 4% | 2% | 0% | 3% | 0% | 0% | 0% | 0% | 1% | 3% | 5% | 14% |
| 3. Developing Field Management Capacity | 0% | 2% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 3% | 0% |
| 4. Improved Policy, Planning and Prog. Development | 1% | 2% | 2% | 3% | 3% | 2% | 1% | 7% | 1% | 7% | 3% | 4% | 16% |
| 5. Enhancing Broader Awareness of IPM | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4% |
| Total: 100% | 1% | 8% | 6% | 3% | 6% | 2% | 1% | 11% | 1% | 9% | 6% | 12% | 34% |
| *BGD = Bangladesh; CMB = Cambodia; CPR = China; IND = India; INS = Indonesia; LAO = Laos; MAL = Malaysia; NEP = Nepal; PHI = Philippines; SRL = Sri Lanka; THA = Thailand; VIE = Vietnam; All = Regional expenditures benefiting all countries |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Summary of Outputs to Which Norwegian Finance Contributed

- Note that as more than one source of funds was used in the countries to which Norway contributed, except Laos and Vietnam it has not always been possible to split out specific outputs as being attributable to Norway (for the performance of the overall Programme –see Main Report).

|  | Outputs as per Project Document |  | Progress at Mid-Point of Phase IV 1998-2000 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Objective 1: Self-reliant training capability where it does not yet exist within government agencies and/or non-government organizations which are planning or managing Community IPM programmes in member countries. |  |  |  |  |  |  |  |
|  | Summary of Training During Phase IV in Countries Visited by The Mission |  |  |  |  |  |  |  |
|  |  |  |  | Cambodia | China | Nepal | Sri Lanka | Vietnam |
|  | Farmer Field Schools (FFS) |  |  |  |  |  |  |  |
|  | No. of FFS |  |  | 681 | ~988 | 271 | 214 | 1,999 |
|  | No. of Trainees |  |  | ~18,400 | ~29,192 | ~ 6,000 | 4240 | ~50,000 |
|  | No. of Women |  |  | N/A | ~ 8,000 | ~ 200 | N/A | ~19,500 |
|  | Non Rice FFS |  |  | 92 | ~15 | 0 | 0 | 174 |
|  | Training of Trainer (TOT) Courses for Goverrnent and NGO Staff |  |  |  |  |  |  |  |
|  | No. of TOT |  |  | 4 | 9 | 2 | 1 | 0 |
|  | No. of Trainees |  |  | 151 | 271 | 71 | 32 | 0 |
|  | No. of Women |  |  | 55 | N/A | N/A | N/A | 0 |
|  | Non Rice TOT |  |  | 3 | 0 | 0 | 0 | 0 |
|  | Farmer TOT Courses |  |  |  |  |  |  |  |
|  | No. of FTOT |  |  | N/A | ~58 | 0 | 11 | 34 |
|  | No. of Trainees |  |  | 250 | ~1,699 | 0 | 230 | 1,276 |
|  | No. of Women |  |  | N/A | ~500 | 0 | N/A | 459 |
|  | Non Rice FTOT |  |  | 200 | ~3 | 0 | 0 | N/A |
|  | Summary |  |  |  |  |  |  |  |
|  | No. of Farmers |  |  | ~ 20,000 | ~29,192 | ~ 6,000 | 4,240 | ~50,000 |
|  | No. of Govt. Trainers |  |  | 150 | ~387 | 71 | 32 | 0 |
|  | No. of Farmer Trainers. |  |  | 450 | ~1,699 | 0 | 230 | 1,276 |
|  | Overall approximate totals: Trained Farmers: 72,000; Government trainers: 2040; Farmer Trainers: 3400 |  |  |  |  |  |  |  |
|  | In Vietnam 83% of all rice growing villages have had at least one FFS and 4% of all Vietnamese farm households have had a family member trained in a rice IPM FFS. |  |  |  |  |  |  |  |
| Outputs: Trainers capable of managing season-long TOT courses without outside help. |  | For total number of trainers and trainees see above table. There are also substantial numbers of trainers from previous phases, especially in Vietnam, so the number of trainers available for continuing expansion of the Programme is substantially higher. In Vietnam, there is now seen to be little need for further training of government trainers as an adequate number are available. In all of the countries, government trainers carry out CIPM training as part of their official duties. In China, each province in the Programme has a structure of IPM Committees from the provincial level down through the counties and townships. However, only in Sichuan would there appear to be a well- institutionalised core group of trainers at the provincial level. |  |  |  |  |  |  |
| Objective 2: Developed content and methods of Community IPM activities appropriate to different farming systems and social conditions |  |  |  |  |  |  |  |  |
| Curricula available for specific farming systems and community needs |  | Work to date has concentrated on paddy rice production with relatively small amounts of work on other crops, particularly vegetables and commercial crops (such as tea and chillies). The close links to the regional vegetable and cotton IPM programmes have facilitated this. Rice IPM is fully covered and curricula are flexibly adjusted in most of the countries each season. Curricula are also designed for the different provinces in each country. An exception seems to be Nepal, where the materials used were from the inter-country Programme. The Mission did note with concern that sometimes materials seemed to concentrate on insect ecology and material was limited, dealing with other pests (such as weeds and fungal and micro-biological pests). Similarly, such subjects as water management and fertiliser, although apparently covered in courses, were not always included in the guides. Business analysis was often not a prominent part of the training. This may contribute to the Mission’s impression that there could be a fall-back to traditional pedagogic methods in some situations. The exceptions are Cambodia and Vietnam which are generally more developed in all respects than the other countries: Cambodia: Curricula cover - plant nutrient management; gender equity; crop- specific technology; on-farm production of pathogens by farmers; rodent management; health and pesticides; and three cropping systems - single crop rice, vegetables, and mung bean. Other activities of particular interest included 4 FFS for the handicapped; Vietnam: Curricula have been developed for: biological studies (including parasites, NPV, Bt); composting; management of soil-borne disease in vegetables; rat management; vegetables; gender; cotton; rice-fish. The following farming systems are covered by curricula: rice-rice; rice-rice-secondary crop (potato; sweet potato; maize; vegetable); rice-secondary crop-rice; industrial crops (soybean-cotton; maize-cotton); and rice-fish. Farmers have developed curricula for: plant genetic resources, including, seed rehabilitation, line selection, variety evaluation and plant breeding. |  |  |  |  |  |  |

| Action research completed by IPM farmers, in collaboration with specialist organizations, which increases the scope and depth of agro-ecological understanding. | Action research has been formally initiated in Cambodia, and Vietnam: - In Cambodia, there have been 47 Action Research (AR) activities (29 on rice and 18 on vegetables). Thirty of these took place in the last wet season. Supported by UNDP, “Farmer Life Schools” have been piloted in 6 locations using approaches and methods adapted from FFS to observe and analyse the social situation within the community. - In Vietnam, there have been 1,171 farmer field studies, focusing on crop management problems, e.g. density, variety evaluation, fertilizer choice and management, and seed rehabilitation. Approximately 800 farmers in 19 provinces participated in farmer-participatory evaluation of IPM programme impact in CIPM villages focusing primarily on economic and qualitative indicators of changed agronomic practices. Elsewhere, the Mission was able to verify that some serious trial work had taken place, but some lacked discovery learning and resembled on-farm trials. Trials also seem to have reinforced some useful practices, such as incorporation of rice straw and composting. |
| --- | --- |
| A range of Community IPM activities designed tested and documented in collaboration with government agencies and/or NGOs . | NGO involvement has varied. In China and Vietnam, traditional bodies, such as the Women’s and the Youth Unions could be important. In Sri Lanka, the NGO Sarvodaya was involved in training. There was little work with other departments or projects to make use of CIPM methods, but in Anhui, China, trainers were used to assist in the Dutch-assisted poverty alleviation programme. In Cambodia, training in CIPM has been provided to NGOs such as NPA, World Education, CRS, Concern, Oxfam Quebec, ADRA, EU/Prasac and CAAEP. In Nepal, NGOs were heavily involved in training with World Education being contracted to carry out 18 FFS and to develop an NGO network as a model for expansion of FFS in Nepal. As well as World Education, the National IPM programme also works with other NGOs: CARE International (4 FFS), two local NGOs, CEAPRED (1 FFS) and SEWA Nepal (1 FFS). With the perspective of longer-term collaboration, the Programme also worked with CEAPRED to develop a vegetable IPM curriculum. World Education has developed curricula for credit and health based on IPM principles. |

| Fora for communicative action established by/for farmers and community groups engaged in IPM activities | Training material was developed on participatory planning and master trainers courses held in Cambodia, Sri Lanka and Vietnam. FFS members gained in confidence, analytical and communication skills. Farmers were trained in facilitation skills as part of FTOT (see above). Many Farmer-Trainers were previously in some form of leadership role within the community but many were not, and in all cases their capacity to make a contribution to local debate has been increased. This is particularly important in the case of women, who are forming an increasingly large proportion of trainees. It is clear that the leadership of FFS closely overlaps that of other village organizations and institutions. It seems likely that in many cases leaders joined the FFS rather than becoming leaders after the FFS experience, but some of the latter has probably occurred. This cross-over of leadership has facilitated the rejuvenation of the other organizations and their use to pursue the resolution of problems defined by the FFS members. Community IPM activities are only beginning to develop. Groups often continue to exist after the FFS and concentrate on helping their neighbours with IPM and extending IPM to other crops. Farmers identify needs for common action on soil preparation, planting and varieties in order to conserve water and to reduce the risk of heavy build-up of pests in isolated fields at the beginning or end of the season. In some cases, farmers also reported that they had rediscovered old practices of communal work. To date, community-level activities identified by farmers outside Indonesia concentrate on improvement of agronomic practices, irrigation, and in some cases marketing, including the development of IPM products. For example, in Vietnam 79 groups worked with disease management, 166 with rat management, 100 with soyabeans and 10 with rice seed. IPM clubs/associations have been widely formed but most of these have not undertaken activities outside their own villages and there seems in some cases to have been a significant top-down element with government trainers forming the leadership. In Vietnam, CIPM has focused on 4 villages in each of 19 provinces which have worked together in TOT, joined in regular monitoring and quality control, and collaborated on field studies. However in Vietnam, IPM clubs have not been financed by the Programme. |
| --- | --- |

| Objective 3: Strengthened management capability for Community IPM programmes within member countries, and improved cooperation among member countries to sustain this capability |  |
| --- | --- |
| Field leaders and trainers with the knowledge, skills and experience required to plan, organise, coordinate and support a wide range of Community IPM activities | In all countries, except Cambodia, Nepal and Sri Lanka, the Programme is nationally managed and has begun to leave the project mode. The development of curricula and the work programme is undertaken primarily by nationals. Institutionalisation has often occurred primarily at provincial and local levels. This is the case in Sri Lanka where the Mahaweli Irrigation Authority is also important and in China and Vietnam. This now reflects itself in quite substantial financial support being mobilised at the local level in these countries. In Vietnam, an estimated 54% of all rice FFS and 60% of all follow-up activities nation-wide were funded from government or other local resources. In all countries, some senior staff have benefited from attendance at inter-country programme meetings. A Team members, have undertaken training assignments in other countries which have enhanced their skills. These are especially from Indonesia, but also from China and Vietnam. The total number of trainers is referred to above, i.e. in excess of 2,000 government trainers for the countries visited. |
| Objective 4: Improved ability of policy-makers and planners to initiate, support and evaluate Community IPM programmes |  |
| Case studies of Community IPM activities, prepared and made available to planners, programme managers and trainers. Studies of special issues completed and results made available as inputs for policy making. | National workshops and studies on pesticides and the health of the farmers have been initiated in an action research framework in Cambodia, Nepal, Sri Lanka and Vietnam. National workshops were also organized (in Vietnam there was a TOT for health). Other case studies include: - Cambodia: Impact of IPM training, Landlessness and Impact of IPM training, Rat and Crab farmer management practice, FTOTs and their contribution to the civil society; - Sri Lanka: Impact Study on Integrated Pest Management Programme in Sri Lanka by a private consultant and Measuring Cost-Effectiveness by the NGO Sarvodaya; - Vietnam: An in-depth study guided by an external consultant of the profitability for farmers of IPM in rice in five provinces; development of IPM system for Brown Plant Hopper (BPH) management in a problem area of unexplained periodic outbreaks - 3-year study, 50-50 cofinanced by FAO-IPM and Ho Chi Minh City; and also studies of training of farmer trainers and IPM activities; Community IPM in Yen Phuong Village; IPM Clubs and Community IPM Programme in Dong Thap Province; Women in IPM Programme-Quang Binh Province. |

| Advice to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects. Assistance to member governments and donors when mutually agreed in programme execution. | The staff member responsible for policy work has only just been appointed. All the concerned line agency staff know about the Programme. Parliamentarians and ministers probably are generally not aware of details, but senior figures often attend field days. In the majority of cases, senior staff responsible for extension, and sometimes for IPM, do not fully understand the total implications of FFS, as distinct from discussions at a demonstration. Advice and support have been provided to the government by the Programme staff stationed in Vietnam. Examples of technical support include: crop loss assessment field studies on leaffolder in 3 provinces, and BPH in 2 provinces to demonstrate to local agriculture officials that they should raise their thresholds for instructing farmers to apply pesticides during outbreak periods. Gender: Work in gender and related issues in addition to the high level of women’s participation in FFS, has included a: - case study on gender and IPM in Nepal; - a workshop in Sichuan China on gender and IPM in 2000. China was able to disseminate the benefits of its progress in mainstreaming an emphasis on women in a workshop which included both the other provinces of China, and Laos and Vietnam. |
| --- | --- |
| Objective 5: Enhanced awareness in member and donor countries about Community IPM activities in Asia |  |
| Information on Community IPM available to the scientific community | There is contact with scientists in China and Vietnam and to a more limited extent other countries for curriculum development and involvement in farmer field studies. In Vietnam, a five-day scientists' and farmers’ workshop was held with five IPM researchers. Elsewhere, scientists have had greater difficulty adapting to discovery learning, as distinct from making recommendations. The Programme website has provided a valuable resource to all engaged in Community IPM and beyond. . |
| Information on IPM activities available to appropriate media organisations and advocacy groups | Progress in reaching the general public has been much greater. Community IPM is publicised in the local press and television. The Programme will also be covered on BBC World television. A newsletter is produced in Nepal. Support has been provided to television with footage. There has been widespread press coverage of FFS training. Examples of contacts with NGOs include the campaigning NGO-MONLAR in Sri Lanka. |