Appendix 4

FAO Inter-Country Programme for Community IPM in Asia

Phase IV Mid-Term Review 2000

China – Summary Country Report

(Note: For Overall Findings – see Main Report)

Contents

page

A: Introduction	2

A.1	The Mission	2

A.2	Status of the Programme at the Start of Phase IV	2

A.3	Support Received from the Regional Programme	3

B: Discussion of Outcomes and Impacts	3

B.1	Results in Terms of Trained Farmers	3

B.2	Impact on the Environment and Health	3

B.3	Economic Benefits to Farmers	4

B.4	Who are the Beneficiaries	4

B.5	Institutional Sustainability	5

B.6	Cost-effectiveness	6

B.7	Benefits from Regional Links	6

C: Major  Conclusions and Recommendations	6

D: Summary of Results Against Immediate Objectives and Outputs	7

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Introduction

## The Mission

- The Mission to China formed part of the Mid-term Review of the Inter-Country Programme for Community IPM in Asia. This review took place some three years into the Fourth Phase of the Five-year Community IPM Programme. The main purposes of the Review as per the Terms of Reference, were on the basis of results and experience to date to assist management in deciding:

  - staffing activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

  - the desirability of, and options for, further technical and financial assistance which could consolidate current work and expand into emerging areas of opportunity.

- The full team consisted of four independent consultants, one representative of the FAO Evaluation Service and one country representative. Three groups were formed for country visits. The two-person team visited China for one week from 11-17 November and consisted of:

- Michele P Pimberg – Consultant – Agro-Ecology specialist;

- John Markie – FAO - Evaluation Service.

- During its visit, the team held discussions with the National Agro-Technical and Extension Service Center (NATESC) in Beijing, which has overall responsibility for the Programme. Field visits were made in Sichuan Province and meetings held with the programme leaders from each of the six provinces where work is ongoing. Preliminary findings of the Mission were discussed with government authorities, representatives of concerned donor governments (Netherlands, Australia, Norway) and with FAO.

- The Mission wishes to express its appreciation to all those in China who provided such warm hospitality and who were always ready to answer questions. The Mission also wishes to emphasise that in such a short visit to such a large country and with most documentation in Chinese it had an inadequate basis for judgement and its conclusions must be treated in that light.

## Status of the Programme at the Start of Phase IV

- In China, the emphasis had been on Farmer-Field School Training (FFS) for IPM and not deepening FFS into other aspects of farm and community development. This has largely continued to be the case during Phase IV.

- In China as a whole, 80.6% of the cultivated area is under cereals and 21.8% under rice. During Phase III, the Programme had been active in 11 provinces but there was some concern both with the quality and the very dispersed nature of the coverage. The number of provinces was reduced to the five most active Anhui, Guangdong, Hubei,  Sichuan and Zhejiang. Hunan was added later but remains the least active. The provinces with a large percentage of rice excluded are now Guangxi, Hainan, Jiangxi and Fujian.

| Table 1: Characteristics of Provinces Covered by the Programme |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Agricultural Households (millions) | Number of Villages | Cultivated Land Area (million ha) | Percentage of Cultivated Area Under Rice |
| Anhui | 9.6 | 31,031 | 6.0 | 21.9% |
| Guangdong | 5.8 | 23,618 | 3.3 | 61.3% |
| Hubei | 7.7 | 33,341 | 5.0 | 37.8% |
| Hunan | 10.2 | 48,576 | 4.0 | 68.7% |
| Sichuan | 15.1 | 55,970 | 9.2 | 26.44% |
| Zhejiang | 4.0 | 44,463 | 2.1 | 61.9% |
| Source – First Agricultural Census of China - 1996 |  |  |  |  |

- During Phase IV, the concentration on rice has been maintained, although with demands from farmers and political pressures there have been moves into export crops and fruit and vegetables. It is not clear that in these cases it has always proved possible to maintain quality of training

## Support Received from the Regional Programme

- The Programme in China has been primarily funded from Netherlands Government Funds in Trust with FAO provided through the Bilateral Assistance Grant for work on the environment. Support has also been provided from the Regional Programme utilising Australian funds in trust.

# Discussion of Outcomes and Impacts

## Results in Terms of Trained Farmers

| Table 2: Summary of Training 1998-2000 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | TOT* |  | FTOT* |  | FFS* |  |
|  | Number | Trainees | Number | Trainees | Number | Trainees |
| Anhui | 1 | 25 | 5 | 108 | 50 | 1,485 |
| Guangdong | 3 | 93 | 10 | 303 | 251 | 6,943 |
| Hubei | 2 | 63 | 7 | 210 | 204 | 6,100 |
| Hunan |  | 0 | 1 | 30 | 52 (99/00) | Est. 1450 |
| Sichuan | 3 | 90 | 31 | 930 | 360 | 11,000 |
| Zhejiang | 0 | 0 | 4 | 118 | 86 | 2,214 |
| * TOT = Training of Government Trainers; FTOT = Training of Farmer Trainers; FFS = Farmer Field Schools |  |  |  |  |  |  |

- There has been a considerable improvement in the quality of training since the last review mission. Training of trainers now follows the full season model as do farmer FFS. Most materials were available only in Chinese but the Mission did note with concern that for materials available in English there was coverage only of insect ecology and no materials dealing with other pests such as weeds and fungal and micro-biological pests. Such subjects as water management and fertiliser, although apparently covered in courses ,were not included in the guides. Business analysis was only introduced at the level of the training of trainers and then very briefly. This may contribute to the Mission’s impression that there could be a fall-back to traditional pedagogic methods in some situations but learning by analysing in the field has also definitely become important and this is a revolution in Chinese extension and bureaucratic approaches.

## Impact on the Environment and Health

- The Programme has been concentrated on insecticide use rather than pesticides as a whole, including fungicides and herbicides. FFS farmers have reduced their sprays of insecticides on rice by about 50%. The use of highly-toxic pesticides appears to have been reduced to close to zero and chemical insecticides have been replaced by bio-insecticides which are widely available. There is, however, a need for better desegregated data on pesticide use by FFS farmers, their neighbours and farmers not involved in FFS.

| Table 3: Reduction in Pesticide Use by Samples of FFS Members (based on before and after and comparison with non-FFS members) |  |  |  |
| --- | --- | --- | --- |
| Province | Year to which Data Refers | Percentage Reduction in Use of Pesticides |  |
|  |  | Overall Reduction | Reduction in Highly Toxic (especially insecticides) |
| Anhui | 1998 | 34% | 93% |
| Guangdong | 1998 | 39% | 100% |
| Hubei | 1998 | 48% | 100% |
| Sichuan | 2000 | 55% | n.a. |
| Zheijang | 2000 | 26% | 94% |
| Note Anhui also showed a 58% drop in pesticide application on citrus (1999) |  |  |  |

- In addition:

  - the effects of the change in pesticide use in communities were also confirmed by anecdotal evidence such as the reduction of the number of pesticide outlets in villages;

  - several provincial and county authorities introduced additional controls on toxic pesticides;

  - there is some evidence of higher levels of bio-diversity in rice fields, in particular increased numbers of spiders, frogs, snakes and fish;

  - rice and other food products are being consumed by farmers and marketed with low or no insecticide contamination. The provinces have placed considerable emphasis on developing commercial IPM products which are in most but not all cases based on FFS;

  - there was good anecdotal evidence of reduced farmer insecticide poisoning.

## Economic Benefits to Farmers

- The application of IPM resulted in reduced costs to farmers for pesticides and increased yields due to improved crop management.

| Table 4: Net Income increases for Samples of FFS Members (based on before and after and comparison with non-FFS members) |  |  |
| --- | --- | --- |
| Province | Year to which Data Refers | Percentage Income Increase |
| Anhui | 1998 | 23% |
| Guangdong | 1998 | 20% |
| Hubei | 1998 | 18% |
| Sichuan | 2000 | 6% |
| Zheijang | 1998 | 16% |

## Who are the Beneficiaries

- The farmers benefited by the Programme are rice farmers, rather than being commercial producers of higher-value crops. The Programme has increasingly targeted women with the growing feminisation of agriculture.

- Provinces include two of the poorest, with the highest level of project activity in Sichuan in the West. The Programme had often trained those who were already active in the community either in bodies such as the Women’s Union and Youth Union or in the groups which remained from the agricultural production teams. The effect on women has been particularly important. It seems that overall the number of women being trained now make up about 30% of the total but in Anhui and possibly Sichuan they are now starting to form the majority. Anhui and Sichuan are also increasingly holding women-only FTOT and FFS with distinct advantages in allowing for expression by women, fitting the FFS to women’s schedules, common educational level and stability of the group as men are away more.

- Both these and other farmers trained:

  - possess enhanced ability to make informed decisions on pest and other aspects of crop management;

  - are active in assisting neighbours in applying IPM;

  - have improved self-confidence and capacity to participate in community organizations.

## Institutional Sustainability

- Central Government  (NATESC): The Programme is nationally managed and does not rely on expatriates for its direction. At the central level of government, there are few staff  who have grown up with the Programme and have an in-depth understanding of it. There appears to be some belief, at least as far as requests to donors, that it is possible to substitute the experiential approach for training of trainers by web-based learning. The mission believes that the web can provide a networked information resource and that refresher training on IPM and other subjects can increasingly be provided to senior government agricultural staff, teachers and researchers through distance learning. However, this can never substitute for the transformation of both attitudes and approaches which is essential in government service and can only take place through experiential learning with farmers in the field.

- It is not clear that in the absence of donor funding NATESC would continue strong central support to the Programme, but this may not be critical with increasing commitment from the provinces which are much larger than the average European country.

- Provinces: All provinces have a structure of committees for CIPM from the provincial to township levels, although the substantive levels of activity are unclear. Substantial funds have been mobilised at all levels to pay for FFS and Training of Trainers. Resources are mobilised at the provincial level, in the counties and townships. Examples of this were particularly strong in Anhui, Sichuan  and Hunan. Most of the provinces seem genuinely committed to continue the Programme in the absence of external assistance and have a body of trained-trainers now available to do this. However, only in Sichuan does there appear to be a clearly designated team of trainers.

- Farmers' Field Schools (FFS): The members of  FFS continue to share a sense of identity, particularly when some have gone on for training as trainers. They actively consult each other on IPM and other matters of farm management and seem to often feel they should share with their neighbours.

- Multiplier Effects - At the institutional level: Trained farmers are more active in village institutions. IPM organization and activity groups have been formed. It is not clear to what extent this remains a top-down process.  There is, however, little evidence of the uptake of the FFS approach by other departments, even within agriculture. Also FFS groups do not generally appear to used by other government departments for work on additional topics in agriculture or in other aspects of life such as health and nutrition.

- Multiplier Effects - At the farm level: Neighbours are evidently very interested in the improvements introduced by farmers who have participated in the FFS and trained farmers help their neighbours. Careful positioning of trainees and the selection of trainees with leadership qualities can thus help multiply the area and farmers covered but it would appear that neighbours do not acquire the observation and learning skills themselves but continue to rely on their neighbours for advice on what to do (in Sichuan this type of information provision has been formalised using FFS farmers in 30 so-called “information stations”).

- There is some evidence that trainees may go on to apply their learning  to IPM in other crops and sometimes may also apply analytical skills to other farm problems, although there is a marked dilution effect as the farmer moves further from rice and further from IPM (in Anhui and Sichuan this has been formalised in interest groups).

## Cost-effectiveness

- High-unit costs for Programme training: When training is funded by the Programme there is a significant problem of high-unit costs (US$ 900 for a full season Farmer Field School covering about 30 farmers,  US$ 4,000 for a 10-day training of trainer course for about 30 Farmers (FTOT) and US$ 50,000 for a season-long training of trainers course for about 30 government staff). There are indications that costs may be lower when courses are funded locally. The strategy of moving to much greater use of farmer trainers also has potential to reduce costs.

## Benefits from Regional Links

- Exchanges have reinforced and supported national learning by decision makers and technical staff but language remains a very significant constraint, and:

  - some experience in the regional programme has been transferred to approach in China (e.g. use of farmer trainers) and China has benefited from help with curriculum design etc., based on regional models;

  - links to other regional programmes (e.g. cotton and vegetables) have facilitated the efficient use of international staff and links between the work of the programmes in China;

  - China was able to disseminate the benefits of its progress in mainstreaming an emphasis in women in Sichuan at a workshop which included both the other provinces of China and Laos and Vietnam.

# Major  Conclusions and Recommendations

- A determined effort should be made to both institutionalise and rapidly expand the coverage of the Programme at national and provincial levels, maintaining the focus on rice which uses more than half the pesticide applied in rice growing areas, including:

  - locating funds from the international community for expanded work in the provinces;

  - work with local-level authorities for greater resource mobilisation in terms of personnel and funds to rapidly increase spread;

  - adopt a strategic node approach to increased spread in priority areas centred on TOT for the county, farmer trainers for the villages and farmer-to-farmer within contiguous farms. In the provinces currently covered by the Programme, with existing trainers (if used), 1 TOT trainer per village per season can reach around 0.2% of villages per season. If farmer trainers can be used to reach the 4 nearest villages in addition to their own, can raise the percentage to 1.0% per season. If the number of TOT trainers can be raised by a multiple of 5 and/or the equivalent of this multiple can be achieved by handling more than one FFS per season, could reach 5% of villages per season and reach 50% of villagers in 10 years which is an acceptable rate of progress);

  - work determinedly to reduce the costs of training for TOT, FTOT and FFS without sacrificing quality;

  - develop core teams of experienced trainer/development staff in each of the provinces;

  - improve monitoring and case studies. There is currently a weak level of information on both activities and their impact.

- Work with the international community to mainstream the CIPM approach to farmer learning in other programmes and projects, including those reaching poorer areas of the country. It is felt that the CIPM approach can be used:

  - in poorer areas for application of FFS to sustainable livelihoods and sustainable natural resource management;

  - in work with other departments to widen both initial FFS and the follow-up activities of FFS into other aspects of agriculture and into such areas as health. However, an FFS should still always start from one system topic as at present with the agro-ecosystem for plant pests.

- In moving into additional crops there should be a flexible approach. The greatest threat to human health and the local environment is often from pesticides on high-value crops especially vegetables, but rice covers the largest area and  probably receives most pesticides in total. Rice is also grown by the poorest and forms the bulk of the diet for the poorest. Rice is grown in water and pesticides enter the water system. An expansion into the western and poorest provinces would necessitate attention to other staple crops. In all cases there should be adequate basic information to formulate a discovery learning curriculum.

- IPM products have great potential and the emphasis on this is welcomed but these should be developed in collaboration with commercial business and sold through commercial outlets, where other food products are sold. The Mission does not believe that a strong demand will be developed through government farm-supply shops. Government should increasingly concentrate on farmer training, and quality management and control for which commercial partners should be charged.

# Summary of Results Against Immediate Objectives and Outputs

| Objective and Outputs as per Project Document | Progress at Mid-Point of Phase IV 1998-2000 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Self-reliant training capability where it does not yet exist within government agencies and/or non-government organizations which are planning or managing Community IPM programmes in member countries. |  |  | Training of Trainers – one-season Course for Government Staff |  | Training of Farmer Trainers - 10 day course |  | Training of Farmers - FFS |  |
|  |  |  | Number | Trainees | Number | Trainees | Number | Trainees |
|  | Anhui |  | 1 | 25 | 5 | 108 | 50 | 1,485 |
|  | Guangdong |  | 3 | 93 | 10 | 303 | 251 | 6,943 |
|  | Hubei |  | 2 | 63 | 7 | 210 | 204 | 6,100 |
|  | Hunan |  | 0 | 0 | 1 | 30 | 52 (99/00) | Est. 1450 |
|  | Sichuan |  | 3 | 90 | 31 | 930 | 360 | 11,000 |
|  | Zhejiang |  | 0 | 0 | 4 | 118 | 86 | 2,214 |
|  | Total estimated |  | 9 | 271 | 58 | 1699 | 1003 | 29192 |
| Outputs: Trainers capable of managing season-long TOT courses without outside help. | Most of the above training was directly supported by the Programme . Each province in the Programme has a structure of IPM Committees from the provincial level down through the counties and townships. However, only in Sichuan would there appear to be a well-institutionalised core group of trainers at provincial level. Training forms a regular part of the official duties of Agricultural Bureau Staff, although incentives are paid in the form of allowances. There has been a considerable improvement in the quality of training since the last review mission. Training of trainers now follows the full- season model as do farmer FFS. Learning by analysing in the field has become the norm and this is a revolution in Chinese extension and bureaucratic approaches. |  |  |  |  |  |  |  |
| Objective 2: Developed content and methods of Community IPM activities appropriate to different farming systems and social conditions: Outputs: Curricula available for specific farming systems and community needs; |  | Curricula have been developed centrally for rice, but there have also been curricula developed at provincial levels for many other crops including tea and vegetables. To varying degrees the provinces revise curricula each year and TOTs are useful in this: Materials include: - FTOT curriculum guide developed in 1998 and revised in each province; - refresher TOT curriculum guide developed in 2000; - TOT curriculum guides which are revised in curriculum development workshops; - An ecology field guide. Most materials were available only in Chinese but the Mission did note with concern that for materials available in English there was coverage only of insect ecology and no material dealing with other pests such as weeds and fungal and micro-biological pests. Such subjects as water management and fertiliser, although apparently covered in courses were not included in the guides. Business analysis was only introduced at the level of the training of trainers and then very shortly. This may contribute to the mission’s impression that there could be a fall-back to traditional pedagogic methods in some situations. |  |  |  |  |  |  |
| Action research completed by IPM farmers in collaboration with specialist organizations, which increases the scope and depth of agro-ecological understanding. |  | No ongoing action research facilities have been developed and research by farmer groups is not well-developed. There are a few cases of research by farmer groups. In the examples quoted to the Mission, these were primarily concerned with control measures for pests. More elaborate studies in Sichuan included: - counting spider webs as ecosystem indicators; - agronomic and irrigation practices for sheath blight in rice; - extension of IPM to citrus which included researchers. In general, these had not become action research but were rather like on-farm trials. Researchers assist with some TOTs but there seems to be little interaction beyond that. |  |  |  |  |  |  |
| A range of Community IPM activities designed tested and documented in collaboration with government agencies and/or NGOs . |  | There is little evidence of FFS being followed up by other departments of government even within agriculture or by bodies such as the women’s union for other activities. One positive example was found in Anhui, where trainers were used to assist in the Dutch-assisted poverty alleviation programme. No activities have been particularly documented |  |  |  |  |  |  |

| Fora for communicative action established by/for farmers and community groups engaged in IPM activities | FFS members gain in confidence, analytical and communication skills. Farmers are trained in facilitation skills as part of FTOT (see table). Many Farmer-Trainers were previously in some form of leadership role within the community but many were not and in all cases their capacity to make a contribution to local debate has been increased. This is particularly important in the case of women who are forming an increasingly large proportion of trainees. Community IPM activities in China are not well-developed beyond the FFS. Groups often continue to exist after the FFS and concentrate on helping their neighbours with IPM and extending IPM to other crops. IPM associations have been formed as pyramids from the village upwards and activities sometimes include competitions. In Sichuan, the structure is formalised as information stations which correspond to the 100 alumni associations. It was not possible for the mission to assess how effective these were. Elsewhere the structures appear to be as much on paper as in reality. Figures provided to the Mission were: - Anhui – 7 IPM farmers' associations with 45 affiliated interest groups (5-10 farmers); - Hubei – 28 associations in 26 villages; - Sichuan - 100 alumni unions with information station function and 30 activity groups. An important community impact is being obtained in the growing emphasis being placed on women with the feminisation of agriculture. Particularly in Anhui and Sichuan, women-only FFS are being organised and FTOT have been held for women trainers. Women are now making up the majority of trainees in these two provinces. |
| --- | --- |
| Objective 3: Strengthened management capability for Community IPM programmes within member countries, and improved cooperation among member countries to sustain this capability Output: Field Leaders and trainers with the knowledge skills and experience required to plan, organise, coordinate and support a wide range of community IPM activities | The Programme is nationally managed and does not rely on expatriates for its direction. At the central level of government, there are few staff who have grown up with the Programme and have an in-depth understanding of it. It is not clear whether in the absence of donor funding NATESC would continue strong central support to the Programme, but this may not be critical with increasing commitment from the provinces which are much larger than the average European country. All provinces have a structure of committees for CIPM from the provincial to township levels, although their substantive levels of activity are unclear. Substantial funds have been mobilised at all levels to pay for FFS and Training of Trainers. Resources are mobilised at the provincial level, in the counties and townships (e.g. Anhui – 1998-2000 US$ 181,000; Hunan – 1999-2000 US$ 96,000; Sichuan 1998-2000 US$ 243,000). Most of the provinces seem genuinely committed to continue the Programme in the absence of external assistance and have a body of trained-trainers now available to do this. However, only in Sichuan does there appear to be a clearly designated team of trainers. Three provincial leaders were trained in English and management for six months in the USA, under separate Netherlands financing. As far as the team could determine, only one of these acquired adequate English to contribute independently to work outside China. The China programme has participated in the various meetings organised regionally by the Programme with 2-3 participants in each. |

| Objective 4: Improved ability of policy-makers and planners to initiate, support and evaluate Community IPM programmes Outputs: | Outputs under Objective 4 were mainly addressed to the Inter-country programme level and limited specific actions were taken in China. |
| --- | --- |
| Case studies of Community IPM activities, prepared and made available to planners, programme managers and trainers. Studies of special issues completed and results made available as inputs for policy making. | A workshop in Sichuan on gender and IPM in August 2000 was able to disseminate the benefits of progress in mainstreaming an emphasis in women which included both the other provinces of China and Laos and Vietnam. A study tour by 13 IPM leaders primarily from the provincial level took place in California in 2000. This tour appears to have been very useful in exposing personnel to IPM and organic farming in a commercial developed country context which has quite some relevance for China. |
| Advice to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects. Assistance to member governments and donors when mutually agreed in programme execution | An adviser has been stationed in Beijing who has provided active assistance in all aspects of programme development and execution. Costs have been shared with the IPM Programme for Cotton in Asia GCP/RAS/164/EC. |
| Objective 5: Enhanced awareness in member and donor countries about Community IPM activities in Asia. Outputs: | Outputs under Objective 5 were mainly addressed to the inter-country programme level and limited specific actions were taken in China. |
| Information on Community IPM available to the scientific community | No specific action, although scientists at the provincial level are involved in TOT and to some extent in provincial committees |
| Information on IPM activities available to appropriate media organisations and advocacy groups | In all provinces, extensive use is made of the print press, radio and television to publicise the programme. |

e.g. Anhui – 1998-2000 US$ 181,000; Hunan – 1999-2000 US$ 96,000; Sichuan 1998-2000 US$ 243,000

Anhui 7 farmers’ associations group 45 interest groups with 5-10 members each; Hubei has 28 associations in 26 villages; Sichuan has 100 associations and 30 groups for information to other farmers (information stations).