Appendix 9

FAO Inter-Country Programme for Community IPM in Asia

Phase IV Mid-Term Review 2000

Vietnam – Summary Country Report

(Note: For Overall Findings – see Main Report)

Contents

page

A: Introduction	2

A.1	The Mission	2

A.2	Status of the Programme	2

A.3	Support Received from the Regional Programme	2

B: Discussion of Outcomes and Impacts	2

B.1	Impact Studies	2

B.2	Coverage	3

B.3	Insecticide Use	3

B.4	Cost-effectiveness of IPM for farmers	3

B.5	Sustainability	3

C: Recommendations	5

C.1	Approach to the Development of CIPM	5

C.2	The Remainder of Phase IV	7

C.3	The Longer Term	7

D: Summary of Results Against Immediate Objectives and Outputs	8

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Introduction

## The Mission

- The Mission to Vietnam formed part of the Mid-term Review of the Inter-Country Programme for Community IPM in Asia. This review took place some three years into the Fourth Phase of the Five-year Community IPM Programme. The main purposes of the review, as per the Terms of Reference, were, on the basis of results and experience to date, to assist management in deciding:

  - staffing activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

  - the desirability of, and options for, further technical and financial assistance which could consolidate current work and expand into emerging areas of opportunity.

- The full team consisted of four independent consultants, one representative of the FAO Evaluation Service and one country representative. Three groups were formed for country visits. The two-person team visited Vietnam for one week from 5-11 November and consisted of:

- Niels Röling – Team Leader – Agricultural and Rural Development Specialist;

- Rene Salazar – Consultant – NGO Specialist in Sustainable Agricultural Development.

- The Mission wishes to express its appreciation to all those in Vietnam who provided such warm hospitality and who were always ready to answer questions and provide information. The Mission also wishes to emphasise that in such a short visit it had of necessity to make judgements on very limited information and its conclusions must be treated in that light.

## Status of the Programme

- The Vietnam Country IPM Programme is currently the largest one in Asia in terms of budget for Phase IV and number of activities. Since its inception in 1992, it has rapidly built up a national capacity for farmer training. In order to achieve rapid outreach of training, over 35 main trainers organized TOTs for PPSD staff, between 1993 and 1996. After completing this national assignment the main trainers returned to their provinces and usually became provincial IPM team leaders. Vietnam now has 1,345 PPD technicians who are TOT-trained rice IPM trainers. In addition, some 3,000 farmer trainers are available.

## Support Received from the Regional Programme

- The Vietnam Programme has received the highest level of funding in the Inter-Country Programme with Norwegian financing, some US$ 3.2 million was provided to date during Phase IV and an international staff member has been stationed in Vietnam.

# Discussion of Outcomes and Impacts

## Impact Studies

- The CIPM Programme in Hanoi has worked to develop tools for impact evaluation, always in close collaboration with the Regional Inter-Country Programme team. An exploratory survey of the qualitative impact of CIPM, during the summer season 2000, used questionnaires mailed to Cum Tinh trainers in 16 provinces. The pilot results still leave a lot to be desired, but some interesting insights were gained and, more importantly, conclusions were drawn about how to improve the qualitative survey methodology.

- A second approach tried, during 1999-2000, was farmer participatory impact evaluation. A TOT on farmer-participatory impact evaluation was held with Cum Tinh trainers from 16 provinces. They carried out pilot exercises and the results were reviewed in a second workshop. Though the quantitative results were excellent, the qualitative ones were considered weak. Hence, a third workshop was held and further evaluation exercises were carried out with results submitted in September 2000. Most of the findings remain to be reviewed and analysed. A case study of Y Yen District, Nam Dinh Province is already available, however, based on participatory evaluation findings. This case study will be developed further as a model to be used in training.

- The Mission was impressed with the emphasis given in the CIPM Programme to quality control and endorses the need to monitor spread effects and impact evaluation as essential for a sustainable CIPM Programme.

## Coverage

- The FAO-supported IPM activities in Vietnam have had considerable impact. Eighty-three percent of all rice growing villages have had at least one rice FFS. Four percent of all Vietnamese farm households have had a member trained in a rice IPM FFS. In all, this amounts to more than half a million alumni from 10,808 FAO-funded, 5,820 locally-funded, and 3,028 other donor-funded FFS. At present, the strategy has been to hold one or two FFS in most villages and then rely on diffusion but the Programme, as yet, has little insight into the extent to which spread of effects beyond those directly trained in FFS has been achieved.

## Insecticide Use

- The use of imported insecticides in rice decreased from 2.7 kg per ha in 1991 to 2.6 kg/ha in 1998. This figure reflects the fact that so far only 4% of households in Vietnam have a member who has been trained in an FFS. Another important issue is the role of the former collectivist structures in both the use of pesticides and the acceptance of IPM. Especially in Northern Vietnam (the South had a less collectivised system), farmers were often directed to spray 100% of the production area with pesticides. The widespread acceptance of IPM has led the same leaders now to support the adoption of IPM practices. According to a qualitative impact study, IPM is high on the agendas of every village meeting in one third of CIPM villages (i.e. four in each of 16 CIPM pilot provinces), and often in the remaining two-thirds. In the south, the situation is very different in that collective decision making systems do not operate there. It would be of interest to compare the diffusion of IPM practices in both areas. It is, furthermore, likely that a battle is ongoing between the general extension and plant protection models to win the hearts of the local leaders. It is likely that pesticide companies are actively involved in this battle.

## Cost-effectiveness of IPM for farmers

- The focus on growing a healthy plant in IPM has helped increase yields and reduce pesticide costs among FFS alumni.

## Sustainability

- Funding: FAO/Norway funds for CIPM activities are being phased out. After the summer of 2001, only the three new CIPM provinces that started FAO/Norway-supported CIPM villages in the summer of 2000 will continue to receive funding. In the last three seasons, 54% of FFS were funded either locally (local government, cooperatives, farmers themselves) or by NGOs and donors, other than Norway. DANIDA has devoted US$ 8.5 million in its US$ 67 million five-year Agricultural Sector Support Programme to Community IPM (CIPM) development. Not counting the host of locally-funded IPM activities, a total of 12 other projects (including that of DANIDA), bringing in US$ 11.6 million in additional funding, operate under the National IPM Programme (10) or collaborate with it (2).

- There is no government line budget item to finance IPM activities, including Community IPM. Limited possibilities exist at the provincial level to shift funds from other budget items to IPM activities. The IPM Group in PPD Hanoi (total 4 people) receive salary supplements from FAO, which will be succeeded shortly by a letter of agreement between FAO and the PPD for the same level of funding. The Master Trainers and IPM Trainers receive a ‘Personal Services Fee’ from FAO on top of their salary for specific extra activities done. Similarly, each CIPM village receives support for activities for at least three seasons. After a village ‘graduates’ (the timing of graduation is decided by local trainers), Community IPM is expected to have become self-sustained. Such fees are also paid by other agencies (NGOs, local governments and so on), the normal practice in Vietnam, given the very low salaries and lack of incentives.

- Institutional Arrangements: The Mission has some doubts about the current sustainability of the institutional support structures established for CIPM at the national level. The PPD centre is not strong enough at present in terms of depth and numbers of people. It relies to a large extent on the dedication of one or two persons. CIPM activities are also not included in the job descriptions of PPD staff.

- At the provincial level, there is a more sustainable base, through Cum Tinh (sub-regional). This is a management structure in which 3 to 4 main trainers are assigned an area comprising their 3 – 4 provinces. Starting with 9 provinces in 1997, the Cum Tinh provinces were expanded to 19 by 2000. Community IPM, including all FFS follow-up activities and farmer organisation, is implemented in pilot villages in each of the 19 provinces. The Cum Tinh teams participated in a series of workshops and training exercises. As a result of these workshops, the following activities for Cum Tinh teams emerged:

  - regular field visits to ongoing IPM activities, which would allow evaluation, and quality monitoring, as well as organising workshops to improve training quality;

  - refresher courses for PPSD trainers and helping trainers in planning and implementing CIPM activities;

  - helping develop Community IPM programmes, including farmer field studies of production issues and pesticide related health risks;

  - consolidating provincial plans for submission to the National IPM Programme, helping to  document IPM activities, and assisting the National IPM Programme to plan, monitor and evaluate provincial CIPM.

- The Cum Tinh management structure has been unique in Vietnam. It seems to have been a very workable idea that built on the strength that had been developed in the previous years and exploited the scarce high-quality person power available to the provinces. The bringing together of the Cum Tinh teams allowed frequent workshops to address management, process and technical issues essential for moving ahead CIPM ahead. The team learned together, planned together and developed a focused approach to CIPM. Importantly, Cum Tinh allowed much needed attention to quality control and evaluation. The Cum Tinh, for example, developed: indicators for a good FFS; procedures for looking at training quality; indicators for a good farmers’ technical meeting; and a farmer training-of-trainers curriculum, combining field visits and workshops.

- A large number of IPM Trainers is now available, including a number of experienced Main Trainers. It is this cadre of professionals, and especially the latter group, that is counted upon to provide the expertise, both technical and in terms of social process (training, follow-up, farmer research, etc.), that is the pillar of the sustainability and continued quality of the National CIPM Programme. At present, a mechanism to counter potential attrition of these trainers is not easily identified. It is difficult to influence the quality of staff that is attracted. The demand on the available cadre of experienced Main Trainers by NGO projects, local government projects and farmer initiatives is beginning to stretch the supply, even though activities in one province can draw upon expertise in others.

- At the national level, the Vietnamese MARD has two main sections relevant for us: the Plant Protection Department and the Extension Department. At the provincial level (DARD), this set-up is mirrored by the PPSD and the Extension Centre. Plant Protection and Extension are equivalent in terms of position in the hierarchy. The two run parallel extension programmes.

- The PPD is responsible for the National IPM Programme, including Community IPM and is the counterpart to the FAO support unit. The Extension Department is responsible for the regular extension programme and is about to benefit from a major World Bank loan. The regular extension programme works with ‘target groups’ of farmers interested in a specific topic. It focuses on short courses and demonstrations following a transfer of technology approach. Pesticide companies work with the Extension Centres. There is a long-standing discussion about the need to amalgamate the two departments but immediate action is unlikely. The current Vice Minister in charge of IPM has given instructions that the staff of the Extension Department use the approaches developed by the Programme. There is however, continued pressure to revert to the traditional and well-understood use of the technology transfer model for IPM activities. An example are ‘IPM Clubs’, a common feature of the IPM activities of other organisations in Vietnam. They are not supported by the Programme for several reasons: concern for sustainability, other priorities for investment with limited funds, and fear that the IPM approach to farmer training will be diluted (the IPM Clubs often receive assistance and leadership from both the PPD and the Extension Department, and may be an avenue for agri-businesses to sell products to farmers).

- The PPD has a mandate for crop protection extension, farmer training and TOT for IPM. It is less congruent with the mandate to expect PPD to be the main source, not only of plant protection technical expertise and ‘extension’, but also of skills with respect to non-formal education methods and approaches, farmer empowerment, farmer organisation and other CIPM follow-up activities. A similar mandate problem would arise if PPD were to engage in FFS for soil fertility (fertiliser management is a major focus in current FFS), marketing, etc. The PPD does provide this training at present and is, in fact, playing an important role in this respect, but the question can be raised whether this special circumstance can be continued. It seems important that the relationship between the two departments becomes more transparent and understood from the perspective of the longer-term sustainability of the national CIPM Programme.

# Recommendations

## Approach to the Development of CIPM

- The Cum Tinh are a remarkable Vietnamese approach to CIPM. Groups of provinces have come together and shared their IPM human resources to carry out quality control and other important functions. In many provinces, they have first worked with one group of four villages, and after their graduation, moved to a second batch of four villages. It would be interesting to establish the effectiveness of this approach to graduating villages and moving on. The ‘graduation’ approach would, where it was followed, allow a unique opportunity to establish what is left of CIPM after certain amounts of time and allow assessing the sustainability of the CIPM.

- Curriculum Development: The Vietnam National IPM Programme has developed and repeatedly used a sound curriculum development process. However, the ability and experience to organise and facilitate the whole process must be given to many more IPM trainers and brought to the attention of PPSD decision-makers. It has been noted that trainers who use a curriculum for a new crop easily revert back to the well-known and often quite different rice FFS model. This is especially the case when trainers are simply given a new curriculum to use, as in sweet potato, which was developed in Indonesia. When they are involved in the development themselves, there is more confidence and the results are better (e.g. rat management and soybeans). This lack of quality and awareness is one of the important motivations for the National IPM Programme team to plan activities to strengthen facilitation and management skills during what remains of Phase IV. These activities will use the development of curricula for maize and dragon fruit as a hands-on learning experience. The dynamic development of agriculture in Vietnam places a high premium on the regular upgrading of FFS curricula.

- Expansion of IPM into Other Crops and Areas: It seems important also to shift the focus of IPM from the ‘Green Revolution’ areas to the rain-fed areas of the country. Such a shift in focus would require developing new curricula, or adapting existing ones, for crops such as maize, sweet potatoes, rain-fed rice, soybeans, and groundnuts.

- The Farmers’ Union and the Women’s Union: The involvement of the Farmers’ Union and the Women’s Union can be valuable and convincing the leadership of those organisations would go a long way to promote IPM. These two organizations formed part of the former statalist structure but seem to some extent and in some locations to be reforming from within towards poverty alleviation and enhancement of the extent to which the voice of ordinary people is heard above. Critical collaboration and capacity building is required, understanding that these two organizations have the potential to be both forces for participatory and empowering education and forces working against it.

- In particular, it seems that it would be worthwhile to focus such efforts on the Vietnam Women’s Union. The Vietnam Women’s Union has 80% rural membership. Like the Farmers’ Union, it has a network down to the commune level. Women are responsible for most agricultural production activities. Feminisation of agriculture is rapidly occurring. The Union is engaged in livelihoods, health promotion, safe farming and environment. It has access to mass media through women’s programmes on radio and TV.

- Role of NGOs: International development NGOs with offices in Vietnam have been important partners for CIPM but they require sustained technical support from the Programme and the strengthening of their own capacities for IPM.

- Collaboration with Universities and Research Institutions: The role of these institutions in supporting CIPM in particular, and the IPM Programme in general is important. The project between the Hanoi Agricultural University and the Norwegian Crop Research Institute within the National IPM Programme is an important step. Well-planned efforts to involve these institutions are recommended for local scientific support and to ensure the possibility of IPM farmers’ access to these institutions. It would seem fruitful to strengthen and expand an alternative paradigm developed by the National IPM Programme for constructive interaction among farmers, IPM trainers and researchers. Individual scientists are recruited as resource persons for farmers’ field studies if their expertise meets farmers’ needs, and if they are interested to work with farmers on that basis. This will hopefully reduce the present situation where university professors consider the Programme a source of funds for a positivist research agenda, while FAO staff deny such requests.

- Strengthening the Provincial Level and Continuing Training: The central PPD base for IPM is very vulnerable to unexpected political and personality changes. It is thus highly recommended to continue strengthening the decentralised provincial level. The upgrading and refresher training of the existing cadre of IPM trainers requires continued attention. Efforts could be made to enhance FFS facilitation and FFS follow-up skills, with less emphasis on technical crop protection and more on non-formal education and institution building, among staff of NGOs, mass organisations, and also the general extension service. In IPM, crop protection and non-formal education are two sides of the same coin, but that does not mean that one could not enhance non-formal education skills among other than crop protection specialists.

- Advocacy: It is essential to create a widespread understanding of the alternative model to technology transfer that has been developed by FAO’s IPM Programme. The Programme has not had a significant role in policy advocacy but it seems important to continue with advocacy activities at the highest levels, perhaps in collaboration with others, including major donors involved in IPM. In this respect, the plans of DANIDA to engage in field studies with high credibility to convince policy makers is to be welcomed. (The FAO Programme funded two such studies in Northern Vietnam in the summer of 2000.) The development of participatory health monitoring of the impact of pesticide spraying allows results that could have an important bearing on advocacy. Future development of participatory monitoring of environmental impact (presently only an idea) could have similar results.

- The Role of Science: Positivist science and technology transfer are not sufficient by themselves to guarantee effective development and productive, sustainable and equitable land use. In such areas as crop protection, soil conservation, irrigation, and vegetable production, professionalism not only includes technical expertise, but also a fundamental understanding of the processes by which people, through interaction, institution building and collective action, shape a ‘soft side of land’ that allows technical knowledge to work for human advancement. In other words, it would seem important to explicitly address, perhaps in one or more national conferences and field training sessions for scientists, the nature of ‘beta/gamma’ science, i.e. the inevitable link between managing people change, on the one hand, and the management of pests, water, trees, soils, etc., for human purposes, on the other.

## The Remainder of Phase IV

- The smooth continuation and realisation of the promise that has emerged during the first three years of the Norway-funded Phase IV in Vietnam requires priority in providing a continuing and sustainable development base in the remaining period. In making suggestions for the last two years, we shall assume that the current FAO team can continue to operate. We also assume that funding will be available from the FAO CIPM Programme to carry out a number of activities. These include: some consultancies (quality monitoring of farmer-to-farmer training, assessing spread effects, evaluating IPM Clubs); the development of at least one additional curriculum; the development of training capacity in the Women’s Union; the deployment of Main Trainers for IPM strengthening tasks; and coverage of the costs of a number of TOT, farmer field studies and other follow-up CIPM activities.

- Specifically, and to some extent summarising some of the remarks made earlier, the following components of Community IPM would seem to require particular attention during the next two years:

  - Fostering the development of a national IPM plan for the PPD. The IPM Division should have government funding for the National IPM programme;

  - Strengthening management capacity of the PPD IPM Group (Hanoi Central) and of the provincial PPSD groups;

  - Strengthening non-formal education skills of IPM trainers, using the development of a maize curriculum as training case;

  - Improving procedures for quality monitoring and impact evaluation, especially with respect to farmer training by other farmers;

  - Documenting (part of) what has been achieved in Vietnam, which would become especially relevant after quality monitoring and impact evaluation;

  - Assessing diffusion of CIPM components and estimating the spread effects achieved;

  - Evaluating the IPM Clubs;

  - Developing an FFS curriculum for one or more other crops, with a special emphasis on poor rain- fed areas and NGO involvement;

  - Developing capacity for IPM training and facilitating CIPM in the Vietnam Women’s Organisation;

  - Advocacy.

## The Longer Term

- The entry of DANIDA and other institutions means that the Inter-country CIPM Programme is no longer the major source of funds for IPM in the country. However, the Mission believes that a longer-term presence of an office of the type now provided through the Inter-country Programme is important. A National Programme office could well remain a lead source, both for the scientific basis of IPM, and for empowering research and education. The many donors and NGOs involved in CIPM lack technical skills and an office to provide underpinning is important. For the time being, FAO’s IPM Programme continues to be the most important institution for facilitating new initiatives, such as those in plant genetic resources (e.g. BUCAP) or the Vietnam National Forum planned by Sweden to address chemical risk. In addition to ‘gap filling’, the following roles for a national office deserve attention:

  - Networking and capturing synergy from collaboration among various IPM actors. This would apply especially to a national M&E network with collaborating projects and NGOs;

  - Continued linkage with cutting edge international scientific and paradigm development;

  - Advocacy and stimulating sustained quality;

  - Stimulating basic new developments including such aspects as development of organic agriculture with IPM marketing and certification of clean products.

# Summary of Results Against Immediate Objectives and Outputs

| Progress at Mid-Point of Phase IV 1998-2000 |  |
| --- | --- |
| Objective 1. To create self-reliant IPM training capability where it does not yet exist within government agencies and/or non-government organisations which are planning or managing Community IPM Programmes in member countries. |  |
| - Between 1992 and the present, eighty-three percent of all rice growing villages had at least one rice FFS. Four percent of all Vietnamese farm households have had a member trained in a rice IPM FFS. In all since 1992, this amounts to more than half a million alumni from 10,808 FAO-funded, 5,820 locally-funded, and 3,028 other donor-funded FFS. At present, the strategy has been to hold one or two FFS in most villages and then rely on diffusion but the Programme has little insight into the extent to which spread of effects beyond those directly trained in FFS has been achieved. - IPM is institutionalised to differing degrees within the formal structure: The Mission has some doubts about the current sustainability of the institutional support structures established for CIPM at the national level. The PPD centre is not strong enough at present in terms of depth and numbers of people. It relies to a large extent on the dedication of one or two persons. CIPM activities are also not included in the job descriptions of PPD staff and funding of CIPM activities is not entered into the regular budget. Conduct of FFS is not part of regular duties. |  |
| Output 1. Trainers capable of managing season-long TOT courses without outside help. | - A large number of IPM Trainers is available, including a number of experienced Main Trainers (there are 1,345 PPSD IPM trainers). - Training has included: 1 TOT for Main Trainers; and 44 rice TOT all completed prior to Phase IV; 32 TOT to train farmers in facilitation skills, FFS (10,808 FAO-funded, 5,820 locally-funded; 3,028 other donor-funded since 1992) 1,999 rice IPM FFS have been completed during Phase IV with support from the Programme. - Training in CIPM has been provided on: cum tinhs and training quality, designing field studies, planning process, health risks of pesticides and impact evaluation. |
| Objective 2. To develop the content and methods of Community IPM activities appropriate to different farming systems and social conditions. |  |
| Output 2.1 Action research (AR) completed by IPM farmers, in collaboration with appropriate specialist organisations, which increases the scope and depth of agro-ecological understanding needed for the design and implementation of other activities. | - No action research facilities (such as in Indonesia, i.e. employing FAO national experts) have been established. PPSD and farmer trainers are responsible for designing and implementing field studies in farmers’ fields. Meetings were held in farmers’ houses or village meeting rooms as local contribution (in kind). - 1,174 field studies were conducted in Community IPM villages. Topics addressed for rice included: variety, fertilizer, transplanting densities, seed rates and pests (see also studies below). |

| Output 2.2 Curricula available for specific farming systems and community needs. |  | Based on work since 1992, the following farming systems are now covered by curricula: rice-rice; rice-rice-secondary crop (sweet potato, vegetable), rice-secondary crop-rice, rice-fish, industrial crops (soybean-cotton;): - Curricula have been developed for: biological studies (including parasites, NPV, Bt), composting*, management of soil-borne diseases* in vegetables, rat management and golden snail management; * of which only those marked with an * were during Phase IV. In addition during Phase IV: - Curricula have been revised for: vegetables, gender and cotton; - Farmers have developed curricula for: plant genetic resources (seed rehabilitation, line selection, variety evaluation, plant breeding) and have developed exercises for farmer TOT. |
| --- | --- | --- |
| Output 2.3 A range of Community IPM activities designed, tested, and documented in collaboration with government agencies and/or NGOs in member countries. |  | CIPM activities include: farmer-to-farmer FFS, field studies, and field days. In Community IPM villages- these are 17% locally funded. In non-Community IPM villages these are 95% locally funded and include a wider range of activities. - FFS (disease management 160 in 18 provinces, rat management 88 in 10 provinces, soybean 17 in 6 provinces, tea 93 in 5 provinces, fruit 33 in 4 provinces, maize 62 in 6 provinces, sugarcane 55 in 4 provinces); - Farmer-to-farmer studies on pesticides and health, 3 provinces; - Field studies (rice 74 in 6 provinces, vegetables 68 in 13 provinces, other crops 89 in 18 provinces) – see also Action Research; - Participatory impact evaluations 28. |
| Output 2.4 Forums for communicative action established by/for farmers and community groups engaged in IPM activities. |  | - Training and meetings (field days 253, farmer technical training 64, farmer-trainer meetings 118, district farmer technical meetings 82, village planning meetings 338); - IPM clubs: 1355 in 34 provinces (these are not funded by the Programme due to absence of quality control and technical support). |
| Objective 3. To strengthen the management capability for Community IPM programmes within member countries, and improve cooperation among member countries in a manner which will sustain this capability. |  |  |
| Output 3.1 Field leaders and trainers with the knowledge, skills and experience required to plan, organise, co-ordinate and support a wide range of Community IPM activities. |  | - Currently, about 10 (“cum tinh” and Amherst graduates). - There are 129 (40 females) CIPM trainers. |
| Objective 4. To improve the ability of policy-makers and planners in member countries to initiate, support and evaluate Community IPM Programmes. |  |  |
| Output 4.1 Case studies of community IPM activities prepared and made available to planners, programme managers, and trainers. |  | Materials and reports are produced at various levels and at national level include brochures, case studies, impact evaluation reports and process documentation of activities. It is very difficult to quantify the number of decision makers exposed to CIPM at various levels, but the number is large (sub-village, village, district, provincial, national) and their level of knowledge is high as demonstrated through support in different ways, especially funding. Their actions taken to support CIPM include: staffing; apprenticeship for IPM trainers who will support National IPM groups; and endorsement and support to the “cum tinh” arrangements. - Community-based IPM case studies in Vietnam during Phase IV, include: Village Planning Meetings; Training Farmers to Become Trainers; book (community based IPM case studies in Vietnam) - Impact studies: The Impact of Community IPM in Y Yen District, Nam Dinh Province and Jonathan Pincus’ Impact Evaluation Report. |
| Output 4.2 Studies of special issues completed, the results of which are made available as inputs for policy making and programme planning in member countries in support of Community IPM Programmes. |  | Special studies included: BPH and rice leaf folder crop assessments, peanut field studies and curriculum development, and rice-fish. These studies have been requested by farmers and have high, direct relevance for them. Results of the studies are consolidated and disseminated. |
| Output 4.3 Advice provided to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects, with special attention paid to the design of community-based approaches. |  | National CIPM meetings are organized and: - About 11Vice Ministers have been exposed to CIPM through the Steering Committee. Many more officials are informed at Department Director-General level; - Provinces organize their own ‘Summing up Meetings for IPM’. There are National IPM Meetings organized by the Programme; - Senior officials include IPM in their programmes when they make field visits for other purposes. |
| Output 4.4 Assistance provided to member governments and interested donors in the execution of projects (or project components) which promote and support Community IPM. |  | Extensive support has been provided to the many other agencies and donors involved in CIPM, including the MARD IPM project funded by DANIDA, the Vietnam Women’s Union ‘Safe Farming – Bac Ninh Province’ funded by AusAID through Australia’s International Women’s Development Agency, the Vietnam Farmers’ Union funded and supported by Danish ADDA, and CIDSE supported by various Catholic Charities. |
| Objective 5. To enhance broader awareness in member and donor countries about Community IPM activities in Asia. |  |  |
| Output 5.1 Information on community IPM available to the scientific community. | - Institutions include: National Institute of Plant Protection; Hanoi Agriculture University #1; Can Tho University; Vietnam Agricultural Science Institute; Fruit Crop Centre (Tien Giang); Agriculture Research Institute (South); Omon Rice Research Institute; Cotton Research Centre; Fishery Research Institute; CAB International; Noragric; CIP. - A number of workshops with participants from the scientific community have been held, these include: curriculum development; Science and Farmers. In addition, scientists provide technical backstopping for certain farmer field studies, e.g. disease management in rice, vegetables, biodiversity, rats. |  |
| Output 5.2 Information on IPM activities available to appropriate media organisations and advocacy groups. | - The amount of press/TV/radio coverage is hard to quantify, a large amount appears locally, with significant amounts at province and national levels (clippings are not collected systematically). |  |