Appendix 3

FAO Inter-Country Programme for Community IPM in Asia

Phase IV Mid-Term Review 2000

Cambodia – Summary Country Report

(Note: For Overall Findings – see Main Report)

Contents

page

A: Introduction	2

A.1	The Mission	2

A.2	Status of the Programme at the Start of Phase IV	2

B: Support Received from the Regional Programme	2

C: Discussion of Outcomes and Impacts	3

C.1	Coverage	3

C.2	Capabilities of Government, NGOs and Farmers	3

C.3	Beneficiaries	4

C.4	Cost-effectiveness	4

C.5	Community Activities	4

C.6	Sustainability	5

C.7	Effectiveness at Policy Level	5

C.8	Benefits from the Regional Programme	5

D: Major  Conclusions and Recommendations	5

D.1	Conclusions	5

D.2	Recommendations	6

E: Summary of Results Against Immediate Objectives and Outputs	8

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Introduction

## The Mission

- The Mission to Cambodia formed part of the Mid-Term Review of the Inter-Country Programme for Community IPM in Asia. This review took place some three years into the Fourth Phase of the Five-year Community IPM Programme. The main purposes of the review, as per the Terms of Reference, were on the basis of results and experience to date to assist management in deciding:

  - staffing activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

  - the desirability of and options for, further technical and financial assistance which could consolidate current work and expand into emerging areas of opportunity.

- The full team consisted of four independent consultants, one representative of the FAO Evaluation Service and one country representative. Three groups were formed for country visits. The two-person team visited Thailand for two days from 17-18 November and consisted of:

- Piao Yongfan – Country Representative from China – Deputy DG Agricultural Extension, China;

- Sean Foley – Consultant – Environmental Management and Agricultural Systems Specialist.

- During its visit, the team held discussions with the Department of Agronomy, Under-Secretary of State for MAFF, World Education, AusAID, DANIDA and  CAAEP. Visits were made to a Farmer TOT course, a Farmers' Life School pilot, an IPM in Schools programme and other FFS follow-up activities.

- The Mission wishes to express its appreciation to all those in Cambodia who provided such warm hospitality and who were always ready to answer questions and provide information. The Mission also wishes to emphasise that in such a short visit it had, of necessity, to make judgements on very limited information and its conclusions must be treated in that light.

## Status of the Programme at the Start of Phase IV

- The special, post-conflict circumstances in Cambodia need to be taken into account when planning or reviewing any assistance programme. As a result of three decades (or more) of conflict, the gender balance and age structure of the Cambodian population is skewed heavily towards women and younger age groups. The destruction of infrastructure, both social and physical, from the conflicts remains largely unrepaired, and the government continues to have very limited capacity to provide adequate basic services, e.g. health and education. More broadly, Cambodian agriculture, on which some 85% of the population depend for their livelihoods, can be classed as ‘low productivity’ due to poor soils, dependence on rain and absent infrastructure; agricultural extensions services are limited to absent.

- Since 1996 the Royal Government of Cambodia, with help from FAO, has developed a strong IPM training capability. This capability has been used to implement a large number of IPM Farmer Field Schools (FFS), funded by a range of donors. The National IPM Programme of the MAFF (Ministry of Agriculture, Forestry and Fisheries) has been the coordinator of these activities.

# Support Received from the Regional Programme

- Up to this time (2000), the role of FAO Community IPM has primarily been to build the capacity of the MAFF’s National IPM Programme, by providing technical and programme support. Over US$ 1.8 million have been provided to Cambodia over the past five years by the Governments of Australia, the Netherlands and Norway, through the FAO’s Community IPM Programme in Asia.

# Discussion of Outcomes and Impacts

## Coverage

- The Programme in Cambodia has expanded rapidly in the last 5 years. It operates in 6 provinces through the Department of Agronomy. Because of limited numbers of government staff being available at the provincial and district levels, the Programme has shifted emphasis in training farmers in IPM in Farmer Field Schools (FFS) to training Farmer Trainers (FT), this is also essential if local bases are to be laid for the evolution towards CIPM; some 250 FT have now been trained.

- As a consequence of these factors, FAO needs to consider focusing its efforts and resources on supporting community-based farmer IPM activities. In particular, FAO needs to consider practical means to help develop the capability of IPM farmers to plan and manage their own activities, including field studies and the training of other farmers by farmers.

- This is an approach that has evolved from the work of the National IPM Programme over the past five years and offers great potential for farmer IPM to make a significant contribution to sustainable rural livelihoods in Cambodia. It is also an area where limited assistance has been provided to date, and it is not on the agenda of the other major IPM donors. This work would also complement the ongoing activities of the MAFF National IPM Programme, by providing much needed assistance in the area of consolidating training skills at province, and particularly, district levels for follow-up activities to IPM farmer fields schools and overall programme planning and management.

## Capabilities of Government, NGOs and Farmers

- Government capabilities: The Ministry of Agriculture (MAFF) has a central team with 5 years of experience in planning and managing the National IPM Programme:

  - MAFF has 150 trainers with the expertise and experience required to organise Farmer Field Schools (FFS) in rice;

  - pilot activities have been completed and training materials produced as a basis for future training in vegetable IPM, rat management, crab management and soil fertility management;

  - results of health studies are available as an input into policy making; and

  - funding is now available from multilateral institutions (e.g. World Bank, IFAD, ADB, UNDP) and bilateral donors (e.g. DANIDA) which is sufficient for all FFS to be run by MAFF during the next 3 years.  UNICEF is also providing funding for schools IPM activities run by the Ministry of Education.

- NGO Capability:

  - World Education has tested and documented IPM in schools in collaboration with Ministry of Education. Funding for the continuation of activities in schools is now available from the Asia Foundation;

  - Handicap International has tested and documented IPM activities with disabled farmers. Funding currently being sought for continuation of this work;

  - Norwegian People’s Aid (NPA) has integrated IPM activities into resettlement programmes in Northwest Cambodia.  NPA has funded the training of trainers and is now supporting Field Schools in this area;

  - Catholic Relief Services (CRS) are utilising IPM Farmer Trainers as part of their community development activities in Svey Reing;

  - collaboration with Concern and OXFAM to establish a local IPM farmer network in Pursat province.

- Farmer Capability: Approximately 20,000 farmers across the country have completed season-long training by attending Farmers' Field Schools, and now have the capability to implement IPM in their own fields:

  - IPM Farmers in at least five provinces have formed groups to carry out field studies and thereby further improve their understanding of production constraints;

  - 254 IPM farmers have completed additional training as trainers, and are now organizing FFS in their own areas.

- The National IPM Programme has achieved remarkable success in terms of the number of farmers which have been trained. There are questions, however, about the broad impact and the sustainability of the Programme. Although 20,000 farmers have completed IPM Field Schools during the last 5 years, they represent less than half of one percent of the agricultural workforce. With the support of DANIDA and the World Bank, it is possible that this figure will be tripled during the coming three years. This represents the limits of the linear training model adopted by the Ministry of Agriculture, which depends on the availability of government staff – in fact, it is estimated that many more government staff will need to be trained to meet these goals.

- The National IPM Programme is constrained by an unavoidable trade-off between the number of FFS which the Ministry can organize, and the amount of support which can be given to other activities, such as field studies and follow-up meetings with groups of farmers who have already graduated from FFS. The experience in Cambodia and other countries in Asia has convinced FAO that follow-up activities are essential for the sustainability of IPM. Pesticides continue to be available and the commercial pressure to use them is increasing. Farmers who graduate from IPM Field Schools have to deal with this pressure. They also want to learn how to solve problems which were not addressed during their training, and, importantly, they want their neighbours to implement IPM, so that the entire community can grow healthy crops.

## Beneficiaries

- In terms of numbers, the principal beneficiaries are farm families located in the main rice growing provinces. No data were available on the breakdown of families according to the amount of land ‘owned’, although farmers in most areas operate farms of about 0.3 ha. It is clear that many of the participants in FFS are young farmers and a significant proportion (up to 50% in some areas, but more usually 20-30%) are women. The formation of IPM farmers' groups in many locations is an indication that these farmers consider the benefits of IPM to be tangible and worth building upon. The Programme has also taken innovative steps in providing training for handicapped farmers, some of whom have gone on to become farmer trainers.

## Cost-effectiveness

- Cost-effectiveness of training: No detailed data are available on the costs of training to date. Costs of using government staff for conducting FFS are known to be significantly higher than using farmer trainers. Much larger-scale FFS training, funded by DANIDA and the World Bank, is about to commence. This will work through the same government units as the FAO Programme.

- Cost-effectiveness of IPM for farmers: The main benefit to farmers is reported in the reduction in inputs costs, specifically for pesticides. This is especially so in Cambodia where many of the pesticides smuggled in from neighbouring countries, are not labelled in Khmer, and are consequently more expensive than usual and used with little understanding of the technical requirements for application. Reducing outlays on pesticides, especially in the low yield ( 2 t/ha) situation of most Cambodian farmers can lead to a major improvement in net returns to the farm family. In addition, reductions in health impacts were reported and these represent an important benefit to farm families as a whole.

## Community Activities

- The pilot project funded by UNDP, Farmer Life Schools, indicated that there was a potential to use an analogous technique to agro-ecosystem analysis for social analysis, so that farmers can develop a better understanding of the problems and opportunities facing their communities. This pilot was being conducted in six locations and appears to hold promise as an active approach to using skills developed in FFS in a wider and different arena. More broadly, the programme was supporting IPM farmer meetings and networking, bring together farmers at the local and inter-provincial levels to discuss both technical and other issues affecting farm communities; a proposal to establish an IPM Resource and Training Centre was also under consideration.

## Sustainability

- The Mission was of the opinion that continuing support is still required, both for the added benefits that the ICP brings to the programme and to maintain and/or improve the quality of FFS and TOT training. In the short term, the expansion of FFS under the DANIDA and World Bank projects is going to place significant additional demands on government trainers, and it is estimated that more trainers will be needed. Sustainability at the local and district levels can be enhanced by providing continuing support to farmer trainers and ensuring follow-up activities. The mission was concerned that some signs of slippage in the quality of FFS (and possibly TOT and farmer orientation training) were appearing, and consider this to be a clear sign that additional attention and resources will be required to maintain quality and, hence, sustainability at the local level.

## Effectiveness at Policy Level

- Policy is an area in which the Programme has met with little success. The Programme has met frequently with senior government officials who have in general been supportive of IPM, and offered assistance in drafting text for a national policy or declaration on IPM. However, to date, this offer has not been taken up by the government. Plans are being made to increase the amount of effort devoted to policy in the coming two years.

## Benefits from the Regional Programme

- The regional programme has provided support in both the form of members of the A Team working with local TOT and for local trainers and managers to gain overseas experience. The linkages to ICP also provide a strong sense of belonging for the local programme team and a means of  keeping up-to-date and obtaining access to technical and other resources otherwise not available in Cambodia.

# Major  Conclusions and Recommendations

- It should be noted that the conclusions and recommendations are based on a limited visit to Cambodia; they have, however, been cross checked with members of the ICP who are familiar with the Cambodian programme.

## Conclusions

- The Cambodian IPM programme has succeeded in training some 20,000 farmers using season-long Farmer Field Schools (FFS) for rice-based farming systems and has backed up this effort by conducting a number of IPM Training of Trainers (TOT) courses. In general, TOT have been focused on training agronomy staff at the provincial level. While initial efforts were spread over 13 provinces, the more recent focus is on 6 provinces. Overall, the Ministry of Agriculture, Forestry and Fisheries (MAFF) now has some 150 experienced trainers capable of conducting FFS.

- The Programme has provided the basis at the provincial level for much larger projects funded by DANIDA and the World Bank which are now commencing. Without the basis of skills and experience developed by the Cambodian IPM programme it would be much more difficult for these large projects to begin; further without the pioneering work by the Cambodian IPM programme it is doubtful if IPM would be included in these projects.

- The Cambodian IPM programme for rice-based systems has also been active in promoting the use of IPM for vegetable farming; in this it complements the work being undertaken by the Cambodian vegetable IPM programme; both are managed by the same team. Preliminary work has been done on preparing training curricula for rat, crab and soil fertility management.

- The Programme has also initiated new approaches to both school education (IPM in Schools) and community analysis (Farmer Life Schools). The first of these is now being implemented by World Education with funding from the Asia Foundation, while the second is reaching the end of a pilot phase funded by UNDP.

- Given the limitations on government staff and funding in spite of large scale donor support for the sector, it appears impossible for the current extension worker to farmer model of IPM training to reach a significant proportion of the farming population in Cambodia within a reasonable time frame. The implication of this is that increasing reliance will need to be placed on farmer-to-farmer IPM training, with the government role shifting to back-up and quality maintenance.

- The development by the programme of three levels of farmer fora (single objective, networking and training, and inter-provincial and/or nation-wide activities) is an important step in supporting horizontal linkages between groups of IPM farmers. The establishment of an IPM Farmer Resource and Training Centre would be an important complementary activity for encouraging horizontal support between farmers’ groups.

- For a variety of reasons, including its rapid expansion, there are worrying signs that quality may not be being maintained in all aspects of FFS training. Three observations which give rise to these concerns are that: Farmer Science may be becoming a rote rather than a creative exercise; training skills for group facilitation (especially for farmer-to-farmer FFS) are not developed to the level necessary; and it may be that in some instances FFS are not being attended by ‘real’ farmers as opposed to a member of their family.

- It is possible that the Cambodian IPM programme has become over-extended in the range of activities it is initiating and/or supporting, worthy though they are in their own right, and in the final two years there is a need to focus clearly on the core objectives of the programme.

## Recommendations

- Four factors now point to the need for FAO to take further steps that will enhance the sustainability of IPM. These are:

  - the task of building IPM training capacity in the government is largely complete. Some 150 government staff have completed Training of Trainers (TOT) courses and the curriculum and structures for the implementation of IPM Field Schools are in place;

  - other agencies will soon become the main source of funds for Field Schools run by the government, e.g. DANIDA and the World Bank;

  - the resources available to FAO for direct support to MAFF for IPM in Cambodia are diminishing. This means that FAO can no longer provide the same level and type of support as in the past;

  - up to the present, the impact of IPM has been limited to the approximately 20,000 farmers who have attended IPM FFS. To ensure sustainability, more emphasis is urgently required on follow-up activities at the farmer level.

- It is recommended that:

  - the Cambodian IPM programme conduct an internal strategic planning exercise to identify and prioritise tasks and activities for the coming two years, in this exercise special attention should be given to identifying the elements of the programme that are linked to maintaining the quality of FFS. On the basis of the results from this exercise, a clear work plan of activities should be prepared for the coming two years;

  - as an element of this exercise, particular attention be paid to the specific role(s) that the FAO IPM Programme could play in complementing the DANIDA and World Bank IPM-funded efforts, especially with regard to providing back-up in the form of follow-up training for farmers who have participated in FFS funded by these projects, technical support for training farmer-trainers (Farmer Training Orientation), follow-up training for agronomy staff who have attended TOT, and other activities related to maintaining training and follow-up quality;

  - in anticipation of the closing of the programme in two years, the Cambodian national programme should conduct a strategic planning exercise to map out an explicit strategy; the group should include representatives of partners and stakeholders in the programme. It is suggested that the organising concept for this exercise should be the ‘nationalisation’ of the programme, as this is relevant to both preparing for the ending of the programme and as a preparatory step in the event the programme is to be continued beyond 2002;

  - the IPM Resource and Training Centre be established and equipped with basic facilities (e.g. information materials, computer and printer, etc.)  and used as the base for improving packaging and dissemination of documentation and other information. Consideration should be given to seeking supporting funds, for establishment and operation, from other IPM projects operating in Cambodia;

  - renewed efforts be made to document, package and disseminate existing and new material developed by the programme, and that an additional staff member be engaged to take on this task and manage the Resource and Training Centre;

  - in recognition of the need for farmers to receive more support for organising and management skills, and for basic accounting skills, two additional staff (national) members be engaged to take on these tasks;

  - for members of the A Team, and other selected trainers, improving English language skills is increasingly important, and an additional staff member (e.g. APO) should be engaged for this specific task;

  - additional staff be engaged for the tasks identified in the main report, with special emphasis given to engaging two staff (one APO and one national) to prepare for and conduct gender training, and ensure that it is incorporated in FFS and TOT curricula.

# Summary of Results Against Immediate Objectives and Outputs

| Progress at Mid-Point of Phase IV 1998-2000 |  |
| --- | --- |
| Objective 1. To create self-reliant IPM training capability where it does not yet exist within government agencies and/or non-government organisations which are planning or managing Community IPM programmes in member countries. |  |
| Output 1.1 Trainers capable of managing season-long TOT courses without outside help. | - IPM is partially institutionalised within formal structures, but no formal National CIPM Programme yet exists, and CIPM takes place within a project framework. However, there are trained government staff in at least 13 provinces whose main task is to provide CIPM organisation and training for FFS; these staff have all participated in at least one TOT course. These provincial staff now provide back-up for 298 (100 were women, 21 were handicapped farmer trainers) of Farmer Trainers (FT), 1st FTO was organized in Nov 1997. - Training in CIPM has been provided to government/NGOs, mainly to provincial staff and Department of Agronomy and Research stations of the government; also to staff from different NGOs such as NPA, World Education, CRS, Concern, Oxfam Quebec, ADRA, EU/Prasac and CAAEP - IPM training and management of provincial training programme are part of regular official duties. - Since 1998, 151 trainers (55 were women) have graduated from TOT courses. - There have been 763 FFS (681 on rice, 61 on Vegetables and 17 on Mung bean and 4 FFS run with participation of handicap farmers) and 7 TOT (4 on rice, 2 on Vegetable and 1 on Mung Bean). - Some 250 Farmer-Trainers have received follow-up training. - Some 200 farmers have received training in facilitation skills. |
| Objective 2. To develop the content and methods of Community IPM activities appropriate to different farming systems and social conditions. |  |
| Output 2.1 Action research (AR) completed by IPM farmers, in collaboration with appropriate specialist organisations, which increases the scope and depth of agro-ecological understanding needed for the design and implementation of other activities. | - There have been 47 AR activities (29 on rice and 18 on vegetables); during the last wet season there were more than 30 AR activities. - Action research is being conducted on several topics, the most important of these is the “Farmer Life Schools” in 6 locations which use approaches and methods adapted from FFS to observe and analyse the social situation within the community. This is currently being piloted, and the work is being undertaken by alumni of FFS/TOT who have developed the methods themselves. Farmers are also conducting fertilizer trials in a number of locations. - Direct linkage between AR and farmers, but still in the early stages of development; linkages are strong as the project is relatively small and can respond quickly to demands for new types of training. - There has been no formal assessment of progress, results to date seem worthwhile. - The Farmer Life Schools are directly relevant to addressing community-level problems, many of which have positive links with farming systems' practices and composting. - A study of farmer-trainer networks has been initiated – ongoing. - There have been significant changes in areas where farmers have attended FFS. - It is still too early to disseminate results from AR activities. |

| Output 2.2 Curricula available for specific farming systems and community needs. | - The following topics are addressed: nutrient management/gender equity/ crop-specific technology/on-farm production of pathogens by farmers/rodent management. - Three cropping systems are covered: single crop rice, vegetables, and mung bean. - No activities are locally funded, except that provincial trainers' basic salary is paid by the government and topped up by the project. |
| --- | --- |
| Output 2.3 A range of Community IPM activities designed, tested, and documented in collaboration with government agencies and/or NGOs in member countries. | - As provincial trainers are government staff and have received CIPM training there is close and continual contact with them. In some areas, e.g. School CIPM, an NGO (World Education) has taken on implementation; links have also been created with Norwegian Peoples Aid, and there are other links to: CARE, other UN agencies, EU/Prasac, and Handicap International. - Linkages to government/NGOs are variable at the national level, as CIPM has not been formally endorsed; there are strong linkages at the provincial level, weaker linkages at the district level due to lack of government staff. At the national level, senior management are more aware and supportive than middle management. - To date 12+ curricula have been developed: vegetable IPM for several crops, rat management, crab management and soil fertility management, Farmer Life Study field guide, health related to pesticides used. - So far 5 curricula have been revised: vegetable, rice and mung bean IPM field exercises, facilitating skills for farmer science, participatory planning activities, and ecological field guide. - Curricula are directly relevant to farmers, as they were developed in response to farmer demand and in collaboration with them. - All key topics/issues covered, but the number of issues which farmers want to address keeps growing, so curricula development is a continuous process. |
| Output 2.4 Forums for communicative action established by/for farmers and community groups engaged in IPM activities. | - There have been 40 Level one (small group follow-up) this season - Level two (regular farmer meetings) have been held in five provinces with some 1,000 farmers. - Most backstopping for these fora is provided by programme staff. - A total of about 10 topics have been addressed in these fora. |
| Objective 3. To strengthen the management capability for Community IPM programmes within member countries, and improve cooperation among member countries in a manner which will sustain this capability. |  |
| Output 3.1 Field leaders and trainers with the knowledge, skills and experience required to plan, organise, co-ordinate and support a wide range of Community IPM activities. | - Four Cambodia nationals are members of the A Team, but the team does not have an institutional base. - There have been 6 study tours each year for A Team meetings. - Seven consultancies have been provided in: soil nutrient management, rat farmer management, health related to pesticides used, farmer life's study, vegetable IPM and participatory planning activities. - Content and quality of CIPM training is acceptable. The FFS training delivered to farmers, the approach and methods are directly comparable to that in other countries, with cultural adaptations where necessary. Maintaining quality is an issue that is recognised; so far it is acceptable but signs exist that further expansion of FFS and using FT to deliver FFS, will require focused additional training and backstopping at local and provincial levels. Advanced courses in planning, managing and organising FFS (and TOT) are under consideration for the near future. - There are strong regional links, primarily to Indonesia, but links to the Vietnam and Thai programmes are expected to grow. - There are some 27 CIPM trainers: 2 from NPPP with CIPM, 7 government IPM trainers, and 18 farmer trainers. |
| Objective 4. To improve the ability of policy-makers and planners in member countries to initiate, support and evaluate Community IPM programmes. |  |
| Output 4.1 Case studies of Community IPM activities prepared and made available to planners, programme managers and trainers. | - To date, 6 case studies: health study, impact of IPM training, landlessness and impact of IPM training, rat and crab farmer management practice, FTs and their contribution to the civil society. |
| Output 4.2 Studies of special issues completed, the results of which are made available as inputs for policy making and programme planning in member countries in support of Community IPM programmes. | - No special studies have been completed yet. |
| Output 4.3 Advice provided to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects, with special attention paid to the design of community-based approaches. | - Decision makers exposed to CIPM include: 2 at high level (ministry), 16 at medium level (Agronomy Department Provincial Agricultural departments) and 13 at provincial level (IPM provincial coordinator). - High-level support from MAFF at most training venues and workshops. - At national level, head of MAFF has a good knowledge and is openly supportive, middle management is less knowledgeable and supportive, including positive support for farmer trainers. - Staff have been provided at provincial level, but no staff are available below this level. Modifications in some regulations (e.g. reporting) are needed. - Regular attendance at major meetings and field events of MAFF staff up to minister level, including Under-Secretary of State, Director of Agronomy. |
| Output 4.4 Assistance provided to member governments and interested donors in the execution of projects (or project components) which promote and support Community IPM. | - Advice and technical support provided to DANIDA, World Bank, IFAD and NGOs for project design and during project inception phases. |
| Objective 5. To enhance broader awareness in member and donor countries about Community IPM activities in Asia. |  |
| Output 5.1 Information on Community IPM available to the scientific community. | - The scientific community in Cambodia is almost non existent, two scientists have been introduced to CIPM. |
| Output 5.2 Information on IPM activities available to appropriate media organisations and advocacy groups. | - Outreach activities have included: brochures, videos, pamphlets, translations of key training materials into Khmer. - Local coverage from MAFF good. Press file kept on activities covered in the media shows over one hundred articles related to IPM and pesticides over the past 5 years in Cambodia English language press. |