Appendix 8

FAO Inter-Country Programme for Community IPM in Asia

Phase IV Mid-Term Review 2000

Thailand – Summary Country Report

(Note: For Overall Findings – see Main Report)

Contents

page

A: Introduction	2

A.1	The Mission	2

A.2	Status of the Programme at the Start of Phase IV	2

A.3	Institutional Framework	2

A.4	Support Received from the Regional Programme	3

B: Discussion of Outcomes and Impacts	3

B.1	Coverage	3

B.2	Beneficiaries	4

B.3	Cost-effectiveness	4

B.4	Community Activities	4

B.5	Sustainability	4

B.6	Effectiveness at Policy Level	4

B.7	Benefits from the Regional Programme	5

C: Major  Conclusions and Recommendations	5

C.1	Conclusions	5

C.2	Recommendations	6

D: Summary of Results Against Immediate Objectives and Outputs	7

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Introduction

## The Mission

- The Mission to Thailand formed part of the Mid-term Review of the Inter-Country Programme for Community IPM in Asia. This review took place some three years into the Fourth Phase of the Five-year Community IPM Programme. The main purposes of the Review, as per the Terms of Reference, were, on the basis of results and experience to date, to assist management in deciding:

  - staffing activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

  - the desirability of, and options for, further technical and financial assistance which could consolidate current work and expand into emerging areas of opportunity.

- The full team consisted of four independent consultants, one representative of the FAO Evaluation Service and one country representative. Three groups were formed for country visits. The two-person team visited Thailand for two days from 17-18 November and consisted of:

- Piao Yongfan – Country Representative from China – Deputy DG Agricultural Extension, China;

- Sean Foley – Consultant – Environmental Management and Agricultural Systems Specialist.

- During its visit, the team held discussions with the Department of Agricultural Extension (DOEA), Thai Education Foundation (TEF) and the Ministry of Education. Visits were made to a Training of Trainers (TOT) course, a BioAgents and FFS (BAFFS) facility, a farmers’ group and an IPM in Schools programme.

- The Mission wishes to express its appreciation to all those in Thailand who provided such warm hospitality and who were always ready to answer questions and provide information. The Mission also wishes to emphasise that in such a short visit it had of necessity to make judgements on very limited information and its conclusions must be treated in that light.

## Status of the Programme at the Start of Phase IV

- The Community IPM (CIPM) programme in Thailand has a different history than most of the programmes in the region. For many years, attempts to initiate Farmer Field Schools (FFS) on a large scale through the Ministry of Agriculture proved unsuccessful, although FFS had been held on a small scale in many areas. In Thailand, ‘IPM’ has a number of meanings most of which do not conform to the practices promoted by FAO IPM. The breakthrough to larger-scale implementation came, when in 1998, a member of the Royal family saw a television programme on IPM, recognised its potential and gave ‘directions’ that such a programme should be taken up by the Ministry of Agriculture. However, during the late 1990s the model of farmer education advocated by CIPM had been enthusiastically taken up by senior staff within the Ministry of Education, and the FFS became the basis of a continuing series of training courses in the Office of the National Education Commission (ONPEC) and Department of Non-Formal Education (DNFE).

## Institutional Framework

- Primary FAO support to IPM activity in Thailand is through three government agencies:

- The Office of the National Education Commission (ONPEC);

- The Department of Non-Formal Education (DNFE), and;

- The Institute for Biological Agriculture and Farmer Field Schools (IBAFFS).

- The ONPEC, in the Department of General Education, Ministry of Education, implements IPM activities for primary school students in some five provinces in the central and northern regions of the country. Primary technical and training support for this has been provided by the Thai Education Foundation (TEF). Backing has been significant at the national level, among teachers and school administrators in numerous localities, the media, and similar initiatives regionally. Although there is strong demand for significant expansion of the Programme, the ability to do so is limited by relatively weak government training and support mechanisms at the province and district levels.

- The DNFE, also in the Ministry of Education, conducts IPM training and field school activities in numerous provinces throughout the country. Similar to ONPEC, technical and training support has been provided by the Thai Education Foundation (TEF), as well as FAO trainers and field visits. Also similar to ONPEC, backing for the work is strong at the central and field levels, but limitations at the middle levels impede more effective Programme implementation. Although relatively weak in areas of agronomy, much innovative work is underway by field level staff involving farmers, students in secondary school equivalency and vocational programmes, prison inmates, and ethnic minority populations. Improvement and expansion of this Programme will depend on continued NGO involvement, as well as strengthened field support structures within the DNFE.

- The IBAFFS, in the Department of Agricultural Extension (DOAE), Ministry of Agriculture and Cooperatives (MOAC), was created in early 1999 as a result of a Royal Initiative and His Majesty the King’s backing for IPM work. IBAFFS includes a national office and nine regional centres in all regions of the country. FAO is providing trainers, technical programme development, and partial financial support to the IBAFFS programme, which has included training and trainers courses and field schools in all regions. In addition, IBAFFS and DOAE staff have provided input into DNFE training and field activities in many local areas. A current restructuring programme in the MOAC is causing uncertainty as to the future existence and roles of many MOAC agencies. This, combined with indistinct definition of roles and relationships between the IBAFFS and the field level offices of the DOAE - which are responsible for the implementation of field schools - has resulted in inadequate strategic programme planning and support for field level activities.

- In addition to the above, the TEF has begun preliminary IPM work with agriculture colleges, in the Department of Vocational Education, Ministry of Education.

## Support Received from the Regional Programme

- There has been a low level of funding and limited international staff time devoted to the IPM Programme in Thailand. It is against this perspective that the effectiveness and impact of the Programme must be judged.

# Discussion of Outcomes and Impacts

## Coverage

- Overall coverage of the Community IPM programme remains small and this is a major disadvantage in demonstrating the efficacy of the Programme to policy makers. The number of farmers fully trained in FFS is 1,330 (in Phase IV), and an unknown number of farmers who have been trained previously. If the plans of the MoA are realised, there will be another 45 TOT conducted in 2,001 and some 370 FFS (in rice, vegetables and other crops) will be conducted. Hence, by the end of Phase IV, it can be expected that, in the order of, 10,000 additional farmers will have been trained. Even if these goals are achieved, the number of farmers covered by the Programme will remain a minuscule proportion of the total number of rice farmers in Thailand. However, the number of trainers participating in TOT in 2001 suggests that the Programme can expand rapidly, provided that sufficient funding is available and, more importantly, that the necessary follow-up programme with TOT alumni and IPM farmers is active and high priority is given to maintaining quality in TOT, FFS and follow-up activities.

## Beneficiaries

- It was not possible to gain an overall picture of who were the beneficiaries are of this phase and previous IPM training. On the limited information available, it appears that beneficiaries are ‘average’ farming families in the main rice (and vegetable) growing areas of the country.

## Cost-effectiveness

- Training: No data are available on the costs of training to date. On the basis of budget estimates made by IBAFFS, it appears that rice FFS will cost approximately US$ 715 and vegetable FFS about US$ 1,430 for vegetables, both including limited follow-up, and the assumption that each course has 25 participants per course, costs per participant would be of the order of US$ 30 for rice and US$ 60 for vegetables. IBAFFS has budgeted the same amount for FFS conducted by farmer trainers, but it is reasonable to expect that actual costs will be substantially lower. No information is available on how these costs compare with ‘traditional’ extension.

- Cost-effectiveness of IPM for farmers: Time was only available to visit one farmers’ group. Discussions with this group suggested that they had achieved reductions in input costs for rice, mostly attributable to not using pesticides, of the order of 30%. They reported small improvements in yields, but attributed most of the advantages to reduced input costs. They also noted that improved family health, through not having contact with poisons, had improved their families’ overall welfare. Currently, these farmers are now experimenting with not burning rice straw and organic fertilisers, both of which they anticipate will increase yields and reduce input costs. In addition, they reported that they are independently experimenting with applying IPM for various vegetable and tree crops.

## Community Activities

- There was no information available on the extent to which the Community IPM approach was influencing activities at the community level. However, the innovative IPM in Schools programme supported by ICP and conducted by TEF, provides another way in which the issues tackled by IPM can be brought to the attention of parents and farmers.

## Sustainability

- The Mission was not able to form a clear view of the sustainability of the benefits from FFS at farmer level, although the general impression was positive. While it was clear that some elements of IPM were being practised by the farmers’ group that was visited, it was not clear to what extent they were following IPM principles and practices as opposed to using bio-agents- as a substitute for pesticides. It is clear that there remains considerable opposition to IPM within the Ministry of Agriculture, although the opposite is true for the Ministry of Education, where the participatory discovery learning approach is set to become the norm for teaching in many areas. If the quality and enthusiasm of the participants in a TOT are a reliable gauge, it is possible that the programme, and the principles and practices it embodies, may significantly influence agricultural extension and pesticide use in the coming years. However, if there is rapid expansion of the programme by DOEA and with government (not FAO) funding, there will be a need to monitor the quality of FFS training and follow-up closely to ensure effectiveness, e.g. farmer understanding and application of IPM principles.

## Effectiveness at Policy Level

- The small scale of the programme to date, and the underlying hostility to the participatory approach to farmer education and belief that pesticides are an essential part of the ‘modern’ agricultural technological package are still prevalent in the Ministry of Agriculture – although it is clear that participation in TOT courses causes participants to re-examine these attitudes. It may well be that effects on policy, both with regard to extension methods and pesticides, may change more as a result of rapidly increasing demands by citizens for ‘clean’ produce. Changes may also arise from active use of IPM FFS and general participatory learning approaches by the Ministry of Education in non-formal and vocational education, and flow-on effects from the IPM in Schools programme – these, however, will take some time to make themselves felt.

## Benefits from the Regional Programme

- The lack of funding for the Programme has meant that only part-time, in-country support and very limited funding for technical support and the IPM in Schools programmes have been possible. Despite these limitations, it is clear that this support has had a catalytic effect on activities, especially when it has coincided with royal support for IPM. It has also led to plans for (overly) rapid expansion of the Programme which need to be more closely thought through.

# Major  Conclusions and Recommendations

(Because of the brevity of the visit to Thailand,

the conclusions and recommendations made are general and based on very limited information)

## Conclusions

- The royal ‘patronage’ afforded to IPM in 1998 provided the breakthrough in beginning its wider acceptance and application through the Ministry of Agriculture. This is now leading to what the Mission sees as an overly ambitious scaling up, that carries with it the clear danger that it will be nearly impossible to maintain quality of training, and follow-up may be more planned than actual. The implementation of this Programme in 2001 will need to be monitored carefully by both the country programme and Regional Office, although it is unclear what corrective action would be possible if problems begin to emerge. The importance of this rapid expansion of IPM is difficult to overstate, given the significance of Thailand as a rice producer and the amount of pesticides used on rice (and vegetables). If it is a ‘success’ then it represents a major step forward for IPM approaches and the ancillary benefits it can bring. If it is a ‘failure’ then it may set back widespread adoption of IPM in Thailand for some years.

- The quality of the extension staff now participating in the TOT is impressive and it is clear that the methods used are leading to the desired outcomes in terms of personal and professional transformation. However, these staff will return to their offices at the provincial level, and it is unclear what proportion of them will be able to continue conducting FFS after they have completed the first one, which is the final part of their TOT. Nor is it clear if they will be in a position to initiate TOT for district or sub-district staff, nor of the effect of their new knowledge on extension approaches generally.

- The use of the IBAFFS units as a locus for expanding IPM training potentially provides a strong logistical base for reaching farmers in the main rice and vegetable growing areas of the country. It also offers the possibility of expanding the availability and quality of bio-agents. However, this potential will only be realised if the quality of training (TOT and FFS) can be maintained and the IBAFFS become centres for supporting farmer studies and science, rather than fall back into the traditional extension pattern. The impact of the coming decentralisation on these centres is unclear at this time, and funding and staffing arrangements beyond 2003 will be critical issues.

- With the direct and active support of the Director-General for General Education, the parallel approach through the Ministry of Education is also conducting TOT and FFS. The DNFE and Department of Vocational Education are planning to allow full participation in an FFS to be used as a credit towards diplomas. More broadly, the discovery learning methods used in TOT and FFS are now to become the standard methods for NFE and vocational education, and possibly other aspects of education, nation-wide. Currently, almost as many people have been trained through TOT conducted by DNFE as by IBAFFS. Cooperation between DFNE and IBAFFS appears to be active and positive, although it probably remains on an informal level.

- The single visit to a farmers’ group using IPM suggests that previous FFS have been quite successful, but it was not possible to make an informed estimate of the number of farmers that are practising IPM. Nor was it clear to what degree the farmers are using IPM, i.e. observation and analysis of their agro-ecosystems to make decisions, as opposed to relying on (locally produced) bio-agents as a substitute for pesticides, as there is a possibility that the analytic aspects of IPM may have declined, and farmer studies and science are playing only a minor role or are absent.

- The IPM in Schools programme, being conducted by TEF, is clearly having a major impact on teaching methods and topics in the limited number of schools in which it is able to operate. Interestingly, the participatory discovery learning methods now appear to be spontaneously diffusing to other teachers and other subjects. Clearly, this approach to popularising IPM and providing students with learning, analytic and investigatory methods which they can apply in many areas of their life, has significant potential. It also offers a means by which the distribution of pesticides (stored, discarded and used) in communities can be documented and their effects traced. The students’ learning, and investigations, may also alert others to the dangers of pesticides for health and the environment, although there is no information on the degree to which students’ new knowledge may be affecting the use of pesticide by their parents, relatives and neighbours. Given that a proportion of these students will go on to become farmers, this is a critical means of ensuring that knowledge about IPM practices can be transmitted to the next generation of farmers and beyond.

## Recommendations

- Currently, the Institute for Biological Agriculture and FFS (IBAFFS) is active in farmer training through involving farmers in activities such as biological intervention in their agro-ecosystems to control pests. However, there is a need for farmers to be able to produce biological agents by themselves, or collectively, using simple practical techniques. There is also a need for more farmer science and studies, especially orientated to developing a better understanding of biodiversity, the role of bio-agents and self-production of bio-agents, as well as their proper application. The curriculum development for farmer science is currently very important. Research institutes could become involved in curriculum development.

- Formation of IPM farmers' alumni or clubs is suggested. This would provide a means to motivate those farmers who are interested in being involved in follow-up activities and improving their skills of agro-ecosystem manipulation using bio-agents. Based on IPM farmer group expansion, an IPM farmer network at district, provincial and national levels might evolve.

- Inter-country exchanges for facilitators and cross-visits are recommended, especially in terms of strengthening farmer science study groups. Trained farmers in Thailand, China and Indonesia are very interested in practising and improving field science studies. The areas of agro-ecological manipulation, include farming systems, water and soil management, varieties and bio-agent production and application, should be included in these exchange activities. The lessons learned in Thailand and Cambodia, for instance, can provide considerable support to other countries in the region, and farmer science would have an opportunity to develop in depth. Exchanges would also assist farmer facilitators in avoiding poor planning and in managing field experiments without misunderstandings of the role biological intervention occurring.

- Follow-up activities of IPM in schools for children should be planned to consolidate and multiply the progress which has already been achieved. Parents’ FFS or “field days” could be considered. Such activities would have the effect of making children more ambitious and confident in their roles as ‘IPM Guides’, either in their families or rice fields, through direct interaction with adults’ activities.

- Strengthening the role of the Non-Formal Education and Vocational education programmes, and other organizations such as NGOs, in IPM is needed to consolidate gains made, and ensure the sustainable development of farmer-centred participatory training (IPM). In addition to general FFS and TOT, the training of farmer leaders and facilitators for farmer-to-farmer training should be conducted with a clearer focus on longer-term objectives.

- Improved interactions between different agencies working on IPM-related activities is needed, so as to enhance IPM programmes and locate them in the ‘mainstream’, while at the same time avoiding competition for projects. Cooperative action would help IPM supporters to be stronger in the face of pressure from pesticide companies, and will strengthen the ability to have an effect on policy directions affecting farmer-centred IPM.

- Policy studies could be speeded up in the remaining two years, as the government and public interest in IPM and farmer training, stimulated by royal support, is quite positive at present, and there are immediate opportunities for improving policies regarding pesticides, health, environmental and farmer associations, etc. It is important that the Programme and its partners do not delay in making full use of this opportunity to establish or improve pesticide-related policies.

- Although the concerns of the Mission regarding the near impossibility of maintaining quality with the rapidly expanding IPM programme in 2001 (and beyond) may be misplaced, it is important that the consequences of a shortfall in training quality be thoroughly analysed in advance by the Programme and its partners, including the Regional Office. Provision may need to be made for additional support, e.g. from members of the A Team.

# Summary of Results Against Immediate Objectives and Outputs

Progress at Mid-Point of Phase IV 1998-2000

| Output 1. Trainers capable of managing season-long TOT courses without outside help. | - On the information available a limited number of trainers have this capability, but may lack experience in depth. Capacity should increase rapidly in 2001 with three TOT planned. Maintenance of quality is a major issue. - Four TOT have been conducted by DOEA with 104 people trained in whole-season TOT courses; 98 people have been trained in whole-season TOT by DNFE. - 141 FFS have been conducted with 1,565 people trained in whole-season FFS courses. Gauging from the TOT participants met, training is meeting its objectives. - IPM is institutionalised within a formal structure in different ways. As regular work of Department of Non-Formal Education (DNFE) with farmers and NFE students. As regular work through the Office of the National Primary Education Commission (ONPEC) with students in primary schools. As part of mission of Institute for Biological Agriculture and Farmer Field Schools (IBAFFS), and within the Department of Agriculture Extension (DOAE) system at province, district and sub-district levels - Training in some places is a regular part of official duties, but linkages to official tasks appear to be fragile. |
| --- | --- |
| Objective 2. To develop the content and methods of Community IPM activities appropriate to different farming systems and social conditions. |  |
| Output 2.1 Action research (AR) completed by IPM farmers, in collaboration with appropriate specialist organisations, which increases the scope and depth of agro-ecological understanding needed for the design and implementation of other activities. | - No specific AR facilities or projects, but many IBAFFS Centres do bio-agent trials with farmers. These are currently focusing on rice (broadcast and transplanted) and vegetables (mostly cabbage, kale, spring onions, and long beans). - There has been no formal evaluation of the effects of IPM on cropping systems and practices. - The IBAFFS provide a potentially effective way of disseminating findings specific to regions, but there has not yet been any consolidation and analysis of research findings. - Overall assessment of work is that it could be expanded and deepened. |

| Output 2.2 Curricula available for specific farming systems and community needs. | - For NFE, two major and several province-specific curricula have been developed; for ONPEC, at least one, with extensive local adaptation; for DOAE, two major draft (TOT and FFS), with ongoing revision and adaptation. - The farming systems covered are rice and vegetables (see above). - Curricula are used for training with adaptations, and are flexible in design. - Curricula adaptation incorporates feedback from AR evaluation activities and workshops. - Not all key issues are covered by curricula and much remains to be done. - No formal evaluation of relevance to farmers accomplished to date. |
| --- | --- |
| Output 2.3 A range of Community IPM activities designed, tested, and documented in collaboration with government agencies and/or NGOs in member countries. | - Training in CIPM is often provided to government/NGOs or in collaboration with government/NGOs. - So far, probably no farmer suggested topics have been taken up, and overall number of topics covered is small. - Funding is severely limited. - Feedback and links to training are variable, estimated overall as unclear and probably weak. |
| Output 2.4 Forums for communicative action established by/for farmers and community groups engaged in IPM activities. | - Although not formally arranged, a few farmers' fora have been started and facilitated (some done in conjunction with TOT field days). |
| Objective 3. To strengthen the management capability for Community IPM programmes within member countries, and improve cooperation among member countries in a manner which will sustain this capability. |  |
| Output 3. Field leaders and trainers with the knowledge, skills and experience required to plan, organise, co-ordinate and support a wide range of Community IPM activities. | - Some 104 people have participated in whole-season TOT conducted by DOEA; 98 have also been trained in courses conducted by DNFA. No formal “A Team” members established, but government/NGO staff have participated in a number of regional “A-Team” activities. Linkages to regional network are significant and close. |
| Objective 4. To improve the ability of policy-makers and planners in member countries to initiate, support and evaluate Community IPM programmes. |  |
| Output 4.1 Case studies of Community IPM activities prepared and made available to planners, programme managers, and trainers. | - No case studies have been conducted so far. - There has been significant involvement of national level staff, especially from the Ministry of Education, DNFE and Vocational Education. Involvement of MoA staff remains problematic, except for staff of DOEA and IBAFFS. - Reports and brochures have been made available. |

| Output 4.2 Studies of special issues completed, the results of which are made available as inputs for policy making and programme planning in member countries in support of Community IPM programmes. | - No special studies have been completed yet. |
| --- | --- |
| Output 4.3 Advice provided to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects, with special attention paid to the design of community-based approaches. | - Probably more contacts and advice provided to the Ministry of Education than Agriculture, due to ready acceptance of CIPM concepts in the former. - Numerous field visits by senior government staff. |
| Output 4.4 Assistance provided to member governments and interested donors in the execution of projects (or project components) which promote and support Community IPM. | Not applicable. |
| Objective 5. To enhance broader awareness in member and donor countries about Community IPM activities in Asia. |  |
| Output 5.1 Information on Community IPM available to the scientific community. | - Information has reached local (applied) scientists via channels within Ministry of Agriculture and Ministry of Education. - Main route of transmission is via IBAFFS centres. |
| Output 5.2 Information on IPM activities available to appropriate media organisations and advocacy groups. | - A moderate level of press coverage has been received. - There is a website on School IPM. |