Appendix 6

FAO Inter-Country Programme for Community IPM in Asia

Phase IV Mid-Term Review 2000

Nepal – Summary Country Report

(Note: For Overall Findings – see Main Report)

Contents

page

A: Introduction	2

A.1	The Mission	2

A.2	Status of the Programme at the Start of Phase IV	2

A.3	Support Received from the Regional Programme	2

B: Discussion of Outcomes and Impacts	2

B.1	Coverage	2

B.2	Beneficiaries and the Focus on Rice	3

B.3	Cost-effectiveness	3

B.4	Community Activities	4

B.5	Sustainability	4

B.6	Effectiveness at Policy Level	4

B.7	Benefits from the Regional Programme	5

C: Major  Conclusions and Recommendations	5

C.1	Conclusions	5

C.2	Recommendations	5

D: Summary of Results Against Immediate Objectives and Outputs	7

Niels Röling - team leader

Sean Foley

John Markie

Michel Pimbert

René Salazar

Piao Yongfan

December 2000

# Introduction

## The Mission

- The Mission to Nepal formed part of the Mid-term Review of the Inter-Country Programme for Community IPM in Asia. This review took place some three years into the Fourth Phase of the Five-year Community IPM Programme. The main purposes of the review, as per the Terms of Reference, were, on the basis of results and experience to date, to assist management in deciding:

  - staffing activities and priorities for the remainder of Phase IV in order to assure that the progress realised so far is consolidated for the future;

  - the desirability of, and options for, further technical and financial assistance which could consolidate current work and expand into emerging areas of opportunity.

- The full team consisted of four independent consultants, one representative of the FAO Evaluation Service and one country representative. Three groups were formed for country visits. The two-person team visited Nepal for four days from 12-17 November and consisted of:

- Niels Röling – Team Leader – Agricultural and Rural Development Specialist;

- Rene Salazar – Consultant – NGO Specialist in Sustainable Agricultural Development.

- The Mission wishes to express its appreciation to all those in Nepal who provided such warm hospitality and who were always ready to answer questions and provide information. The Mission also wishes to emphasise that in such a short visit it had, of necessity, to make judgements on very limited information and its conclusions must be treated in that light.

## Status of the Programme at the Start of Phase IV

- The IPM Programme only started in 1997 with a FAO-TCP of US$ 318,000 to enhance the capacity of field trainers. At this time, there was no regular IPM team and money was inefficiently used. Nepal became a member country of FAO’s Inter-Country Programme on Community IPM in Asia in September 1998. However, funding arrived only in February 1999 when the FAO-TCP was completed.

## Support Received from the Regional Programme

- There has been a low level of funding and limited international staff time devoted to the IPM Programme in Nepal, as funding was very limited. The stationing of the Regional Training Officer in Nepal has assisted the development of the national Programme. It is against this perspective that the effectiveness and impact of the Programme must be judged.

# Discussion of Outcomes and Impacts

## Coverage

- Given the very short time since IPM activities started in Nepal, the achievements on the ground are impressive. In each of 35 rice-growing districts (out of the total of 75), mainly in the Terai, one District Plant Protection Officer has been trained in a first TOT (1998); a second TOT was held in 1999. Some of the 35 trainers from this second TOT are posted in some of the 35 districts. Nepal now has a total of 63 active IPM Trainers; those who have gone for graduate work are likely to become active in the near future. By the time of the Mission’s visit, and with FAO funding, a total of 188 FFS had been organised by District Assistant Plant Protection Officers (APPOs) and 35 by farmers. Regular Nepal Government District agricultural development budgets funded an additional 63 FFS. A total of 6,000 farmers have been trained with FAO funding, significantly more than the objective of 5,000. Farmer associations have begun to be formed (the Mission was present at the initiation of one).

- An additional 18 FFS were funded by the Programme through World Education (the majority of the funds it received went into developing an NGO network as the basis for a model for expansion of FFS in Nepal). As well as World Education, the National IPM Programme also works with other NGOs: CARE International (4 FFS), two local NGOs, CEAPRED (1 FFS) and SEWA Nepal (1 FFS). With the perspective of longer-term collaboration, the Programme also worked with CEAPRED to develop a vegetable IPM curriculum. It is important that a strong technical base is provided to the NGOs as they often have communications, but not agricultural expertise.

## Beneficiaries and the Focus on Rice

- Focus on Rice: The Mission believes that the Programme’s focus on rice is correct, as rice is the most important crop in the country and rice-growing practices provide the greatest threat to ecological sustainability in the lowlands. The IPM Programme is most effective in crops and farming systems where chemical-based and ecologically unsustainable technologies are practised. In 1996 and 1997, serious outbreaks of BPH motivated urgent attention to IPM. Because of this, it was necessary to start the Programme in wet-rice farming systems, which cover some 1.5 million ha. Success in rice IPM needs to be achieved first before farmers and policy makers will expand the Programme to other crops. There is an increasing demand from farmers and from policy makers to expand the IPM Programme to vegetables and cotton. The Mission feels that expanding the Programme to vegetables is logical and necessary. A curriculum workshop is being planned by the IPM team in March 2001 that will involve different actors and institutions, including key scientists from NARC.

- Beneficiaries: The focus on rice by the Programme does, however, mean that the Programme is serving farmers in relatively more favoured conditions rather than those in marginal lands growing other more minor rain-fed crops. In 1999, 52% of FFS participants were literate farmers, 38% were educated (more than just literate but may have reached or finished high school), and only 10% were illiterate. In a country with a high illiteracy rate, especially among women, this is an indication that the Programme is currently reaching the less poor farmers in the country. Of the 6,000 farmers who participated in the FFS by 2000, a third or around 2,000 were women. It is also highly possible that in communities where the caste system is strong, the higher caste members have greater access to IPM FFS.

- The Mission feels that the danger of IPM being monopolised by local “elite” still needs attention and conscious intervention. However, it is recognised that the less poor farmers have the time and are in the best position to experiment and take risks with IPM. Furthermore, the economic differences among the rice farmers are not great compared with the difference between rice farmers and the poorest of the poor in the community, those who have no access to land.

- It was also noted that the present emphasis is on FFS close to roads and district agricultural offices. This is unavoidable if trained trainers are to be utilised efficiently but needs further examination with the use of farmer trainers in the longer term. NGOs involved in the IPM Programme in Nepal led by World Education (WE) have potential to reach distant areas, to consciously focus on the poorer sectors of the community, to focus on women and to focus on illiterate farmers as their beneficiaries. The Mission believes that an important value of the involvement of NGOs is its potential to reach and expand more rapidly the IPM FFS to poorer sections of the community. This potential advantage is currently under-emphasised.

## Cost-effectiveness

- Training: Due to the newness of the Programme, it has not yet been possible to develop clear cost-effectiveness comparisons of IPM training but it was noted that separate support to staff to carry out FFS had been limited to travel expenses.

- Cost-effectiveness of IPM for farmers: No data is available on the changes in inputs costs for rice farmers using IPM, but it is reasonable to conclude that eliminating or decreasing the use of pesticides would result in substantial savings (in other countries these range from about 20% to 40% of inputs costs). In vegetable farming similar savings could be expected.

## Community Activities

- The main IPM partner in Nepal is an International NGO, World Education (WE). This organisation had a long history with IPM, most notably in Indonesia and in other countries in Southeast Asia. WE’s longer-term strategy in the IPM Programme is to focus on women, on illiterates, on lower castes, on the poorer sector, and in communities distant from district centres. The Mission feels that by having NGO partners in IPM in Nepal, the National IPM Programme can reach sectors and areas where the government component will be less effective or cannot reach. The NGO component should be more than just an additional and parallel delivery system, as NGOs have freedom to develop more innovative approaches; are better placed to work on the empowerment agenda; and in relating IPM work to challenging and slowly changing the structures that make people poor and powerless. An option is to develop a curriculum for literacy training that is based on IPM (as has already been developed for credit and health).

- The second strategy of WE is to build an NGO IPM network. The aim is to build IPM capacities of NGOs and to assist these NGOs to implement IPM FFS and to engage in other activities; at the moment, it is working with three NGOs (to gain experience). While the IPM Programme implemented through the government presumes the institutional stability of its line offices in the districts, the institutional strength of NGOs needs to be built up as part of WE operations. However, the resources being used for capacity building need to be reviewed and balanced with resources actually used for farmer training.

## Sustainability

- IPM is established within the government structure, but the national HQ team has only two professional staff. It is part of the longer-term government plans, and will be incorporated in the government budget structure. District APPOs do not, as yet, have FFS written into their job descriptions, although IPM is a key component of their jobs and, in practice, they spend 75% of their time on FFS. IPM seems to have been embraced by higher officials in the MOA and the Secretary of MOA sees it as a way to reduce production costs and become more competitive with India. The large AREP project, funded by the World Bank, to support agricultural research and extension activities at the national and district levels aims at decentralised, bottom-up development, for which the FFS is said to be the likely model. At the national level, AREP favours collaborative outreach activities of the NARC, which offer opportunities for collaboration with IPM curriculum development. In all, IPM in Nepal seems to have good opportunities that require careful guidance and nurturing in the initial start-up phase, while the Programme is still small and vulnerable. At this stage rapid expansion could easily derail the Programme and rob it of its ‘active ingredients’.

- The greatest strength has been built up in the 35 districts where the Programme is operating, and the Mission feels that efforts to strengthen the Programme institutionally should focus on these districts. The national government’s move towards decentralisation, when effectively implemented, will hopefully support this. In line with this observation, the Mission also recommends that Letters of Agreement  with the government should be specified in such a way as to flexibly facilitate work at the district level.

## Effectiveness at Policy Level

- In terms of operational policy, the Programme currently has a unique opportunity to help the Ministry of Agriculture reorient its extension programme in the districts. It is presently considering adoption of the FFS as its main approach, so as to allow District Extension Centres to become real partners of farmers, not sources of (sometimes inappropriate) solutions.

- In the area of research, NARC, the National Agricultural Research Council, is more or less independent from the Ministry of Agriculture. It is currently in a process of retooling within the context of the World Bank-funded Agricultural Research and Extension Programme (AREP), and in this process it is focusing on outreach activities, so as to allow it to engage in partnerships with other research bodies and stakeholders in agricultural development. It is strengthening seven Regional Research Centres to make it more responsive to the field and demand-driven. NARC is engaged in various ‘IPM’ (read biological control) studies and eager to make a mark in this area. Clearly, there are complementary research opportunities that are possible in this area.

## Benefits from the Regional Programme

- The Mission believes that the ICP team has crucial contributions to make to such areas as technical support in science (e.g. health monitoring) and methodology (e.g. quality control and impact evaluation). Furthermore, the creative core of the CIPM Programme in terms of the scientific base and the evolving IPM process, is still largely based in Indonesia. The importance of the continued access to a think-tank, a clearing house for global intellectual development, and a centre of inspiration, was not in doubt. A typical example where the ICP could make a vital contribution is in the development of an explicit curriculum development procedure discussed linking IPM and scientific research.

# Major  Conclusions and Recommendations

(Because of the brevity of the visit to Nepal, the conclusions the Mission drew and recommendations

made are general and, unfortunately, based on limited review of the Nepali IPM Programme)

## Conclusions

- With the limited budget available, the Programme has both established a solid cadre of trainers within the government and local NGOs and trained a significant number of farmers during the last two years. The strong representation of women in the Programme is also significant.

- While to date the national Programme lacks a permanent institutional base, it is clear that the progress it has made and the fact that it offers an attractive alternative model for extension services, places it advantageously with regard to both building and institutional base and having a major influence on the direction of extension service delivery in Nepal.

- Collaboration with NGOs from the outset of the Programme has been necessary but has also added breadth to the Programme, allowing IPM to reach communities that are beyond the reach of government services, and offering means of initiating innovations for literacy, health and credit training by NGOs.

- The growing links with NARC, offer opportunities for collaboration on farmer-driven research agendas that fit well with the philosophy and practice of IPM. Links of this type will become increasingly important as the Programme expands the area in which it is working, and the associated technical challenges that this will bring, and for extension into IPM for vegetables and, possibly, cotton.

- Despite the progress made in the last two years, the Programme is not sustainable without continuing funding and technical support.

## Recommendations

- IPM and Regular Extension:. One important challenge is the coming on stream of the World Bank supported renewal of the district level Extension Service Centre activities, building on the FFS model. In fact, the Mission was told repeatedly that scaling up the number of FFS is not going to be a problem in Nepal. However, a rapid expansion in 23 of the 35 IPM districts is also a threat, as it could result in a loss of focus and of key attributes that make the Programme work. For example, the emphasis on follow-up activities as an indispensable element in the sustainability of IPM might be overlooked. Therefore, great attention should be paid to providing sufficient TOTs for junior technicians and other extension staff and to strengthening quality monitoring and impact evaluation. The one TOT planned so far might not be sufficient for this.

- The Development of a Vegetable Curriculum: A second important challenge is the very strong demand for the expansion of IPM to vegetables, fruit trees and cotton. From an ecological point of view, especially for expansion to vegetables, it seems important. This demand is based on the success of IPM in rice and the desire to achieve similar results in crops that really matter to the farmers in terms of cash income. The Mission, therefore, wholeheartedly agrees with the National IPM Programme’s ideas for the development of a vegetable IPM curriculum and related activities. It suggests that efforts be made via NEDA (Dutch Technical Assistance) to provide funding for expanding the Regional Vegetable IPM Programme to include Nepal.

- The Link with Scientific Research: A related and important challenge is the link with NARC, the National Agricultural Research Council. But the MTR Mission felt that, notwithstanding the self-professed change of paradigm of NARC, much remains to be done in terms of actual procedures for bringing to bear NARC’s scientific knowledge for the participatory development of IPM curricula in such areas as vegetables, pulses, post-harvest treatment, and ‘Living Soils’. The Mission therefore recommends that the Programme, together with AREP and NARC, and with help of the ICP in Jakarta, develop a participatory curriculum development procedure which pays attention to the design of the interface between basic science and farmer practice.

- Essential Conditions: For the activities suggested to really work and to establish a sound foundation for a rapid expansion of effective IPM activities in Nepal, the Mission has identified two essential conditions: first, the present National IPM Programme team needs to stay in place until the end of the two years currently envisaged; and second, more attention needs to be paid to the development of transparent financial procedures that give donors confidence that aid money is well-spent.

- Pesticide Disposal: Related to the National IPM Programme activity is the need to deal with the disposal of obsolete pesticides, of which large quantities are stored in Nepal. The Norwegian group specialising in this work, SINTEF, is probably the most appropriate for this, which could be combined with training and adult education of the stakeholders in pesticide importation and storage, to prevent future recurrence. The Mission feels that this could be an important activity under the National IPM Programme in the coming two years.

- Longer-term development of CIPM: The Mission feels that in the longer term, policy in CIPM should also give attention to:

  - the development of value added and quality in higher-value crops which can meet the tourist market and export markets in India. This will better boost farm and national incomes than efforts to compete with India in rice production;

  - the development of CIPM approaches for poor and distant communities, applying the same methodologies to other aspects of hill farming.

# Summary of Results Against Immediate Objectives and Outputs

| Progress at Mid-Point of Phase IV 1998-2000 |  |
| --- | --- |
| Objective 1. To create self-reliant IPM training capability where it does not yet exist within government agencies and/or non-government organisations which are planning or managing Community IPM programmes in member countries. |  |
| Output 1. Trainers capable of managing season-long TOT courses without outside help. | IPM is not yet institutionalised, increasingly FFS are organised by the District Agricultural Development Offices (DADO) and are seen as the new ‘extension’ method. Currently, in 35 out of 75 districts, APPOs (and some NGO staff) are trained and implement IPM activities. Mostly with FAO funding, but more and more DADOs are being allocated Government funding for FFS. Training is a regular part of official duties, some 75% of the time of IPM trainers is spent on IPM and is written into their job description, but not FFS as such. Training has been as follows during Phase IV: - Pilot Farmers TOT for Master Trainers; - 2 (season-long) TOT for government staff/NGOs. Of the approximately 70 people trained in TOT, about 60 are available at present (others study abroad, promoted or transferred to other projects); - 5 (10-day) TOT courses for farmers' training ,135 who have conducted 34 FFS; - 188 FFS (34 were FAO-funded and organised by APPOs and/or farmers; 18 organised by NGOs through World Education with FAO funding; 2 organised by CARE Nepal; 63 were government- funded and organised by IPM trainers). FAO-IPM has focused on rice. The government has started with FFS in vegetables with government funding. Also, increasingly FFS on IPM in rice is funded with government money through DADOs. |
| Objective 2. To develop the content and methods of Community IPM activities appropriate to different farming systems and social conditions. |  |
| Output 2.1 Action research (AR) completed by IPM farmers, in collaboration with appropriate specialist organisations, which increases the scope and depth of agro-ecological understanding needed for the design and implementation of other activities. | No formal Action Research (AR) has been conducted. This year a start has been made with 17 studies by and with farmers as a follow-up activity after the first FFS on rice. Focus has been on: rice system IPM (rice – rice – vegetables; rice – vegetables – vegetables); IPM in potato, tomato, eggplant, crucifers; for 2001, a curriculum will be developed for vegetable IPM, with experience from the field studies cum pilot FFS conducted by government officers and NGOs. Also NARC expertise will be involved. Overall assessment of work is that a good start has been made on AR but it needs improvement. APPOs need more practice to assess the ‘real needs’ of farmers hence the relevance of topics is hard to assess. Some collaborative links have been established with NARC. AR has resulted in some varietal selection, changes in fertiliser management and seed selection procedures have been improved. Findings are disseminated locally to some extent. |
| Output 2.2 Curricula available for specific farming systems and community needs. | Rice is the only curricula developed, and it is flexible and relevant to farmer needs; all key topics are covered and it has been translated into Nepali. Other materials used are from the inter-country Programme. Curricula have been revised and translated for participatory planning, and farmers' TOT. |

| Output 2.3 A range of Community IPM activities designed, tested, and documented in collaboration with government agencies and/or NGOs in member countries. |  | NGOs were heavily involved in training with World Education being contracted to carry out 18 FFS and develop an NGO network as a model for expansion of FFS in Nepal. As well as World Education, the National IPM Programme also works with other NGOs: CARE International (4 FFS), two local NGOs, CEAPRED (1 FFS) and SEWA Nepal (1 FFS). With the perspective of longer-term collaboration, the Programme also worked with CEAPRED to develop a vegetable IPM curriculum. World Education has developed curricula for credit and health based on IPM principles. The following workshops have been held: - Participatory Planning (10 days: 5 days theoretical, 5 days practicum in field); - Science and Farmers (10 days: 5 days class, 5 days field); Farmers TOT Curriculum Development. CIPM training has been started: 12 groups have implemented participatory planning activities. 12 farmers studies have been conducted as follow-up. Farmer-suggested studies have included: varietal trials (blast resistance), weed management and fertiliser management. It may be noted that these are carried out in groups but the “C” is not very evident in CIPM. |
| --- | --- | --- |
| Output 2.4 Forums for communicative action established by/for farmers and community groups engaged in IPM activities. |  | See also above - Several topics were addressed: another FFS in Rice (favourite), rice-fish production, bee-keeping, varietal trial, fertiliser management studies. Facilitation skills are part of TOT training. |
| Objective 3. To strengthen the management capability for Community IPM Programmes within member countries, and improve cooperation among member countries in a manner which will sustain this capability. |  |  |
| Output 3. Field leaders and trainers with the knowledge, skills and experience required to plan, organise, co-ordinate and support a wide range of Community IPM activities. |  | There has been no opportunity yet for a Nepali to be trained as a member of the A Team, and no consultancies have been undertaken. Inter-country support has consisted of: three Indonesians and one Philippine A Team trainers, who assisted in workshops in 2000, an Indonesian trainer assisted in the TOT in 1999. Linkages to the regional network are weak. |
| Objective 4. To improve the ability of policy-makers and planners in member countries to initiate, support and evaluate Community IPM programmes. |  |  |
| Output 4.1 Case studies of community IPM activities prepared and made available to planners, programme managers and trainers. | In terms of case studies, so far only a brief report describing the experience of including gender in IPM has been prepared. During seminars, papers are presented and distributed on the National IPM Programme. To date, meetings, seminars and workshops have been the main means of reaching Government planners and managers. At the national level, the Minister and his Secretary are aware of IPM. The Director-General and Deputy Director-General have attended several ceremonies and occasions for IPM training activities. High-level officials are members of the national IPM steering committee (incl. E.D of NARC). At the district level, most DADOs are actively involved and show a high interest in IPM. Only at the district level, ADOs are (most of them) aware of the real meaning and methodology of IPM activities. At a higher level, a few know about FFS and there is general enthusiasm about the approach. At NARC they confuse IPM with biological control. There might be a national policy to use FFS as a nation-wide approach in agricultural extension, replacing the ‘mini-kit’ approach. |  |
| Output 4.2 Studies of special issues completed, the results of which are made available as inputs for policy making and programme planning in member countries in support of Community IPM programmes. | No special studies have been completed yet. |  |
| Output 4.3 Advice provided to member governments, local government officials, NGOs and community groups and interested donors in support of the formulation, appraisal, management and evaluation of IPM training projects, with special attention paid to the design of community-based approaches. | See above |  |
| Output 4.4 Assistance provided to member governments and interested donors in the execution of projects (or project components) which promote and support Community IPM. | Not applicable. |  |
| Objective 5. To enhance broader awareness in member and donor countries about Community IPM activities in Asia. |  |  |
| Output 5.1 Information on Community IPM available to the scientific community. | Limited exposure to scientists, who tend to confuse IPM with bio-control. |  |
| Output 5.2 Information on IPM activities available to appropriate media organisations and advocacy groups. | National IPM Newsletter is produced on a regular basis (Nepali). Several times FFS have received coverage in newspapers and on radio. |  |

The 9th Plan 1998-2003 and the 20-year Prospective Plan

Although the Mission did not have time to investigate this issue further, it is convinced that IPM in post-harvest issues (especially use of pesticides in storage of produce) is potentially very important. Large percentages of the product harvested are said to be lost in storage.