## Slide 1: Road Map of the Food Security and Nutrition Program (FSNP) of Kyrgyz Republic for 2015-2017 and beyond

## Slide 2: Road Map Structure
FSNP in Kyrgyzstan has four targets: food availability, food accessibility, food utilization and food safety.
For each target the Road Map suggest a set of activities by priorities with involved organizations.
Program outcomes are structure in a timeline within and beyond the current FSNP period.

## Slide 3: FOOD AVAILABILITY
 | Implemented/ Ongoing Activities | Actors | Activities in 2017 | Actors | New Program | Actors
Priority 1 – Strengthen domestic production |  |  |  |  |  | 
1.1. Framework 1.2. Target support 1.3. Information support 1.4. Key products 1.5. Fortified food | Information system Credit support to food producers Infrastructure and services Wheat purchase Climate change Improved seeds and livestock Capacity building preparation | ME MoAM MF FSMR SAEPF MoEd SRS MES MoH | Trainings Investment projects Cluster approach Information system Priority food Improved seeds and livestock Capacity building Infrastructure and services Information campaign | ME MoAM MF FSMR SAEPF MoEd SRS MES MoH | Target producers Feasibility studies Fortified food system work Climate change Priority food Trainings Capacity building Infrastructure and services Information campaign | ME MoAM MF FSMR SAEPF MoEd SRS MES MoH
Priority 2 – Food trade regulation |  |  |  |  |  | 
1.6. Wheat import 1.7. Domestic producers | Wheat contracting and supply | ME MF MEA MoAM FSMR | Food markets analysis and recommendations | ME | Wheat contracting and supply Food market analysis and recommendations | ME MF MEA MoAM FSMR
Priority 3- Infrastructure |  |  |  |  |  | 
1.8. Capacity building 1.9. Food storages | Food reserves monitoring | MoAM FSMR | Food reserves monitoring | MoAM FSMR | Needs assessment Target units selection Trainings Infrastructure Methodology Food reserves monitoring | MoAM FSMR KRSU

## Slide 4: FOOD ACCESSABILITY
 | Implemented/ Ongoing Activities | Actors | Activities in 2017 | Actors | New Program | Actors
Priority 1 – Public management |  |  |  |  |  | 
2.1. Food legislation 2.2. – 2.3. Food reserves 2.4. Price regulation 2.5. Social support 2.6. – 2.7. Climate change 2.8. Capacity building 2.9. Information system | Food reserves optimization Population survey Amendments in the food security and nutrition law | MoAM IAWG ME MSD MoH NSC FSMR MF FS Council | Trainings Price assessment Survey methodology Climate change losses analysis Infrastructure Capacity building | ME MoAM MF FSMR SAEPF MoEd SRS MES MoH FS Council | New antimonopoly law Price assessment New food security law and support Capacity building Infrastructure Price regulation | ME MoAM MF FSMR SAEPF MoEd SRS MES MoH KNAU
Priority 2 – Food market stability |  |  |  |  |  | 
2.10. Price regulation 2.11. Warning system | Anti-inflation measures Food security warning system Information system | ME MF NB MEA MoAM FSMR AMA | Information campaign Food balances analysis | ME | Taxation measures Information campaign Food balances analysis Assessment methodology | ME MF MEA MoAM FSMR
Priority 3- Social support |  |  |  |  |  | 
2.12. – 2.14. Capacity building, methodology, transparency | Food support needs assessment | MSD | Social support Information campaign | MSD MoAM SF FS Coincil | Needs assessment Trainings Social support Information campaign | MoAM FSMR MSD SF SALSGIR
Priority 4- Income growth |  |  |  |  |  | 
2.15.-2.16. Income growth 2.17. Capacity building | Home craft support | MSD ME MF | Farmers and vulnerable people training | MSD LSG | Income generation program Job creation Farmers and vulnerable people training | MSD ME MF LSG APTE SALSGIR

## Slide 5: FOOD UTILIZATION
 | Implemented/ Ongoing Activities | Actors | Activities in 2017 | Actors | New Program | Actors
Priority 1 – Institutional sustainability |  |  |  |  |  | 
3.1. Coordination 3.2. Nutrition legislation 3.3. Capacity building | Functional analysis | MoAM MoH |  |  | Curriculum adoption- Nutrition modules Capacity building Intersectoral platform Law improvement | MoH MoAM ME MoEd
Priority 2 – Food diversity |  |  |  |  |  | 
3.4. Diet for kids (<5 y) 3.5. Schoolchild diet 3.6. School nutrition 3.7. School programs 3.8. Female diet | Food for exhausted kids Pregnant women treatment Information campaign Micronutrient “Gulazyk” Needs assessment | MoH MoEd | Information campaign Trainings Infrastructure | MoH MoEd | Curriculum development Capacity building/ Trainings Legislation School children assessment Micronutrient “Gulazyk” Information campaign Obesity prevention School nutrition concept | MoH MoEd
Priority 3- Information support |  |  |  |  |  | 
3.9. – 3.11. Healthy diet, marketing, consumption 3.12. Capacity building and dissemination | Discussions Monitoring | MoH MoAM ME | Information campaign Capacity building Discussions | MoH MoAM | Law change Information campaign Capacity building Trainings Promotion plan | MoH MoAM ME
Priority 4- Integrated information system |  |  |  |  |  | 
3.13. - 3.15. Information system and monitoring 3.16. Monitoring system for neural tube | Neural tube Methodology Trainings Knowledge exchange | MoAM MoH NSC |  |  | Information system Data analysis Neural tube implementation Legislation Knowledge exchange Software | MoAM MoH NSC SCS

## Slide 6: FOOD SAFETY
 | Implemented/ Ongoing Activities | Actors | Activities in 2017 | Actors | New Program | Actors
Priority 1 – Food safety management |  |  |  |  |  | 
4.1. Optimization 4.2. Veterinary practice |  |  |  |  | Functional analysis Veterinary legislation adoption | GO MoAM SIVPSS
Priority 2 – Veterinary regulation |  |  |  |  |  | 
4.3. Veterinary system reform |  |  | Harmonization of legislation | MoAM SIVPSS ME MoH MEA | Legislation inventory Harmonization of legislation | MoAM SIVPSS ME MoH MEA
Priority 3- Food safety infrastructure |  |  |  |  |  | 
4.4. – 4.6. Laboratories |  |  | Laboratories renovation Deregulation measures Laboratories accreditation |  | Laboratories accreditation Tax incentives | ME MF CSM ME SIVPSS RCVDE
Priority 4- Technical standards control |  |  |  |  |  | 
4.7. Control implementation 4.8. Capacity building for standards 4.9. Private sector | Technical regulation | MoH MoAM SIVPSS MoEd KSTU |  |  | Technical regulation Tax incentives HAACP regulation HACCP department HACCP trainings | MoH MoAM ME SIVPSS MoEd KSTU MF
Priority 5- Sanitary and veterinary control |  |  |  |  |  | 
4.10. Control system 4.11. Veterinary zones | Control procedures | SIVPSS MoH SCS ME |  |  | Control procedures Sanitary regulations Feasibility study | SIVPSS MoH SCS ME Dairy Union

## Slide 7: Abbreviations
AMA - Anti-Monopoly Regulation Agency Under the Government of the Kyrgyz Republic
APTE - Agency of Professional Technical Education under the Ministry of Education
CSM ME- Centre for Standardization and Metrology under the Ministry of Economy
FSMR – Fund of the State Material Reserves
FS Council- Food Security Council
GO - Government Office
HACCP - Hazard analysis and critical control points
IAWG – Inter- Agency Working Group
KNAU- Kyrgyz National Agrarian University
KRSU – Kyrgyz-Russian Slavonic University
KSTU - Kyrgyz State Technical University
LSG- Local Self-Government (Municipal Governments)
ME - Ministry of Economy
MoAM - Ministry of Agriculture, Food Industry, and Melioration
MF- Ministry of Finance
MoEd – Ministry of Education and Science
MoH- Ministry of Healthcare
MSD - Ministry of Labor and Social Development
MEA – Ministry of External Affairs
MES – Ministry of Emergency Situations
MLMY – Ministry of Labor, Migration, and Youth
NB – National Bank
NSC –National Statistical Committee
RCVDE- Republican Centre for Veterinary Diagnosis and Examination of the State Inspectorate for Veterinary and Phytosanitary Safety
SALSGIR - State Agency for Local Self-Government and Inter-Ethnic Relations under the Government of Kyrgyz Republic
SAEPF - State Agency on Environment Protection and Forestry
SRS – State Registration Service
SF- Social Fund
SIVPSS- State Inspectorate for Veterinary and Phytosanitary Safety under the Government of the Kyrgyz Republic
SCS- State Customs Service