AgWA Steering Committee/Partners’ Meeting

March, 18-19th 2014, Addis Ababa, Ethiopia

SUMMARY OF KEY ISSUES RAISED AND WAY FORWARD

1. Key issues to consider on AgWA’s thematic scope of work

  - Smallholder (family farming)/ poverty reduction

  - Rainfed systems

  - Multiple use services

  - Ecosystem services approach

  - River basin approach and River basin organizations (RBOs) as partners

  - Emphasize AgWA’s role on AWM beyond CAADP (i.e. improving water use efficiency, enhancing water productivity, etc)

2. Way forward. AgWA secretariat and partners to work on the following:

- AgWA vision

- Mapping of actors / stakeholders for CAADP implementation. To use current structures as much as possible (RECs/CAADP FPs)

- Criteria for country selection in proposals

- Results based Framework

- On partnership’s governance

  - To prepare a Constitution (defining roles of members, who gets in the Steering Committee and for how long)

  - Definition of application process / form to become part of the Steering Committee (SC) and reaching out to members.

  - Work on legal status: to hire a legal adviser to assess pros and cons of different alternatives of becoming a legal entity.

- On resource mobilization

  - To work together with ARID and CILSS on a proposal on Knowledge-sharing in Sahel to be funded by the World Bank.

  - Establishing a consortium with partners to apply for funds for specific activities.

  - Undertaking scoping on resources

- AgWA, together with CARE, will work on materializing element 6 in Basket Fund (Biannual publication of the state of the art of AWM in Africa) and event co-organisation

- AgWA, together with WaterNet, will organize a joint session in the WaterNet/WARFSA/GWP-SA Symposium to be held in Malawi in October 2014

- AgWA will lead the creation of a Taskforce for the follow-up of the Eastern Africa Sub-regional Workshop on Addressing the Challenges of Water Scarcity in East Africa and Strengthening Resilience to Drought. In particular to:

  - Clarify taskforce(s) role and ToRs as committee develops its governance structure (FL to lead)

  - Link to SC and non-SC members, potentially in development of taskforce(s)

  - Action points under the Taskforce should be re-examined by the SC