Form 12.2. Workshop preparation checklist.

- Check

- Identify appropriate funding sources for the workshop and prepare written agreements on the objectives, size and structure of the workshop. All financial and administrative matters must be clarified in writing, including how the financial resources will be managed.

- Ensure that proper auditing will be performed and specify exactly what type of expenses will be covered by the workshop budget. Most often, a full-time position is required to take care of all practical matters starting at least 2 months prior to the workshop.

- Conduct pre-workshop meetings during which you will:

  - identify key collaborators and their contributions (host institute, sponsors, etc.);

  - identify facilitator(s);

  - generate a list of potential participants;

  - select a date for conducting the workshop;

  - decide on a list of potential speakers for each session for which a speaker is required.

- Estimate workshop costs and cost-sharing across partners if appropriate.

- Send invitations at least three weeks before the event for national workshops. For international workshops, 2 months’ notice is the absolute minimum. If the travel costs will be covered by the organizers, clear and written instructions of the fare class, maximum costs and cost documentation must be provided.

- Identify and reserve a workshop location that (ideally) has:

  - a plenary room large enough for the number of participants;

  - break-out rooms, or a room large enough for small groups to work in the same room without disturbing each other;

  - on-site accommodation.

- Make arrangements with a food and beverage supplier for lunch and breaks. Take into account food needs/preferences for international workshops in which cultural and religious considerations may specify food choices.

- Finalize the agenda and confirm presenters, and clarify in writing their financial support (travel, accommodation, honorarium, etc.).

- Hold a training meeting for small-group facilitators 1 week prior to the workshop if small-group sessions are to be included.

- Collect necessary equipment and materials prior to the workshop:

  - notebooks and pens for participants;

  - pads of flip-chart paper and markers;

  - name tags;

  - copies of all handouts to be distributed.

- Obtain overhead and LCD projectors, including spare equipment, and ensure the 	availability of technical assistance prior to and during the workshop.